## General
Procurement Plan
I General
1 | Project Information
| Project Name: | Integrated Irrigation Improvement & Management Project
| Country: | Arab Republic of Egypt
| Project ID: | P073977
| Loan/Credit Numbers: | EGT-7291
| Component | Meet Yazid
2 | Bank's approval date of Procurement Plan | Original:28/2/2008
Revision 1:3/12/2008
Update 16/11/2011
Update 10/9/2012
Update 4/2/2013
Update January 16, 2014
3 | Date of General Procurement Notice | 2005-05-01
II Goods, Work and Non-Consulting Services Thresholds
1 | Prior Review Threshold Procurement Decisions subject to Prior Review by the Bank as stated in the Loan Agreement. The Loan Agreement was amended on 2 November 2012. The amended Loan Agreement stated that "The Procurement Plan shall set forth those contracts, which shall be subject to the Bank's Prior Review. All other contracts shall be subject to Post Review by the Bank"
1a | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods | more than or equal 250,000
| Works | more than or equal 500,000
1b | Procurement Method | Procurement Method Threshold (USD) | Comments
| ICB (Goods) | more than or equal 500,000
| NCB (Goods) | Less than 500,000
| Shopping (Goods) | Less than or equal 20,000
| ICB (Works) | More than or equal 10,000,000
| NCB (Works) | Less than 10,000,000
| Shopping (Works) | Less than 50,000

## Goods
Procurement Plan for Goods | [20 empty] | Updated 12/12/2013
Arab republic of Egypt EGT-7291: Integrated Irrigation Improvement & Management Project Original:28/2/2008
Proc Plan Updated on January 16, 2014
Completed
SLNo | Package reference No/ Contract No | Description of Goods | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date) | Expenditure incurred to Date
1 | IIIMP/ICB/G- 01-2007 | Vehicles(Lot A) 64 Double cabin Pick-Up and Spare Parts increased to 73 | ICB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | [8 empty] | 8146461 | EGP | Global Cars & Spare Parts
Revised
[5 empty] | Actual |  |  |  |  | 2006-10-19 | 2006-12-21 | 2007-02-10 | 2007-04-02 | 2007-04-02 | 2007-08-09 | 2007-08-14 | 2007-09-09 |  |  |  | 2007-11-14
2 | IIIMP/ICB/G- 01-2007 | Vehicles(Lot B) 20 4X4 Wheel Drive Utility Vehicles and Spare Parts increased to 23 | ICB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | [8 empty] | 3542269.08 | EGP | Global Cars & Spare Parts
Revised
[5 empty] | Actual |  |  |  |  | 2006-10-19 | 2006-12-21 | 2007-02-10 | 2007-04-02 | 2007-04-02 | 2007-07-18 | 2007-07-18 | 2007-09-04 |  |  |  | 2008-02-21
3 | IIIMP/ICB/G- 08-2007 | Supply of Subsurface Drainage Laterals Laying Machines | ICB | IBRD | Planned |  |  | Prior | No | [8 empty] | 489750 | EUR | Steenbergen Hollanddrain B.V | 2008-01-31
Revised
[5 empty] | Actual |  |  |  |  | 2007-02-12 | 2007-02-22 | 2007-03-18 | 2007-04-30 | 2007-04-30 | 2007-07-18 | 2007-07-18 | 2007-09-30 |  |  |  | Completed
4 | IIIMP/ICB/G- 09-2007 | Supply of Subsurface Drainage Collectors Laying Machines | ICB | IBRD | Planned |  |  | Prior | No | [8 empty] | 439,500+7000 | EUR+LE | Inter - Drain Sales B.V | 2008-01-16
Revised
[5 empty] | Actual |  |  |  |  | 2007-02-12 | 2007-02-22 | 2007-03-18 | 2007-05-02 | 2007-05-02 | 2007-07-18 | 2007-07-18 | 2007-09-17 |  |  |  | Completed
5 | IIIMP/ICB/G- 04-2008 | 150 km PVC pipes with different diameters | ICB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | [8 empty] | 2853510 | EGP | Al-Hakeem Plast | 2008-05-31
Revised
[5 empty] | Actual |  |  |  |  | 2007-07-15 | 2007-07-18 | 2007-08-02 | 2007-08-26 | 2007-08-26 | 2007-11-08 | 2007-12-05 | 2008-01-02 |  |  |  | 2008-06-11
6 | IIIMP/SHOPPING 01-2007 | 6000 m PVC pipes with 200 mm diameters | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2007-07-18: N/A; 2007-12-05: N/A | 113816 | EGP | Inter-Plast for PVC Pipes
Revised
[5 empty] | Actual |  |  |  |  | 2007-05-31 |  | 2007-05-31 | 2007-06-07 | 2007-06-07 | 2007-06-14 |  | 2007-07-10 |  |  |  | 2007-07-21
7 | IIIMP/SHOPPING 02-2008 | ArcEditor licence PMU | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2007-07-18: N/A; 2007-12-05: N/A | 74200 | EGP | Quality Standard
Revised
[5 empty] | Actual |  |  |  |  | 2007-07-15: 2008-02-26; 2007-08-02: 2008-02-27; 2007-11-08: 2008-03-10; 2008-01-02: 2008-03-20 |  |  |  | 2008-03-26
8 | IIIMP/SHOPPING 03-2008 | ArcEditor licence for Behira | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2007-07-18: N/A; 2007-12-05: N/A | 74200 | EGP | Quality Standard
Revised
[5 empty] | Actual |  |  |  |  | 2007-07-15: 2008-02-26; 2007-08-02: 2008-02-27; 2007-11-08: 2008-03-10; 2008-01-02: 2008-03-20 |  |  |  | 2008-03-26
9 | IIIMP/SHOPPING 04-2008 | ArcEditor licence for Kafr El-Sheikh | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2007-07-18: N/A; 2007-12-05: N/A | 74200 | EGP | Quality Standard
Revised
[5 empty] | Actual |  |  |  |  | 2007-07-15: 2008-02-26; 2007-08-02: 2008-02-27; 2007-11-08: 2008-03-09; 2008-01-02: 2008-03-20 |  |  |  | 2008-03-26
10 | IIIMP/SHOPPING 05-2008 | ArcEditor licence for Tanta | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2007-07-18: N/A; 2007-12-05: N/A | 74200 | EGP | Quality Standard
Revised
[5 empty] | Actual |  |  |  |  | 2007-07-15: 2008-02-26; 2007-08-02: 2008-02-27; 2007-11-08: 2008-03-13; 2008-01-02: 2008-03-20 |  |  |  | 2008-03-26
11 | IIIMP/SHOPPING 06-2008 | A0 Plotters (3) | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2007-07-18: N/A; 2007-12-05: N/A | 97500 | EGP | Global Computec
Revised
[5 empty] | Actual |  |  |  |  | 2007-07-15: 2008-08-18; 2007-11-08: 2008-09-08; 2008-01-02: 2008-09-11 |  |  |  | 2008-09-28
12 | IIIMP/SHOPPING 07-2008 | A0 scanner (1) | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2007-07-18: N/A; 2007-12-05: N/A | 99000 | EGP | TIC Computing
Revised
[5 empty] | Actual |  |  |  |  | 2007-07-15: 2008-08-18; 2007-11-08: 2008-09-02; 2008-01-02: 2008-09-11 |  |  |  | 2008-10-23
13 | IIIMPSHOPPING 09-2008 | Water quality testing instruments (8) | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2007-07-18: N/A; 2007-12-05: N/A | 108072 | EGP | Chemical&Technical services
Revised
[5 empty] | Actual |  |  |  |  | 2008-11-20 |  | 2008-12-04 | 2008-12-19 | 2008-12-19 | 2008-12-24 |  | 2009-01-06 |  |  |  | 2009-05-11
14 | IIIMP/SHOPPING 10-2009 | 4000 m PVC pipes with 180 mm diameters | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2007-12-05: N/A | 88469 | EGP | Al-Ameen for Pipes
Revised
[5 empty] | Actual |  |  |  |  | 2009-03-31 | 2009-04-02 | 2009-04-06 | 2009-04-14 | 2009-04-14 | 2009-04-23 |  | 2009-04-30 |  |  |  | 2009-05-21
15 | IIIMP/SHOPPING 11-2009 | 5000 m PVC pipes with 180 & 200 mm diameters | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2007-07-18: N/A; 2007-12-05: N/A | 108979 | EGP | Al-Ameen for Pipes
Revised
[5 empty] | Actual |  |  |  |  | 2009-06-08 |  | 2009-06-14 | 2009-06-21 | 2009-06-21 | 2009-06-28 |  | 2009-07-05 |  |  |  | 2009-10-20
16 | IIIMP/PMU/G6-ICB/2009 | 400 km PVC pipes with different diameters | ICB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | [8 empty] | 6106046 | EGP | Canal Plastic Company for Pipes & Fittings | 2010-12-05
[5 empty] | Revised | [15 empty] | 2011-06-05
[5 empty] | Actual |  |  |  |  | 2009-02-12 | 2009-05-10 | 2009-05-27 | 2009-07-12 | 2009-07-12 | 2009-08-19 | 2009-08-23 | 2009-12-06 |  |  |  | 2011-05-23
17 | IIIMP/SHOPPING 08-2008 | 4000 m PVC pipes with 200 mm diameters | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2009-05-10: N/A; 2009-05-27: N/A; 2009-08-23: N/A | 105464 | EGP | Goldan Pipe for make PVC
Revised
[5 empty] | Actual |  |  |  |  | 2008-11-20 |  |  | 2008-12-04 | 2008-12-04 | 2008-12-25 |  | 2009-01-06 |  |  |  | 2009-02-04
18 | IIIMP/SHOPPING/ 12-2009 | 1 Total Station + 2 Theodolite + 10 spirit level | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2009-05-10: N/A; 2009-05-27: N/A; 2009-08-23: N/A | 106602.05 | EGP | Cairo Engineering & Technical
Revised
[5 empty] | Actual |  |  |  |  | 2009-07-12: 2009-07-20; 2009-07-12: 2009-07-20; 2009-08-19: 2009-08-17; 2009-12-06: 2009-09-03 |  |  |  | 2009-09-16
19 | IIIMP/SHOPPING/G13-2009 | 10 GPS + 6 Steel Measuring Tape | Shopping | CA (100%) | Planned |  |  | Post | No | 2009-05-10: N/A; 2009-05-27: N/A; 2009-08-23: N/A | 33899 | EGP | Surveying systems company
Revised
[5 empty] | Actual |  |  |  |  | 2009-07-12: 2009-10-01; 2009-07-12: 2009-10-01; 2009-08-19: 2009-11-09; 2009-12-06: 2009-11-10 |  |  |  | 2009-11-19
20 | IIIMP/SHOPPING/G14-2009 | Conductivity, Salinity, TDS, Specific conductance temperature meter +6 Rechargeable battery | Shopping | CA (100%) | Planned |  |  | Post | No | 2009-05-10: N/A; 2009-05-27: N/A; 2009-08-23: N/A | 20493 | EGP | Giga systems company
Revised
[5 empty] | Actual |  |  |  |  | 2009-07-12: 2009-10-01; 2009-07-12: 2009-10-01; 2009-08-19: 2009-11-09; 2009-12-06: 2009-11-10 |  |  |  | 2009-12-09
21 | IIIMP/PMU/G7-NCB/2011 | The Supply of Motorcycles and Tricycles | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-02-12: 2010-06-01; 2009-05-27: 2010-12-15; 2009-07-12: 2011-01-15; 2009-12-06: 2011-03-01 | 731280 | EGP | Ibrahem Mahmoud Ibrahem company for Production of Motorcycles and its Spare Parts
[5 empty] | Revised | [15 empty] | 2012-04-02
[5 empty] | Revised |  |  |  |  | 2010-12-14 | 2011-01-23 | 2011-03-21 | 2011-05-02 | 2011-05-02 | 2011-06-21 | 2011-06-27 | Tend. Cancelled
[5 empty] | Revised |  |  |  |  | 2011-07-20 |  | 2011-08-19 | 2011-09-18 | 2011-09-18 | 2011-10-18 |  | 2011-11-17
[5 empty] | Actual |  |  |  |  | 2011-07-19 | 2011-07-24 | 2011-08-24 | 2011-09-29 | 2011-09-29 | 2011-12-13 | 2011-12-13 | 2011-12-28 |  |  |  | 2012-02-01
22 | IIIMP/SHOPPING/G 21-2010 | Supply of GPSs | Shopping | CA (100%) | Planned |  |  | Post | No | 2011-06-01 | N/A | 2011-07-01 |  |  |  | N/A | 2011-08-30 | 11000 | EGP | Zoom Technologies | 2011-09-14
Revised
[5 empty] | Actual |  |  |  |  | 2010-11-24 |  | 2010-11-24 | 2010-12-02 | 2010-12-04 |  |  | 2010-12-19 |  |  |  | 2011-03-14
23 | IIIMP/PMU/SHORT-LIST/G22-2010 | Supply of Current meters and survey equipment | SHORT-LIST | CA (100%) | Planned |  |  | Prior | No | 2011-06-01 | N/A | 2011-09-01 |  | 2011-07-31 |  | N/A | 2011-08-30 | 303380 | EGP | Cairo Engineeering & Manufacturing Co. | 2011-09-14
Revised
[5 empty] | Actual |  |  |  |  | 2011-07-19: 15-Dec.-10 |  |  |  | 2011-06-16
24 | IIIMP/PMU/NCB/G25-2011 | Supply of Spinit Level | Shopping | CA (100%) | Planned |  |  | Post | No | 2011-07-24: N/A; 2011-12-13: N/A | 27720 | EGP | Technoscient
Revised
[5 empty] | Actual |  |  |  |  | 2011-07-19: 2011-01-04; 2011-08-24: 2011-01-05; 2011-09-29: 2011-01-13; 2011-12-28: 2011-01-26 |  |  |  | 2011-03-14
25 | IIIMP/PMU/NCB/G26-2011 | Supply of Total Station | Shopping | CA (100%) | Actual |  |  | Post | No | 2011-07-24: N/A; 2011-12-13: N/A | 46000 | EGP | Surveying Syatems
[10 empty] | 2011-01-04 |  | 2011-01-05 | 2011-01-13 | 2011-01-19 | 2011-01-20 |  | 2011-01-26 |  |  |  | 2011-03-14
26 | IIIMP/PMU/G8-NCBG27-2012 | Supply of Computers & Printers | NCB | CA (100%) | Planned |  |  | Post | No | 2011-07-19: 2012-01-15; 2011-07-24: N/A; 2011-12-13: 2012-04-16; 2011-12-13: N/A | 48300 | EGP | CNS Group Company + Leaders for Computers and Electronics Company
Revised
[5 empty] | Actual | [6 empty] | 2012-02-27 | 2012-03-14 | 2012-03-14 | 2012-04-08 |  | 2012-04-22 |  |  |  | 2012-05-28
27 | IIIMP/SHOPPING/G 15-2012 | Supply of PVC Welding Machines | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2011-06-01 | N/A | 2011-07-01 |  |  |  | N/A | 2011-08-30 | 32725 | EGP | Cairo Center for Tools&Machinery | 2012-11-05
[5 empty] | Revised |  |  |  |  | 2011-07-19: 2012-12-20; 2011-08-24: 2012-12-25; 2011-12-28: 2013-01-09
[5 empty] | Actual |  |  |  |  | 2012-09-10 |  | 2012-09-15 | 2012-09-30 | 2012-09-30 | 2012-10-03 |  | 2012-10-24 |  |  |  | 2012-12-15
28 | IIIMP/SHOPPING/G16-2012 | Supply of Angle Grinders | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2011-06-01 | N/A | 2011-07-01 |  |  |  | N/A | 2011-08-30 | 5720 | EGP | Cairo Center for Tools&Machinery | 2012-12-24
[5 empty] | Revised |  |  |  |  | 2011-07-19: 2012-12-20; 2011-08-24: 2012-12-25; 2011-12-28: 2013-01-09
[5 empty] | Actual |  |  |  |  | 2012-09-10 |  | 2012-09-15 | 2012-09-30 | 2012-09-30 | 2012-10-03 |  | 2012-10-24 |  |  |  | 2012-12-15
29 | IIIMP/SHOPPING/G 17-2012 | Supply of Water Pumps | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2011-06-01 | N/A | 2011-07-01 |  |  |  | N/A | 2011-08-30 | 30250 | EGP | Cairo Center for Tools&Machinery | 2012-11-05
[5 empty] | Revised |  |  |  |  | 2011-07-19: 2012-12-25; 2011-08-24: 2012-12-30; 2011-12-28: 2013-01-14
[5 empty] | Actual |  |  |  |  | 2012-09-10 |  | 2012-09-15 | 2012-09-30 | 2012-09-30 | 2012-10-03 |  | 2012-10-24 |  |  |  | 2012-12-15
30 | IIIMP/SHOPPING/G 18-2012 | Supply of Generators | Shopping | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2011-06-01 | N/A | 2011-07-01 |  |  |  | N/A | 2011-08-30 | 68200 | EGP | Cairo Center for Tools&Machinery | 2012-12-24
[5 empty] | Revised |  |  |  |  | 2011-07-19: 2012-12-25; 2011-08-24: 2012-12-30; 2011-12-28: 2013-01-14
[5 empty] | Actual |  |  |  |  | 2012-09-10 |  | 2012-09-15 | 2012-09-30 | 2012-09-30 | 2012-10-03 |  | 2012-10-24 |  |  |  | 2013-02-06
Ongoing
SLNo | Package reference No/ Contract No | Description of Goods | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date) | Expenditure incurred to Date
1 | IIIMP/ICB/G- 05-2009 | Supply, delivery, Installation and commissioning of Ultra Sonic Flow Measurement Equipment Including Data Processing and Interpretation Software | ICB | IBRD | Planned |  |  | Prior | No | 2011-12-28: 2010-05-01 | 3918360 | EGP | Hydro Vision Gmbh. | 2011-03-20
[5 empty] | Revised | [15 empty] | 2013-12-31
[5 empty] | Actual |  |  |  |  | 2009-07-09 | 2009-08-09 | 2009-09-06 | 2009-11-04 | 2009-11-04 | 2010-03-28 | 2010-03-31 | 2010-06-03
#REF! | IIIMP/PMU/G7-NCB/2011 | The Supply of Motorcycles and Tricycles | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-07-09: 2010-06-01; 2009-09-06: 2010-12-15; 2009-11-04: 2011-01-15; 2010-06-03: 2011-03-01 | 731280 | EGP | Ibrahem Mahmoud Ibrahem company for Production of Motorcycles and its Spare Parts
2 | IIIMP/PMU/NCB/G20-2013 | Supply of PVC Pipes for Marwa | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2009-07-09: 2011-06-01; 2009-09-06: 2011-07-01; 2009-11-04: 2011-07-31; 2010-06-03: 2011-08-30 | 2055000 | EGP | Al-Ameen company for PVC Pipes | 2012-06-29
[5 empty] | Revised |  |  |  |  | 2009-07-09: 2013-07-10; 2009-09-06: 2013-08-09; 2009-11-04: 2013-09-08; 2010-06-03: 2013-10-08 |  |  |  | 2014-04-06
[5 empty] | Actual |  |  |  |  | 2013-07-02 | 2013-08-21 | 2013-08-29 | 2013-09-30 | 2013-09-30 | 2013-11-05 | 2013-11-10
Planned
SL No | Package reference No/ Contract No | Description of Goods | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date) | Expenditure incurred to Date
1 | IIIMP/SHOPPING/G 19-2011 | Supply of Boats | Cancelled | CA (100%) | Planned |  |  | Post | No | 2011-06-01 | N/A | 2011-09-01 |  |  |  | N/A | 2011-08-30 |  |  |  | 2011-09-14
[5 empty] | Revised |  |  |  |  | 2009-07-09: 2012-05-01; 2009-09-06: 2012-05-16; 2010-06-03: 2012-05-31 |  |  |  | 2012-06-15
[5 empty] | Actual |  |  |  |  | 2009-07-09: Cancelled
2 | IIIMP/SHOPPING/G 20-2010 | Supply of accessories needed for current meters | Cancelled | CA (100%) | Planned |  |  | Post | No | 2011-06-01 | N/A | 2011-09-01 |  |  |  | N/A | 2011-08-30 |  |  |  | 2011-09-14
[5 empty] | Revised |  |  |  |  | 2009-07-09: 2012-06-10; 2009-09-06: 2012-06-25; 2010-06-03: 2012-07-10 |  |  |  | 2012-07-25
[5 empty] | Actual |  |  |  |  | 2009-07-09: Cancelled
3 | IIIMP/PMU/NCB/G 24- | Supply of Mortorcycles | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2009-07-09: 2012-03-15; 2009-09-06: 2012-03-30; 2010-06-03: 2012-04-14 |  |  |  | 2012-05-14
[5 empty] | Revised |  |  |  |  | 2009-07-09: 2014-03-15; 2009-09-06: 2014-04-14; 2009-11-04: 2014-05-14; 2010-06-03: 2014-06-13 |  |  |  | 2014-09-11
Actual
4 | IIIMP/PMU/NCB/G28- | Goods For Mesqa Electrifications 1 | Cancelled | IBRD (90%) GoE (30%) | Planned |  |  | Post | No | 2009-07-09: 2012-11-20; 2009-09-06: 2012-12-20; 2009-11-04: 2013-01-19; 2010-06-03: 2013-02-18 |  |  |  | 2013-05-19
[5 empty] | Revised |  |  |  |  | 2009-07-09: Tender Cancelld
Actual
5 | IIIMP/PMU/ICB-G29- | Supply of Tractor, Combinders, Trailer & Pressor | Cancelled | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-07-09: 2013-03-01; 2009-09-06: 2013-03-31; 2009-11-04: 2013-04-30; 2010-06-03: 2013-05-30 |  |  |  | 2013-08-28
[5 empty] | Revised |  |  |  |  | 2009-07-09: 2014-03-01; 2009-09-06: 2014-03-31; 2009-11-04: 2014-04-30; 2010-06-03: 2014-05-30
Actual
6 | IIIMP/PMU/NCB/G30- | Goods For Mesqa Electrifications 2 | Cancelled | IBRD (90%) GoE (30%) | Planned |  |  | Prior | No | 2009-07-09: 2013-05-01; 2009-09-06: 2013-05-31; 2009-11-04: 2013-06-30; 2010-06-03: 2013-07-30 |  |  |  | 2013-10-28
[5 empty] | Revised |  |  |  |  | 2009-07-09: Cancelld
Actual
7 | IIIMP/PMU/NCB/G31- | Goods For Mesqa Electrifications 3 | Cancelled | IBRD (90%) GoE (30%) | Planned |  |  | Prior | No | 2009-07-09: 2013-09-01; 2009-09-06: 2013-10-01; 2009-11-04: 2013-10-31; 2010-06-03: 2013-11-30 |  |  |  | 2014-02-28
[5 empty] | Revised |  |  |  |  | 2009-07-09: Cancelld
Actual
8 | IIIMP/PMU/ICBG32- | Supply of PVC Pipes for Marwa | Cancelled | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-07-09: 2011-06-01; 2009-09-06: 2011-07-01; 2009-11-04: 2011-07-31; 2010-06-03: 2011-08-30 |  |  |  | 2013-06-29
[5 empty] | Revised |  |  |  |  | 2009-07-09: 2014-03-01; 2009-09-06: 2014-03-31; 2009-11-04: 2014-04-30; 2010-06-03: 2014-05-30 |  |  |  | 2014-11-26
Actual

## Electrification
Procurement Plan for Electrification Work (Meet Yazeed Area) | [21 empty] | Updated 12/12/2013
Arab republic of Egypt EGT-7291: Integrated Irrigation Improvement & Management Project Original:28/2/2008
Completed
SL No | District | Package reference No/ Contract No | Description of Works | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)
1 | Sidi Ghazy | IIIMP/IIS/MTYZ/ELL&ELM-04-2010 | Low and Medium Volt Electrification Moheet | Direct | GoE | Planned |  |  | n/a | No | 2010-08-01 | [6 empty] | 2010-11-01 |  | 1611126 | EGP | The North Delta for electricity distribution | 2011-02-27
[6 empty] | Revised | [16 empty] | 2011-07-20
[6 empty] | Actual |  |  |  |  | 2010-04-06 | [5 empty] | 2010-10-28 | 2010-10-28 |  |  |  |  | 2011-07-20
Total completed contracts
Ongoing
SL No | District | Package reference No/ Contract No | Description of Works | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)
1 | Gharb El-Mahalla +Qotor | IIIMP/IIS/MTYZ/ELM-01-2009 | Medium Volt Electrification for Gharb El-Mahalla | NCB | GoE | Planned |  |  | n/a | No | 2009-04-28 | 2009-06-07 | 2009-06-26 | 2009-06-26 | 2009-07-05 | 2009-07-18 | 2009-07-23 | 2009-08-27 |  | 11859940 | EGP | El-Sherka El-Ama General Company for Electrical Projects (ELEGECT) | 2011-09-25
[6 empty] | Revised | [16 empty] | 2013-03-25
[6 empty] | Actual |  |  |  |  | 2009-05-28 | 2009-07-07 | 2009-07-26 | 2009-07-26 | 2009-08-04 | 2009-08-17 | 2009-08-22 | 2009-09-26 |  |  |  |  | 2013-07-25
2 | Gharb El-Mahalla +Qotor | IIIMP/IIS/MTYZ/ELL-01-2009 | Low Volt Electrification for Gharb El-Mahalla | NCB | GoE | Planned |  |  | n/a | No | 2009-07-30 | 2009-08-24 | 2009-09-15 | 2009-09-15 | 2009-09-25 | 2009-10-17 | 2009-10-24 | 2009-11-20 |  | 11296244 | EGP | El-Sherka El-Ama General Company for Electrical Projects (ELEGECT) | 2011-12-19
[6 empty] | Revised | [16 empty] | 2013-04-19
[6 empty] | Actual |  |  |  |  | 2009-08-29 | 2009-09-23 | 2009-10-15 | 2009-10-15 | 2009-10-25 | 2009-11-16 | 2009-11-23 | 2009-12-20 |  |  |  |  | 2013-07-20
3 | Gharb El-Mahalla +Qotor | IIIMP/IIS/MTYZ/ELM-02-2009 | Double Medium Volt Electrification for Gharb El-Mahalla and Qotor | NCB | GoE | Planned |  |  | n/a | No | 2009-09-15 | 2009-10-24 | 2009-11-14 | 2009-11-14 | 2009-11-23 | 2009-12-05 | 2010-01-08 | 2010-01-17 |  | 4179047 | EGP | Electoro ElHany for Contracting and Electrical installations Company | 2010-10-15
[6 empty] | Revised | [16 empty] | 2011-06-09
[6 empty] | Actual |  |  |  |  | 2009-10-15 | 2009-11-23 | 2009-12-14 | 2009-12-14 | 2009-12-23 | 2010-01-04 | 2010-02-07 | 2010-02-16 |  |  |  |  | 2011-06-09
4 | Sidi Ghazy + Kafr El Shiekh | IIIMP/IIS/MTYZ/ELM-03-2010 | Medium Volt Electrification for Marsa EL Gamal & El Zawya (Phase 1) | NCB | GoE | Planned |  |  | n/a | No | 2010-07-16 | 2010-07-30 | 2010-08-16 | 2010-08-16 | 2010-08-31 | 2010-09-11 | 2010-09-14 | 2010-10-28 |  | 8385222.5 | EGP | Electoro ElHany for Contracting and Electrical installations Company | 2011-11-26
[6 empty] | Revised | [16 empty] | 2013-04-26
[6 empty] | Actual |  |  |  |  | 2010-08-15 | 2010-08-29 | 2010-09-15 | 2010-09-15 | 2010-09-30 | 2010-10-11 | 2010-10-14 | 2010-11-27 |  |  |  |  | 2013-11-26
5 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/ELL-02-2010 | Low Volt Electrification for Marsa EL Gamal & El Zawya (Phase 1) | NCB | GoE | Planned |  |  | n/a | No | 2010-08-15: 2012-04-04; 2010-08-29: 2012-05-04; 2010-09-15: 2012-06-03; 2010-11-27: 2011-07-03 |  | 8785382.45 | EGP | Electoro ElHany for Contracting and Electrical installations Company | 2012-05-07
[6 empty] | Revised | [16 empty] | 2013-05-07
[6 empty] | Actual |  |  |  |  | 2010-11-25 | 2010-12-25 | 2011-01-16 | 2011-01-16 | 2011-01-20 | 2011-03-15 | 2011-03-29 | 2011-05-08 |  |  |  |  | 2013-11-07
6 | Sidi Ghazy + Kafr El Shiekh | IIIMP/IIS/MTYZ/ELL-03-2013 | Low Volt Electrification for Kafr El Shiekh 1 (El Halafy) | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-12-01 | 2012-12-08 | 2012-12-29 | 2012-12-29 | 2013-01-13 | 2013-01-28 | 2013-02-12 | 2013-03-14 |  | 4544748 | EGP | El Alamia for Engineering & Contracting | 2014-07-29
[6 empty] | Revised |  |  |  |  | 2013-03-01 | 2013-03-08 | 2013-03-24 | 2013-04-21 | 2013-04-21 | 2013-06-01 | 2013-06-16 | 2013-07-16 | 2013-07-31
[6 empty] | Actual |  |  |  |  | 2013-02-07 | 2013-03-03 | 2013-03-17 | 2013-04-16 | 2013-04-16 | 2013-05-30 | 2013-06-27 | 2013-07-30 | 2013-07-30
7 | Sidi Ghazy + Kafr El Shiekh | IIIMP/IIS/MTYZ/ELM-04 | Medium Volt Electrification for Kafr El Shiekh 1 (El Halafy) | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-11-20 | 2012-11-27 | 2012-12-18 | 2012-12-18 | 2013-01-02 | 2013-01-17 | 2013-02-01 | 2013-03-03 |  | 5248887.52 | EGP | El Alamia for Engineering & Contracting | 2014-07-29
[6 empty] | Revised |  |  |  |  | 2013-03-20 | 2013-03-27 | 2013-03-24 | 2013-04-21 | 2013-04-21 | 2013-06-01 | 2013-06-16 | 2013-07-16 | 2013-07-31
[6 empty] | Actual |  |  |  |  | 2013-02-07 | 2013-03-03 | 2013-03-17 | 2013-04-17 | 2013-04-17 | 2013-05-30 | 2013-06-27 | 2013-07-30 | 2013-07-30
8 | Sidi Ghazy + Kafr El Shiekh | IIIMP/IIS/MTYZ/ELM-05-2013 | Medium Volt Electrification for Kafr El Shiekh 2 (Feeder) | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-12-10 | 2012-12-17 | 2013-01-07 | 2013-01-07 | 2013-01-22 | 2013-02-06 | 2013-02-21 | 2013-03-23 |  | 3845427.77 | EGP | El Alamia for Engineering & Contracting | 2014-07-29
[6 empty] | Revised |  |  |  |  | 2013-03-10 | 2013-03-17 | 2013-03-24 | 2013-04-21 | 2013-04-21 | 2013-06-01 | 2013-06-16 | 2013-07-16 | 2013-07-31
[6 empty] | Actual |  |  |  |  | 2013-02-07 | 2013-03-03 | 2013-03-17 | 2013-04-18 | 2013-04-18 | 2013-05-30 | 2013-06-27 | 2013-07-30 | 2013-07-30
Total ongoing contracts
Planned
SL No | District | Package reference No/ Contract No | Description of Works | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)
1 | Sidi Ghazy + Kafr El Shiekh | IIIMP/IIS/MTYZ/ELM-06 | Medium Volt Electrification for the rest of Kafr El Shiekh 3 (Daramally) | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-07-01 | 2013-07-08 | 2013-07-29 | 2013-07-29 | 2013-08-13 | 2013-08-28 | 2013-09-12 | 2013-10-12 |  |  |  |  | 2014-10-12
[6 empty] | Revised |  |  |  |  | 2013-07-01 | 2013-07-08 | 2014-02-01 | 2014-03-01 | 2014-03-01 | 2014-03-22 | 2014-04-06 | 2014-05-06 | 2014-05-21 |  |  |  | 2015-05-20
[6 empty] | Actual |  |  |  |  | 2013-07-01: 2013-10-09; 2013-07-08: 2013-11-12
2 | Sidi Ghazy + Kafr El Shiekh | IIIMP/IIS/MTYZ/ELL-04 | Low Volt Electrification for Kafr El Shiekh 2 (Daramally) | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-12-01 | 2013-12-08 | 2013-12-29 | 2013-12-29 | 2014-01-13 | 2014-01-28 | 2014-02-12 | 2014-03-14 |  |  |  |  | 2015-03-14
[6 empty] | Revised |  |  |  |  | 2013-07-01 | 2013-07-08 | 2014-02-01 | 2014-03-01 | 2014-03-01 | 2014-03-22 | 2014-04-06 | 2014-05-06 | 2014-05-21 |  |  |  | 2015-05-20
[6 empty] | Actual |  |  |  |  | 2013-07-01: 2013-10-09; 2013-07-08: 2013-11-12
3 | Various |  | Electric connections for the Ultrasonic equipment sites at Meet Yazeed- South | Direct | GoE | Planned |  |  | Post | No | 2013-07-01: 2012-03-01; 2013-07-08: 2012-03-16; 2014-05-06: 1900-01-29 |  |  |  | 2012-11-28
[6 empty] | Revised |  |  |  |  | 2013-07-01: 2012-08-01; 2013-07-08: 2012-08-16; 2014-05-06: 2012-08-30 |  |  |  | 2014-06-01
[6 empty] | Actual |  |  |  |  | Done | Done | Done | N/A | N/A | N/A | N/A | Done
4 | Various |  | Electric connections for the Ultrasonic equipment sites at Meet Yazeed- North | Direct | GoE | Planned |  |  | Post | No | 2013-07-01: 2012-03-01; 2013-07-08: 2012-03-16; 2014-05-06: 1900-01-29 |  |  |  | 2012-11-28
[6 empty] | Revised |  |  |  |  | 2013-07-01: 2012-08-15; 2013-07-08: 2012-08-30; 2014-05-06: 2012-09-06 |  |  |  | 2014-06-01
[6 empty] | Actual |  |  |  |  | Done | Done | Done | N/A | N/A | N/A | N/A | Done

## Main Canals
Procurement Plan for Main Canal Rehabilitation Works (Meet Yazid Area) | [22 empty] | Updated 12/12/2013
Arab republic of Egypt EGT-7291: Integrated Irrigation Improvement & Management Project Original:28/2/2008
Completed
SL No | District | Package reference No/ Contract No | Description of Works | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)
Total completed contracts
Ongoing
SL No | District | Package reference No/ Contract No | Description of Works | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)
1 | Qotor | IIIMP/MAIN-CANAL/MTYZ/3-2012 | Stabilize Embankments at km 24.330 to km 26.754 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2011-02-01 |  | 2011-03-03 | 2011-04-02 | 2011-04-02 |  |  |  | 2011-05-02 | 1418250 | EGP | Egyptian Integrated for contracting(Medeco) | 2014-02-28
[6 empty] | Revised |  |  |  |  | 2012-09-15 |  | 2012-12-15 | 2013-01-14 | 2013-01-14 |  |  | 2013-03-16 | 2013-03-23
[6 empty] | Actual |  |  |  |  | 2012-09-06 | 2012-09-12 | 2012-12-15 | 2013-01-15 | 2013-01-15 |  | 2013-04-01 | 2013-04-24 | 2013-04-28
2 | Qotor | IIIMP/MAIN-CANAL/MTYZ/4-2012 | Raise & Widen Embankments of Meet Yazeed Canal at Different Locations From Km 21.500 to Km 34.00 & Removal of Remains at Bridge Mit Yazid km 33+160 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2011-02-15 |  | 2011-03-17 | 2011-04-16 | 2011-04-16 |  |  |  | 2011-05-16 | 6761000 | EGP | moradex Company for Construction | 2014-04-18
[6 empty] | Revised |  |  |  |  | 2012-09-15 |  | 2012-12-15 | 2013-01-14 | 2013-01-14 |  |  | 2013-03-17 | 2013-03-24
[6 empty] | Actual |  |  |  |  | 2012-10-03 | 2012-11-05 | 2012-12-15 | 2013-01-16 | 2013-01-16 | Retendering
[6 empty] | Revised | [5 empty] | 2013-03-18 | 2013-04-01 | 2013-05-01 | 2013-05-01 | 2013-06-01 | 2013-06-08 | 2013-06-15 | 2013-06-22
[6 empty] | Actual |  |  |  |  | 2013-03-18 | 2013-03-18 | 2013-04-11 | 2013-05-13 | 2013-05-13 | 2013-07-02 | 2013-07-28 | 2013-08-19 | 2013-08-19
3 | Kafr El-Sheikh | IIIMP/MAIN-CANAL/MTYZ/10-2013 | Embankment Stability El Zawia at km 19.110 - 19.730 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-18: 2011-02-28; 2013-04-11: 2011-03-30; 2013-05-13: 2011-04-29; 2013-05-13: 2011-04-29; 2013-08-19: 2011-05-29 | 8816053.06 | EGP | Abo Taleb Company for Contracting | 2012-11-19
[6 empty] | Revised |  |  |  |  | 2012-12-10 |  | 2012-12-15 | 2013-01-14 | 2013-01-14 | 2013-05-16 | 2013-05-23 | 2013-05-30 | 2013-06-06 |  |  |  | 2014-04-05
[6 empty] | Actual |  |  |  |  | 2012-11-05 | 2012-11-16 | 2013-02-09 | 2013-03-13 | 2013-03-13 |  | 2013-05-19
4 | Kafr El-Sheikh | IIIMP/MAIN-CANAL/MTYZ/11-2013 | Embankment Stability El Zawia at km 19.730 -20.360 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-18: 2011-02-28; 2013-04-11: 2011-03-30; 2013-05-13: 2011-04-29; 2013-05-13: 2011-04-29; 2013-08-19: 2011-05-29 | 8768147.2 | EGP | Manetso Masr for Contracting | 2012-11-19
[6 empty] | Revised |  |  |  |  | 2012-12-20 |  | 2012-12-15 | 2013-01-14 | 2013-01-14 | 2013-05-16 | 2013-05-23 | 2013-05-30 | 2013-06-06 |  |  |  | 2014-04-05
[6 empty] | Actual |  |  |  |  | 2012-11-05 | 2012-11-16 | 2013-02-09 | 2013-03-14 | 2013-03-14 |  | 2013-05-19
Total ongoing contracts
Planned
SL No | District | Package reference No/ Contract No | Description of Works | Procurement method | Fund Source(s) | Status |  |  | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)
1 | Gharb El Mahalla | IIIMP/MAIN-CANAL/MTYZ/1-2012 | Repair Road Bridge at Mit-Yazid km 4+745 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-18: 2011-01-01; 2013-04-11: 2011-06-01; 2013-05-13: 2011-07-01; 2013-05-13: 2011-07-01; 2013-08-19: 2011-07-31 |  |  |  | 2011-11-28
[6 empty] | Revised | [6 empty] | 2012-12-15 | 2013-01-14 | 2013-01-14 | 2013-03-04 | 2013-03-11 | 2013-03-18 | 2013-03-25 |  |  |  | 2013-07-24
[6 empty] | Actual |  |  |  |  | 2011-07-20 | 2011-10-04 | 2012-12-15 | 2013-01-17 | 2013-01-17 |  | 2013-05-16 | Retendering
[6 empty] | Revised | [6 empty] | 2014-02-01 | 2014-03-03 | 2014-03-03 | 2014-04-02 | 2014-04-17 | 2014-05-02 | 2014-05-09 |  |  |  | 2014-09-07
Actual
2 | Kafr El-Sheikh | IIIMP/MAIN-CANAL/MTYZ/6- | Embankment Stability Meet Yazeed km 61.300 - 62.100 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-18: 2011-02-28; 2013-04-11: 2011-03-30; 2013-05-13: 2011-04-29; 2013-05-13: 2011-04-29; 2013-08-19: 2011-05-29 |  |  |  | 2013-03-24
[6 empty] | Revised |  |  |  |  | 2012-11-15 |  | 2014-04-01 | 2014-05-02 | 2014-05-02 | 2014-06-01 | 2014-06-16 | 2014-07-01 | 2014-07-08 |  |  |  | 2015-05-07
[6 empty] | Actual |  |  |  |  | 2013-03-18: 2012-11-04; 2013-03-18: 2012-11-16
3 | Kafr El-Sheikh | IIIMP/MAIN-CANAL/MTYZ/7- | Embankment Stability Meet Yazeed km 61.800 - 62.600 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-18: 2011-02-28; 2013-04-11: 2011-03-30; 2013-05-13: 2011-04-29; 2013-05-13: 2011-04-29; 2013-08-19: 2011-05-29 |  |  |  | 2013-03-24
[6 empty] | Revised |  |  |  |  | 2012-11-15 |  | 2014-04-01 | 2014-05-02 | 2014-05-02 | 2014-06-01 | 2014-06-16 | 2014-07-01 | 2014-07-08 |  |  |  | 2015-05-07
[6 empty] | Actual |  |  |  |  | 2013-03-18: 2012-11-04; 2013-03-18: 2012-11-16
4 | Kafr El-Sheikh | IIIMP/MAIN-CANAL/MTYZ/8- | Embankment Stability Meet Yazeed km 62.600 - 63.300 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-18: 2011-02-28; 2013-04-11: 2011-03-30; 2013-05-13: 2011-04-29; 2013-05-13: 2011-04-29; 2013-08-19: 2011-05-29 |  |  |  | 2013-03-24
[6 empty] | Revised |  |  |  |  | 2012-11-15 |  | 2014-04-01 | 2014-05-02 | 2014-05-02 | 2014-06-01 | 2014-06-16 | 2014-07-01 | 2014-07-08 |  |  |  | 2015-05-07
[6 empty] | Actual |  |  |  |  | 2013-03-18: 2012-11-04; 2013-03-18: 2012-11-16
5 | Qotor | IIIMP/MAIN-CANAL/MTYZ/2-2012 | Inspection and Rehabilitation of Siphons at Samatay and Beltag,Mit Yazid Km 19-21 | Beltag Done by force account and Samaty investigation done
Cancelled
6 | Qotor | IIIMP/MAIN-CANAL/MTYZ/5- | Scour at bridge Mit Yazid km33+160 | Included in another contract
Cancelled
7 | Kafr El-Sheikh | IIIMP/MAIN-CANAL/MTYZ/9- | Raising Embankment El Zawia LS km 3.7-4.0 and km 6.20-7.80 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-18: 2011-03-15; 2013-04-11: 2011-04-14; 2013-05-13: 2011-05-14; 2013-05-13: 2011-05-14; 2013-08-19: 2011-06-13 |  |  |  | 2012-12-04
[6 empty] | Revised |  |  |  |  | 2014-02-25 |  | 2014-03-27 | 2014-04-26 | 2014-04-26 | 2014-05-12 | 2014-05-19 | 2014-05-26 | 2014-06-02 |  |  |  | 2015-08-26
Actual
8 | Gharb El Mahalla | IIIMP/MAIN-CANAL/MTYZ/12- | Scour at bridge cluster at Mit Yazid km 4+721 | Under investig. stable or active | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-18: 2012-01-01; 2013-04-11: 2012-01-31; 2013-05-13: 2012-03-01; 2013-05-13: 2012-03-01; 2013-08-19: 2012-03-31 |  |  |  | 2012-09-30
[6 empty] | Revised |  |  |  |  | 2014-04-01 |  | 2014-05-01 | 2014-05-31 | 2014-05-31 | 2014-06-16 | 2014-06-23 | 2014-06-30 | 2014-07-07 |  |  |  | 2015-01-03
[6 empty] | Actual | [16 empty] | Under investigation
9 | Gharb El Mahalla | IIIMP/MAIN-CANAL/MTYZ/13- | Replacement of siphon at Samatai, km 19+777 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-18: 2012-01-05; 2013-04-11: 2012-02-04; 2013-05-13: 2012-03-05; 2013-05-13: 2012-03-05; 2013-08-19: 2012-04-04 |  |  |  | 2014-03-03
[6 empty] | Revised |  |  |  |  | 2014-02-15 |  | 2014-03-17 | 2014-04-16 | 2014-04-16 | 2014-06-01 | 2014-06-08 | 2014-06-15 | 2014-06-22 |  |  |  | 2015-12-20
Actual
10 | Gharb El Mahalla | IIIMP/MAIN-CANAL/MTYZ/14- | Scour at Samatai Siphon at Mit Yazid km 19+777 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-18: 2012-12-20; 2013-04-11: 2012-12-25; 2013-08-19: 2013-02-08 |  |  |  | 2013-03-10
[6 empty] | Revised | [6 empty] | 2014-05-01 | 2014-05-31 | 2014-05-31 | 2014-06-16 | 2014-06-23 | 2014-06-30 | 2014-05-16 |  |  |  | 2014-07-15
[6 empty] | Actual |  |  |  |  | 2013-03-18: 2013-02-28
PS
Contract No. IIIMP/MAIN-CANAL/MTYZ/14 will be funded by Gov or included with Contract No. IIIMP/MAIN-CANAL/MTYZ/13

## Branch Canals
Procurement Plan for Branch Canal Rehabilitation Works (Meet Yazeed Area) | [22 empty] | Updated 12/12/2013
Arab republic of Egypt EGT-7291: Integrated Irrigation Improvement & Management Project Original:28/2/2008
Completed
SL No | District | Package reference No/ Contract No | Description of Works | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)
1 | Gharb El-Mahalla | IIIMP/IIS/MITYZ/W01-2008 | Mesqa intake contract for Mit Yazid direct Right from intake to km 21.600 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2007-06-26 | 2007-07-14 | 2007-07-21 | 2007-08-15 | 2007-08-15 | 2007-09-08 | 2007-10-03 | 2007-10-24 |  | 1536757.2 | EGP | Adel Abdel Azez El- Shahawy Company | 2009-03-14
[6 empty] | Revised | [16 empty] | 2009-10-20
[6 empty] | Actual |  |  |  |  | 2007-09-18 | 2007-11-28 | 2008-02-09 | 2008-03-01 | 2008-03-01 | 2008-03-27 | 2008-04-06 | 2008-04-21 | 2008-04-22 |  |  |  | 2010-03-01
2 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/W02-2008 | Mesqa intake contract for Mit Yazid direct Left from intake to km 21.601 & Nisheel El-Gededa & Khadiga | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2007-06-26 | 2007-07-14 | 2007-07-21 | 2007-08-15 | 2007-08-15 | 2007-09-08 | 2007-10-03 | 2007-10-30 |  | 2707429.19 | EGP | Adel Abdel Azez El- Shahawy Company | 2009-03-14
[6 empty] | Revised | [16 empty] | 2009-04-20
[6 empty] | Actual |  |  |  |  | 2007-10-10 | 2008-01-03 | 2008-02-09 | 2008-03-02 | 2008-03-02 | 2008-03-25 | 2008-04-06 | 2008-04-21 | 2008-04-22 |  |  |  | 2009-10-20
3 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/W03-2008 | Improvement of Works for Nesheel Canal and its Branches | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2007-06-26 | 2007-07-02 | 2007-07-14 | 2007-07-21 | 2007-08-15 | 2007-09-08 | 2007-09-22 | 2007-10-03 |  | 4701350 | EGP | Ibrahem Mohammed Abo Borda Office | 2010-05-08
Revised
[6 empty] | Actual |  |  |  |  | 2008-11-25 | 2008-12-01 | 2008-12-18 | 2009-01-17 | 2009-01-17 | 2009-03-03 | 2009-03-24 | 2009-04-30 | 2009-05-09 |  |  |  | 2010-05-08
4 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/W04-2008 | Mesqa Intakes along Bahr Nemra El-Banwan & Ahmed Basha Rashid Canals | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2007-06-26 | 2007-07-14 | 2007-07-21 | 2007-08-15 | 2007-08-15 | 2007-09-08 | 2007-10-03 | 2007-10-24 |  | 3640600 | EGP | El Asar Office for Contracting | 2009-04-20
[6 empty] | Revised | [16 empty] | 2009-06-20
[6 empty] | Actual |  |  |  |  | 2007-09-18 | 2007-11-21 | 2008-02-09 | 2008-03-03 | 2008-03-03 | 2008-03-25 | 2008-04-06 | 2008-04-21 | 2008-04-21 |  |  |  | 2009-06-20
5 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/W05-2010 | Improvement of Mesqa intakes on Mares EL - Gamle from head to km 10.000& Kafr EL Morabeen& El Bashair& Mafroza ( Kafr El Sheikh District - Kafr El Sheikh Gov.) | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2007-09-18: 2011-01-01; 2008-04-21: 2011-04-01 | 5854660 | EGP | El Asar Office for Contracting | 2011-07-14
[6 empty] | Revised |  |  |  |  | 2008-04-21: 2010-07-01
[6 empty] | Actual |  |  |  |  | 2010-05-09 | 2010-05-13 | 2010-05-22 | 2010-06-22 | 2010-06-22 | 2010-07-01 | 2010-07-21 | 2010-09-15 | 2010-09-15 |  |  |  | 2011-10-13
6 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/W06-2010 | Mesqa intake Works for EL - Shamarka EL - Gedida & Shorafa canals and Direct El Zawia canal Right Side from km 5.963 to 6.252 Mit Yazeed Command Area in Kafr El Sheikh District | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-09-15: 2011-06-15 | 1221750 | EGP | Cooperative Society for Architectural Works | 2012-03-09
[6 empty] | Revised | [16 empty] | 2013-03-09
[6 empty] | Actual |  |  |  |  | 2010-09-22 | 2010-12-06 | 2010-12-18 | 2011-01-31 | 2011-01-31 | 2011-02-28 | 2011-05-23 | 2011-07-10 | 2011-07-10 |  |  |  | 2012-12-09
7 | Various | IIIMP/IS/MTYZ/W2 2011 | Preparation of civil works for ultrasonic flow meters and water levels equipment along meet yazeed canal and its branches | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2010-09-22: 2011-02-15; 2010-12-18: 2011-06-01; 2011-01-31: 2011-07-01; 2011-01-31: 2011-07-01; 2011-07-10: 2011-07-31 | 1140068.75 | EGP | Eng. Abrahem Abo Bourda Office | 2012-02-06
[6 empty] | Revised |  |  |  |  | 2011-07-10: 2011-09-30; 2011-07-10: 2011-10-01 |  |  |  | 2013-03-05
[6 empty] | Actual |  |  |  |  | 2011-03-03 | N/A | 2011-04-09 | 2011-05-09 | 2011-05-09 |  | N/A | 2011-08-10 | 2011-08-10 |  |  |  | 2013-01-05
Total completed contracts
Ongoing
SL No | District | Package reference No/ Contract No | Description of Works | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)
1 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/W-07-2010 | Mesqa intakes contract for El Zawia Right Side Ganabias No. 2,3,4 and the Branch of Ganabia 3, and the Al Zawia Left Side Ganabias No. 2,3,4,5,6 and Kom Al-Roz Al Kadema and Kom Al Roz Al Gadida - Mit Yazeed Command Area | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2011-06-02 |  | 2011-07-02 | 2011-08-01 | 2011-08-01 |  |  | 2011-08-31 | 2011-09-15 | 4030495.5 | EGP | Cooperative Socicty for Construction &Development | 2012-09-30
[6 empty] | Revised |  |  |  |  | 2010-11-09 |  | 2011-07-21 | 2011-08-20 | 2011-08-20 |  |  | 2011-11-19 | 2011-11-26 |  |  |  | 2012-12-31
[6 empty] | Actual |  |  |  |  | 2011-01-27 | 2011-07-07 | 2011-07-25 | 2011-08-25 | 2011-08-25 | 2011-10-16 | 2011-10-19 | 2011-12-01 | 2011-12-01
2 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/W08/2012 | Bahr Nemra and Other Branch Canals Rehabilitation Mit Yazid Command Area | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2011-06-03 |  | 2011-07-03 | 2011-08-02 | 2011-08-02 |  |  | 2011-09-01 | 2011-09-16 | 6137721 | EGP | El Asar Office for contracting | 2013-03-20
[6 empty] | Revised |  |  |  |  | 2011-07-25: 2012-02-01; 2011-08-25: 2012-03-02; 2011-08-25: 2012-03-02; 2011-12-01: 2012-04-01; 2011-12-01: 2012-04-08 |  |  |  | 2013-03-20
[6 empty] | Actual |  |  |  |  | 2011-05-02 | 2011-10-18 | 2012-01-04 | 2012-02-06 | 2012-02-06 | 2012-03-11 | 2012-03-12 | 2012-04-21 | 2012-04-21
3 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/W09-2012 | Dakalt and Other Branch Canals Rehabilitation Mit Yazid Command Area | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2011-06-05 |  | 2011-07-05 | 2011-08-04 | 2011-08-04 |  |  | 2011-09-03 | 2011-09-18 | 8994600 | EGP | Ahmed Abo Eleneen | 2012-03-16
[6 empty] | Revised |  |  |  |  | 2012-01-04: 2012-02-01; 2012-02-06: 2012-03-02; 2012-02-06: 2012-03-02; 2012-04-21: 2012-04-01; 2012-04-21: 2012-04-08
[6 empty] | Revised |  |  |  |  | 2011-05-02 | 2011-10-18 | 2012-01-04 | 2012-02-07 | 2012-02-07 | 2012-03-19 | 2012-03-20 | Tender Cancelled
[6 empty] | Revised |  |  |  |  | 2012-01-04: 2012-10-10; 2012-02-06: 2012-11-09; 2012-02-06: 2012-11-09; 2012-04-21: 2013-04-08; 2012-04-21: 2013-04-15
[6 empty] | Actual |  |  |  |  | 2011-05-02: 2012-03-19; 2011-10-18: 2012-03-20; 2012-01-04: Done; 2012-02-06: 2012-11-17; 2012-02-06: 2012-11-17 |  |  |  | 2014-03-29
[11 empty] | 2012-03-19 | 2012-03-20 | 2012-10-17 | 2012-11-17 | 2012-11-17 | 2013-03-17 | 2013-03-31 | 2013-04-30 | 2013-05-02
4 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/W10-A | NesheelEl Gedeeda and El Shoka Branch Canals Rehabilitation Mit Yazid Command Area | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-03-01 |  | 2012-03-31 | 2012-04-30 | 2012-04-30 |  |  | 2012-05-30 | 2012-06-06 | 2658275 | EGP | El Asar Office for contracting | 2013-11-30
[6 empty] | Revised |  |  |  |  | 2012-08-15 |  | 2012-09-14 | 2012-10-14 | 2012-10-14 |  |  | 2013-04-01 | 2013-04-08
[6 empty] | Actual |  |  |  |  | 2012-08-23 | 2012-09-12 | 2012-10-17 | 2012-11-18 | 2012-11-18 | 2012-12-16 | 2013-02-18 | 2013-04-01 | 2013-04-01
5 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/W10-B-2012 | Mars El Gamal and Other Canals Rehabilitation Mit Yazid Command Area | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-03-01 |  | 2012-03-31 | 2012-04-30 | 2012-04-30 |  |  | 2012-05-30 | 2012-06-06 | 1842968.89 | EGP | Al-Amro Office for Contracting | 2013-11-23
[6 empty] | Revised |  |  |  |  | 2012-09-15 |  | 2012-11-20 | 2012-12-20 | 2012-12-20 |  |  | 2013-03-29 | 2013-04-05
[6 empty] | Actual |  |  |  |  | 2012-10-04 | 2012-11-05 | 5/12/25012 | 2013-01-15 | 2013-01-15 | 2013-01-21 | 2013-02-18 | 2013-03-24 | 2013-03-24
6 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/W10-C-2012 | Koum EL Roz El Kadeema and Other Canals Rehabilitation Mit Yazid Command Area | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-03-01 |  | 2012-03-31 | 2012-04-30 | 2012-04-30 |  |  | 2012-05-30 | 2012-06-06 | 4417252 | EGP | Cooperative Socicty for Construction &Development | 2014-02-23
[6 empty] | Revised |  |  |  |  | 2012-09-10 |  | 2012-10-10 | 2012-11-09 | 2012-11-09 |  |  | 2013-03-24 | 2013-03-31
[6 empty] | Actual |  |  |  |  | 2012-09-05 | 2012-09-13 | 2012-10-17 | 2012-11-19 | 2012-11-19 | 2012-12-16 | 2013-02-18 | 2013-03-23 | 2013-03-24
7 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/W11-2012 | El Halafy and Other Branch Canals Rehabilitation Mit Yazid Command Area | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-03-01 |  | 2012-03-31 | 2012-04-30 | 2012-04-30 |  |  | 2012-05-30 | 2012-06-06 | 5111825 | EGP | el Amana for General Contracting | 2014-02-27
[6 empty] | Revised |  |  |  |  | 2012-09-15 |  | 2012-11-20 | 2012-12-20 | 2012-12-20 |  |  | 2013-04-01 | 2013-04-08
[6 empty] | Actual |  |  |  |  | 2012-10-04 | 2012-11-05 | 2012-12-07 | 2013-01-06 | 2013-01-06 | 2013-01-21 | 2013-03-04 | 2013-04-01 | 2013-04-01
Total ongoing contracts
Planned
SL No | District | Package reference No/ Contract No | Description of Works | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)

## Mesqa Improvement
Procurement Plan for Meska Improvement Rehabilitation Works (Meet Yazeed Area) | [24 empty] | Updated 12/12/2013
Arab republic of Egypt EGT-7291: Integrated Irrigation Improvement & Management Project Original:28/2/2008
Completed
SL No | District | Package reference No/ Contract No | Name in Arabic | Description of Works | Area (fed) | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date) | Nots
1 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-02-2009 |  | Meska Improvement Works for Bahr Nemra Left Side from Intake to the Km 4.8 | 990 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-10-01 | 2009-10-11 | 2009-06-27 | 2009-07-28 | 2009-07-28 | 2009-08-05 | 2009-08-19 | 2010-01-10 |  | 5229560 | EGP | Al-Amro Office for Contracting | 2010-07-09
[8 empty] | Revised |  |  |  |  | 2009-05-03 | 2009-03-19 | 2009-04-15 | 2009-05-15 | 2009-05-15 | 2009-10-10 | 2009-10-18 | 2009-11-18 |  |  |  |  | 2010-12-31
[8 empty] | Actual |  |  |  |  | 2009-04-28 | 2009-05-24 | 2009-06-27 | 2009-07-27 | 2009-07-27 | 2009-08-13 | 2009-08-17 | 2009-09-10 | 2009-09-10 |  |  |  | 2010-12-30
2 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-03-2009 |  | Meska Improvement Works for Bahr Nemra Right Side from Intake to the Km 4.8 | 1447 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-04-01 | 2009-04-11 | 2009-04-18 | 2009-05-19 | 2009-05-19 | 2009-06-19 | 2009-09-02 | 2009-09-14 |  | 7995413.3 | EGP | Al-Amro Office for Contracting | 2010-07-09
[8 empty] | Revised | [16 empty] | 2010-12-31
[8 empty] | Actual |  |  |  |  | 2009-04-30 | 2009-05-24 | 2009-06-27 | 2009-07-28 | 2009-07-28 | 2009-08-13 | 2009-08-19 | 2009-09-10 | 2009-09-10 |  |  |  | 2010-12-31
3 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-06-2009 |  | Mesqa Improvement Works in El Banawan Branch Canal - Left Side from the intake to the End | 1218 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-01-03 | 2010-01-13 | 2010-01-20 | 2010-02-21 | 2010-02-21 | 2010-03-21 | 2010-04-04 | 2010-04-18 |  | 7049083 | EGP | Al-Amro Office for Contracting | 2010-08-02
[8 empty] | Revised |  |  |  |  | 2009-05-24: 2009-08-23; 2009-07-28: 2009-10-12; 2009-08-13: 2009-10-26
[8 empty] | Actual |  |  |  |  | 2009-06-21 | 2009-06-23 | 2009-07-08 | 2009-08-09 | 2010-08-09 | 2009-08-23 | 2009-08-30 | 2009-10-03 | 2009-10-03 |  |  |  | 2010-07-19
4 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-09-2009 |  | Improvement of Mesqas and Delivery Works for Al Mohet canal (Sidi Gazi District - Kafr Elshiekh ) | 1001 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2012-06-01 |  | 2012-07-01 | 2012-07-31 | 2012-07-31 |  |  | 2012-08-30 | 2012-09-06 | 5283708 | EGP | Al-Amro Office for Contracting | 2010-12-25
[8 empty] | Revised |  |  |  |  | 2009-04-30: 2011-01-01; 2009-09-10: 2011-03-01 |  |  |  | 2011-02-25
[8 empty] | Actual |  |  |  |  | 2009-07-21 | 2009-08-23 | 2010-02-10 | 2010-03-10 | 2010-03-10 | 2010-03-21 | 2010-03-31 | 2010-04-26 | 2010-04-26 |  |  |  | 2011-02-25
5 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-10-2009 |  | Mesqa Improvement Works in Nesheel El-Kadima Branch Canal Right Bank from the Intake to the End | 1109 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-10-01 | 2009-10-12 | 2009-10-19 | 2009-11-19 | 2009-11-19 | 2009-12-19 | 2010-01-02 | 2010-01-22 |  | 7824367.2 | EGP | Abnaa Ahmed Hamed Samaha Company Alexandria | 2010-09-01
[8 empty] | Revised |  |  |  |  | 2009-08-23: 2009-08-30; 2010-03-10: 2009-10-18 |  |  |  | 2011-01-01
[8 empty] | Actual |  |  |  |  | 2009-08-13 | 2009-09-01 | 2009-09-12 | 2009-10-13 | 2009-10-13 | 2009-11-08 | 2009-11-23 | 2010-01-02 | 2010-01-02 |  |  |  | 2011-01-01
6 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-11-2009 |  | Meska Improvement Works in Neshil El-Kadima Branch canal Left bank from Km 8.145 to the end | 910 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-10-01 | 2009-10-12 | 2009-10-19 | 2009-11-19 | 2009-11-19 | 2009-12-19 | 2010-01-02 | 2010-01-22 |  | 5745916.8 | EGP | Al-Huda Company for Contracting | 2010-08-25
[8 empty] | Revised | [16 empty] | 2011-01-25
[8 empty] | Actual |  |  |  |  | 2009-08-13 | 2009-09-01 | 2009-09-12 | 2009-10-14 | 2009-10-14 | 2009-10-29 | 2009-11-23 | 2009-12-26 | 2009-12-26 |  |  |  | 2011-01-25
7 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-13-2009 |  | Mesqa Improvement Works for Waslet Nesheel and El-Shiekha Branch canals | 1028 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-10-01 | 2009-10-12 | 2009-10-19 | 2009-11-19 | 2009-11-19 | 2009-12-19 | 2010-01-02 | 2010-01-22 |  | 5494475 | EGP | Al-Amro Office for Contracting | 2010-09-19
[8 empty] | Revised | [16 empty] | 2011-01-19
[8 empty] | Actual |  |  |  |  | 2009-09-16 | 2009-10-18 | 2009-11-07 | 2009-12-06 | 2009-12-06 | 2009-12-27 | 2010-01-05 | 2010-01-20 | 2010-01-20 |  |  |  | 2011-01-19
8 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-14-2009 |  | Mesqa Improvement Works for Nesheel El-Kadima Branch canal Left bank from intake to Km 8.145 | 944 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-11-01 | 2009-11-12 | 2009-11-19 | 2009-12-20 | 2009-12-20 | 2010-01-20 | 2010-02-03 | 2010-02-17 |  | 5494892.6 | EGP | El- Aaser for Contracting | 2010-11-14
[8 empty] | Revised | [16 empty] | 2011-01-14
[8 empty] | Actual |  |  |  |  | 2009-11-22 | 2009-12-08 | 2009-12-22 | 2010-01-19 | 2010-01-19 | 2010-02-04 | 2010-02-21 | 2010-03-15 | 2010-03-15 |  |  |  | 2011-01-14
9 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-15-2009 |  | Mesqa Improvement Works for Bahr Nemra Branch canal left Bank from km. 4.800 to km 7.000 | 834 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-10-01 | 2009-10-11 | 2009-10-18 | 2009-11-19 | 2009-11-19 | 2009-12-19 | 2010-01-02 | 2010-01-14 |  | 3643182.5 | EGP | Adel Abdel Azez El- Shahawy Company | 2010-11-09
Revised
[8 empty] | Actual |  |  |  |  | 2009-11-18 | 2009-12-07 | 2009-12-22 | 2010-01-20 | 2010-01-20 | 2010-02-04 | 2010-02-21 | 2010-03-10 | 2010-03-10 |  |  |  | 2010-11-09
10 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-16-2009 |  | Mesqa Improvement Works for Direct Mit Yazid canal Right Bank from KM 12.480 to KM 19.900 | 978 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-05-03 | 2010-05-13 | 2010-05-20 | 2010-06-21 | 2010-06-21 | 2010-07-21 | 2010-08-04 | 2010-08-18 |  | 4352865 | EGP | Upper Egypt General Contracting Company | 2010-11-09
[8 empty] | Revised | [16 empty] | 2011-01-08
[8 empty] | Actual |  |  |  |  | 2009-11-18 | 2009-12-08 | 2009-12-21 | 2010-01-21 | 2010-01-21 | 2010-02-04 | 2010-02-21 | 2010-03-10 | 2010-03-10 |  |  |  | Completed
11 | Qotor | IIIMP/IIS/MTYZ/MQ-19-2010 |  | Mesqas Improvement Works for Direct Mit Yazid left Bank from KM 20.515 to KM 22.065 - Qptor District | 1215 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-03-01 | 2010-03-15 | 2010-03-31 | 2010-04-30 | 2010-04-30 |  |  | 2010-05-30 | 2010-06-06 | 5316344.82 | EGP | Al Amro Contracting Office Damanhour Egypt | 2011-02-25
[8 empty] | Revised | [16 empty] | 2011-03-25
[8 empty] | Actual |  |  |  |  | 2010-01-26 | 2010-02-25 | 2010-03-06 | 2010-04-06 | 2010-04-06 | 2010-05-09 | 2010-05-27 | 2010-06-26 | 2010-06-26 |  |  |  | 2011-03-14
12 | Desok | IIIMP/IIS/MTYZ/F/COM 1 2008 |  | Completion of improvement of Civil Works in Manaifa area (IIP-1) | 4127 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-03-01 |  | 2010-03-31 | 2010-04-30 | 2010-04-30 | 2010-05-10 | 2010-05-20 | 2010-05-30 | 2010-06-06 | 7194607.2 | EGP | Al-Amro Office for Contracting | 2010-03-09
[8 empty] | Revised |  |  |  |  | 2010-06-26: 2010-07-01
[8 empty] | Actual |  |  |  |  | 2008-08-26 | 2008-09-02 | 2008-10-26 | 2008-11-16 | 2008-11-16 | 2008-12-18 | 2009-02-11 | 2009-03-01 | 2009-03-10 |  |  |  | 2010-03-13
13 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-22-2010 |  | Mesqas Improvement Works for Mars El Gamle (RS) - from head to km 6.504 in Kafr El-Shiekh District | 972 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-03-01 | 2010-03-15 | 2010-03-25 | 2010-04-25 | 2010-04-25 | 2010-05-10 | 2010-05-20 | 2010-06-01 | 2010-06-10 | 4545531.76 | EGP | Dar El - Sahaba company | 2011-07-31
[8 empty] | Revised |  |  |  |  | 2008-08-26: 2010-10-01; 2009-03-01: 2010-11-01; 2009-03-10: 2010-11-15
[8 empty] | Actual |  |  |  |  | 2010-05-09 | 2010-05-13 | 2010-08-07 | 2010-09-21 | 2010-09-21 | 2010-10-05 | 2010-10-27 | 2010-12-01 | 2010-12-01 |  |  |  | 2011-07-30
14 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-24-2010 |  | Mesqa Improvement Works for Mars EL - Gamle (RS), from Km 6.686 to km 9.886 and in Kafr El-Morabin ,Kafr El-Shiekh District | 957 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-05-09: 2012-12-01; 2010-12-01: 2010-03-01 | 3990886.74 | EGP | Al-Amro Office for Contracting | 2011-07-31
[8 empty] | Revised |  |  |  |  | 2010-05-09: 2010-08-08; 2010-12-01: 2010-11-05; 2010-12-01: 2010-11-15 |  |  |  | 2013-07-31
[8 empty] | Actual |  |  |  |  | 2010-06-07 | 2010-06-28 | 2010-08-07 | 2010-09-23 | 2010-09-23 | 2010-10-05 | 2010-10-24 | 2010-12-01 | 2010-12-01 |  |  |  | 2013-03-28
15 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-25-2010 |  | Mesqa Improvement of Mars El Gamal Canal Left Bank from 3.835 km to 9.828 km - Mit Yazeed Command Area | 1446 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-09-01 |  | 2010-10-01 | 2010-10-31 | 2010-10-31 |  |  | 2010-11-30 | 2010-12-15 | 7654842 | EGP | Al-Amro Office for Contracting | 2012-03-25
[8 empty] | Revised |  |  |  |  | 2010-08-07: 2011-02-13; 2010-09-23: 2011-03-13; 2010-12-01: 2011-07-18 |  |  |  | 2012-10-25
[8 empty] | Revised |  |  |  |  | 2010-08-08 | 2010-09-22 | 2010-09-27 | 2010-11-08 | 2011-11-08 | 2011-01-09 | 2011-01-13 | Tender Cancelled |  |  |  |  | 2013-06-25
[8 empty] | Actual |  |  |  |  | 2010-09-21 | 2011-01-27 | 2011-01-22 | 2011-02-26 | 2011-02-26 | 2011-04-12 | 2011-06-21 | 2011-07-26 | 2011-07-26
16 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-32-2010 |  | Mesqa Improvement Works Contract for Kom Al - Roz Al- Kadeema Canal from Km 3.8 to end - Mit Yazeed Command Area Area | 1285 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-06-07: 2009-10-01; 2010-12-01: 2009-09-01 | 6759847.2 | EGP | Mansour Company for Trde& Contracting | 2012-02-14
[8 empty] | Revised |  |  |  |  | 2010-12-01 |  | 2010-12-24 | 2011-01-24 | 2011-01-24 |  |  | 2011-06-15 | 2011-06-15 |  |  |  | 2013-12-14
[8 empty] | Actual |  |  |  |  | 2010-10-24 | 2010-12-06 | 18-dec2010 | 2011-01-30 | 2011-01-30 | 2011-03-20 | 2011-04-13 | 2011-06-15 | 2011-06-15 |  |  |  | 2013-01-16
Total completed contracts |  |  |  |  | 12646
Ongoing
SL No | District | Package reference No/ Contract No | Name in Arabic | Description of Works | Area (fed) | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date) | Nots
1 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-01-2009 |  | Meska Improvement Works in Mit Yazid Direct from intake km 9.120 | 1144 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-10-01 | 2009-10-11 | 2009-10-18 | 2009-11-18 | 2009-11-18 | 2009-12-17 | 2009-12-31 | 2010-01-10 |  | 5495136 | EGP | Ali Youssry Company for Contracting | 2010-09-14
[8 empty] | Revised | [16 empty] | 2011-01-29
[8 empty] | Revised |  |  |  |  | 2010-12-01: Tender Cancelled
[8 empty] | Revised |  |  |  |  | 2010-12-01: Tender Cancelled |  |  |  | 2013-07-15
[8 empty] | Actual |  |  |  |  | 2009-02-05 | 2009-03-19 | 2009-08-29 | 2009-09-28 | 2009-09-28 | 2009-10-15 | 2009-10-29 | 2009-11-09 | 2009-11-15
2 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-04-2009 |  | Meska Improvement Works for Direct Mit Yazid canal Direct -Left side km 10.410 to KM 19.900 | 1524 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-11-01 | 2009-11-12 | 2009-11-19 | 2009-12-20 | 2009-12-20 | 2010-01-20 | 2010-02-03 | 2010-02-17 |  | 6789465 | EGP | Benass company for Constraction | 2010-10-04
[8 empty] | Revised |  |  |  |  | 2009-11-09: Tender Cancelled |  |  |  | 2013-09-05
[8 empty] | Actual |  |  |  |  | 2009-05-03 | 2009-05-27 | 2009-08-29 | 2009-09-26 | 2009-09-26 | 2009-10-26 | 2009-11-05 | 2009-12-15 | 2009-12-05
3 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-05-2009 |  | Meska Improvement Works in Bahr Nemra Branch Canal - Right Side from Km 4.8 to the end | 1071 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-01-03 | 2010-01-13 | 2010-01-20 | 2010-02-21 | 2010-02-21 | 2010-03-21 | 2010-04-04 | 2010-04-18 |  | 5766755 | EGP | Ali Youssry Company for Contracting | 2010-07-25
[8 empty] | Revised |  |  |  |  | 2009-11-15: 2009-09-26 |  |  |  | 2013-09-05
[8 empty] | Actual |  |  |  |  | 2009-06-21 | 2009-06-23 | 2009-07-08 | 2009-08-08 | 2009-08-08 | 2009-08-23 | 2009-08-30 | 2009-09-26 | 2009-12-03
4 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-07-2009 |  | Mesqa Improvement Works in El Banawan Branch canal Right Side | 1103 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-03-01 | 2010-03-11 | 2010-03-18 | 2010-04-18 | 2010-04-18 | 2010-05-18 | 2010-06-01 | 2010-06-15 |  | 4795585 | EGP | Benass company for Constraction | 2010-09-14
[8 empty] | Revised |  |  |  |  | 2009-08-08: 2009-10-13; 2009-08-23: 2009-10-26
[8 empty] | Revised |  |  |  |  | 2009-06-21 | 2009-06-23 | 2009-07-08 | 2009-08-08 | 2009-08-08 | 2009-10-15 |  | Tender Cancelled |  |  |  |  | 2013-09-05
[8 empty] | Actual |  |  |  |  | 2009-06-21 | 2009-06-23 | 2009-08-29 | 2009-09-27 | 2009-09-27 | 2009-10-15 | 2009-10-29 | 2009-11-12 | 2009-11-15
5 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-08-2009 |  | Mesqa Improvement Works in Khadiga Branch canal | 1305 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-10-01 | 2009-10-12 | 2009-10-29 | 2009-11-19 | 2009-11-19 | 2009-12-19 | 2010-01-02 | 2010-01-22 |  | 7628525 | EGP | Ali Youssry Company for Contracting | 2010-08-25
[8 empty] | Revised |  |  |  |  | 2009-06-23: 2009-09-01; 2009-09-27: 2009-10-14 |  |  |  | 2013-09-05
[8 empty] | Actual |  |  |  |  | 2009-07-11 | 2009-08-23 | 2009-09-12 | 2009-10-12 | 2009-10-12 | 2009-11-08 | 2009-11-23 | 2009-12-26 | 2009-12-26
6 | Gharb El-Mahalla | IIIMP/IIS/MTYZ/MQ-12-2009 |  | Meska Improvement Works in Nesheel El-Gadida Branch canal from Head to the End | 960 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-02-06 | 2010-02-13 | 2010-02-20 | 2010-03-23 | 2010-03-23 | 2010-04-22 | 2010-05-02 | 2010-05-15 |  | 4858162 | EGP | Ali Youssry Company for Contracting | 2010-09-30
[8 empty] | Revised | [16 empty] | 2013-09-05
[8 empty] | Actual |  |  |  |  | 2009-09-01 | 2009-10-18 | 2009-11-07 | 2009-12-05 | 2009-12-05 | 2009-12-27 | 2010-01-05 | 2010-02-01 | 2010-02-01
7 | Qotor | IIIMP/IIS/MTYZ/MQ-17-2009 |  | Mesqas Improvement Works for Direct Mit Yazid -Right Bank- from KM 20.530 to KM 26.340 (Qotor District) | 823 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-06-03 | 2010-06-13 | 2010-06-20 | 2010-07-21 | 2010-07-21 | 2010-08-21 | 2010-09-04 | 2010-09-18 | 2010-05-01 | 3235810 | EGP | Upper Egypt General Contracting Company | 2011-01-25
[8 empty] | Revised |  |  |  |  | 2010-01-05: 2010-05-16 |  |  |  | 2013-09-25
[8 empty] | Actual |  |  |  |  | 2009-12-23 | 2010-01-10 | 2010-01-31 | 2010-02-28 | 2010-02-28 | 2010-03-11 | 2010-05-06 | 2010-05-26 | 2010-05-26
8 | Qotor | IIIMP/IIS/MTYZ/MQ-18-2009 |  | Mesqas Improvement Works for Direct Mit Yazid -left Bank- from KM 20.270 to KM 20.500 | 986 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-07-03 | 2010-07-13 | 2010-07-20 | 2010-08-21 | 2010-08-21 | 2010-09-21 | 2010-10-04 | 2010-10-18 | 2010-05-01 | 4298790 | EGP | Upper Egypt General Contracting Company | 2011-01-25
[8 empty] | Revised | [5 empty] | 2010-03-02 | 2010-03-06 | 2010-04-08 | 2010-04-08 | 2010-05-09 | 2010-05-16 |  | 2010-05-01 |  |  |  | 2013-11-25
[8 empty] | Actual |  |  |  |  | 2009-12-30 | 2010-01-24 | 2010-01-31 | 2010-03-01 | 2010-03-01 | 2010-03-11 | 2010-05-06 | 2010-05-26 | 2010-05-26
9 | Qotor | IIIMP/IIS/MTYZ/MQ-20-2010 |  | Mesqas Improvement Works for Mit Yazid Dir Right Bank from KM 31.580 to KM 32.610 - Qotor District | 1357 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2009-02-05 | 2009-03-19 | 2009-04-15 | 2009-05-16 | 2009-05-16 | 2009-10-10 | 2009-10-18 | 2009-11-18 |  | 7123249.5 | EGP | Al Amro Contracting Office Damanhour Egypt | 2011-05-14
[8 empty] | Revised | [16 empty] | 2013-12-14
[8 empty] | Actual |  |  |  |  | 2010-02-04 | 2010-02-25 | 2010-03-06 | 2010-04-07 | 2010-04-07 | 2010-05-09 | 2010-08-12 | 2010-09-15 | 2010-09-15
10 | Qotor | IIIMP/IIS/MTYZ/MQ-21-2010 |  | Mesqa Improvement Works for Mit Yazid Dir (LS) from KM 24.780 - KM 26.650 in Qotor District | 1082 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2008-06-17 | 2008-06-27 | 2008-07-27 | 2008-08-27 | 2008-08-27 | 2008-10-27 | 2008-11-25 | 2008-12-17 |  | 6054433.75 | EGP | Al-Amro Office for Contracting | 2011-07-30
[8 empty] | Revised |  |  |  |  | 2010-02-04: 2010-07-01; 2010-09-15: 2010-11-30
[8 empty] | Revised |  |  |  |  | 2010-02-23 | 2010-03-02 | 2010-03-06 | 2010-04-08 | 2010-04-08 | 2010-05-09 | 2010-07-21 | Tender Cancelled |  |  |  |  | 2013-10-31
[8 empty] | Actual |  |  |  |  | 2010-02-23 | 2010-07-21 | 2010-08-07 | 2010-09-07 | 2010-09-07 | 2010-11-08 | 2010-11-10 | 2010-12-01 | 2010-12-01
11 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-23-2010 |  | Mesqa Improvement Works for Mars El- Gamle (LS)- from head to km 3.439 and kafr El-Morabin in Kafr El-Shiekh District | 1040 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-02-23: 2012-11-01; 2010-12-01: 2010-02-01 | 4436071.15 | EGP | Egyptian Contracting Company (Mokhtar Ibrahim) | 2011-07-31
[8 empty] | Revised |  |  |  |  | 2010-02-23: 2010-06-06; 2010-12-01: 2010-11-01; 2010-12-01: 2010-11-02 |  |  |  | 2013-10-31
[8 empty] | Actual |  |  |  |  | 2010-06-07 | 2010-06-23 | 2010-08-07 | 2010-09-22 | 2010-09-22 | 2010-10-05 | 2010-10-25 | 2010-12-01 | 2010-12-01
12 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-26-2010 |  | Mesqa Improvement Works Contract for Al- Mafrooza- Right Bank and Al Mafrooza AL Sharkia canal - Mit Yazeed Command Area | 1048 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-06-07: 2010-09-01; 2010-12-01: 2010-12-01 | 4327417.15 | EGP | Adel Abdel Azez El- Shahawy Company | 2012-04-14
[8 empty] | Revised |  |  |  |  | 2010-06-07: 2011-01-01; 2010-08-07: 2011-02-13; 2010-09-22: 2011-03-13; 2010-12-01: 2011-07-15 |  |  |  | 2012-10-14
[8 empty] | Revised |  |  |  |  | 2010-08-08 | 2010-09-22 | 2010-09-27 | 2010-11-09 | 2010-11-09 | 2011-01-09 | 2011-01-13 | Tender Cancelled |  |  |  |  | 2013-11-14
[8 empty] | Actual |  |  |  |  | 2010-09-21 | 2011-01-27 | 2011-01-22 | 2011-02-27 | 2011-02-27 | 2011-05-10 | 2011-07-11 | 2011-08-15 | 2011-08-15
13 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-27-2010 |  | Mesqa Improvement Works Contract for Al- Mafrooza- left Bank and Al Mafrooza AL Gadeeda - Mit Yazeed Command Area | 979 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-06-07: 2010-09-01; 2010-12-01: 2010-12-01 | 3867722.72 | EGP | Al-Amro Office for Contracting | 2012-04-14
[8 empty] | Revised |  |  |  |  | 2010-08-07: 2011-02-13; 2010-09-22: 2011-03-13; 2010-12-01: 2011-07-15 |  |  |  | 2013-02-14
[8 empty] | Revised |  |  |  |  | 2010-08-08 | 2010-09-22 | 2010-09-27 | 2010-11-10 | 2010-11-10 | 2011-01-09 | 2011-01-13 | Tender Cancelled |  |  |  |  | 2013-11-14
[8 empty] | Actual |  |  |  |  | 2010-09-21 | 2011-01-27 | 2011-01-22 | 2011-02-28 | 2011-02-28 | 2011-04-12 | 2011-07-12 | 2011-08-15 | 2011-08-15
14 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-28-2010 |  | Mesqa Improvement Works Contract for Al Bashair canal - Branch from Mars El Gamal canal - Mit Yazeed Command Area | 1464 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-06-07: 2010-09-01; 2010-12-01: 2010-12-01 | 6078248.7 | EGP | Dar El - Sahaba company | 2012-03-09
[8 empty] | Revised |  |  |  |  | 2010-06-07: 2011-03-01; 2010-08-07: 2011-02-13; 2010-09-22: 2011-03-13; 2010-12-01: 2011-07-15 |  |  |  | 2012-11-09
[8 empty] | Revised |  |  |  |  | 2010-08-08 | 2010-09-22 | 2010-09-27 | 2010-11-11 | 2010-11-11 | 2011-01-09 | 2011-01-13 | Tender Cancelled |  |  |  |  | 2013-11-09
[8 empty] | Actual |  |  |  |  | 2010-09-21 | 2011-01-27 | 2011-01-22 | 2011-03-01 | 2011-03-01 | 2011-04-12 | 2011-06-20 | 2011-07-10 | 2011-07-10
15 | Kafr El Sheikh | IIIMP/IIS/MTYZ/MQ-29-2010 |  | Mesqa Improvement Works Contract for El Shorafa canal and direct El Zawia from km 5.963 to 6.252 km | 1084 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-06-07: 2011-01-01; 2010-12-01: 2011-04-01 | 5717101.15 | EGP | Al-Amro Office for Contracting | 2011-11-04
[8 empty] | Revised |  |  |  |  | 2011-02-01 |  | 2010-12-05 | 2011-01-05 | 2011-01-05 |  |  | 2011-03-01 | 2011-03-08 |  |  |  | 2013-11-04
[8 empty] | Actual |  |  |  |  | 2010-09-22 | 2010-11-02 | 2010-11-10 | 2011-01-09 | 2011-01-09 | 2011-01-18 | 2011-01-23 | 2011-01-30 | 2011-03-05
16 | Kafr El Shiekh | IIIMP/IIS/MTYZ/MQ-30-2010 |  | Meska Improvement Works contracts for Kom El Roz El Kadima from intake to km 3.80 and Tahwelet Kom El Roz El Kadima canal | 1143 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-09-22: 2011-10-01; 2011-01-30: 2011-12-30; 2011-03-05: 2012-01-06 | 5773506.76 | EGP | Al-Amro Office for Contracting | 2011-11-04
[8 empty] | Revised |  |  |  |  | 2010-11-10: 2010-12-05; 2011-01-09: 2011-01-05; 2011-01-09: 2011-01-05; 2011-03-05: 2011-03-01 |  |  |  | 2013-11-04
[8 empty] | Actual |  |  |  |  | 2010-09-22 | 2010-11-04 | 2010-11-10 | 2011-01-10 | 2011-01-10 | 2011-01-18 | 2011-01-23 | 26-Fer-2011 | 2011-03-05
17 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-31-2010 |  | Mesqa Improvement Works Contract for Al - Shamarqa Al- Gededa Canal - Mit Yazeed Command Area | 1039 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-09-22: 2012-10-01; 2011-01-30: 2011-01-01 | 5086437.15 | EGP | Egyptian Contracting Company (Mokhtar Ibrahim) | 2012-02-14
[8 empty] | Revised | [5 empty] | 2010-10-30 | 2010-12-05 | 2011-01-05 | 2011-01-05 |  |  | 2011-06-15 | 2011-06-15 |  |  |  | 2013-12-14
[8 empty] | Actual |  |  |  |  | 2010-10-24 | 2010-11-09 | 18-dec2010 | 2011-01-29 | 2011-01-29 | 2011-03-20 | 2011-04-12 | 2011-06-15 | 2011-06-15
18 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-33-2010 | تطوير المساقى على ترعة كوم الرز الجديدة بهندسة كفر الشيخ - ترعة ميت يزيد | Mesqa Improvement Works Contract for Kom EL - Roz EL - Gedida Canal - Mit Yazeed Command Area | 1780 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-01-01 |  | 2012-01-31 | 2012-03-01 | 2012-03-01 |  |  | 2012-03-31 | 2012-04-07 | 10145056.52 | EGP | Cooperative Socicty for Construction &Development | 2014-08-21
[5 empty] | 1360 |  |  | Revised |  |  |  |  | 2011-01-01 |  | 2013-03-13 | 2013-04-12 | 2013-04-12 | 2013-05-29 | 2013-06-12 | 2013-06-26 | 2013-07-03
[8 empty] | Actual |  |  |  |  | 2013-01-16 | 2013-02-26 | 2013-04-08 | 2013-05-08 | 2013-05-08 |  | 2013-06-27 | Tender Cancelled
[13 empty] | 2013-07-07 | 2013-07-11 | 2013-07-18 | 2013-08-18 | 2013-08-18 | 2013-09-09 | 2013-09-19 | 2013-10-22 | 2013-10-22
19 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-34-2010 |  | Mesqa Improvement Works Contract for Al - Gnabia 2 canal the Right side of Al Zawia Canal - Mit Yazeed Command Area | 752 | NCB | IBRD (90%)GoE (10%) | Revised |  |  | Post | No | 2013-07-07: 2010-12-01; 2013-10-22: 2012-04-01; 2013-10-22: 2012-04-07 | 5544402.5 | EGP | Cooperative Socicty for Construction &Development | 2012-12-03
[8 empty] | Actual |  |  |  |  | 2010-11-09 | 2010-12-12 | 2011-07-25 | 2011-08-23 | 2011-08-23 | 2012-04-05 | 2012-04-09 | Tender Cancelled
[8 empty] | Revised | [6 empty] | 2013-03-13 | 2013-04-12 | 2013-04-12 | 2013-05-30 | 2013-06-13 | 2013-06-27 | 2013-07-04 |  |  |  | 2014-03-05
[8 empty] | Actual |  |  |  |  | 2013-01-16 | 2013-02-26 | 2013-04-08 | 2013-05-09 | 2013-05-09 |  |  | Tender Cancelled
[13 empty] | 2013-07-07 | 2013-07-11 |  |  |  | 2013-09-09 |  | Tender Cancelled
[13 empty] | 2013-09-09 | 2013-09-17 | 2013-09-25 | 2013-10-27 | 2013-10-27 | 2013-12-05 | 2013-12-12
20 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-36-2012 | تطوير المساقى على الجانبية 3&4 بر ايمن ترعة الزاوية من ك 1.300 للنهاية | Meska Improvement Works for Kafr El Sheekh 15 on El Ganabiet (3) RS El Zawiet from km 1.300m until the end and El Ganabiet | 918.2 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2011-11-01 |  | 2011-01-01 | 2011-02-01 | 2011-02-01 |  |  | 2012-02-01 | 2012-02-16 | 6229337.3 | EGP | Al-Amro Office for Contracting | 2012-10-13
[8 empty] | Revised |  |  |  |  | 2013-03-08 |  | 2013-03-14 | 2013-04-13 | 2013-04-13 | 2013-06-02 | 2013-06-16 | 2013-06-30 | 2013-07-07 |  |  |  | 2014-03-08
[8 empty] | Actual |  |  |  |  | 2013-01-16 | 2013-02-27 | 2013-04-08 | 2013-05-12 | 2013-05-12 |  |  | Tender Cancelled
[13 empty] | 2013-07-07 | 2013-07-11 | 2013-07-18 | 2013-08-20 | 2013-08-20 | 2013-09-09 |  | Tender Cancelled
[13 empty] | 2013-09-09 | 2013-09-17 | 2013-09-25 | 2013-10-28 | 2013-10-28 | 2013-12-05 | 2013-12-12
21 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-37-2012 |  | Meska Improvement Works for Sidi Gazy 2 on El Halafey canal LS from km 6.00 | 910.1 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2010-12-26 |  | 2011-11-20 | 2011-12-20 | 2011-12-20 |  |  | 2012-01-19 | 2012-01-26 | 5578886 | EGP | Al-Amro Office for Contracting | 2014-08-26
[8 empty] | Revised |  |  |  |  | 2013-03-10 |  | 2013-03-18 | 2013-04-17 | 2013-04-17 | 2013-06-03 | 2013-06-17 | 2013-07-01 | 2013-07-08
[8 empty] | Actual |  |  |  |  | 2013-01-16 | 2013-03-03 | 2013-04-08 | 2013-05-13 | 2013-05-13 |  | 2013-06-27 | Tender Cancelled
[8 empty] | Actual |  |  |  |  | 2013-07-07 | 2013-07-11 | 2013-07-18 | 2013-08-21 | 2013-08-21 | 2013-09-09 | 2013-09-19 |  | 2013-10-27
22 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-38-2013 |  | Meska Improvement Works for Sidi Gazy 3 on El Halafey canal LS from km 6.00 until km 7.500 | 648 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2010-12-26 |  | 2011-11-20 | 2011-12-20 | 2011-12-20 |  |  | 2012-01-19 | 2012-01-26 | 5354243.6 | EGP | khtab & Sawahly for General Contracting | 2012-09-22
[8 empty] | Revised |  |  |  |  | 2013-03-12 |  | 2013-05-10 | 2013-06-09 | 2013-06-09 | 2013-06-30 | 2013-07-14 | 2013-07-28 | 2013-08-04 |  |  |  | 2014-04-05
[8 empty] | Actual |  |  |  |  | 2013-04-17 | 2013-04-24 | 2013-05-29 | 2013-07-07 | 2013-07-07 |  |  | 2013-10-27
23 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-42-2013 |  | Meska Improvement Works for Sidi Gazy 6 on RS El Halafey from intake to km 6.950 | 622 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-01-01 |  | 2012-01-31 | 2012-03-01 | 2012-03-01 |  |  | 2012-03-31 | 2012-04-07 | 4088367.05 | EGP | Cooperative Socicty for Construction &Development | 2012-12-03 | El Halafy Right Side from Intak to km5.800
[8 empty] | Revised |  |  |  |  | 2013-03-25 |  | 2013-05-12 | 2013-06-11 | 2013-06-11 | 2013-07-02 | 2013-07-16 | 2013-07-30 | 2013-08-06 |  |  |  | 2014-04-06
[8 empty] | Actual |  |  |  |  | 2013-04-17 | 2013-04-24 | 2013-05-29 | 2013-07-08 | 2013-07-08 | 2013-07-25 | 2013-08-06 | 2013-09-15 | 2013-09-15
24 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-43 |  | Meska Improvement Works for Sidi Gazy 7 on RS El Halafey from km 5.800 until km 9.490 | 926 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-01-01 |  | 2012-01-31 | 2012-03-01 | 2012-03-01 |  |  | 2012-03-31 | 2012-04-07 | 8517480 | EGP | khtab & Sawahly for General Contracting | 2014-09-09 | El Halafy Right Side from km5.800 to km 9.490
[8 empty] | Revised |  |  |  |  | 2013-03-27 |  | 2013-04-26 | 2013-05-26 | 2013-05-26 | 2013-06-13 | 2013-06-27 | 2013-07-11 | 2013-07-18
[8 empty] | Actual |  |  |  |  | 2013-03-20 | 2013-04-01 | 2013-04-23 | 2013-05-23 | 2013-05-23 | 2013-07-08 | 2013-07-11 | Tender Cancelled
[8 empty] | Actual |  |  |  |  | 2013-07-08 | 2013-07-11 | 2013-07-24 | 2013-08-25 | 2013-08-25 | 2013-09-15 | 2013-09-24 | Done | 2013-11-10
25 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-44/2012 | تطوير مساقى ترعة الحلافى بر ايمن من ك 9.490 الى ك 14.445 ترعة ميت يزيد - كفر الشيخ | El Halafey canal LS from km 9,940 to km 14,445 | 1328 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Prior | No | 2012-01-15 |  | 2012-02-14 | 2012-03-15 | 2012-03-15 |  |  | 2012-04-14 | 2012-04-21 | 6972726.9 | EGP | Dar El - Sahaba company | 2014-01-16
[8 empty] | Revised |  |  |  |  | 2012-11-01 |  | 2012-12-01 | 2012-12-31 | 2012-12-31 |  |  | 2013-01-30 | 2013-02-06
[8 empty] | Actual |  |  |  |  | 2012-09-05 | 2012-09-13 | 2012-10-17 | 2012-11-20 | 2012-11-20 | 2013-01-16 | 2013-02-09 | 2013-03-17 | 2013-03-17
26 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-45-2013 | تطوير المساقى على الترعة الحلافى بر ايسر من ك 14.914 للنهاية بمركز سيدى غازى رقم 9 | Meska Improvement Works for Sidi Gazy 9 on El Halafy canal RS from K 14,914 until end | 1665 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-02-01 |  | 2012-03-02 | 2012-04-01 | 2012-04-01 |  |  | 2012-05-01 | 2012-05-08 | 12635247 | EGP | Dar El - Sahaba company | 10 month contract
[8 empty] | Revised |  |  |  |  | 2013-03-01 |  | 2013-03-15 | 2013-04-14 | 2013-04-14 | 2013-06-04 | 2013-06-18 | 2013-07-02 | 2013-07-09
[8 empty] | Actual |  |  |  |  | 2012-11-27 | 2013-02-28 | 2013-04-08 | 2013-05-14 | 2013-05-14 |  |  | Tender Cancelled
[8 empty] | Actual |  |  |  |  | 2013-07-07 | 2013-07-11 | 2013-07-18 | 2013-08-22 | 2013-08-22 | 2013-09-09 | 2013-09-19
27 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-47-2012 | تطوير مساقى ترعة الحلافى بر ايسر من ك 13.500 الى ك 17.435 ترعة ميت يزيد - كفر الشيخ | El Halafey canal LS from km 13,500 to km 17,435 | 1436 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Prior | No | 2012-02-15 |  | 2012-03-16 | 2012-04-15 | 2012-04-15 |  |  | 2012-05-15 | 2012-05-22 | 9322364.8 | EGP | Dar El - Sahaba company | 2014-01-16
[8 empty] | Revised |  |  |  |  | 2013-01-01 |  | 2013-01-31 | 2013-03-02 | 2013-03-02 |  |  | 2013-04-01 | 2013-04-08
[8 empty] | Actual |  |  |  |  | 2012-09-05 | 2012-09-13 | 2012-10-17 | 2012-11-21 | 2012-11-21 | 2012-12-24 | 2013-02-09 | 2013-03-17 | 2013-03-17
28 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-48-2013 |  | Meska Improvement Works for Sidi Gazy 12 on LS El Halafey from km 17.435 until the end | 831 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-02-15 |  | 2012-03-16 | 2012-04-15 | 2012-04-15 |  |  | 2012-05-15 | 2012-05-22 | 6815595.4 | EGP | Dar El - Sahaba company | 10 month contract
[8 empty] | Revised |  |  |  |  | 2013-03-05 |  | 2013-04-04 | 2013-05-04 | 2013-05-04 | 2013-06-16 | 2013-06-30 | 2013-07-14 | 2013-07-21
[8 empty] | Actual |  |  |  |  | 2013-03-20 | 2013-04-01 | 2013-04-23 | 2013-05-26 | 2013-05-26 | 2013-07-08 | 2013-07-11 | Tender Cancelled
[8 empty] | Actual |  |  |  |  | 2013-07-08 | 2013-07-11 | 2013-07-24 | 2013-08-26 | 2013-08-26 | 2013-09-15 | 2013-09-24 | 2013-10-27 | Done
29 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-49 |  | Meska Improvement Works for Sidi Gazy 13 on LS El Marbet from km 5.580 + El Melaha | 1153 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-02-20 |  | 2012-03-21 | 2012-04-20 | 2012-04-20 |  |  | 2012-05-20 | 2012-05-27 | 9955112.32 | EGP | Al-Amro Office for Contracting | 2014-08-26
[8 empty] | Revised |  |  |  |  | 2013-03-05 |  | 2013-07-14 | 2013-08-13 | 2013-08-13 | 2013-09-03 | 2013-09-17 | 2013-10-01 | 2013-10-08
[8 empty] | Actual |  |  |  |  | 2013-05-12 | 2013-06-09 | 2013-07-10 | 2013-08-12 | 2013-08-12 | 2013-08-26 |  | 2013-10-27 | 2013-10-27
30 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-50 |  | Meska Improvement Works for Sidi Gazy 14 on LS El Marbet from km 5.580 until the end + El Sant | 1073 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-03-03 |  | 2012-04-02 | 2012-05-02 | 2012-05-02 |  |  | 2012-06-01 | 2012-06-08 | 8770645.6 | EGP | Al-Amro Office for Contracting | 10 month contract
[8 empty] | Revised |  |  |  |  | 2013-04-01 |  | 2013-07-15 | 2013-08-14 | 2013-08-14 | 2013-09-04 | 2013-09-18 | 2013-10-02 | 2013-10-09
[8 empty] | Actual |  |  |  |  | 2013-05-12 | 2013-06-09 | 2013-07-10 | 2013-08-13 | 2013-08-13 | 2013-08-26 | 2013-09-01 | Tender Cancelled
[8 empty] | Actual |  |  |  |  | 2013-08-26 | 2013-09-01 | 2013-09-25 | 2013-10-29 | 2013-10-29 | 2013-12-05 | 2013-12-12
31 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-54 |  | Meska Improvement Works for Sidi Gazy 18 on LS El Daramly from intake until km 3.500 | 1130 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-21 |  | 2013-04-20 | 2013-05-20 | 2013-05-20 |  |  | 2013-06-19 | 2013-06-26 | 10985850.88 | EGP | Al-Amro Office for Contracting | 2014-08-26
[8 empty] | Revised |  |  |  |  | 2012-12-24: 2013-06-17; 2013-02-09: 2013-07-01; 2013-03-17: 2013-07-15; 2013-03-17: 2013-07-22
[8 empty] | Actual |  |  |  |  | 2013-03-20 | 2013-04-01 | 2013-04-23 | 2013-05-27 | 2013-05-27 | 2013-07-08 | 2013-07-11 | Tender Cancelled
[13 empty] | 2013-07-08 | 2013-07-11 | 2013-07-24 | 2013-08-27 | 2013-08-27 |  | 2013-09-26 | 2013-10-27 | 2013-10-27
32 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-55 |  | Meska Improvement Works for Sidi Gazy 19 on LS El Daramly from km 4.800 until km 7.400 | 1063 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-04-09 |  | 2013-05-09 | 2013-06-08 | 2013-06-08 | 2013-06-24 | 2013-07-01 | 2013-07-08 | 2013-07-15 | 9198069.95 | EGP | khtab & Sawahly for General Contracting | 2014-03-14
Revised
[8 empty] | Actual |  |  |  |  | 2013-04-17 | 2013-04-24 | 2013-05-29 | 2013-07-09 | 2013-07-09 | 2013-07-25 | 2013-08-06
33 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-56 |  | Meska Improvement Works for Sidi Gazy 20 on LS El Daramly from km7.527 until the end | 1314 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-04-17 |  | 2013-05-17 | 2013-06-16 | 2013-06-16 | 2013-07-02 | 2013-07-09 | 2013-07-16 | 2013-07-23 | 12602131 | EGP | Cooperative Socicty for Construction &Development | 2014-08-14
Revised
[8 empty] | Actual |  |  |  |  | 2013-04-17 | 2013-04-24 | 2013-05-29 | 2013-07-10 | 2013-07-10 | 2013-07-25 | 2013-08-06 | 2013-09-15 | 2013-09-15
34 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-57 |  | Meska Improvement Works for Sidi Gazy 21 on RS El Daramly from intake to km 6.300 | 1086 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-04-22 |  | 2013-05-22 | 2013-06-21 | 2013-06-21 | 2013-07-07 | 2013-07-14 | 2013-07-21 | 2013-07-28 | 9438540 | EGP | El safa company for Contracting | 2014-03-27
[8 empty] | Revised | [6 empty] | 2013-07-15 | 2013-08-14 | 2013-08-14 | 2013-09-04 | 2013-09-18 | 2013-10-02 | 2013-10-09 |  |  |  | 2014-06-08
[8 empty] | Actual |  |  |  |  | 2013-05-12 | 2013-06-09 | 2013-07-10 | 2013-08-14 | 2013-08-14 | 2013-09-02 | 2013-09-16
35 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-58 |  | Meska Improvement Works for Sidi Gazy 22 on RS El Daramly from km 6.300 to the end | 1353 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-04-22 |  | 2013-05-22 | 2013-06-21 | 2013-06-21 | 2013-07-07 | 2013-07-14 | 2013-07-21 | 2013-07-28 | 11769915.7 | EGP | Eliet for Contracting | 2014-03-27
[8 empty] | Revised | [6 empty] | 2013-07-15 | 2013-08-14 | 2013-08-14 | 2013-09-04 | 2013-09-18 | 2013-10-02 | 2013-10-09 |  |  |  | 2014-06-08
[8 empty] | Actual |  |  |  |  | 2013-05-12 | 2013-06-09 | 2013-07-10 | 2013-08-15 | 2013-08-15 | 2013-09-02 | 2013-09-16 | 2013-11-03
Total ongoing contracts |  |  |  |  | 31497.3
Planned
SL No | District | Package reference No/ Contract No | Name in Arabic | Description of Works | Area (fed) | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date) | Nots
1 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-35-2010 |  | Mesqa Improvement Works Contract for Al Ganabia 3 and its Branch Canal the Right Side of EL Zawia Canal from head to km 1.300 - Mit Yazeed Command Area | 1458 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-11-01 |  | 2011-07-25 | 2011-08-24 | 2011-08-24 |  |  | 2011-11-23 | 2011-11-30 |  | EGP |  | 2012-07-27
|  | Contract MTYZ/MQ-21 moved to | [5 empty] | Revised |  |  |  |  | 2013-05-12: 2010-12-01; 2013-11-03: 2012-04-01 | 2012-04-07 |  |  |  | 2012-12-03
|  | this area | [5 empty] | Actual |  |  |  |  | 2010-11-09 | 2010-12-12 | 2011-07-25 | 2011-08-24 | 2011-08-24 | 2012-04-05 | 2012-04-09 | Tender Cancelled
2 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-39- |  | Meska Improvement Works for Sidi Gazy 4 | 1359.6 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2011-02-01 |  | 2011-11-20 | 2011-12-20 | 2011-12-20 |  |  | 2012-01-19 | 2012-01-26 |  |  |  | 2012-09-22
[8 empty] | Revised |  |  |  |  | 2013-10-01 |  | 2013-06-10 | 2013-07-10 | 2013-07-10 | 2013-07-31 | 2013-08-14 | 2013-08-28 | 2013-09-04 |  |  |  | 2014-05-06
Actual
3 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-40 |  | Meska Improvement Works for Kafr El Sheekh 16 | 1150 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-01-01 |  | 2012-01-31 | 2012-03-01 | 2012-03-01 |  |  | 2012-03-31 | 2012-04-07 |  |  |  | 2012-12-03 | Ganabia(2-3-4-5-6) El Zawia+El Zaker Left Side
[8 empty] | Revised |  |  |  |  | 2014-04-01 |  | 2014-06-05 | 2014-07-05 | 2014-07-05 | 2014-07-26 | 2014-08-09 | 2014-08-23 | 2014-08-30 |  |  |  | 2015-04-29
Actual
4 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-41 |  | Meska Improvement Works for Kafr El Sheekh 17 | 1250 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-01-01 |  | 2012-01-31 | 2012-03-01 | 2012-03-01 |  |  | 2012-03-31 | 2012-04-07 |  |  |  | 2012-12-03 | El Zawia Direct from km 17.5 to End
[8 empty] | Revised |  |  |  |  | 2014-04-15 |  | 2014-06-19 | 2014-07-19 | 2014-07-19 | 2014-08-09 | 2014-08-23 | 2014-09-06 | 2014-09-13 |  |  |  | 2015-05-15
Actual
PS
The Area of Contract No. IIIMP/IIS/MTYZ/MQ-35-2010 is now implemented under the Contract No. IIIMP/IIS/MTYZ/21 /2010, as the area of Contract 21 was disputed by the farmers.
5 | Kafr El-Sheikh | IIIMP/IIS/MTYZ/MQ-46 |  | Meska Improvement Works for Kafr El Sheekh 18 | 950 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-02-01 |  | 2012-03-02 | 2012-04-01 | 2012-04-01 |  |  | 2012-05-01 | 2012-05-08 |  |  |  | 2013-01-03
[8 empty] | Revised |  |  |  |  | 2014-05-01 |  | 2014-07-05 | 2014-08-04 | 2014-08-04 | 2014-08-25 | 2014-09-08 | 2014-09-22 | 2014-09-29 |  |  |  | 2015-05-31
Actual
6 | Garb El Mahala | IIIMP/IIS/MTYZ/MQ-70 |  | Meska Improvement Works for Gharb El Mahala | 950 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2014-06-01 |  | 2014-07-01 | 2014-07-31 | 2014-07-31 |  |  | 2014-08-30 | 2014-09-06 |  |  |  | 2015-05-04
Revised
Actual
7 | Various | IIIMP/IIS/MTYZ/IIP1-MQ-01 |  | First Meska Improvement Works at IIP1 Area |  | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-01-01 |  | 2012-01-31 | 2012-03-01 | 2012-03-01 |  |  | 2012-03-31 | 2012-04-07 |  |  |  | 2012-12-03
[8 empty] | Revised |  |  |  |  | 2014-10-01 |  | 2014-10-31 | 2014-11-30 | 2014-11-30 | 2014-12-21 | 2015-01-04 | 2015-01-18 | 2015-01-25 |  |  |  | 2015-09-23
Actual
8 | Various | IIIMP/IIS/MTYZ/IIP1-MQ-02 |  | Second Meska Improvement Works at IIP1 Area |  | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-03-01 |  | 2012-03-31 | 2012-04-30 | 2012-04-30 |  |  | 2012-05-30 | 2012-06-06 |  |  |  | 2013-02-01
[8 empty] | Revised |  |  |  |  | 2013-04-01 |  | 2013-05-01 | 2013-05-31 | 2013-05-31 | 2013-06-21 | 2013-07-05 | 2013-07-19 | 2013-07-26 |  |  |  | 2014-03-25
Actual
9 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-51 |  | Meska Improvement Works for Sidi Gazy 15 | 1250 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-03-17 |  | 2012-04-16 | 2012-05-16 | 2012-05-16 |  |  | 2012-06-15 | 2012-06-22 |  |  |  | 2013-02-17
[8 empty] | Revised |  |  |  |  | 2013-04-15 |  | 2013-05-15 | 2013-06-14 | 2013-06-14 | 2013-07-05 | 2013-07-19 | 2013-08-02 | 2013-08-09 |  |  |  | 2014-04-06
Actual
10 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-52 |  | Meska Improvement Works for Sidi Gazy 16 | 1650 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-02 |  | 2013-04-01 | 2013-05-01 | 2013-05-01 |  |  | 2013-05-31 | 2013-06-07 |  |  |  | 2014-02-06
Revised
Actual
11 | Sidi Ghazey | IIIMP/IIS/MTYZ/MQ-53 |  | Meska Improvement Works for Sidi Gazy 17 | 1550 | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2013-03-16 |  | 2013-04-15 | 2013-05-15 | 2013-05-15 |  |  | 2013-06-14 | 2013-06-21 |  |  |  | 2014-02-20
Revised
Actual
12 | Various | IIIMP/IIS/MTYZ/REINST |  | Reinstatment of Mesqas at Meet Yazed Command Area |  | Cancelled | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2012-12-27 |  | 2013-01-26 | 2013-02-25 | 2013-02-25 |  |  | 2013-03-27 | 2013-04-03 |  |  |  | 2013-11-29
[8 empty] | Revised |  |  |  |  | 2013-06-15 |  | 2013-07-15 | 2013-08-14 | 2013-08-14 | 2013-09-04 | 2013-09-18 | 2013-10-02 | 2013-10-09 |  |  |  | 2014-06-10
Actual

## Drainage
Procurement Plan for Drainage Rehabilitation Works (Meet Yazeed Area) | [23 empty] | Updated 12/12/2013
Arab republic of Egypt EGT-7291: Integrated Irrigation Improvement & Management Project Original:28/2/2008
Completed
SL No | District | Package reference No/ Contract No | Description of Works | Area (fed) | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)
1 | Gharb El-Mahalla | IIIMP/EPAD/MTYZ/W01-2007 | Open drainage works of Gharb ElMehalla Drains | - | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2007-05-15 |  | 2007-06-14 | 2007-07-14 | 2007-07-14 |  |  | 2007-11-21 |  | 1489700 | EGP | Mohamed Ibrahim Saeid Abo Taleb | 2009-05-31
Revised
[7 empty] | Actual |  |  |  |  | 2007-05-31 |  | 2007-08-12 | 2007-08-29 | 2007-08-29 | 2007-10-09 | 2007-11-07 | 2007-12-01 | 2007-12-01 |  |  |  | 2009-05-31
2 | Sidi Ghazy | IIIMP/EPAD/MTYZ/W02-2008 | Rehabilitation of Brides and Pitching of Open Drains in Sidy Ghazi District -Meet Yazid Commmand Area | - | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2008-09-15 |  | 2008-10-15 | 2008-11-14 | 2008-11-14 |  |  | 2009-02-01 |  | 6724500 | EGP | Hamid Ahmed Ali El Banna Office | 2011-04-30
Revised
[7 empty] | Actual |  |  |  |  | 2008-11-17 | 2008-11-24 | 2009-01-21 | 2009-02-23 | 2009-02-23 | 2009-03-19 | 2009-03-19 | 2009-04-29 | 2009-05-01 |  |  |  | 2011-04-30
3 | East Sidi Salem | IIIMP/EPAD/MTYZ/W03-2010 | Pitching work on Nemra Thamnia El Asfal Drain | - | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-04-01 |  | 2010-05-01 | 2010-05-31 | 2010-05-31 |  |  | 2010-06-01 | 2010-12-15 | 2535950 | EGP | El-Masrea for Integrated Contracting | 2012-05-01
[7 empty] | Revised |  |  |  |  | 2009-01-21: 2010-08-26; 2009-02-23: 2010-09-15; 2009-04-29: 2011-05-15; 2009-05-01: 2011-05-20
[7 empty] | Actual |  |  |  |  | 2010-01-11 | 2010-03-21 | 2010-08-25 | 2010-09-15 | 2010-09-15 | 2011-03-06 | 2011-03-28 | 2011-05-02 | 2011-05-02 |  |  |  | 2012-04-10
4 | East Sidi Salem | IIIMP/EPAD/MTYZ/SSD01 2009 | Subsurface Drainage works in Nemra Thamnia Al Asfal area ) | 4000 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-01-11: 2008-09-15; 2010-08-25: 2008-10-15; 2010-09-15: 2008-11-14; 2010-09-15: 2008-11-14; 2011-05-02: 2009-02-01 | 9949250 | EGP | El-Rashedia Company for General Contracting | 2012-01-16
Revised
[7 empty] | Actual |  |  |  |  | 2009-07-02 | 2009-07-14 | 2009-08-19 | 2009-09-27 | 2009-09-27 | 2009-12-13 | 2009-12-16 | 2010-01-09 | 2010-01-16 |  |  |  | 2011-07-31
5 | Gharb El-Mahalla | IIIMP/EPADP/MTYZ/SSD03 2010 | Replacement and Rehabilitation of Subsurface Drainage Network in Abshaway 1st | 3000 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-01-01 |  | 2010-01-31 | 2010-03-02 | 2010-03-02 |  |  | 2010-05-06 | 2010-12-31 | 6694970.1 | EGP | Al - Eman company for contracting | 2012-08-31
[7 empty] | Revised |  |  |  |  | 2009-07-02: 2010-06-01; 2010-01-09: 2011-01-10; 2010-01-16: 2011-01-15
[7 empty] | Actual |  |  |  |  | 2010-06-13 | 2010-06-23 | 2010-08-24 | 2010-09-27 | 2010-09-27 | 2010-12-22 | 2011-01-18 | 2011-03-01 | 2011-03-01 |  |  |  | 2012-08-30
6 | Qotor | IIIMP/EPADP/MTYZ/SSD04 2010 | Replacement and Rehabilitation of Subsurface Drainage works in Matbool 2nd (A) Meet Yazied Commmand Area | 1700 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-06-13: 2011-02-01; 2010-08-24: 2011-03-03; 2010-09-27: 2011-04-02; 2010-09-27: 2011-04-02; 2011-03-01: 2011-06-01 | 4769940 | EGP | El Halowagi Company and his Partner | 2013-06-04
[7 empty] | Revised |  |  |  |  | 2010-08-01 |  | 2011-04-07 | 2011-05-07 | 2011-05-07 |  |  | 2011-10-01 | 2011-10-01
[7 empty] | Actual |  |  |  |  | 2010-09-30 | 2010-11-11 | 2011-04-05 | 2011-05-07 | 2011-05-07 | 2011-09-05 | 2011-09-20 | 2011-10-01 | 2011-10-05 |  |  |  | 2012-07-10
7 | Qotor | IIIMP/EPADP/MTYZ/SSD05 2010 | Replacement and Rehabilitation of Subsurface Drainage works in Matbool 2 nd (B) | 2200 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-09-30: 2011-02-01; 2011-04-05: 2011-03-03; 2011-05-07: 2011-04-02; 2011-05-07: 2011-04-02; 2011-10-01: 2011-06-01 | 6264510 | EGP | El Salam Company for General Contracting | 2013-05-31
[7 empty] | Revised |  |  |  |  | 2010-08-01 |  | 2011-04-07 | 2011-05-07 | 2011-05-07 |  |  | 2011-09-23 | 2011-10-01 |  |  |  | 2013-03-31
[7 empty] | Actual |  |  |  |  | 2010-09-30 | 2010-11-11 | 2011-04-05 | 2011-05-10 | 2011-05-10 | 2011-09-05 | 2011-09-20 | 2011-10-01 | 2011-10-01 |  |  |  | 2012-09-16
8 | Kafr El Shiekh | IIIMP/EPADP/MTYZ/SSD06 2010 | Replacement and Rehabilitation of Subsurface Drainage works in El-Khadima and Al-Boteita (B) | 2900 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-03-01 |  | 2010-03-31 | 2010-04-30 | 2010-04-30 |  |  | 2010-07-01 | 2010-12-31 | 7408193.75 | EGP | El Halowagi Company and his Partner | 2013-12-01
[7 empty] | Revised |  |  |  |  | 2010-06-01 |  | 2011-04-07 | 2011-05-07 | 2011-05-07 |  |  | 2012-04-10 | 2012-04-25 |  |  |  | 2013-12-01
[7 empty] | Actual |  |  |  |  | 2010-09-30 | 2010-11-04 | 2011-04-04 | 2011-05-12 | 2011-05-12 | 2012-03-29 | 2012-04-04 | 2012-06-02 | 2012-06-07
9 | Gharb El-Mahalla | IIIMP/EPADP/MTYZ/SSD10-B | Replacement and Rehabilitation of Subsurface Drainage works in Neshil (B) | 1850 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 01-Jan-12 |  | 2012-01-31 | 2012-03-01 | 2012-03-01 |  |  | 31-Mar-12 | 2012-04-15 | 4277850 | EGP | El Salam Company for General Contracting | 2014-04-14
[7 empty] | Revised |  |  |  |  | 2012-02-01 |  | 2012-04-20 | 2012-07-02 | 2012-07-02 |  |  | 2012-09-20 | 2012-10-05 |  |  |  | 2014-04-14
[7 empty] | Actual |  |  |  |  | 2012-01-23 | 2012-02-26 | 2012-05-05 | 2012-06-12 | 2012-06-12 | 2012-08-26 | 2012-09-10 | 2012-10-15 | 2012-10-15 |  |  |  | 2013-04-29
Total completed contracts |  |  |  | 8700 | [16 empty] | 21414160.1 | 2461.3977 | unit rate
Ongoing
SL No | District | Package reference No/ Contract No | Description of Works | Area (fed) | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)
1 | Gharb El-Mahalla | IIIMP/EPADP/MTYZ/SSD02 2009 | Replacement and Rehabilitation of Subsurface Drainage works in the command area of Abshoway 2nd | 3000 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2010-08-14 |  | 2010-09-13 | 2010-10-13 | 2010-10-13 |  |  | 2010-11-15 | 2010-12-01 | 7417499.25 | EGP | Egyptian Company for Irrigation and Drainage | 2012-11-09
[7 empty] | Revised |  |  |  |  | 2012-01-23: 2010-12-02; 2012-10-15: 2011-01-10; 2012-10-15: 2011-01-15 |  |  |  | 2012-11-09
[7 empty] | Actual |  |  |  |  | 2010-04-21 | 2010-04-27 | 2010-05-09 | 2010-06-12 | 2010-06-12 | 2010-12-30 | 2011-03-28 | 2011-04-27 | 2011-05-10
2 | Kafr El Shiekh | IIIMP/EPADP/MTYZ/SSD14-2011 | Replacement and Rehabilitation of Subsurface Drainage works in El-Khadima frist(A) | 2600 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2011-03-01 |  | 2011-03-31 | 2011-04-30 | 2011-04-30 |  |  | 2011-07-01 | 2011-07-07 | 6903051 | EGP | El Halowagi Company and his Partner | 2013-09-30
[7 empty] | Revised |  |  |  |  | 2010-05-09: 2011-08-01; 2010-06-12: 2011-08-31; 2010-06-12: 2011-08-31; 2011-04-27: 2012-04-10; 2011-05-10: 2012-04-25 |  |  |  | 2013-09-30
[7 empty] | Actual |  |  |  |  | 2011-01-09 | 2011-05-29 | 2011-08-28 | 2011-09-29 | 2011-09-29 | 2012-02-21 | 2012-02-23 | 2012-03-22 | 2012-04-01
3 | Qotor | IIIMP/EPADP/MTYZ/SSD07-A | Replacement and Rehabilitation of Subsurface Drainage works in Matbool 1st and Kafr El-Taifa (A) | 2900 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2011-03-01 |  | 2011-03-31 | 2011-04-30 | 2011-04-30 |  |  | 2011-07-01 | 2010-12-31 | 6932502.5 | EGP | El Salam Company for General Contracting | 2013-04-20
[7 empty] | Revised |  |  |  |  | 2012-12-01 |  | 2012-09-15 | 2012-10-15 | 2012-10-15 |  |  | 2012-11-14 | 2012-11-29 |  |  |  | 2014-05-14
[7 empty] | Actual |  |  |  |  | 2012-01-04 | 2012-02-26 | 2012-06-04 | 2012-07-09 | 2012-07-09 | 2012-09-27 | 2012-10-01 | 2012-11-15 | 2012-11-15
4 | Qotor | IIIMP/EPADP/MTYZ/SSD07-B | Replacement and Rehabilitation of Subsurface Drainage works in Matbool 1st and Kafr El-Taifa (B) | 2200 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 2011-03-01 |  | 2011-03-31 | 2011-04-30 | 2011-04-30 |  |  | 2011-07-01 | 2010-12-31 | 5469780.1 | EGP | El Salam Company for General Contracting | 2014-11-01
[7 empty] | Revised |  |  |  |  | 2012-12-15 |  | 2012-11-15 | 2012-12-15 | 2012-12-15 |  |  | 2013-03-30 | 2013-04-14
[7 empty] | Actual |  |  |  |  | 2012-01-04 | 2012-02-26 | 2012-11-14 | 2012-12-18 | 2012-12-18 | 2013-02-13 | 2013-02-13 | 2013-02-11 | 2013-05-02
5 | Gharb El-Mahalla | IIIMP/EPADP/MTYZ/SSD08-2012 | Replacement and Rehabilitation of Subsurface Drainage works in samtay first | 2800 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2012-04-01 |  | 2012-05-01 | 2012-05-31 | 2012-05-31 |  |  | 2012-06-30 | 2011-03-07 | 8262580 | EGP | El Tokhy for Contracting | 2014-02-28
[7 empty] | Revised |  |  |  |  | 2011-01-01 |  | 2012-05-01 | 2012-05-31 | 2012-05-31 |  |  | 2012-07-31 | 2012-08-15 |  |  |  | 2014-02-28
[7 empty] | Actual |  |  |  |  | 2012-01-23 | 2012-01-26 | 2012-04-08 | 2012-05-13 | 2012-05-13 | 2012-07-17 | 2012-07-18 | 2012-09-01 | 2012-09-01
6 | Gharb El-Mahalla | IIIMP/EPADP/MTYZ/SSD09-2011 | Replacement and Rehabilitation of Subsurface Drainage works in samtay Scond | 3000 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 2012-04-01 |  | 2012-05-01 | 2012-05-31 | 2012-05-31 |  |  | 2012-06-30 | 2012-07-15 | 6669810.65 | EGP | Al - Iman company for General contracting | 2013-07-14
[7 empty] | Revised |  |  |  |  | 2011-03-01 |  | 2011-08-15 | 2011-09-14 | 2011-09-14 |  |  | 2012-03-01 | 2012-03-16 |  |  |  | 2013-07-14
[7 empty] | Actual |  |  |  |  | 2011-02-10 | 2011-05-29 | 2011-08-09 | 2011-09-12 | 2011-09-12 | 2011-12-04 | 2011-12-07 | 2012-01-15 | 2012-01-15
7 | Kafr El Shiekh | IIIMP/EPADP/MTYZ/SSD11-A | Replacement and Rehabilitation of Subsurface Drainage works in El Arian (A) | 2400 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 01-Apr-13 |  | 2013-05-01 | 2013-05-31 | 2013-05-31 |  |  | 30-Jun-13 | 2013-07-15 | 5673270 | EGP | Engineer Awad Taha Gad Osman | 2014-04-30
[7 empty] | Revised |  |  |  |  | 2012-04-05 |  | 2012-05-05 | 2012-06-04 | 2012-06-04 |  |  | 2012-08-01 | 2012-08-16 |  |  |  | 2014-04-30
[7 empty] | Actual |  |  |  |  | 2011-08-17 | 2011-10-27 | 2012-05-05 | 2012-06-10 | 2012-06-10 | 2012-08-26 | 2012-09-12 | 2012-11-01 | 2012-11-01
8 | Kafr El Shiekh | IIIMP/EPADP/MTYZ/SSD11-B | Replacement and Rehabilitation of Subsurface Drainage works in El Arian (B) | 2300 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 01-Apr-13 |  | 2013-05-01 | 2013-05-31 | 2013-05-31 |  |  | 30-Jun-13 | 2013-07-15 | 5604823.36 | EGP | El Salam Company for General Contracting | 2014-05-14
[7 empty] | Revised |  |  |  |  | 2012-03-16 |  | 2012-04-15 | 2012-05-15 | 2012-05-15 |  |  | 2012-08-01 | 2012-08-16 |  |  |  | 2014-05-14
[7 empty] | Actual |  |  |  |  | 2011-08-17 | 2011-10-27 | 2012-05-05 | 2012-06-11 | 2012-06-11 | 2012-08-28 | 2012-09-27 | 2012-11-15 | 2012-11-15
9 | Gharb El-Mahalla | IIIMP/EPADP/MTYZ/SSD10-A | Replacement and Rehabilitation of Subsurface Drainage works in Neshil (A) | 2700 | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Prior | No | 01-Jan-12 |  | 2012-01-31 | 2012-03-01 | 2012-03-01 |  |  | 31-Mar-12 | 2012-04-15 | 6327046.75 | EGP | Upper Egypt for General Contracting | 2014-05-14
[7 empty] | Revised |  |  |  |  | 2012-02-01 |  | 2012-09-15 | 2012-10-15 | 2012-10-15 |  |  | 2012-11-14 | 2012-11-29 |  |  |  | 2014-05-14
[7 empty] | Actual |  |  |  |  | 2012-01-23 | 2012-02-26 | 2012-06-04 | 2012-07-08 | 2012-07-08 | 2012-09-13 | 2012-09-26 | 2012-11-15 | 2012-11-15
10 | Qotor | IIIMP/EPADP/MTYZ/SSD12-2012 | Replacement and Rehabilitation of Subsurface Drainage works in Meniat Maser | 3350 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 01-May-13 |  | 2013-05-31 | 2013-06-30 | 2013-06-30 |  |  | 30-Jul-13 | 2013-08-14 | 7191888 | EGP | El Halowagi Company and his Partner | 18 month contract
[7 empty] | Revised |  |  |  |  | 2013-02-25 |  | 2013-03-27 | 2013-04-26 | 2013-04-26 | 2013-07-11 | 2013-07-18 | 2013-07-25 | 2013-08-09
[7 empty] | Actual |  |  |  |  | 2012-08-23 | 2012-09-27 | 2012-12-08 | 2013-01-08 | 2013-01-08 | 2013-05-18 | 2013-11-06 | Done | Done
11 | Kafr El Shiekh | IIIMP/EPADP/MTYZ/SSD13-A/2013 | Replacement and Rehabilitation of Subsurface Drainage works for the extension Nemra Thamnia El Asfal Drain | 2250 | NCB | IBRD (90%)GoE (10%) | Planned |  |  | Post | No | 01-Jul-13 |  | 2013-07-31 | 2013-08-30 | 2013-08-30 |  |  | 29-Sep-13 | 2013-10-14 | 5175056 | EGP | Mohamed Abdalla Zaid | 18 month contract
[7 empty] | Revised |  |  |  |  | 2013-03-15 |  | 2013-03-27 | 2013-04-26 | 2013-04-26 | 2013-07-11 | 2013-07-18 | 2013-07-25 | 2013-08-09
[7 empty] | Actual |  |  |  |  | 2013-02-19 | 2013-02-25 | 2013-04-10 | 2013-05-13 | 2013-05-13 |  | 2013-07-30 | Done | Done
Total ongoing contracts | [11 empty] | 2012-11-15: 1900-05-04
Planned
SL No | District | Package reference No/ Contract No | Description of Works | Area (fed) | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s&or Pmu No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s&or Pmu No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date)

## Miscellaneous
Procurement Plan for Miscellaneous Works (Meet Yazeed Area) | [22 empty] | Updated 12/12/2013 | Updated: 14/4/2010
Arab republic of Egypt EGT-7291: Integrated Irrigation Improvement & Management Project Original:28/2/2008
Proc Plan Updated on January 16, 2014
Completed
SL No | District | Package reference No/ Contract No | Description of Works | Procurement method | Fund Source(s) | Status | Estimated Cost | Currency | Review by Bank (prior/post) | Domestic Preference (yes/no) | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date) | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | BER (Date) | Bank’s No Objection to BER and Contract Award (Date) | Contract Signing (Date) | Contract Commencement (Date) | Contract Value | Contract Currency | Name, City, and Country of Contractor | Contract Completion (Date) | Completion of Contract (Date)
1 | Qotor | IIIMP/IS/MTYZ/MIS 02 2009 | Civil works of Integrated Irrigation district in Qotor | NCB | CA (75%) GoE (25%) | Planned |  |  | Post | No |  | N/A |  |  |  |  | N/A |  |  | 247175 | EGP | Waled Abd El Fatah Darawesh | 2009-12-18 | 2009-04-20
Revised
[6 empty] | Actual |  |  |  |  | 2009-08-15 |  | 2009-09-08 | 2009-09-13 | 2009-09-13 |  |  | 2009-10-19 |  |  |  |  | 2010-02-04 | 2009-08-20
2 | Gharb El-Mahalla | IIIMP/IS/MTYZ/MIS 01 2009 | Civil works of Integrated Irrigation district in Gharb El-Mahalla | NCB | CA (75%) GoE (25%) | Planned |  |  | Post | No |  | N/A |  |  |  |  | N/A |  |  | 250368 | EGP | Ramdon Morce Morce | 2009-12-14 | 2009-03-14
Revised
[6 empty] | Actual |  |  |  |  | 2009-08-15 |  | 2009-09-08 | 2009-09-12 | 2009-09-12 |  |  | 2009-10-15 |  |  |  |  | 2009-12-14 | 2009-09-14
3 | Sidi Ghazy | IIIMP/IS/MTYZ/MIS 03 2009 | Civil works and preparation of Integrated Irrigation district in Sidi Ghazy | NCB | CA (75%) GoE (25%) | Planned |  |  | Post | No |  | N/A |  |  |  |  | N/A |  |  | 1152988 | EGP | Hamdi Hamed Abd El Moghaney | 2010-05-31
Revised
[6 empty] | Actual |  |  |  |  | 2009-06-01 | [6 empty] | 2009-09-30 | 2009-10-01 |  |  |  | 2010-05-29
4 | Kafr El Shiekh | IIIMP/IS/MTYZ/MIS 05 2010 | Civil works and preparation of Integrated Irrigation district in Kafr El Shiekh | Shopping | GoE | Planned |  |  | Post | No |  | N/A |  |  |  |  | N/A |  |  | 26186 | EGP | Osama Hamad
Revised
[6 empty] | Actual | [11 empty] | 2008-11-30 |  |  |  |  | 2009-01-26
5 | Kafr El Shiekh | IIIMP/IS/MTYZ/MIS 01 2010 | Steel Sheds for Storage and protection kafr El Shiekh | NCB | IBRD (70%) GoE (30%) | Planned |  |  | Post | No | 2010-01-01 | N/A |  |  |  |  | N/A |  |  | 387757.5 | EGP | New Metal for mineral constructions and contracting | 2010-11-01
Revised
[6 empty] | Actual | [6 empty] | 2010-02-12 | 2010-03-23 | 2010-03-23 | 2010-05-18 |  | 2012-06-28 | 2010-05-02 |  |  |  | 2010-07-06
6 | Various | IIIMP/IS/MTYZ/MIS 06 2011 | Civil works of Integrated Irrigation district in Samanud & Gharb El-Mahalla | NCB | CA (75%) GoE (25%) | Planned | [10 empty] | N/A |  |  | 1199218.8 | EGP | El Rehab For Contracting
Revised
[6 empty] | Actual | [6 empty] | 2011-03-12 | 2011-03-21 | 2011-03-21 | 2011-05-02 |  | 2012-06-01 | 2011-06-01 |  |  |  | 2012-03-15
7 | Various | IIIMP/IS/MTYZ/MIS 07 2011 | Civil works of Integrated Irrigation district in Shark El-Mahalla-Bshbesh& Qotor | NCB | CA (75%) GoE (25%) | Planned | [10 empty] | N/A |  |  | 1175876.5 | EGP | Ibraheem Ali El Issaway
Revised
[6 empty] | Actual | [6 empty] | 2011-03-12 | 2011-03-22 | 2011-03-22 | 2011-04-20 |  | 2011-06-01 | 2011-06-01 |  |  |  | 2012-05-10
8 | Various | IIIMP/IS/MTYZ/MIS 08 2011 | Civil works of Integrated Irrigation district in Basuon & Kafr El-Ziat | NCB | CA (75%) GoE (25%) | Planned | [10 empty] | N/A |  |  | 1805258.9 | EGP | Khatab El Sawahely
Revised
[6 empty] | Actual | [6 empty] | 2011-03-12 | 2011-03-21 | 2011-03-21 | 2011-05-02 |  | 2011-06-01 | 2011-06-01 |  |  |  | 2012-03-10