## General and Thresholds
Procurement Plan
I. General
1. | Project Information
| Project Name: | Transportation Corridors Project
| Country: | Iraq
Project ID:
| Loan/Credit Numbers: | P131550
2. | Bank's approval date of Procurement Plan | Original: 9/24/2013
Revision 1:
3. | Date of General Procurement Notice | 2013-07-12
II. Goods, Work and Non-Consulting Services Thresholds
1. | Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement: [Thresholds for applicable procurement methods (not limited to the list below) will be determined by the Procurement Specialist /Procurement Accredited Staff based on the assessment of the implementing agency’s capacity.]
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods | >= 0.5 million and any direct contract regardless of value
| Works | >= 5 million and any direct contract regardless of value
| Non-Consultant Services | >= 0.5 million and any direct contract regardless of value
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| ICB and LIB (Goods) | > 500,000
| NCB (Goods) | ≤ 500,000
| Shopping (Goods) | ≤ 100,000
| ICB (Works) | > 5 million
| NCB (Works) | ≤ 5 million
| Shopping (Works) | ≤ 200,000
2. | Prequalification. Bidders for R7, R8 , and R9 shall be prequlified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines.
No
3. | Proposed Procedures for CDD Components (as per paragraph 3.17 of the Guidelines): Refer to the relevant CDD project implementation document approved by the Bank: Not Applicable
4. | Reference to (if any) Project Operational/Procurement Manual: Master Implmnetation Manual
5. | Any Other Special Procurement Arrangements: advance procurement and retroactive financing is applicable under this project
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Consulting Firms (Competitive) | 0.2 million
| Consulting Firms (Sole Source) | All
| Individual Consultants (Competitive) | 0.1 million
| Individual Consultants (Sole Source) | All
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
QCBS
QCB
FCS
LCS
| CQS | 0.3 million
Consulting Firms (Sole Source)
Individual Consultants (Competitive)
Individual Consultants (Sole Source)
ICB (Non-Consultant Services)
Include all methods authorized by the loan agreement
2. | Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $_200,000 ______equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
| Note: OPCPR list of ceilings can be found here: | http://go.worldbank.org/MKXO98RY40
3. | Any Other Special Selection Arrangements:advance procurement and retroactive financing is applicable under this project
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet

## Works and Goods
Transport Corridors Project: GDRB Part- Works and Goods
Revised Procurement Plan: May,2 2017
Procurement Ref.# | Description | Governorate | length(km) | Financed by | procurement method | Review By Bank | Plan /Actual | Submission of BID | interval (day) | WB No Objection | interval (day) | Invitation to BID | interval (day) | Deadline for submission Application of BID | interval (day) | PQ Evaluation Report | interval (day) | WB No Objection | interval (day) | Issue BDs | interval (day) | Bids Opening | interval (day) | Bids Evaluation Report | interval (day) | WB No Objection | interval (day) | Contract Award | interval (day) | Contract Signing | interval (day) | Commencement | Duration Date | Completion | Comments
To be implemendted by GDRB
TCP.W.KRG.A6 | Construction of Girshen and Suheila Highway | Duhok Governorate | 20 | WB | ICB | PRIOR | P | 2014-03-01 | 7 | 2014-03-08 | 7 | 2014-03-15 | 42 | 2014-04-26 | 42 | 2014-06-07 | 14 | 2014-06-21 | 7 | 2014-06-28 | 45 | 2014-08-12 | 28 | 2014-09-09 | 14 | 2014-09-23 | 7 | 2014-09-30 | 28 | 2014-10-28 | 21 | 2014-11-18 | 1095 | 2017-11-17 | HGG - Turkey
[7 empty] | R | 2016-05-23 | 7 | 2016-05-30 | 3 | 2016-08-04 | 49 | 2016-09-22 | 21 | 2016-10-13 | 14 | 2016-10-27 | 3 | 2016-10-30 | 42 | 2016-12-11 | 28 | 2017-01-08 | 14 | 2017-01-22 | 7 | 2017-01-29 | 28 | 2017-02-26 | 21 | 2017-03-19 | 900 | 2019-09-05
[7 empty] | A | [5 empty] | 56 | 2016-09-29 | Not applicable because no prequalification was required | [6 empty] | 2016-09-29 | 28 | 2017-01-15 | 57 | 2017-03-13 | 43 | 2017-04-25
Formulas:
WB No Objection = [Submission of BID]+[interval (day)]
WB No Objection = [PQ Evaluation Report]+[interval (day)]
Invitation to BID = [WB No Objection]+[interval (day)]
PQ Evaluation Report = P7+[interval (day)]
PQ Evaluation Report = [interval (day)]+P8
Issue BDs = [WB No Objection]+[interval (day)]
Bids Opening = [Issue BDs]+[interval (day)]
Bids Evaluation Report = [Bids Opening]+[interval (day)]
Contract Award = [WB No Objection]+[interval (day)]
Contract Signing = [Contract Award]+[interval (day)]
Commencement = [Contract Signing]+[interval (day)]
Completion = [Commencement]+[Duration Date]

## Consultancy Services
Transport Corridors Project- GBRD Part - Consultancy Services
Revised Procurement Plan -MAY-2- 2017
Package/ Reference No. | Description of Services | Financining by | Bank Review | Method of Selection | Plan /Actual | Adverti- sement EOI/ Readiness | Interval /days | Submission of EOIs | Interval /days | Short listing and Preparation of RFP | Interval /days | No Objection | Interval /days | Issue RFP | Interval /days | Expected Proposal Submission | Interval /days | Technical Evaluation | Interval /days | No Objection | Interval /days | Submission of Combined Tech and Fin Eval Report and Negotiated Contract | Interval /days | No Objection Combined Eval Report and Negotiated Contract | Interval /days | Contract Award | Interval /days | Start Date | Interval /days | Comple- tion Date | Commnets
.
TCP.CON.QCBS.KRG.A7 | Engineering Supervision Services - Road section between Girshen & Suheila |  | Prior | QCBS | P | 2014-02-15 | 28 | 2014-03-15 | 28 | 2014-04-12 | 7 | 2014-04-19 | 3 | 2014-04-22 | 42 | 2014-06-03 | 42 | 2014-07-15 | 7 | 2014-07-22 | 28 | 2014-08-19 | 7 | 2014-08-26 | 3 | 2014-08-29 | 14 | 2014-09-12 | 1095 | 2017-09-11
|  |  | Prior | QCBS | R | 2016-05-19 | 19 | 2016-06-07 | 14 | 2016-07-28 | 3 | 2016-07-31 | 5 | 2016-08-05 | 45 | 2016-09-19 | 21 | 2016-10-10 | 7 | 2016-10-17 | 28 | 2016-11-14 | 7 | 2016-11-21 | 3 | 2016-11-24 | 14 | 2016-12-08 | 900 | 2019-05-27 | BOTEK - ASMIN
|  |  |  | QCBS | A | 2016-05-19 | 19 | 2016-06-07 | 47 | 2016-07-24 | 5 | 2016-07-29 | 25 | 2016-08-23 | 52 | 2016-09-26 | 83 | 2016-12-18 | 2 | 2016-12-20 | 24 | 2017-01-13 | 13 | 2017-01-26 | 89 | 2017-04-25
.
TCP.CON.QCBS.KRG.B2 (A)-(C) | Technical Assistance - Organization and Capacity Improvement |  | Prior | QCBS | P | 2014-02-01 | 28 | 2014-03-01 | 28 | 2014-03-29 | 7 | 2014-04-05 | 3 | 2014-04-08 | 42 | 2014-05-20 | 42 | 2014-07-01 | 7 | 2014-07-08 | 28 | 2014-08-05 | 7 | 2014-08-12 | 3 | 2014-08-15 | 14 | 2014-08-29 | 365 | 2015-08-29
|  |  | Post |  | R | 2016-01-15 | 28 | 2016-02-12 | 28 | 2016-03-11 | 7 | 2016-03-18 | 3 | 2016-03-21 | 42 | 2016-05-02 | 42 | 2016-06-13 | 7 | 2016-06-20 | 29 | 2016-07-19 | 7 | 2016-07-26 | 3 | 2016-07-29 | 14 | 2016-08-12 | 365 | 2017-08-12
A
.
TCP.CON.QCBS.KRG.B2 (D) | Technical Assistance -Information and Communication System |  | Prior | QCBS | P | 2014-09-01 | 28 | 2014-09-29 | 28 | 2014-10-27 | 7 | 2014-11-03 | 3 | 2014-11-06 | 42 | 2014-12-18 | 42 | 2015-01-29 | 7 | 2015-02-05 | 28 | 2015-03-05 | 7 | 2015-03-12 | 3 | 2015-03-15 | 14 | 2015-03-29 | 365 | 2016-03-28
|  |  | Post | CQS | R | 2016-03-01 | 28 | 2016-03-29 | 28 | 2016-04-26 | 7 | 2016-05-03 | 3 | 2016-05-06 | 42 | 2016-06-17 | 42 | 2016-07-29 | 7 | 2016-08-05 | 28 | 2016-09-02 | 7 | 2016-09-09 | 3 | 2016-09-12 | 14 | 2016-09-26 | 365 | 2017-09-26
A
TCP.CON.QCBS.KRG.B2 (D2) | Technical Assistance -update and complete the road asset management |  | Prior | QCBS | P | 2014-07-01 | 28 | 2014-07-29 | 28 | 2014-08-26 | 7 | 2014-09-02 | 3 | 2014-09-05 | 42 | 2014-10-17 | 42 | 2014-11-28 | 7 | 2014-12-05 | 28 | 2015-01-02 | 7 | 2015-01-09 | 3 | 2015-01-12 | 14 | 2015-01-26 | 365 | 2016-01-26
[5 empty] | R | 2016-06-01 | 28 | 2016-06-29 | 28 | 2016-07-27 | 7 | 2016-08-03 | 3 | 2016-08-06 | 42 | 2016-09-17 | 42 | 2016-10-29 | 7 | 2016-11-05 | 28 | 2016-12-03 | 7 | 2016-12-10 | 3 | 2016-12-13 | 14 | 2016-12-27 | 365 | 2017-12-27
TCP.CON.QCBS.KRG.B2 (E&H) | Training and Study Tours for managerial and technical staff of GDRB |  | Prior | QCBS | P | 2014-09-01 | 28 | 2014-09-29 | 28 | 2014-10-27 | 7 | 2014-11-03 | 3 | 2014-11-06 | 42 | 2014-12-18 | 42 | 2015-01-29 | 7 | 2015-02-05 | 28 | 2015-03-05 | 7 | 2015-03-12 | 3 | 2015-03-15 | 14 | 2015-03-29 | 365 | 2016-03-28
|  |  | Post | CQS | R | 2016-03-01 | 28 | 2016-03-29 | 28 | 2016-04-26 | 7 | 2016-05-03 | 3 | 2016-05-06 | 42 | 2016-06-17 | 42 | 2016-07-29 | 7 | 2016-08-05 | 28 | 2016-09-02 | 7 | 2016-09-09 | 3 | 2016-09-12 | 14 | 2016-09-26 | 365 | 2017-09-26
A
TCP.CON.QCBS.KRG.B4 (B) | Technical Assistance - Training of Local Contractors and Consultants |  | Prior | CQS | P | 2017-03-01 | 14 | 2017-03-15 | 0 | 2017-03-15 | 14 | 2017-03-29 | 0 | Call of proposals |  |  | 30 | 2017-04-28 | 14 | Not Applicable |  |  | 7 | 2017-05-05 | 7 | 2017-05-12 | 7 | 2017-05-19 | 126 | 2017-09-22
|  |  | Post |  | R
A
TCP.CON.C2 (A) | Technical Audit |  | Prior | QCBS | P | 2014-06-01 | 28 | 2014-06-29 | 28 | 2014-07-27 | 7 | 2014-08-03 | 3 | 2014-08-06 | 42 | 2014-09-17 | 42 | 2014-10-29 | 7 | 2014-11-05 | 28 | 2014-12-03 | 7 | 2014-12-10 | 3 | 2014-12-13 | 14 | 2014-12-27 | 1215 | 2018-04-25
[5 empty] | R | 2016-02-01 | 28 | 2016-02-29 | 28 | 2016-03-28 | 7 | 2016-04-04 | 3 | 2016-04-07 | 42 | 2016-05-19 | 42 | 2016-06-30 | 7 | 2016-07-07 | 28 | 2016-08-04 | 7 | 2016-08-11 | 3 | 2016-08-14 | 14 | 2016-08-28 | 1215 | 2019-12-26
A
TCP.CON.C2 (B) | FInancial Audit |  | Prior | CQS | P | 2014-06-01 | 28 | 2014-06-29 | 28 | 2014-07-27 | 7 | 2014-08-03 | 3 | 2014-08-06 | 42 | 2014-09-17 | 42 | 2014-10-29 | 7 | 2014-11-05 | 28 | 2014-12-03 | 7 | 2014-12-10 | 3 | 2014-12-13 | 14 | 2014-12-27 | 1215 | 2018-04-25
[5 empty] | R | 2016-06-01 | 28 | 2016-06-29 | 28 | 2016-07-27 | 7 | 2016-08-03 | 3 | 2016-08-06 | 42 | 2016-09-17 | 42 | 2016-10-29 | 7 | 2016-11-05 | 28 | 2016-12-03 | 7 | 2016-12-10 | 3 | 2016-12-13 | 14 | 2016-12-27 | 1215 | 2020-04-25
[5 empty] | A | 2015-06-16 | 72 | 2015-08-27 | Two companies submit proposal | [10 empty] | 2016-10-04
TCP.CON.IC.C2 (C1) | Individual Technical Expert / Procurement |  | Prior\Post | IC | P | 2014-06-01 | 6 | 2014-06-07 | [16 empty] | 28 | 2014-06-29 | 14 | 2014-07-13 | 365 | 2015-07-13
[5 empty] | R | 2015-05-21 | 6 | 2015-05-27 | [17 empty] | 2015-01-06 | 14 | 2015-01-20 | 365 |  | ELIE NAIM
|  |  | Prior |  | A |  |  | 2015-07-03 | [15 empty] | 30/7/2015 |  | 2015-08-08 | 29 | 2015-09-06 | 365 | 2016-09-05
TCP.CON.IC.C2 (C1) -A1 |  |  | Post |  | A |  |  | 2016-07-03 | [15 empty] | 30/7/2015 |  | 2016-09-05 | 1 | 2016-09-06 | 365 | 2017-09-06 | Extension for one year / same price
TCP.CON.IC.C2 (C2) | Individual Technical Expert /Social expert |  | Post | IC | P | 2014-06-01 | 6 | 2014-06-07 | [16 empty] | 28 | 2014-06-29 | 14 | 2014-07-13 | 180 | 2015-01-09
[5 empty] | R | 2016-01-15 | 6 | 2016-01-21 | [17 empty] | 2016-01-02 | 14 | 2016-01-16 | 180 | 2016-07-14
A
TCP.CON.IC.C2 (C3) | Individual Technical Expert / Environmental expert |  | Post | IC | P | 2014-06-01 | 6 | 2014-06-07 | [16 empty] | 28 | 2014-06-29 | 14 | 2014-07-13 | 180 | 2015-01-09
[5 empty] | R | 2016-01-15 | 6 | 2016-01-21 | [17 empty] | 2016-02-01 | 14 | 2016-02-15 | 180 | 2016-08-13
A
Restructuring revision
Total budgeted
Formulas:
Submission of EOIs = [Adverti- sement EOI/ Readiness]+[Interval /days]
Submission of EOIs = [Interval /days]+[Adverti- sement EOI/ Readiness]
Short listing and Preparation of RFP = [Submission of EOIs]+[Interval /days]
Short listing and Preparation of RFP = [Interval /days]+[Submission of EOIs]
No Objection = [Short listing and Preparation of RFP]+[Interval /days]
No Objection = [Technical Evaluation]+[Interval /days]
Issue RFP = [No Objection]+[Interval /days]
Issue RFP = [Interval /days]+[No Objection]
Expected Proposal Submission = [Issue RFP]+[Interval /days]
Expected Proposal Submission = [Issue RFP, row above]+[Interval /days]
Technical Evaluation = [Expected Proposal Submission]+[Interval /days]
Technical Evaluation = [No Objection]+[Interval /days]
Contract Award = Z7+[Interval /days]
Contract Award = [Adverti- sement EOI/ Readiness]+[Interval /days]
Start Date = [Contract Award]+[Interval /days]
Comple- tion Date = [Start Date]+[Interval /days]