## Settings (hidden)
Prior | Version: | 1
Post | Last changed: | 2009-04-13
| Revised by: | Andrew Alexander Jacobs
Firm
Individual
Yes
No
Goods
Works
Non-Consulting Services

## General
Sample Procurement Plan
I. General
1. | Project Information
| Project Name: | Greater Beirut Water Supply Project
| Country: | Lebanon
| Project ID: | IBRD 7010
| Loan/Credit Numbers: | 7967-LE/
2. | Bank's approval date of Procurement Plan | Original:
Revision 1:
Add new revisions
3. | Date of General Procurement Notice | 2011-01-24
II. Goods, Work and Non-Consulting Services Thresholds
1. | Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement: [Thresholds for applicable procurement methods (not limited to the list below) will be determined by the Procurement Specialist /Procurement Accredited Staff based on the assessment of the implementing agency’s capacity.]
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods | 250000
| Works | 500000
| Operational Cost | 2000
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| ICB and LIB (Goods) | ≥200,000.00
| NCB (Goods) | <200,000.00
| Shopping (Goods) | < 50,000.00
| ICB (Works) | ≥5,000,000.00
| NCB (Works) | <5,000,000.00
| Shopping (Works) | <50,000.00
2. | Prequalification. Bidders for __WTP_______ shall be prequlified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines.
3. | Proposed Procedures for CDD Components (as per paragraph 3.17 of the Guidelines): Refer to the relevant CDD project implementation document approved by the Bank
4. | Reference to (if any) Project Operational/Procurement Manual:
5. | Any Other Special Procurement Arrangements:Retroactive financing between Oct 1, 2010 and Loan Signing Date (≤12 months). Expenditures will not exceed a total of USD 12 million
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Consulting Firms (Competitive) | 100000
| Individual Consultants (Competitive) | 50000
| SSS | All
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| QCBS | Default
| QBS | TBD
| SSS | TBD
| LCS | TBD
| CQS | TBD
2. | Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $__equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
| Note: OPCPR list of ceilings can be found here: | http://go.worldbank.org/MKXO98RY40
3. | Any Other Special Selection Arrangements: Retroactive financing between Oct 1, 2010 and Loan Signing Date (≤12 months). Expenditures will not exceed a total of
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet
IV. Implementing Agency Capacity Building Activities with Time Schedule: See attached "Capacity Building" sheet

## Grand Summary
Category | Total Estimate (USD) | Awarded Contracts (USD) | Estimate of Remaining Contracts (USD) | WB share of Awarded Contracts (USD) | BMLWE share of awarded contracts (USD) | Expenditure incurred to Date (USD) | Expenditure incurred to Date WB part (USD) | Expenditure incurred BMLWE part (USD)
WORKS | 0 |  | 0 |  |  | 0 | 0 | 0
GOODS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONSULTING SERVICES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OPERATIONAL COST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PMU |  |  | 0 |  |  | 0 | 0 | 0
CAPACITY BUILDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL GBWSP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Detailed Summary
Type of Activity | Package/ Reference No. | Description of Goods/ Works | World Bank part | BMLWE part |  | Estimated Cost and Date of Estimate | Estimated Cost and Date of Estimate World Bank part | Estimated Cost and Date of Estimate BMLWE part | Name, City, and Country of Contractor (incl. Zip Code if US) | Contract Value | Contract Currency | Contract Value converted to US$ | Contract Value converted to US$ WB part | Contract Value converted to US$ BMLWE part | Contract Value converted to US$ CDR part | Expenditure incurred to Date converted to US$ | Expenditure incurred to Date WB part | Expenditure incurred to Date BMLWE part | Expenditure incurred to Date CDR part | Remaining | Remaining WB part | Remaining BMLWE part | Remaining CDR part
GOODS & WORKS | BWW2-1 | Distribution Networks, Pumping Stations & Reservoirs – Zone A | 2.5% | 97.5% | Planned |  |  |  | Cooperativa Edile Appennino scarl ITALY | 0 | USD | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW2-2 | Distribution Networks, Pumping Stations & Reservoirs – Zone B | 2.5% | 97.5% | Planned |  |  |  | JCC/WARD LEBANON | 0 | USD | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Amended |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW2-3 | Distribution Networks, Pumping Stations & Reservoirs – Zone C | 2.5% | 97.5% | Planned |  |  |  | VODOKANALPROEKT – METALPROEKT INGENEERING AD, Bulgaria | 0 | USD | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Amended |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW2-4 | Distribution Networks, Pumping Stations & Reservoirs – Zone D | 2.5% | 97.5% | Planned |  |  |  | LINDENBERG - EMIRATES LLC | 0 | USD | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Amended |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW1-A | Tunnel & Transfer lines | 100% on fixed part | 0% | Planned |  |  |  | COOPERATIVA MURATORI CEMENTISTI DI RAVENNA ITALY | 0 | USD | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Amended |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW1-C | Reservoirs & Transmission lines | 100% | 0% | Planned |  |  |  | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW1-B | Wardanieh Water Treatment Plant | 5% | 95% | Planned |  |  |  | OTV FRANCE |  | USD & Euros | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW2-5 | Meters (Canceled) | 5% | 95% | Planned | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW3-2-2 | Scada System for the Greater Beirut Project | 66% | 34% | Planned |  |  |  | EMCO Engineering LTD LEBANON |  | USD | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW3-2-3 | Supply, installaion and commissioning of water meters and data acquisition in a pilot zone in Beirut project | 66% | 34% | Planned |  |  |  | Nazih Braidi Est. for Engineering and Contracting LEBANON |  | USD | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWG3-2-4 | Fax machine Shopping | 66% | 34% | Planned |  |  |  | Sacotel (Badaro - Lebanon) |  | US$ | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0
| BWG3-2-5 | Computers Shopping | 66% | 34% | Planned |  |  |  | HCC Hannoun Computer Co Lebanon |  | US$ | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| BWG3-2-14 | Photocopy machine Multi feeder | 66% | 34% | Planned | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW3-4 | DMA and leak detection | 100% | 0% | Planned | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW3-5 | Coastal Metn DMA and leak detection | 100% | 0% | Planned | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW3-6 | Water Meters | 100% | 0% | Planned | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW3-7 | Coastal Metn Water Meters | 100% | 0% | Planned | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| BWW3-8 | Water Loss reduction and management in Achrafieh | 100% | 0% | Planned | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| TOTAL GOOD & WORKS | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
CONSULTING SERVICES | BWC1-A | Supervision of Tunnel & Transfer lines | 100% | 0% | Planned |  |  |  | Dar al Handasah shair & partners - D2 Consult International JV |  | US$ | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| #REF! |  |  |  | Revised
| #REF! |  |  |  | Actual
| BWC1-B | Supervision of Wardanieh Water Treatment Plant | 5% | 95% | Planned |  |  |  | Cabinet d'Etude Marc Merlin France |  | € & US$ | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| #REF! |  |  |  | Revised
| #REF! |  |  |  | Actual
| BWC1-C | Supervision of Reservoirs & Transmission lines | 0% | 100% | Planned |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 |  |  |  | Revised
| 0 |  |  |  | Actual
| BWC2-1 | Water Distribution Networks Design & Supervision | 2.5% | 97.5% | Planned |  |  |  | DAR AL HANDASAH NAZIH TALEB & PARTNERS SAFEGE JV (Lebanon-France) |  | € & L.L. | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 |  |  |  | Revised
| 0 |  |  |  | Amended
| BWC2-2 | Supervision of Meters | 5% | 95% | Planned |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 |  |  |  | Revised
| 0 |  |  |  | Actual
| BWC3-2 | BMLWE External Audit | 66% | 34% | Planned |  |  |  | USAMAH TABBARAH & CO Auditors & Consultants - NEXIA INTERNATIONAL, Beirut, Lebanon |  | L.L. | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 |  |  |  | Revised
| 0 |  |  |  | Actual
| BWC3-2-1 | PROJECT External Audit | 66% | 34% | Planned |  |  |  | Talal Abu Ghazaleh & Co. Lebanon |  | US$ | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 |  |  |  | Revised
| 0 |  |  |  | Actual
| BWC1-1 | Other Consultancies |  |  | Planned | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 |  |  |  | Revised
| 0 |  |  |  | Actual
| BWC3-2-2 | PROJECT External Audit (3 years) | 66% | 34% | Planned |  |  |  | Talal Abu Ghazaleh & Co. Lebanon |  | US$ | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 |  |  | Revised
| 0 | 0 |  |  | Actual
| BWC3-2-3 | PROJECT External Audit (2017-2018-2019) | 66% | 34% | Planned |  |  |  | Talal Abu Ghazaleh & Co. Lebanon |  | US$ | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 |  |  | Revised
| 0 | 0 |  |  | Actual
| BWC3-3 | Supervision of loss reduction management contract (PBC) | 100% | 0% | Planned | [5 empty] | US$ | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 |  |  | Revised
| 0 | 0 |  |  | Actual
| BWC3-2-4 | BMLWE External Audit (2016) | 100% | 0% | Planned |  |  |  | Talal Abu Ghazaleh & Co. Lebanon |  | US$ | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 |  |  | Revised
| 0 | 0 |  |  | Actual
| BWC3-2-5 | BMLWE External Audit (2017-2018-2019) | 100% | 0% | Planned | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 |  |  | Revised
| 0 | 0 |  |  | Actual
| BWC3-5 | Accounting consultant | 100% | 0% | Planned | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 |  |  | Revised
| 0 | 0 |  |  | Actual
| TOTAL CONSULTING SERVICES | [10 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
OPERATIONAL COST | BWG3-2-6 | Stationary Shopping (2014) | 66% | 34% | Planned | 0 | 0 | 0 | Librairie Halim (Dora - Lebanon)
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0
| BWG3-2-7 | Consumables Shopping (2014) | 66% | 34% | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWG3-2-8 | Paper Shredder Shopping | 66% | 34% | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWG3-2-9 | Insurance for 2 vehicules (2014) | 66% | 34% | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWG3-2-10 | Fuel oil for 2 vehicules (2014) | 66% | 34% | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWG3-2-11 | Stationary Shopping (2015) | 66% | 34% | Planned | 0 | 0 | 0 | Maliks (Beirut - Lebanon)
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0
| BWG3-2-12 | Fuel oil for 2 vehicules (2015) | 66% | 34% | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWG3-2-13 | Consumables Shopping (2015) | 66% | 34% | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWG3-2-14-1 | Maintenance for office equipments | 66% | 34% | Planned | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0
| BWG3-2-15 | Domain Server Fees | 66% | 34% | Planned | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0
| BWG3-2-16 | Stationary Shopping (2016) | 66% | 34% | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWG3-2-17 | Fuel oil for 2 vehicules (2016) | 66% | 34% | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWG3-2-18 | Consumables Shopping | 66% | 34% | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWG3-2-19 | Maintenance for office equipments (2016) | 66% | 34% | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Revised | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | Actual | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| TOTAL OPERATIONAL COST | [10 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
PMU | BWC3-1 | PMU BMLWE | 66% | 34% | [8 empty] | 0 | 0 | [8 empty] | 0
| BWC3-4 | PMU BMLWE | 100%
| BWC1-4 | PMU CDR | 100% | [9 empty] | 0 | [9 empty] | 0
| TOTAL PMU | [11 empty] | 0 | 0 | [8 empty] | 0
CAPACITY BUILDING | BWC3-2-1-1 | Training for WB financed projects | 66% | 34% | [7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWC3-2-1-2 | Training for WB financed projects | 66% | 34% |  | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| BWC3-2-1-3 | Training for WB financed projects | 66% | 34% |  | 0 | [5 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
| TOTAL CAPACITY BUILDING | [10 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
TOTAL GBWSP | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0

## Summary financial-physical %
Component | Package/ Reference No. | Description of Goods/ Works | World Bank part | BMLWE part | Pad Amount | Total Pad Amount | Contract/Estimated Amount | Contract/Estimated Total Amount | Physical Completed % | Paid Amount | Total Paid Amount | Percentage Paid | Remaining physical Quantities % | Remaining Amount | Total Remaining Amount | Percentage Amount Remaining | Contract/Estimated Value converted to US$ WB part | Contract Value converted to US$ BMLWE part | Contract Value converted to US$ CDR part | Expenditure incurred to Date WB part | Expenditure incurred to Date BMLWE part | Expenditure incurred to Date CDR part | Remaining WB part | Remaining BMLWE part | Remaining CDR part
I | BWW1-A | Tunnel & Transfer lines | 100% on fixed part | 0% |  |  |  |  | 90% | 0 | 0 |  | 10% | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [13 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [13 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
| BWC1-A | Supervision of Tunnel & Transfer lines | 100% | 0% |  |  |  |  | 0% |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
| #REF! | [16 empty] | 0 |  |  |  |  | 0 | 0 | 0
| #REF! | [16 empty] | 0 |  |  |  |  | 0 | 0 | 0
| BWW1-B | Wardanieh Water Treatment Plant | 5% | 95% |  |  |  |  | 0% | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [13 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [13 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
| BWC1-B | Supervision of Wardanieh Water Treatment Plant | 5% | 95% |  |  |  |  | 0% |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
| #REF! | [16 empty] | 0 |  |  |  |  | 0 | 0 | 0
| #REF! | [16 empty] | 0 |  |  |  |  | 0 | 0 | 0
| BWW1-C | Reservoirs & Transmission lines | 100% | 0% |  |  |  |  | 0% |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [13 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [13 empty] | 0 |  | 0 | 0 |  | 0 | 0 | 0
| BWC1-C | Supervision of Reservoirs & Transmission lines | 100% | 0% |  |  |  |  | 0% |  |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | [16 empty] | 0 |  |  |  |  | 0 | 0 | 0
| 0 | [16 empty] | 0 |  |  |  |  | 0 | 0 | 0
| BWC1-D | PMU CDR | 100% |  |  |  | 0 | 0 |  | 0 |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0 | 0
| Sub-Total I | [5 empty] | 0 | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
II | BWW2-1 | Distribution Networks, Pumping Stations & Reservoirs – Zone A | 2.5% | 97.5% |  | 0 |  | 0 | 100% | 0 | 0 |  | 0% | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [12 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [12 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| BWW2-2 | Distribution Networks, Pumping Stations & Reservoirs – Zone B | 2.5% | 97.5% |  |  |  |  | 100% | 0 |  |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [12 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [12 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| BWW2-3 | Distribution Networks, Pumping Stations & Reservoirs – Zone C | 2.5% | 97.5% |  |  |  |  | 100% | 0 |  |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [12 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [12 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| BWW2-4 | Distribution Networks, Pumping Stations & Reservoirs – Zone D | 2.5% | 97.5% |  |  |  |  | 95% | 0 |  |  | 5% | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [12 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [12 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| BWC2-1 | Water Distribution Networks Design & Supervision | 2.5% | 97.5% |  | 0 |  | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
0
0
| BWW2-5 | Meters (Canceled) | 5% | 95% |  | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [12 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0% | 0% | [12 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| BWC2-2 | Supervision of Meters | 5% | 95% |  | 0 | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| 0 | [15 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0
| 0 | [15 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0
| Sub-Total II |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
III | BWC3-1 | PMU BMLWE | 66% | 34% |  |  | 0 | 0
|  | Utility Strengthening | 66% | 34% |  |  | 0 | 0
|  | Studies | 66% | 34% |  |  | 0 | 0
| BWC3-2 | BMLWE External Audit | 66% | 34% |  |  | 0 | 0
| BWC3-2-1 | PROJECT External Audit | 66% | 34% |  |  | 0 | 0
| BWC3-2-2 | PROJECT External Audit (3 years) | 66% | 34% |  |  | 0 | 0
| BWC3-2-3 | PROJECT External Audit (2017-2018-2019) | 66% | 34% |  |  | 0 | 0
| BWC3-3 | Supervision of loss reduction management contract (PBC) | 100% | 0%
| BWC3-2-4 | BMLWE External Audit (2016) | 100% | 0%
| BWC3-2-5 | BMLWE External Audit (2017-2018-2019) | 100% | 0
| BWC3-5 | Accounting consultant | 100% | 0
| BWC3-4 | PMU BMLWE | 100% | 0%
| BWW3-2-2 | Scada System for the Greater Beirut Project | 66% | 34% |  |  |  |  | 80% | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0
| BWW3-2-3 | Supply, installaion and commissioning of water meters and data acquisition in a pilot zone in Beirut project | 66% | 34% |  |  |  |  | 0% | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
| BWW3-4 | DMA and leak detection | 100% | 0%
| BWW3-5 | Coastal Metn DMA and leak detection | 100% | 0%
| BWW3-6 | Water Meters | 100% | 0%
| BWW3-7 | Coastal Metn Water Meters | 100% | 0%
| BWW3-8 | Water Loss reduction and management in Achrafieh | 100% | 0%
| Sub-Total III |  |  |  |  | 0
GRAND TOTAL

## Goods and WorksPP
Procurement Plan for Goods/Works/Non-Consulting Services
Lebanon IBRD 7010: Greater Beirut Water Supply Project 7967-LE/
** Applicable in case of Bank's prior review | [13 empty] | Prequalification
| SL No. | Package/ Reference No. | Description of Goods/ Works | Goods/ Works/ NCS | Estimated Cost and Date of Estimate | World Bank part | BMLWE part | Estimated Cost and Date of Estimate World Bank part | Estimated Cost and Date of Estimate BMLWE part | Currency of Estimated Cost | Review by Bank (Prior/ Post) | Method of Selection | Domestic Preference (yes/no) | Prequalification (yes/no) | No Objection from Bank for Draft Prequalification documents (Date)** | No Objection from Bank for Evaluation of Prequalification Application (Date)** | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | Contract Award Decision (Date) | Bank’s No Objection to Bid Evaluation Report and Contract Award (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract Value converted to US$ | Contract Value converted to US$ WB part | Contract Value converted to US$ BMLWE part | Contract Value converted to US$ CDR part | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Completion of Contract (Date) | Expenditure incurred to Date converted to US$ | Expenditure incurred to Date WB part | Expenditure incurred to Date BMLWE part | Expenditure incurred to Date CDR part | Expenditure incurred to Date % | Physical Completed % | Remaining $ | Remaining WB part $ | Remaining BMLWE part $ | Remaining CDR part $ | Amount Remaining % | Physical Remaining % | Remarks
Planned | 1 | BWW2-1 | Distribution Networks, Pumping Stations & Reservoirs – Zone A | Works | 10920000 | 2.5% | 97.5% | 248747.1526 | 10671252.8474 | USD | Prior | ICB | NO | NO |  |  | 2012-03-01 | 2012-03-22 | 2012-04-06 | 2012-05-17 | 2012-05-17 | 2012-07-10 | 2012-07-17 | 2012-08-21 |  | USD | 0 | 0 | 0 |  | 6822/2014 | Cooperativa Edile Appennino scarl ITALY | 2015-11-30 | [5 empty] | 100% |  |  |  |  | #VALUE! | 0%
Revised |  |  |  |  | 18000000 |  |  | 410022.779 | 17589977.221
Actual |  |  |  |  | 17980514.26 |  |  | 409578.9125 | 17570935.3475
Amended |  |  |  |  | 17980262.49 |  |  | 409573.1774 | 17570689.3126 | [7 empty] | 2013-09-02 | 2014-02-03 | 2014-02-20 | 2014-04-10 | 2014-04-10 | 2014-05-19 | 2014-06-04 | 2014-08-06 | [8 empty] | 2018-04-10
Planned | 2 | BWW2-2 | Distribution Networks, Pumping Stations & Reservoirs – Zone B | Works | 9685000 | 2.5% | 97.5% | 220615.0342 | 9464384.9658 | USD | Prior | ICB | NO | NO |  |  | 2012-02-13 | 2012-02-27 | 2012-03-13 | 2012-04-23 | 2012-04-23 | 2012-06-04 | 2012-06-18 | 2012-07-23 |  | USD | 0 | 0 | 0 |  | 7018/2014 | JCC/WARD LEBANON | 2015-12-30 | [5 empty] | 100% |  |  |  |  | #VALUE! | 0%
Revised |  |  |  |  | 15000000 |  |  | 341685.6492 | 14658314.3508
Actual |  |  |  |  | 11772173.6248 |  |  | 268158.8525 | 11504014.7723
Amended |  |  |  |  | 9830790.18 |  |  | 223935.995 | 9606854.185 | [7 empty] | 2013-09-02 | 2014-02-03 | 2014-03-13 | 2014-05-06 | 2014-05-06 | 2014-06-02 | 2014-07-09 | 2014-08-06 | [8 empty] | 2018-08-23
Planned | 3 | BWW2-3 | Distribution Networks, Pumping Stations & Reservoirs – Zone C | Works | 10289500 | 2.5% | 97.5% | 234384.9658 | 10055115.0342 | USD | Prior | ICB | NO | NO |  |  | 2012-02-13 | 2012-02-27 | 2012-03-20 | 2012-04-30 | 2012-04-30 | 2012-06-14 | 2012-06-28 | 2012-08-02 |  | USD | 0 | 0 | 0 |  | 605/2014 | VODOKANALPROEKT – METALPROEKT INGENEERING AD, Bulgaria | 2015-05-21 | [5 empty] | 100% |  |  |  |  | #VALUE! | 0%
Revised |  |  |  |  | 25000000 |  |  | 569476.082 | 24430523.918
Actual |  |  |  |  | 22833974.2632 |  |  | 520136.088 | 22313838.1752
Amended |  |  |  |  | 22833665.5632 |  |  | 520129.0561 | 22313536.5071 | [7 empty] | 2013-02-13 | 2013-07-02 | 2013-07-25 | 2013-09-24 | 2013-09-24 | 2013-12-24 | 2014-01-10 | 2014-01-28 | [8 empty] | 2018-04-12
Planned | 4 | BWW2-4 | Distribution Networks, Pumping Stations & Reservoirs – Zone D | Works | 9488700 | 2.5% | 97.5% | 216143.508 | 9272556.492 | USD | Prior | ICB | NO | NO |  |  | 2012-03-01 | 2012-03-22 | 2012-06-13 | 2012-05-24 | 2012-05-24 | 2012-07-17 | 2012-07-24 | 2012-08-28 |  | USD | 0 | 0 | 0 |  | 3403/2015 | LINDENBERG - EMIRATES LLC | 2015-02-27 | [5 empty] | 95% |  |  |  |  | 100% | 5%
Revised |  |  |  |  | 13000000 |  |  | 296127.5626 | 12703872.4374 | [23 empty] | 2019-06-05
Actual |  |  |  |  | 0 |  |  | 0 | 0
Amended |  |  |  |  | 283.43 |  |  | 6.4563 | 276.9737 | [7 empty] | 2013-12-20 | 2014-10-03 | 2014-11-06 | 2015-01-07 | 2015-01-07 | 2015-03-31 | 2015-04-22 | 2015-05-27
Planned | 5 | BWW1-A | Tunnel & Transfer lines | Works | 159000000 | 100% on fixed part | 0% | 159000000 | 0 | USD | Prior | ICB | NO | YES | 2011-01-28 | 2011-05-13 | 2011-06-03 | 2011-06-10 | 2011-06-07 | 2011-08-01 | 2011-08-01 | 2011-12-05 | 2011-12-12 | 2012-01-09 |  | USD | 0 | 177204749.64 | 0 | -177204749.64 | 10902 | COOPERATIVA MURATORI CEMENTISTI DI RAVENNA ITALY | 2014-12-24 | [5 empty] | 90% |  |  |  |  | 100% | 10%
Revised |  |  |  |  | 182300000 |  |  | 182300000 | 0 | [23 empty] | 2019-01-30
Actual |  |  |  |  | 196989701.01 |  |  | 177204749.64 | 0 | [5 empty] | 2011-11-21 | 2013-01-17 | 2013-02-28 | 2013-07-17 | 2013-09-24 | 2014-05-12 | 2014-05-12 | 2015-03-17 | 2015-06-02 | 2015-07-06
Planned | 6 | BWW1-C | Reservoirs & Transmission lines | Works | 18400000 | 100% | 0% | 18400000 | 0 | USD | Prior | ICB | NO | No |  |  | 2011-08-03 | 2011-08-10 | 2011-08-11 | 2011-09-08 | 2011-09-08 | 2011-12-07 | 2011-12-14 | 2011-12-29 |  |  | 0 | 0 | 0 |  |  |  | 2014-12-24 | [10 empty] | 100% | 100%
Revised |  |  |  |  | 45000000 |  |  | 45000000 | 0 | [5 empty] | 2013-07-17: 2017-11-30 | [8 empty] | 2019-01-30
Actual | [7 empty] | 0 | 0 | [5 empty] | 2013-02-28: 2014-08-01
Planned | 7 | BWW1-B | Wardanieh Water Treatment Plant | Works | 49500000 | 5% | 95% | 2260273.9726 | 47239726.0274 | USD | Prior | ICB | NO | YES | [11 empty] | USD & Euros | 41805767.6189 | 1908939.1607 | 39896828.4582 |  | 4997/2017 | OTV FRANCE | 2014-02-18 |  |  |  |  | 0% | 5% |  |  |  |  | 100% | 95%
Revised | [7 empty] | 0 | 0 | [23 empty] | 2019-11-30
Actual |  |  |  |  | 41805767.6189 |  |  | 1908939.1607 | 39896828.4582 | [5 empty] | 2014-04-28 | 2015-08-20 | 2015-04-20 | 2016-12-08 | 2016-12-12 | 2017-03-15 | 2017-03-15 | 2017-08-11 | 2017-08-24 | 2017-09-15
Planned | 8 | BWW2-5 | Meters (Canceled) | Works | 19400000 | 5% | 95% | 885844.7489 | 18514155.2511 | USD | Prior | ICB | NO | No | [12 empty] | 0 | 0 | 0 | [14 empty] | 100% | 100%
Revised
Actual |  |  |  |  | 0 |  |  | 0 | 0
Planned | 12 | BWW3-2-2 | Scada System for the Greater Beirut Project | Works | 4000000 | 66% | 34% | 2553191.4894 | 1446808.5106 | USD | Prior | ICB | NO | YES | 2015-07-27 | 2015-10-20 | 2015-07-27 | 2015-10-20 | 2015-11-02 | 2015-12-21 | 2015-12-21 | 2016-01-18 | 2016-02-01 | 2016-03-01 |  | USD | 0 | 0 | 0 |  | 3955/A | EMCO Engineering LTD LEBANON | 2020-03-02 | [5 empty] | 80% |  |  |  |  | 100% | 20%
Revised | [7 empty] | 0 | 0 | [23 empty] | 2020-07-07
Actual | [7 empty] | 0 | 0 | [5 empty] | 2015-07-27 | 2016-02-04 | 2015-07-27 | 2015-12-20 | 2016-02-08 | 2016-04-15 | 2016-04-15 | 2016-06-09 | 2016-05-25 | 2016-07-06 | [8 empty] | .
Planned | 13 | BWW3-2-3 | Supply, installaion and commissioning of water meters and data acquisition in a pilot zone in Beirut project | Works | 5000000 | 66% | 34% | 3191489.3617 | 1808510.6383 | USD | Prior | ICB | NO | YES | [11 empty] | USD | 0 | 0 | 0 |  |  | Nazih Braidi Est. for Engineering and Contracting LEBANON | [11 empty] | 100% | 100%
Revised | [7 empty] | 0 | 0 | [23 empty] | 2020-02-06
Actual | [7 empty] | 0 | 0 | [8 empty] | 2016-03-24 | 2016-09-01 | 2016-10-13 | 2016-10-13 | 2017-12-22 | 2016-12-12 | 2017-02-06
Planned | 9 | BWG3-2-4 | Fax machine Shopping | Goods | 200 | 66% | 34% | 127.6596 | 72.3404 | USD | Post | Shopping | NO | No | 2015-03-17: 2014-03-03; 2015-07-06: 2014-03-18 |  | US$ | 0 | 0 | 0 |  | 128A | Sacotel (Badaro - Lebanon) | 2014-03-25 | [5 empty] | 100% |  |  |  |  | 100% | 0% | 1 fax machine
Revised | [7 empty] | 0 | 0
Actual |  |  |  |  | 279.18 |  |  | 178.2 | 100.98 | [5 empty] | 2015-03-17: 2014-04-02; 2015-07-06: 2014-04-02 | [8 empty] | 2014-04-02
Planned | 10 | BWG3-2-5 | Computers Shopping | Goods | 7500 | 66% | 34% | 4787.234 | 2712.766 | USD | Post | Shopping | NO | No | 2015-03-17: 2014-03-03; 2015-07-06: 2014-03-18 |  | US$ | 0 | 0 | 0 |  |  | HCC Hannoun Computer Co Lebanon | 2014-03-25 | [5 empty] | 100% |  |  |  |  | 100% | 0% | 6 computers/Laptops, printer
Revised | [7 empty] | 0 | 0 | [5 empty] | 2015-03-17: 2014-08-01
Actual | [7 empty] | 0 | 0 | [5 empty] | 2015-03-17: 2014-09-11; 2015-07-06: 2014-10-01 | [8 empty] | 2014-12-30
Planned | 11 | BWG3-2-14 | Photocopy machine Multi feeder | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Shopping | NO | No | 2015-03-17: 2015-02-12; 2015-07-06: 2015-02-26 |  |  | 0 | 0 | 0 |  |  |  | 2015-03-26 | [10 empty] | 100% | 100%
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0
Planned | 12 | BWW3-4 | DMA and leak detection | Works |  | 100% | 0% | 0 | 0 | USD | Prior | RfB | NO | Yes | 2018-11-15 | 2018-12-06 | 2018-08-31 | 2018-11-15 | 2019-03-26 | 2019-05-16 | 2019-05-16 | 2019-06-14 | 2019-06-28 | 2019-07-12 |  |  | 0 | 0 | 0 |  |  |  | 2020-11-30 | [10 empty] | 100% | 100%
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0
Planned | 13 | BWW3-5 | Coastal Metn DMA and leak detection | Works |  | 100% | 0% | 0 | 0 | USD | Prior | RfB | NO | No | [12 empty] | 0 | 0 | 0 | [14 empty] | 100% | 100%
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0
Planned | 14 | BWW3-6 | Water Meters | Works |  | 100% | 0% | 0 | 0 | USD | Prior | RfB | NO | Yes | 2018-11-15 | 2018-12-06 | 2018-08-31 | 2018-11-15 | 2019-04-01 | 2019-05-16 | 2019-05-16 | 2019-06-18 | 2019-07-03 | 2019-07-18 |  |  | 0 | 0 | 0 |  |  |  | 2020-11-30 | [10 empty] | 100% | 100%
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0
Planned | 15 | BWW3-7 | Coastal Metn Water Meters | Works |  | 100% | 0% | 0 | 0 | USD | Prior | RfB | NO | No | [12 empty] | 0 | 0 | 0 | [14 empty] | 100% | 100%
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0
Planned | 16 | BWW3-8 | Water Loss reduction and management in Achrafieh | Works |  | 100% | 0% | 0 | 0 | USD | Prior | RfB | NO | Yes | 2018-11-15 | 2019-07-08 |  | 2018-11-15 | 2019-07-25 | 2019-08-28 | 2019-08-28 | 2019-09-05 | 2019-09-12 | 2019-10-03 |  |  | 0 | 0 | 0 |  |  |  | 2020-11-30 | [10 empty] | 100% | 100%
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0 | [5 empty] | 2011-11-21: 2019-02-14; 2013-02-28: 2018-12-17
0
Formulas:
Completion of Contract (Date) = [Contract Signed (Date)]+4*365+2
Completion of Contract (Date) = [Contract Signed (Date), row below]+1462

## Consulting ServicesPP
Procurement Plan for Consultant Services
Lebanon IBRD 7010: Greater Beirut Water Supply Project 7967-LE/
** Applicable in case of Bank's prior review | [15 empty] | In some contracts, one or more of these approvals may be contained in one Bank communication.
| SL No. | Package/ Reference No. | Description of Services | Estimated Cost | World Bank part | BMLWE part | Estimated Cost and Date of Estimate World Bank part | Estimated Cost and Date of Estimate BMLWE part | Currency of Estimated Cost | Review by Bank (Prior/ Post) | Type of Consultant (Firm/ Individual) | Method of Selection | Advertising for Short listing (Date) | TOR/Shortlist to be Finalised (Date) | RFP Final Draft to be forwarded to the Bank (Date) | No Objection from Bank for TOR (Date)** | No Objection from Bank for Shortlist (Date)** | No Objection from Bank for Final RFP (Date)** | RFP Issued (Date) | Proposal Submission Deadline (Date) | No Objection by the Bank to the Technical Evaluation Report (Date)** | No Objection by the Bank (Technical/ #Combined/ Draft Contract/ Final Contract) (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Contract Value converted to US$ | Contract Value converted to US$ WB part | Contract Value converted to US$ BMLWE part | Name, City, and Country of Contractor (incl. Zip Code if US) | Services Completion (Date) | Expenses Incurred to Date Converted to US$ | Expenditure incurred to Date WB part | Expenditure incurred to Date BMLWE part | Expenditure incurred to Date % | Remaining | Remaining WB part | Remaining BMLWE part | Amount Remaining % | Remarks
Planned | 01 | BWC1-A | Supervision of Tunnel & Transfer lines | 6390000 | 100% | 0% | 6390000 | 0 |  |  |  |  | 2011-04-03 | 2011-05-05 | 2011-05-05 | 2011-06-08 | 2011-05-12 | 2011-06-08 | 2011-06-09 | 2011-07-06 | 2011-08-03 | 2011-08-24 | 2015-01-05 | 6351500 | US$ | 18338 |  | 0 | 0 | Dar al Handasah shair & partners - D2 Consult International JV | 2015-01-23 |  |  | 0 |  | 0 | 0 | 0
Revised |  |  |  | 7284000 |  |  | 7284000 | 0 | USD | Prior | Firm | QCBS | [18 empty] | 2019-01-30
Actual |  |  |  | 6477259.7 |  |  | 6477259.7 | 0 |  |  |  |  | 2011-09-09 | 2011-12-27 | 2012-07-12 | 2013-03-15 | 2012-01-22 | 2013-03-15 | 2013-05-29 | 2013-07-05 | 2014-04-15 | 2014-11-26
Planned | 02 | BWC1-B | Supervision of Wardanieh Water Treatment Plant | 1500000 | 5% | 95% | 68493.1507 | 1431506.8493 |  |  |  |  | 2011-08-30 | 2011-10-04 | 2011-10-05 | 2011-10-19 | 2011-10-18 | 2011-10-19 | 2011-10-20 | 2011-11-15 | 2011-12-13 | 2012-01-10 | 2018-02-02 | 989,708.24 € & 886,500 US$ | € & US$ |  |  | 0 | 0 | Cabinet d'Etude Marc Merlin France | 2014-03-18 |  |  |  |  | 0 | 0 | 0
Revised | [6 empty] | 0 | 0 | USD | Prior | Firm | QCBS | [8 empty] | 2017-10-12 | 2017-10-19 | [8 empty] | 2019-11-30
Actual | [6 empty] | 0 | 0 |  |  |  |  | 2015-04-28 | 2017-04-25 | 2017-04-25 | 2017-04-26 | 2017-04-25 | 2017-04-26 | 2017-08-19 | 2017-09-14
Planned | 03 | BWC1-C | Supervision of Reservoirs & Transmission lines | 710000 | 100% | 0% | 710000 | 0 |  |  |  |  | 2011-05-17 | 2011-07-14 | 2011-08-04 | 2011-08-10 | 2011-08-01 | 2011-08-10 | 2011-08-11 | 2011-09-07 | 2011-10-05 | 2011-10-26 | [5 empty] | 0 | 0 |  | 2015-01-23 |  |  |  |  | 0 | 0 | 0
Revised |  |  |  | 808000 |  |  | 808000 | 0 | USD | Prior | Firm | QCBS | [9 empty] | 2017-11-11 | [8 empty] | 2019-01-30
Actual | [6 empty] | 0 | 0 |  |  |  |  | 2011-09-09 | 2011-12-27 | 2012-07-12 | 2013-03-15 | 2012-01-22 | 2013-03-15 | 2013-05-29 | 2013-07-05 | 2014-04-15
Planned | 04 | BWC2-1 | Water Distribution Networks Design & Supervision | 2150000 | 2.5% | 97.5% | 616800 | 2101025.0569 | [14 empty] | 2012-03-28 |  | € & L.L. | 7/MA |  | 0 | 0 | DAR AL HANDASAH NAZIH TALEB & PARTNERS SAFEGE JV (Lebanon-France) | 2016-01-29 |  |  |  |  | 0 | 0 | 0
Revised | [6 empty] | 0 | 0 | USD | Prior | Firm | QCBS | [18 empty] | 2019-04-10
Actual |  |  |  | 2131449.8002 |  |  | 48552.3872 | 2082897.413 | [15 empty] | 117,511.24 € & 2,972,309,536.36 L.L.
Amended |  |  |  | 2858042 |  |  | 65103.4624 | 2792938.5376 |  |  |  |  | 2011-02-10 | 2011-08-04 | 2011-08-12 | 2011-09-07 | 2011-08-19 | 2011-09-07 | 2011-09-08 | 2011-10-12 | 2011-11-04 | 2011-12-08 |  | 117,511.24 € & 5,520,633,906.65 L.L.
Planned | 05 | BWC2-2 | Supervision of Meters (Canceled activity) To be done by BMLWE | 600000 | 5% | 95%
Revised | [8 empty] | USD | Prior | Firm | QCBS
Actual
Planned | 06 | BWC3-2 | BMLWE External Audit | 55000 | 66% | 34% | 35106.383 | 19893.617 | [14 empty] | 2011-11-12 | 81400000 | L.L. | 207/MA |  | 0 | 0 | USAMAH TABBARAH & CO Auditors & Consultants - NEXIA INTERNATIONAL, Beirut, Lebanon | 2011-11-18 |  |  |  |  | 0 | 0 | 0
Revised | [6 empty] | 0 | 0 | USD | Prior | Firm | LC | [9 empty] | retroactive
Actual | [6 empty] | 0 | 0 |  |  |  |  | 2011-05-31 | 2011-03-14 | 2011-04-14 | 2011-04-16 | 2011-04-16 | 2011-04-16 | 2011-09-05 | 2011-09-26 | 2011-10-05 | 2014-02-04 | [8 empty] | 2012-02-12
Planned | 07 | BWC3-2-1 | PROJECT External Audit 2014 | 25000 | 66% | 34% | 15957.4468 | 9042.5532 |  |  |  |  | 2014-03-06 | 2014-02-10 | 2014-02-10 | 2014-02-20 | 2014-03-25 | 2014-02-20 | 2014-04-03 | 2014-04-22 | 2014-05-02 | 2014-05-09 | 2014-06-03 | 3929.2 | US$ |  |  | 0 | 0 | Talal Abu Ghazaleh & Co. Lebanon | 2014-06-14 |  |  |  |  | 0 | 0 | 0
Revised | [6 empty] | 0 | 0 | USD | Post | Firm | LC
Actual |  |  |  | 3929.2 |  |  | 2508 | 1421.2 | [5 empty] | 2014-02-10 | 2014-02-10 | 2014-05-02 | 2014-05-02 | 2014-05-02 | 2014-05-19 | 2014-06-02 | 2014-06-03 | 2014-06-11 | [8 empty] | 2014-06-30
Planned | 08 | BWC1-1 | Other Consultancies | [32 empty] | 0 | 0 | 0
Revised | [8 empty] | USD | Prior | Firm | QCBS-IC
Actual
Planned | 09 | BWC3-2-2 | PROJECT External Audit (3 years) |  | 66% | 34% | 0 | 0 | [5 empty] | 2015-01-15 | 2015-01-15 | 2015-01-22 | 2015-01-15 | 2015-01-22 | 2015-02-05 | 2015-02-26 | 2015-03-05 | 2015-03-19 |  |  | US$ |  |  |  |  | Talal Abu Ghazaleh & Co. Lebanon | 2015-04-30 |  |  | 0 |  | 0 | 0 | 0
Revised | [6 empty] | 0 | 0 | USD | Post | Firm | LC | [18 empty] | 2017-06-30
Actual | [6 empty] | 0 | 0 | [5 empty] | 2015-03-16 | 2015-03-16 | 2015-03-19 | 2015-03-19 | 2015-03-19 | 2015-04-03 | 2015-05-12
Planned | 10 | BWC3-2-3 | PROJECT External Audit (2017-2018-2019) |  | 66% | 34% | [7 empty] | 2014-06-11: 2018-09-04 | 2018-09-07 |  | US$ |  |  |  |  | Talal Abu Ghazaleh & Co. Lebanon | 2019-06-30 |  |  |  |  | 0 | 0 | 0
Revised | [8 empty] | USD | Post | Firm | SS
Actual
Planned | 11 | BWC3-3 | Supervision of loss reduction management contract (PBC) |  | 100% | 0% | [7 empty] | 2018-09-18 | 2018-09-25 | 2018-10-02 | 2018-11-01 | 2018-11-16 | 2018-12-01 | 2019-01-25 | 2019-02-07 | 2019-02-25 | 2019-03-27 |  | US$ | [10 empty] | 0 | 0 | 0
Revised | [8 empty] | USD | Prior | Firm | CQBS
Actual
Planned | 12 | BWC3-4 | PMU BMLWE (several contracts) |  | 100% | 0% | [18 empty] | US$ | [10 empty] | 0 | 0 | 0
Revised | [8 empty] | USD | Post | Individual | IC
Actual
Planned | 13 | BWC3-2-4 | BMLWE External Audit (2016) |  | 66% | 34% | 0 | 0 | [5 empty] | 2019-03-27: 2018-06-28 |  | US$ |  |  |  |  | Talal Abu Ghazaleh & Co. Lebanon |  |  |  | 0 |  | 0 | 0 | 0
Revised | [6 empty] | 0 | 0 | USD | Post | Firm | SS | [18 empty] | 2018-10-31
Actual | [6 empty] | 0 | 0
Planned | 13 | BWC3-2-5 | BMLWE External Audit (2017-2018-2019) |  | 66% | 34% | 0 | 0 | [5 empty] | 2019-03-27: 2018-11-01 | [10 empty] | 0 |  | 0 | 0 | 0
Revised | [6 empty] | 0 | 0 | USD | Post | Firm | SS
Actual | [6 empty] | 0 | 0
Planned | 14 | BWC3-5 | Accounting consultant |  | 66% | 34% | 0 | 0 |  |  |  |  | 2019-01-25 | 2018-09-18: 2019-01-25; 2019-01-25: 2019-02-11; 2019-03-27: 2019-02-18 | [10 empty] | 0 |  | 0 | 0 | 0
Revised | [6 empty] | 0 | 0 | USD | Post | Firm | LC
Actual | [6 empty] | 0 | 0

## Operational CostPP
Procurement Plan for Goods/Works/Non-Consulting Services
Lebanon IBRD 7010: Greater Beirut Water Supply Project 7967-LE/
** Applicable in case of Bank's prior review | [13 empty] | Prequalification
| SL No. | Package/ Reference No. | Description of Goods/ Works | Goods/ Works/ NCS | Estimated Cost and Date of Estimate | World Bank part | BMLWE part | Estimated Cost and Date of Estimate World Bank part | Estimated Cost and Date of Estimate BMLWE part | Currency of Estimated Cost | Review by Bank (Prior/ Post) | Method of Selection | Domestic Preference (yes/no) | Prequalification (yes/no) | No Objection from Bank for Draft Prequalification documents (Date)** | No Objection from Bank for Evaluation of Prequalification Application (Date)** | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | Contract Award Decision (Date) | Bank’s No Objection to Bid Evaulation Report and Contract Award (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract Value converted to US$ | Contract Value converted to US$ WB part | Contract Value converted to US$ BMLWE part | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Completion of Contract (Date) | Expenditure incurred to Date | Expenditure incurred to Date WB part | Expenditure incurred to Date BMLWE part | Remaining | Remaining WB part | Remaining BMLWE part | Remarks
Planned | 01 | BWG3-2-6 | Stationary Shopping (2014) | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Shopping | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  | US$ | 0 | 0 | 0 | 191A | Librairie Halim (Dora - Lebanon) | 2014-03-25 | 0 | 0 | 0 | 0 | 0 | 0
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0 | [12 empty] | 2014-05-15 |  | 2014-04-15 | [7 empty] | 2014-05-23
Planned | 02 | BWG3-2-7 | Consumables Shopping (2014) | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Single Source | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 0 | 0 | 0 |  |  | 2014-12-31 |  | 0 | 0 | 0 | 0 | 0 | Office daily consumables
Revised | [7 empty] | 0 | 0 | [12 empty] | 2014-08-01 |  | 2014-08-15 | [7 empty] | 2014-08-22
Actual | [7 empty] | 0 | 0
Planned | 03 | BWG3-2-8 | Paper Shredder Shopping | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Shopping | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 0 | 0 | 0 |  |  | 2014-03-25 |  | 0 | 0 | 0 | 0 | 0
Revised | [7 empty] | 0 | 0 | [12 empty] | 2015-08-01 |  | 2015-08-15 | [7 empty] | 2015-08-22
Actual | [7 empty] | 0 | 0
Planned | 04 | BWG3-2-9 | Insurance for 2 vehicules (2014) | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Shopping | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 0 | 0 | 0 |  |  | 2014-03-25 |  | 0 | 0 | 0 | 0 | 0
Revised | [7 empty] | 0 | 0 | [12 empty] | 2014-08-01 |  | 2014-08-15 | [7 empty] | 2014-08-22
Actual | [7 empty] | 0 | 0
Planned | 05 | BWG3-2-10 | Fuel oil for 2 vehicules (2014) | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Single Source | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 0 | 0 | 0 |  |  | 2014-12-31 |  | 0 | 0 | 0 | 0 | 0
Revised | [7 empty] | 0 | 0 | [12 empty] | 2014-08-01 |  | 2014-08-15 | [7 empty] | 2014-08-22
Actual | [7 empty] | 0 | 0
Planned | 06 | BWG3-2-11 | Stationary Shopping (2015) | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Shopping | NO | No | [7 empty] | 2015-01-30 |  | 2015-02-13 |  | US$ | 0 |  | 0 | 794A | Maliks (Beirut - Lebanon) |  |  |  |  | 0 | 0
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0 | [12 empty] | 2015-08-12 |  | 2015-08-13 | [7 empty] | 2015-08-15
Planned | 07 | BWG3-2-12 | Fuel oil for 2 vehicules (2015) | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Single Source | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 0 | 0 | 0 |  |  | 2014-12-31 |  | 0 | 0 | 0 | 0 | 0
Revised | [7 empty] | 0 | 0 | [12 empty] | 2015-08-01 |  | 2015-08-15 | [7 empty] | 2015-08-22
Actual | [7 empty] | 0 | 0
Planned | 08 | BWG3-2-13 | Consumables Shopping (2015) | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Single Source | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 0 | 0 | 0 |  |  | 2014-12-31 |  | 0 | 0 | 0 | 0 | 0 | Office daily consumables
Revised | [7 empty] | 0 | 0 | [12 empty] | 2015-08-01 |  | 2015-08-15 | [7 empty] | 2015-08-22
Actual | [7 empty] | 0 | 0
Planned | 09 | BWG3-2-14-1 | Maintenance for office equipments | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Single Source | NO | No | [11 empty] | US$ | 0 | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 | Photocopy, coffee, fax, … - Repair Computer
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0 | [12 empty] | 2015-01-01 |  | 2015-01-01 | [7 empty] | 2015-12-31
Planned | 10 | BWG3-2-15 | Domain Server Fees | Non-Consulting Services |  | 66% | 34% | 0 | 0 | USD | Post | Single Source | NO | No | [11 empty] | US$ | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | Domain IDM for 4 years
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0 | [12 empty] | 2015-03-19 |  | 2015-03-19 | [7 empty] | 2015-03-19
Planned | 11 | BWG3-2-16 | Stationary Shopping (2016) | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Shopping | NO | No | [7 empty] | 2016-03-07 |  | 2016-03-25 | [7 empty] | 2016-12-31 |  | 0 | 0 | 0 | 0 | 0
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0
Planned | 12 | BWG3-2-17 | Fuel oil for 2 vehicules (2016) | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Single Source | NO | No | [7 empty] | 2016-03-07 |  | 2016-03-25 |  |  | 0 | 0 | 0 |  |  | 2016-12-31 |  | 0 | 0 | 0 | 0 | 0
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0
Planned | 13 | BWG3-2-18 | Consumables Shopping | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Single Source | NO | No | [7 empty] | 2016-03-07 |  | 2016-03-25 |  |  | 0 | 0 | 0 |  |  | 2019-12-31 |  | 0 | 0 | 0 | 0 | 0 | Office daily consumables, operational cost, advertising, etc…
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0
Planned | 14 | BWG3-2-19 | Maintenance for office equipments (2016) | Goods |  | 66% | 34% | 0 | 0 | USD | Post | Single Source | NO | No | [7 empty] | 2016-03-07 |  | 2016-03-25 | [11 empty] | 0 | 0 | 0
Revised | [7 empty] | 0 | 0
Actual | [7 empty] | 0 | 0
Formulas:
Contract Signed (Date) = [Contract Award Decision (Date)]+14
Completion of Contract (Date) = [Contract Signed (Date)]+7

## PMUPP
Procurement Plan for Consultant Services
Lebanon IBRD 7010: Greater Beirut Water Supply Project 7967-LE/
** Applicable in case of Bank's prior review
2019-03-01 | SL No. | Package/ Reference No. | Description of Services | Estimated Cost | Currency of Estimated Cost | Review by Bank (Prior/ Post) | Type of Consultant (Firm/ Individual) | Method of Selection | Contract Signed (Date) | Contract Start (Date) | Contract Value | Contract Currency | Converted Contract Value in US$ | Contract No. | World Bank part | BMLWE part | Estimated Cost and Date of Estimate World Bank part | Estimated Cost and Date of Estimate BMLWE part | Name of Consultant | Services Completion (Date) | Expenses Incurred to Date | Expenses Incurred to Date World Bank part | Expenses Incurred to Date BMLWE part | Remaining World Bank part | Remaining BMLWE part | Remaining CDR part | Remarks
Actual | 1-1 | BWC3-1-1-1 | Project Coordinator |  | USD | Post | Individual | IC | 2010-12-24 | 2010-12-01 | 108000000 | L.L. | 71641.791 |  | 66% | 34% | 47283.5821 | 24358.209 | Randa Daher | 2011-11-30 | 71641.791 | 47283.5821 | 24358.209 | 0 | 0
Actual | 1-2 | BWC3-1-1-2 | [6 empty] | 2012-01-01 | 2011-12-01 | 108000000 | L.L. | 71641.791 |  | 66% | 34% | 47283.5821 | 24358.209 |  | 2012-11-30 | 71641.791 | 47283.5821 | 24358.209 | 0 | 0 |  | Extension in new contract form
Actual | 1-3 | BWC3-1-1-3 | [6 empty] | 2013-01-01 | 2012-12-01 | 108000000 | L.L. | 71641.79 |  | 66% | 34% | 47283.5814 | 24358.2086 |  | 2013-11-30 | 71641.79 | 47283.5814 | 24358.2086 | 0 | 0 |  | Extension in new contract form
Actual | 1-3-1 | BWC3-1-1-3-1 | [6 empty] | 2013-12-01 | 2013-12-01 | 0 | USD | 0 |  | 66% | 34% | 0 | 0 |  | 2013-12-31 |  | 0 | 0 | 0 | 0 |  | Addendum
Actual | 1-4 | BWC3-1-1-4 | [6 empty] | 2014-01-23 | 2014-01-01 | 72000 | USD | 72000 |  | 66% | 34% | 47520 | 24480 |  | 2014-12-31 | 72000 | 47520 | 24480 | 0 | 0 |  | Contract extension
Actual | 1-5 | BWC3-1-1-5 | [6 empty] | 2015-01-02 | 2015-01-01 | 75600 | USD | 75600 |  | 66% | 34% | 49896 | 25704 |  | 2015-12-31 | 75600 | 49896 | 25704 | 0 | 0 |  | Contract extension
Actual | 1-6 | BWC3-1-1-6 | [6 empty] | 2016-02-23 | 2016-01-01 | 39690 | USD | 39690 |  | 66% | 34% | 26195.4 | 13494.6 |  | 2016-06-30 | 39690 | 26195.4 | 13494.6 | 0 | 0 |  | Contract extension
Actual | 1-7 | BWC3-1-1-7 | [6 empty] | 2016-03-14 | 2013-12-01 | 6000 | USD | 6000 |  | 66% | 34% | 3960 | 2040 |  | 2013-12-31 | 0 | 3960 | 0 | 0 | 2040 |  | Contract extension
Actual | 1-8 | BWC3-1-1-8 | [6 empty] | 2016-07-05 | 2016-07-01 | 39690 | USD | 39690 |  | 66% | 34% | 26195.4 | 13494.6 |  | 2016-12-31 | 39690 | 26195.4 | 13494.6 | 0 | 0 |  | Contract extension
Actual | 1-9 | BWC3-1-1-9 | [6 empty] | 2017-01-18 | 2017-01-01 | 87600 | USD | 87600 |  | 66% | 34% | 57816 | 29784 |  | 2017-12-31 | 87600 | 57816 | 29784 | 0 | 0 |  | Contract extension
Actual | 1-10 | BWC3-1-1-10 | [6 empty] | 2018-01-29 | 2018-01-01 | 99590.4 | USD | 99590.4 |  | 66% | 34% | 63360 | 36230.4 |  | 2018-12-31 | 99590.4 | 63360 | 36230.4
Planned | 1-11 | BWC3-1-1-11 | [6 empty] | 2019-01-17 | 2019-01-01 | 99590.4 | USD | 99590.4 |  | 66% | 34% | 63360 | 36230.4 |  | 2019-12-31 | 16598.4 | 10560 | 6038.4 | 52800 | 30192 |  | Contract extension
Actual | 2-1 | BWC3-1-2-1 | Project Operations Advisor |  | USD | Post | Individual | IC | 2012-06-01 | 2012-06-01 | 126000000 | L.L. | 83582.0896 |  | 66% | 34% | 55164.1791 | 28417.9104 | Randa Nemer | 2013-06-01 | 83582.0896 | 55164.1791 | 28417.9104 | 0 | 0
Actual | 2-2 | BWC3-1-2-2 | [6 empty] | 2013-06-01 | 2013-06-01 | 126000000 | L.L. | 83582.0896 |  | 66% | 34% | 55164.1791 | 28417.9104 |  | 2014-06-01 | 83582.0896 | 55164.1791 | 28417.9104 | 0 | 0 |  | Contract extension
Actual | 2-3 | BWC3-1-2-3 | [6 empty] | 2014-06-01 | 2014-06-01 | 49000 | USD | 49000 |  | 66% | 34% | 32340 | 16660 |  | 2014-12-31 | 49000 | 32340 | 16660 | 0 | 0 |  | Contract extension
Actual | 2-4 | BWC3-1-2-4 | [6 empty] | 2015-01-02 | 2015-06-01 | 49000 | USD | 49000 |  | 66% | 34% | 32340 | 16660 |  | 2015-12-31 | 49000 | 32340 | 16660 | 0 | 0 |  | Contract extension
Actual | 2-5 | BWC3-1-2-5 | [6 empty] | 2016-02-15 | 2016-01-01 | 46305 | USD | 46305 |  | 66% | 34% | 30561.3 | 15743.7 |  | 2016-06-30 | 46305 | 30561.3 | 15743.7 | 0 | 0 |  | Contract extension
Actual | 4-1 | BWC3-1-4-1 | Procurement Specialist |  | USD | Post | Individual | IC | 2010-12-24 | 2010-11-01 | 99000000 | L.L. | 65671.6418 |  | 66% | 34% | 43343.2836 | 22328.3582 | Bassam Nasrallah | 2011-10-31 | 65671.6418 | 43343.2836 | 22328.3582 | 0 | 0
Actual | 4-2 | BWC3-1-4-2 | [6 empty] | 2012-01-01 | 2011-11-01 | 99000000 | L.L. | 65671.64 |  | 66% | 34% | 43343.2824 | 22328.3576 |  | 2012-10-31 | 65671.64 | 43343.2824 | 22328.3576 | 0 | 0 |  | Extension in new contract form
Actual | 4-3 | BWC3-1-4-3 | [6 empty] | 2013-01-01 | 2012-11-01 | 99000000 | L.L. | 65671.64 |  | 66% | 34% | 43343.2824 | 22328.3576 |  | 2013-10-31 | 65671.64 | 43343.2824 | 22328.3576 | 0 | 0 |  | Extension in new contract form
Actual | 4-3-1 | BWC3-1-4-3-1 | [6 empty] | 2013-11-01 | 2013-11-01 | 11000 | USD | 11000 |  | 66% | 34% | 7260 | 3740 |  | 2013-12-31 |  | 0 | 0 | 7260 | 3740 |  | Addendum
Actual | 4-4 | BWC3-1-4-4 | [6 empty] | 2014-01-23 | 2014-01-01 | 66000 | USD | 66000 |  | 66% | 34% | 43560 | 22440 |  | 2014-12-31 | 66000 | 43560 | 22440 | 0 | 0 |  | Contract extension
Actual | 4-5 | BWC3-1-4-5 | [6 empty] | 2015-01-02 | 2015-01-01 | 11550 | USD | 11550 |  | 66% | 34% | 7623 | 3927 |  | 2015-12-31 | 11550 | 7623 | 3927 |  |  |  | Contract extension Ended on February 28, 2015
Actual | 4-6 | BWC3-1-4-6 | [6 empty] | 2016-03-14 | 2013-11-01 | 11000 | USD | 11000 |  | 66% | 34% | 7260 | 3740 |  | 2013-12-31 | 0 | 0 | 0 | 7260 | 3740 |  | Contract extension
Actual | 5-1 | BWC3-1-5-1 | Financial Manager |  | USD | Post | Individual | IC | 2010-12-24 | 2010-11-01 | 99000000 | L.L. | 65671.6418 |  | 66% | 34% | 43343.2836 | 22328.3582 | Nizar Najem | 2011-10-31 | 65671.6418 | 43343.2836 | 22328.3582 | 0 | 0
Actual | 5-2 | BWC3-1-5-2 | [6 empty] | 2012-01-01 | 2011-11-01 | 99000000 | L.L. | 65671.64 |  | 66% | 34% | 43343.2824 | 22328.3576 |  | 2012-10-31 | 65671.64 | 43343.2824 | 22328.3576 | 0 | 0 |  | Extension in new contract form
Actual | 5-3 | BWC3-1-5-3 | [6 empty] | 2013-01-01 | 2012-11-01 | 99000000 | L.L. | 65671.64 |  | 66% | 34% | 43343.2824 | 22328.3576 |  | 2013-10-31 | 65671.64 | 43343.2824 | 22328.3576 | 0 | 0 |  | Extension in new contract form
Actual | 5-3-1 | BWC3-1-5-3-1 | [6 empty] | 2013-11-01 | 2013-11-01 | 1833.3333 | USD | 1833.3333 |  | 66% | 34% | 1210 | 623.3333 |  | 2013-12-31 |  | 0 | 0 | 1210 | 623.3333 |  | Addendum
Actual | 5-4 | BWC3-1-5-4 | [6 empty] | 2014-01-23 | 2014-01-01 | 66000 | USD | 66000 |  | 66% | 34% | 43560 | 22440 |  | 2014-12-31 | 66000 | 43560 | 22440 | 0 | 0 |  | Contract extension
Actual | 5-5 | BWC3-1-5-5 | [6 empty] | 2016-03-14 | 2013-11-01 | 11000 | USD | 11000 |  | 66% | 34% | 7260 | 3740 |  | 2013-12-31 | 0 | 0 | 0 | 7260 | 3740 |  | Contract extension
Actual | 6-1 | BWC3-1-6-1 | Administrative Assistant |  | USD | Post | Individual | IC | 2012-03-30 | 2012-03-30 | 18000000 | L.L. | 11940 |  | 66% | 34% | 7880.4 | 4059.6 | Farah Farraj | 2013-03-29 | 11940 | 7880.4 | 4059.6 | 0 | 0
Actual | 6-2 | BWC3-1-6-2 | [6 empty] | 2013-03-30 | 2013-03-30 | 18000000 | L.L. | 11940 |  | 66% | 34% | 7880.4 | 4059.6 |  | 2014-03-29 | 11940 | 7880.4 | 4059.6 | 0 | 0 |  | Extension in new contract form
Actual | 6-3 | BWC3-1-6-3 | [6 empty] | 2014-03-30 | 2014-03-30 | 9000 | USD | 9000 |  | 66% | 34% | 5940 | 3060 |  | 2014-12-31 | 9000 | 5940 | 3060 | 0 | 0 |  | Contract extension
Actual | 6-4 | BWC3-1-6-4 | [6 empty] | 2015-01-02 | 2015-01-01 | 12600 | USD | 12600 |  | 66% | 34% | 8316 | 4284 |  | 2015-12-31 | 12600 | 8316 | 4284 | 0 | 0 |  | Contract extension
Actual | 6-5 | BWC3-1-6-5 | [6 empty] | 2016-02-15 | 2016-01-01 | 6615 | USD | 6615 |  | 66% | 34% | 4365.9 | 2249.1 |  | 2016-06-30 | 6615 | 4365.9 | 2249.1 | 0 | 0 |  | Contract extension
Actual | 6-6 | BWC3-1-6-6 | [6 empty] | 2016-07-05 | 2016-07-01 | 6615 | USD | 6615 |  | 66% | 34% | 4365.9 | 2249.1 |  | 2016-12-31 | 6615 | 4365.9 | 2249.1 | 0 | 0 |  | Contract extension
Actual | 6-7 | BWC3-1-6-7 | [6 empty] | 2017-01-18 | 2017-01-01 | 15000 | USD | 15000 |  | 66% | 34% | 9900 | 5100 |  | 2017-12-31 | 15000 | 9900 | 5100 | 0 | 0 |  | Contract extension
Actual | 6-8 | BWC3-1-6-8 | [6 empty] | 2018-01-29 | 2018-01-01 | 18000 | USD | 18000 |  | 66% | 34% | 11880 | 6120 |  | 2018-12-31 | 18000 | 11880 | 6120 | 0 | 0 |  | Contract extension
Planned | 6-9 | BWC3-1-6-9 | [6 empty] | 2019-01-17 | 2019-01-01 | 18000 | USD | 18000 |  | 66% | 34% | 11880 | 6120 |  | 2019-12-31 | 3000 | 1980 | 1020 | 9900 | 5100 |  | Contract extension
Actual | 7-1 | BWC3-1-7-1 | Electro Mechanical Eng |  | USD | Post | Individual | IC | 2012-03-01 | 2012-03-30 | 73000000 | L.L. | 48425 |  | 66% | 34% | 31960.5 | 16464.5 | Mazen Hammoud | 2013-03-29 | 48425 | 31960.5 | 16464.5 | 0 | 0
Actual | 7-2 | BWC3-1-7-2 | [6 empty] | 2013-03-01 | 2013-03-30 | 73000000 | L.L. | 48425 |  | 66% | 34% | 31960.5 | 16464.5 |  | 2014-03-29 | 48425 | 31960.5 | 16464.5 | 0 | 0 |  | Extension in new contract form
Actual | 7-3 | BWC3-1-7-3 | [6 empty] | 2014-03-30 | 2014-03-30 | 36500 | USD | 36500 |  | 66% | 34% | 24090 | 12410 |  | 2014-12-31 | 36500 | 24090 | 12410 | 0 | 0 |  | Contract extension
Actual | 7-4 | BWC3-1-7-4 | [6 empty] | 2015-01-02 | 2015-01-01 | 51093 | USD | 51093 |  | 66% | 34% | 33721.38 | 17371.62 |  | 2015-12-31 | 51093 | 33721.38 | 17371.62 | 0 | 0 |  | Contract extension
Actual | 8-1 | BWC3-1-8-1 | Monitoring & Evaluation |  | USD | Post | Individual | IC | 2012-03-01 | 2012-03-01 | 108000000 | L.L. | 71641.791 |  | 66% | 34% | 47283.5821 | 24358.209 | Joseph deeb | 2013-02-28 | 71641.791 | 47283.5821 | 24358.209 | 0 | 0
Actual | 8-2 | BWC3-1-8-2 | [6 empty] | 2013-03-01 | 2013-03-01 | 108000000 | L.L. | 71641.791 |  | 66% | 34% | 47283.5821 | 24358.209 |  | 2014-02-28 | 71641.791 | 47283.5821 | 24358.209 | 0 | 0 |  | Extension in new contract form
Actual | 8-3 | BWC3-1-8-3 | [6 empty] | 2014-03-01 | 2014-03-01 | 60000 | USD | 60000 |  | 66% | 34% | 39600 | 20400 |  | 2014-12-31 | 60000 | 39600 | 20400 | 0 | 0 |  | Contract extension
Actual | 8-4 | BWC3-1-8-4 | [6 empty] | 2015-01-02 | 2015-01-01 | 75600 | USD | 75600 |  | 66% | 34% | 49896 | 25704 |  | 2015-12-31 | 75600 | 49896 | 25704 | 0 | 0 |  | Contract extension
Actual | 8-5 | BWC3-1-8-5 | [6 empty] | 2016-02-15 | 2016-01-01 | 39690 | USD | 39690 |  | 66% | 34% | 26195.4 | 13494.6 |  | 2016-06-30 | 39690 | 26195.4 | 13494.6 | 0 | 0 |  | Contract extension
Actual | 8-6 | BWC3-1-8-6 | [6 empty] | 2016-07-05 | 2016-07-01 | 39690 | USD | 39690 |  | 66% | 34% | 26195.4 | 13494.6 |  | 2016-12-31 | 39690 | 26195.4 | 13494.6 | 0 | 0 |  | Contract extension
Actual | 8-7 | BWC3-1-8-7 | [6 empty] | 2017-01-18 | 2017-01-01 | 79380 | USD | 79380 |  | 66% | 34% | 52390.8 | 26989.2 |  | 2017-12-31 | 79380 | 52390.8 | 26989.2 | 0 | 0 |  | Contract extension
Planned | 8-8 | BWC3-1-8-8 | [6 empty] | 2018-01-29 | 2018-01-01 | 90565 | USD | 90565 |  | 66% | 34% | 57617.9873 | 32947.0127 |  | 2018-12-31 | 90565 | 57617.9873 | 32947.0127 | 0 | 0 |  | Contract extension
Actual | 9-1 | BWC3-1-9-1 | Civil/Water Engineer |  | USD | Post | Individual | IC | 2012-03-01 | 2012-03-30 | 100000000 | L.L. | 66335 |  | 66% | 34% | 43781.1 | 22553.9 | Farid Maalouf | 2013-03-29 | 66335 | 43781.1 | 22553.9 | 0 | 0
Actual | 9-2 | BWC3-1-9-2 | [6 empty] | 2013-03-01 | 2013-03-30 | 100000000 | L.L. | 66335 |  | 66% | 34% | 43781.1 | 22553.9 |  | 2014-01-31 | 55279.1667 | 36484.25 | 18794.9167 |  |  |  | Extension in new contract form
Actual | 10-1 | BWC3-1-10-1 | Operational Support |  | USD | Post | Individual | IC | 2012-03-01 | 2012-03-01 | 72000000 | L.L. | 47761 |  | 66% | 34% | 31522.26 | 16238.74 | Patrick Khoury | 2013-02-28 | 47761 | 31522.26 | 16238.74 | 0 | 0
Actual | 10-2 | BWC3-1-10-2 | [6 empty] | 2013-03-01 | 2013-03-01 | 72000000 | L.L. | 47761 |  | 66% | 34% | 31522.26 | 16238.74 |  | 2014-02-28 | 47761 | 31522.26 | 16238.74 | 0 | 0 |  | Extension in new contract form
Actual | 10-3 | BWC3-1-10-3 | [6 empty] | 2014-03-01 | 2014-03-01 | 40000 | USD | 40000 |  | 66% | 34% | 26400 | 13600 |  | 2014-12-31 | 40000 | 26400 | 13600 | 0 | 0 |  | Contract extension
Actual | 10-4 | BWC3-1-10-4 | [6 empty] | 2015-01-02 | 2015-01-01 | 50400 | USD | 50400 |  | 66% | 34% | 33264 | 17136 |  | 2015-12-31 | 50400 | 33264 | 17136 | 0 | 0 |  | Contract extension
Actual | 10-5 | BWC3-1-10-5 | [6 empty] | 2016-02-15 | 2016-01-01 | 26460 | USD | 26460 |  | 66% | 34% | 17463.6 | 8996.4 |  | 2016-06-30 | 26460 | 17463.6 | 8996.4 | 0 | 0 |  | Contract extension
Actual | 10-6 | BWC3-1-10-6 | [6 empty] | 2016-07-05 | 2016-07-01 | 26460 | USD | 26460 |  | 66% | 34% | 17463.6 | 8996.4 |  | 2016-12-31 | 26460 | 17463.6 | 8996.4 | 0 | 0 |  | Contract extension
Actual | 10-7 | BWC3-1-10-7 | [6 empty] | 2017-01-18 | 2017-01-01 | 52920 | USD | 52920 |  | 66% | 34% | 34927.2 | 17992.8 |  | 2017-12-31 | 52920 | 34927.2 | 17992.8 | 0 | 0 |  | Contract extension
Planned | 10-8 | BWC3-1-10-8 | [6 empty] | 2018-01-29 | 2018-01-01 | 57600 | USD | 57600 |  | 66% | 34% | 38016 | 19584 |  | 2018-12-31 | 57600 | 38016 | 19584 | 0 | 0 |  | Contract extension
Actual | 11-1 | BWC3-1-11-1 | Civil Engineer |  | USD | Post | Individual | IC | 2012-05-01 | 2012-05-01 | 82000000 | L.L. | 54394.69 |  | 66% | 34% | 35900.4954 | 18494.1946 | Michel Youssef | 2013-04-30 | 54394.69 | 35900.4954 | 18494.1946 | 0 | 0
Actual | 11-2 | BWC3-1-11-2 | [6 empty] | 2013-05-01 | 2013-05-01 | 82000000 | L.L. | 54394.69 |  | 66% | 34% | 35900.4954 | 18494.1946 |  | 2014-04-30 | 54394.69 | 35900.4954 | 18494.1946 | 0 | 0 |  | Extension in new contract form
Actual | 11-3 | BWC3-1-11-3 | [6 empty] | 2014-05-01 | 2014-05-01 | 36444.4444 | USD | 36444.44 |  | 66% | 34% | 24053.3304 | 12391.1096 |  | 2014-12-31 | 36444.44 | 24053.3304 | 12391.1096 | 0 | 0 |  | Contract extension
Actual | 11-4 | BWC3-1-11-4 | [6 empty] | 2015-01-02 | 2015-01-01 | 57393 | USD | 57393 |  | 66% | 34% | 37879.38 | 19513.62 |  | 2015-12-31 | 57393 | 37879.38 | 19513.62 | 0 | 0 |  | Contract extension
Actual | 11-5 | BWC3-1-11-5 | [6 empty] | 2016-02-15 | 2016-01-01 | 30131 | USD | 30131 |  | 66% | 34% | 19886.46 | 10244.54 |  | 2016-06-30 | 30131 | 19886.46 | 10244.54 | 0 | 0 |  | Contract extension
Actual | 11-6 | BWC3-1-11-6 | [6 empty] | 2016-07-05 | 2016-07-01 | 30132 | USD | 30132 |  | 66% | 34% | 19887.12 | 10244.88 |  | 2016-12-31 | 30132 | 19887.12 | 10244.88 | 0 | 0 |  | Contract extension
Actual | 11-7 | BWC3-1-11-7 | [6 empty] | 2017-01-18 | 2017-01-01 | 66000 | USD | 66000 |  | 66% | 34% | 43560 | 22440 |  | 2017-12-31 | 66000 | 43560 | 22440 | 0 | 0 |  | Contract extension
Actual | 11-8 | BWC3-1-11-8 | [6 empty] | 2018-01-29 | 2018-01-01 | 74693 | USD | 74693 |  | 66% | 34% | 47520.1272 | 27172.8728 |  | 2018-12-31 | 74693 | 47520.1272 | 27172.8728 | 0 | 0 |  | Contract extension
Planned | 11-9 | BWC3-1-11-9 | [6 empty] | 2019-01-17 | 2019-01-01 | 74693 | USD | 74693 |  | 66% | 34% | 47520.1272 | 27172.8728 |  | 2019-12-31 | 12448.8333 | 7920.0212 | 4528.8121 | 39600.106 | 22644.0606 |  | Contract extension
Actual | 12-1 | BWC3-1-12-1 | Admin Assistant MoEW |  | USD | Post | Individual | IC | 2012-05-01 | 2012-05-01 | 72000000 | L.L. | 47761.19 |  | 66% | 34% | 31522.3854 | 16238.8046 | Ziad Najjar | 2013-04-30 | 47761.19 | 31522.3854 | 16238.8046 | 0 | 0
Actual | 12-2 | BWC3-1-12-2 | [6 empty] | 2013-05-01 | 2013-05-01 | 72000000 | L.L. | 47761.19 |  | 66% | 34% | 31522.3854 | 16238.8046 |  | 2014-04-30 | 47761.19 | 31522.3854 | 16238.8046 | 0 | 0 |  | Extension in new contract form
Actual | 12-3 | BWC3-1-12-3 | [6 empty] | 2014-05-01 | 2014-05-01 | 32000 | USD | 32000 |  | 66% | 34% | 21120 | 10880 |  | 2014-12-31 | 32000 | 21120 | 10880 | 0 | 0 |  | Contract extension
Actual | 12-4 | BWC3-1-12-4 | [6 empty] | 2015-01-02 | 2015-01-01 | 50400 | USD | 50400 |  | 66% | 34% | 33264 | 17136 |  | 2015-12-31 | 50400 | 33264 | 17136 | 0 | 0 |  | Contract extension
Actual | 12-5 | BWC3-1-12-5 | [6 empty] | 2016-02-15 | 2016-01-01 | 26460 | USD | 26460 |  | 66% | 34% | 17463.6 | 8996.4 |  | 2016-06-30 | 26460 | 17463.6 | 8996.4 | 0 | 0 |  | Contract extension
Actual | 12-6 | BWC3-1-12-6 | [6 empty] | 2016-07-05 | 2016-07-01 | 26460 | USD | 26460 |  | 66% | 34% | 17463.6 | 8996.4 |  | 2016-12-31 | 26460 | 17463.6 | 8996.4 | 0 | 0 |  | Contract extension
Actual | 12-7 | BWC3-1-12-7 | [6 empty] | 2017-01-18 | 2017-01-01 | 52920 | USD | 52920 |  | 66% | 34% | 34927.2 | 17992.8 |  | 2017-12-31 | 52920 | 34927.2 | 17992.8 | 0 | 0 |  | Contract extension
Planned | 12-8 | BWC3-1-12-8 | [6 empty] | 2018-01-29 | 2018-01-01 | 74692.8 | USD | 74692.8 |  | 66% | 34% | 47520 | 27172.8 |  | 2018-12-31 | 74692.8 | 47520 | 27172.8 | 0 | 0 |  | Contract extension
Actual | 13-1 | BWC3-1-13-1 | Admin Assistant |  | USD | Post | Individual | IC | 2010-12-24 | 2010-12-24 | 54000000 | L.L. | 35820.8955 |  | 66% | 34% | 23641.791 | 12179.1045 | Rolly Dagher | 2011-05-13 | 13764.51 | 9084.5766 | 4679.9334
Actual | 14-1 | BWC3-1-14-1 | Project Legal Advisor |  | USD | Post | Individual | IC | 2012-06-01 | 2012-06-01 | 63000000 | L.L. | 41791 |  | 66% | 34% | 27582.06 | 14208.94 | Walid Dagher | 2013-05-31 | 41791 | 27582.06 | 14208.94 | 0 | 0
Actual | 14-2 | BWC3-1-14-2 | [6 empty] | 2013-06-01 | 2013-06-01 | 63000000 | L.L. | 41791 |  | 66% | 34% | 27582.06 | 14208.94 |  | 2014-05-31 | 41791 | 27582.06 | 14208.94 | 0 | 0 |  | Extension in new contract form
Actual | 14-3 | BWC3-1-14-3 | [6 empty] | 2014-06-01 | 2014-06-01 | 17500 | USD | 17500 |  | 66% | 34% | 11550 | 5950 |  | 2014-12-31 | 17500 | 11550 | 5950 | 0 | 0 |  | Contract extension
Actual | 14-4 | BWC3-1-14-4 | [6 empty] | 2015-01-02 | 2015-01-01 | 31500 | USD | 31500 |  | 66% | 34% | 20790 | 10710 |  | 2015-12-31 | 31500 | 20790 | 10710 | 0 | 0 |  | Contract extension
Actual | 14-5 | BWC3-1-14-5 | [6 empty] | 2016-02-15 | 2016-01-01 | 16536 | USD | 16536 |  | 66% | 34% | 10913.76 | 5622.24 |  | 2016-06-30 | 16536 | 10913.76 | 5622.24 | 0 | 0 |  | Contract extension
Actual | 14-6 | BWC3-1-14-6 | [6 empty] | 2016-07-05 | 2016-07-01 | 16536 | USD | 16536 |  | 66% | 34% | 10913.76 | 5622.24 |  | 2016-12-31 | 16536 | 10913.76 | 5622.24 | 0 | 0 |  | Contract extension
Actual | 14-7 | BWC3-1-14-7 | [6 empty] | 2017-01-18 | 2017-01-01 | 33072 | USD | 33072 |  | 66% | 34% | 21827.52 | 11244.48 |  | 2017-12-31 | 33072 | 21827.52 | 11244.48 | 0 | 0 |  | Contract extension
Actual | 14-8 | BWC3-1-14-8 | [6 empty] | 2018-01-29 | 2018-01-01 | 33072 | USD | 33072 |  | 66% | 34% | 21827.52 | 11244.48 |  | 2018-12-31 | 33072 | 21827.52 | 11244.48 | 0 | 0 |  | Contract extension
Planned | 14-9 | BWC3-1-14-9 | [6 empty] | 2019-01-17 | 2019-01-01 | 15000 | USD | 15000 |  | 66% | 34% | 9900 | 5100 |  | 2019-06-30 | 5000 | 3300 | 1700 | 6600 | 3400 |  | Contract extension
Actual | 15-1 | BWC3-1-15-1 | Water Engineer |  | USD | Post | Individual | IC | 2012-03-01 | 2012-03-30 | 82000000 | L.L. | 54394.7 |  | 66% | 34% | 35900.502 | 18494.198 | Ahmad El Hajj | 2013-03-29 | 54394.7 | 35900.502 | 18494.198 | 0 | 0
Actual | 15-2 | BWC3-1-15-2 | [6 empty] | 2013-03-01 | 2013-03-30 | 82000000 | L.L. | 54394.7 |  | 66% | 34% | 35900.502 | 18494.198 |  | 2014-03-29 | 54394.7 | 35900.502 | 18494.198 | 0 | 0 |  | Extension in new contract form
Actual | 15-3 | BWC3-1-15-3 | [6 empty] | 2014-03-30 | 2014-03-30 | 41000 | USD | 41000 |  | 66% | 34% | 27060 | 13940 |  | 2014-12-31 | 41000 | 27060 | 13940 | 0 | 0 |  | Contract extension
Actual | 15-4 | BWC3-1-15-4 | [6 empty] | 2015-01-02 | 2015-01-01 | 57393 | USD | 57393 |  | 66% | 34% | 37879.38 | 19513.62 |  | 2015-12-31 | 57393 | 37879.38 | 19513.62 | 0 | 0 |  | Contract extension
Actual | 15-5 | BWC3-1-15-5 | [6 empty] | 2016-02-15 | 2016-01-01 | 30131 | USD | 30131 |  | 66% | 34% | 19886.46 | 10244.54 |  | 2016-06-30 | 30131 | 19886.46 | 10244.54 | 0 | 0 |  | Contract extension
Actual | 15-6 | BWC3-1-15-6 | [6 empty] | 2016-07-05 | 2016-07-01 | 30132 | USD | 30132 |  | 66% | 34% | 19887.12 | 10244.88 |  | 2016-12-31 | 30132 | 19887.12 | 10244.88 | 0 | 0 |  | Contract extension
Actual | 15-7 | BWC3-1-15-7 | [6 empty] | 2017-01-18 | 2017-01-01 | 60264 | USD | 60264 |  | 66% | 34% | 39774.24 | 20489.76 |  | 2017-12-31 | 60264 | 39774.24 | 20489.76 | 0 | 0 |  | Contract extension
Planned | 15-8 | BWC3-1-15-8 | [6 empty] | 2018-01-29 | 2018-01-01 | 63600 | USD | 63600 |  | 66% | 34% | 41976 | 21624 |  | 2018-12-31 | 37100 | 24486 | 12614 | 17490 | 9010 |  | Contract extension
Actual | 16-1 | BWC3-1-16-1 | ESIA Specialist |  | USD | Post | Individual | IC | 2012-10-01 | 2012-10-01 | 42000000 | L.L. | 27860.69 |  | 66% | 34% | 18388.0554 | 9472.6346 | Noushig Kaloustian | 2013-09-30 | 27860.69 | 18388.0554 | 9472.6346 | 0 | 0
Actual | 16-2 | BWC3-1-16-2 | [6 empty] | 2013-10-01 | 2013-10-01 | 35000 | USD | 35000 |  | 66% | 34% | 23100 | 11900 |  | 2014-12-31 | 35000 | 23100 | 11900 | 0 | 0 |  | Extension in new contract form
Actual | 16-3 | BWC3-1-16-3 | [6 empty] | 2015-01-02 | 2015-01-01 | 29400 | USD | 29400 |  | 66% | 34% | 19404 | 9996 |  | 2015-12-31 | 29400 | 19404 | 9996 | 0 | 0 |  | Contract extension
Actual | 16-4 | BWC3-1-16-4 | [6 empty] | 2016-02-15 | 2016-01-01 | 15435 | USD | 15435 |  | 66% | 34% | 10187.1 | 5247.9 |  | 2016-06-30 | 15435 | 10187.1 | 5247.9 | 0 | 0 |  | Contract extension
Actual | 16-5 | BWC3-1-16-5 | [6 empty] | 2016-07-05 | 2016-07-01 | 15435 | USD | 15435 |  | 66% | 34% | 10187.1 | 5247.9 |  | 2016-12-31 | 15435 | 10187.1 | 5247.9 | 0 | 0 |  | Contract extension
Actual | 16-6 | BWC3-1-16-6 | [6 empty] | 2017-01-18 | 2017-01-01 | 34200 | USD | 34200 |  | 66% | 34% | 22572 | 11628 |  | 2017-12-31 | 34200 | 22572 | 11628 | 0 | 0 |  | Contract extension
Planned | 16-7 | BWC3-1-16-7 | [6 empty] | 2018-01-29 | 2018-01-01 | 38400 | USD | 38400 |  | 66% | 34% | 25344 | 13056 |  | 2018-12-31 | 3200 | 2112 | 1088 |  |  |  | Contract extension
Actual | 18-1 | BWC3-1-18-1 | Financial Officer |  | USD | Post | Individual | IC | 2015-01-02 | 2015-01-01 | 66000 | USD | 66000 |  | 66% | 34% | 43560 | 22440 | Mike Chalah | 2015-12-31 | 66000 | 43560 | 22440 | 0 | 0 |  | New Contract
Actual | 18-2 | BWC3-1-18-2 | [7 empty] | 2016-04-01 | 13500 | USD | 13500 |  | 66% | 34% | 8910 | 4590 |  | 2016-12-31 | 13500 | 8910 | 4590 | 0 | 0 |  | Addendum 1
Actual | 18-3 | BWC3-1-18-3 | [6 empty] | 2017-01-18 | 2017-01-01 | 24000 | USD | 24000 |  | 66% | 34% | 15840 | 8160 |  | 2017-12-31 | 24000 | 15840 | 8160 | 0 | 0 |  | Contract extension
Actual | 18-4 | BWC3-1-18-4 | [6 empty] | 2018-01-29 | 2018-01-01 | 24000 | USD | 24000 |  | 66% | 34% | 15840 | 8160 |  | 2018-12-31 | 24000 | 15840 | 8160 | 0 | 0 |  | Contract extension
Planned | 18-5 | BWC3-1-18-5 | [6 empty] | 2019-01-17 | 2019-01-01 | 24000 | USD | 24000 |  | 66% | 34% | 15840 | 8160 |  | 2019-12-31 | 4000 | 2640 | 1360 | 13200 | 6800 |  | Contract extension
Actual | 19-1 | BWC3-1-19-1 | Civil Engineer |  | USD | Post | Individual | IC | 2017-01-18 | 2017-01-01 |  | USD | 0 |  | 66% | 34% | 0 | 0 | Roger Medlej | 2017-12-31 | 0 | 0 | 0 | 0 | 0 |  | New Contract
Actual | 19-2 | BWC3-1-19-2 | [6 empty] | 2018-01-29 | 2018-01-01 |  | USD | 0 |  | 66% | 34% | 0 | 0 |  | 2018-12-31 | 0 | 0 | 0 | 0 | 0 |  | Contract extension
Planned | 19-3 | BWC3-1-19-3 | [6 empty] | 2019-01-17 | 2019-01-01 |  | USD | 0 |  | 66% | 34% | 0 | 0 |  | 2019-12-31 | 0 | 0 | 0 | 0 | 0 |  | Contract extension
Actual | 20-1 | BWC3-1-20-1 | Electro Mechanical Eng |  | USD | Post | Individual | IC | 2017-01-18 | 2017-01-01 |  | USD | 0 |  | 66% | 34% | 0 | 0 | Fadi Haidar | 2017-12-31 | 0 | 0 | 0 | 0 | 0 |  | New Contract
Actual | 20-2 | BWC3-1-20-2 | [6 empty] | 2018-01-29 | 2018-01-01 |  | USD | 0 |  | 66% | 34% | 0 | 0 |  | 2018-12-31 | 0 | 0 | 0 | 0 | 0 |  | Contract extension
Planned | 20-3 | BWC3-1-20-3 | [6 empty] | 2019-01-17 | 2019-01-01 |  | USD | 0 |  | 66% | 34% | 0 | 0 |  | 2019-12-31 | 0 | 0 | 0 | 0 | 0 |  | Contract extension
TOTAL PMU BMLWE
Actual | 3-1 | BWC1-4-1-1 | Project Engineer |  | USD | Post | Individual | IC | 2011-03-01 | 2011-03-01 |  | USD |  |  | 100% | 0% | 0 | 0 | Elie Moussalli | 2012-01-30 |  | 0 | 0 |  | 0
Actual | 3-2 | BWC1-4-1-2 | [6 empty] | 2012-02-01 | 2012-02-01 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2012-12-31 |  | 0 | 0 |  | 0 |  | Contract extension
Actual | 3-3 | BWC1-4-1-3 | [6 empty] | 2013-01-01 | 2013-01-01 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2013-11-30 |  | 0 | 0 |  | 0 |  | Contract extension
Actual | 3-4 | BWC1-4-1-4 | [6 empty] | 2013-12-01 | 2013-12-01 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2014-10-30 |  | 0 | 0 |  | 0 |  | Contract extension
Actual | 3-5 | BWC1-4-1-5 | [6 empty] | 2014-11-12 | 2014-11-01 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2015-09-30 |  | 0 | 0 |  | 0 |  | Contract extension
Actual | 3-6 | BWC1-4-1-6 | [6 empty] | 2015-10-01 | 2015-10-01 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2016-08-31 |  | 0 |  |  |  |  | Contract extension
Actual | 3-7 | BWC1-4-1-7 | [6 empty] | 2016-09-01 | 2016-09-01 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2017-07-31 |  | 0 | 0 |  | 0 |  | Contract extension
Actual | 3-8 | BWC1-4-1-8 | [6 empty] | 2017-08-01 | 2017-08-01 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2018-06-30 |  | 0 | 0 |  | 0 |  | Contract extension
Planned | 3-9 | BWC1-4-1-8 | [6 empty] | 2018-07-01 | 2018-07-01 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2019-05-31 |  | 0 | 0 |  | 0 |  | Contract extension
Actual | 17-1 | BWC1-4-2-1 | Finacial Specialist |  | USD | Post | Individual | IC | 2013-10-03 | 2013-09-15 |  | USD |  |  | 100% | 0% | 0 | 0 | Bruna Sehnaoui | 2014-08-14 |  | 0 | 0 |  | 0
Actual | 17-2 | BWC1-4-2-2 | [6 empty] | 2014-09-22 | 2014-08-15 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2015-07-14 |  | 0 | 0 |  | 0 |  | Contract extension
Actual | 17-3 | BWC1-4-2-3 | [6 empty] | 2015-07-15 | 2015-07-15 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2016-06-14 |  | 0 | 0 |  | 0 |  | Contract extension
Actual | 17-4 | BWC1-4-2-4 | [6 empty] | 2016-06-15 | 2016-06-15 |  | USD |  |  | 100% | 0% | 0 |  |  | 2017-05-14 |  | 0 | 0 |  | 0 |  | Contract extension Ended on January 16, 2017
Actual | 21-1 | BWC1-4-3-1 | Finacial Officer |  | USD | Post | Individual | IC | 2017-04-01 | 2017-04-01 |  | USD |  |  | 100% | 0% | 0 | 0 | Raghida Chour | 2018-03-31 |  | 0 | 0 |  | 0 |  | New Contract
Actual | 21-2 | BWC1-4-3-2 | [6 empty] | 2018-04-01 | 2018-04-01 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2019-02-28 |  | 0 | 0 |  | 0 |  | Contract extension
Planned | 21-3 | BWC1-4-3-3 | [6 empty] | 2019-03-01 | 2019-03-01 |  | USD |  |  | 100% | 0% | 0 | 0 |  | 2020-01-31 |  | 0 | 0 |  | 0 |  | Contract extension
TOTAL PMU CDR | [12 empty] | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0
Formulas:
Services Completion (Date) = [Contract Start (Date)]+365
Services Completion (Date) = [Contract Start (Date)]+365-30
Contract Start (Date) = [Contract Signed (Date)]
Contract Signed (Date) = [Contract Start (Date)]

## Capacity BuildingPP
Capacity Building Activities
SL No. | Package/ Reference No. | Expected Outcome/ Activity Description | Estimated Cost | World Bank part | BMLWE part | Estimated Duration | Start Date | Completion Date | Cost converted to US$ | Cost World Bank part | Cost BMLWE part | Expenses Incurred to Date Converted to US$ | Expenditure incurred to Date WB part | Expenditure incurred to Date BMLWE part | Remaining | Remaining WB part | Remaining BMLWE part | Comments
1 | BWC3-2-1-1 | Training for WB financed projects |  | 66% | 34% | 4 days | 2011-05-03 | 2011-05-06 | [9 empty] | Bassam Nasrallah training
2 | BWC3-2-1-2 | Training for WB financed projects |  | 66% | 34% | 4 days | 2015-09-16 | 2015-09-19 | [9 empty] | Malta Training
3 | BWC3-2-1-3 | Training for WB financed projects |  | 66% | 34% | 12 days | 2015-09-15 | 2015-09-26 | [9 empty] | Randa Daher Training