**DRAFT**

**Borrower**

**Federal Ministry of Finance of Somalia**

**Project Implementing Entity**

**Ministry of Planning, Investment & Economic Development**

**Somali Integrated Statistics and Economic Planning Capacity Building (P171160)**

**ENVIRONMENTAL AND SOCIAL**

**COMMITMENT PLAN (ESCP)**

**November, 2019 (DM Package)**

**Borrower: Federal Ministry of Finance of Somalia**

**Project Implementing Entity: Ministry of Planning, Investment & Economic Development**

**Project Title: Somali Integrated Statistics and Economic Planning Capacity Building (P171160)**

**ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN (ESCP)**

1. The Federal Government of Somalia (FGS) is planning to implement the Somali Integrated Statistics and Economic Planning Capacity Building Project (the ***Project***), with the involvement of Ministry of Planning, Investment & Economic Development. The World Bank has agreed to provide financing for the Project.
2. The FGS will implement material measures and actions so that the Project is implemented in accordance with the World Bank Environmental and Social Standards (***ESSs***). This Environmental and Social Commitment Plan (***ESCP***) sets out a summary of the material measures and actions.
3. In particular, this ESCP requires compliance with the provisions set out in the Stakeholder Engagement Plan developed for this Project and Labor Management Procedures to be developed for the Project
4. The table below summarizes the material measures and actions that are required as well as the timing of the material measures and actions. The FGS is responsible for compliance with all requirements of the ESCP even when implementation of specific measures and actions is conducted by the Ministry, agency or unit referenced in point 1. above.
5. Implementation of the material measures and actions set out in this ESCP will be monitored and reported to the Bank by the FGS as required by the ESCP and the conditions of the legal agreement, and the Bank will monitor and assess progress and completion of the material measures and actions throughout implementation of the Project.
6. As agreed by the Bank and the FGS, this ESCP may be revised from time to time during Project implementation, to reflect adaptive management of Project changes and unforeseen circumstances or in response to assessment of Project performance conducted under the ESCP itself. In such circumstances, the FGS will agree to the changes with the Bank and will update the ESCP to reflect such changes. Agreement on changes to the ESCP will be documented through the exchange of letters signed between the Bank and the FGS. The FGS will promptly disclose the updated ESCP.
7. Where Project changes, unforeseen circumstances, or Project performance result in changes to the risks and impacts during Project implementation, the FGS shall provide additional funds, if needed, to implement actions and measures to address such risks and impacts.

| **SOMALI INTEGRATED STATISTICS AND ECONOMIC PLANNING CAPACITY BUILDING (P171160)****ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN** **As of July 1, 2019** |
| --- |
| ***Summary of the Material Measures and Actions to Mitigate the Project’s Potential Environmental and Social Risks and Impacts*** | ***Timeframe*** | ***Responsibility / Authority and Resources/Funding Committed*** |  ***Date of Completion***  |
| **ESCP Monitoring and Reporting** |
| 0.1 | **REGULAR REPORTING**: Prepare and submit regular monitoring reports on the safeguard’s performance of the Project, including, inter alia, implementation of the ESCP, and any E&S documentation prepared or to be prepared and implemented under the ESCP, in form and substance acceptable to the Association. | Quarterly (every 3 months) reports submitted to the Association throughout Project implementation.Mid-term and completion reports will also be required at times determined during project implementation.  | Project Implementation Unit (PIU) The cost of monitoring and reporting will be incorporated the overall Project management costs | Throughout Project implementation First reporting to complete within three months following the project effectiveness |
| 0.2 | **INCIDENTS AND ACCIDENTS NOTIFICATION**: Promptly notify any incident or accident related or having an impact on the Project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers. Provide sufficient detail regarding the incident or accident, indicating immediate measures taken to address it, and include information provided by any contractor and supervising entity, as appropriate. | Promptly after taking notice of the incident or accident. Any incident or accident shall be notified to the Association within 24 hours after taking note of the incident or accident | PIU Funding from Project Budget | Promptly after taking notice of the incident or accident. |
| **SUMMARY ASSESSMENT** |
| **ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS** |
| 1.1 | **ORGANIZATIONAL STRUCTURE**: A Project implementation unit (PIU) will be set up at MoPIED,* M&E will also oversee safeguard
 | * PIU: Prior to project effectiveness
 | PIU  | * PIU: Project effectiveness date
 |
| 1.3 | **PERMIT, CONSENTS AND AUTHORIZATIONS:**Though none are anticipated, the project will obtain and thereafter comply with any permits, consents and authorizations that are required for the Project from relevant national authorities**.**  | All relevant permits, consents and authorizations: before commencement of related Project activities | MoPIED , Ministry of Planning and National Development Somaliland Central Statistics Department | * Securing permits as indicated and compliance with the permits throughout Project implementation.
 |
| **ESS 2: LABOR AND WORKING CONDITIONS**  |
| 2.1 | **LABOR MANAGEMENT PROCEDURES (LMP)**: Consistent with the LMP and ESS2, develop and implement labor management procedures to address labor risks, including (but not limited to) the following key mitigations:-Occupational, health and safety (OHS) measures;-Emergency preparedness and response;-Grievance redress mechanism for project workers: -Project workers training; and | Incorporation of relevant provisions of LMP into procurement documents (including in the form of contractor’s LMP)  | PIU  | * Ongoing monitoring and enforcement.
 |
| **ESS 3: RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT**  |
| 3.1 | This standard is not relevant for the Project |  |  |  |
| **ESS 4: COMMUNITY HEALTH AND SAFETY** |
| Relevant provisions on ESS4 will be addressed in SEP and LMP |
| 4.1 | **GBV AND SEA RISKS**: GBV risks under the project are anticipated to be low. While contextual risk of GBV, it is not anticipated that project activities will contribute to or worsen existing risks; the number of enumerators entering a given community to undertake survey work will be likely be low, with limited impact community or household dynamics. Basic mitigation measures will be undertaken including;* enumerators sign Codes of Conduct and receive
* basic training on expected behavior and consequences for breach of the code.
* GBV-sensitive GBV measures for a complaint’s mechanism will be explored and where feasible,
* GBV service providers will be identified in areas of implementation in advance of survey activities.
 | GBV-related provisions prior to project works commencement. | PIU  | * Within the specified timeframe and throughout Project implementation.
 |
| 4.2 | **SECURITY PERSONNEL.**Security personnel to be deployed as part of project personnel must adopt of codes of conduct, GBV and SEA. The LMP will include provision for a Code of Conduct governing all security personnel hired to protect this Project**.** | Timeframe for preparation of the LMP indicated in action 2.1 above | PIU  | * Throughout Project implementation
 |
| 4.3 | **Data Privacy and Confidentiality**Statistics authorities will set up a mechanism to strengthen coordination of statistical activities across the (NSS) by engaging all producers of official data. Sector Statistics Working Groups (SWGs) will be formed, where data producers will plan and coordinate policy and activities relating to their sectors. SWGs will ensure that statistic products based on administrative data systems are being produced and disseminated according to international best practice* Code of Practice. This will be designed and promoted across the NSS to ensure that trustworthy statistics are produced across the NSS;
* Sector Statistics Plans. Continue to encourage sectors which will not yet have them to design and implement these plans aligned to the NSDS;
* Data anonymization and confidentiality must be assured at all stages of collection, storage, analysis and dissemination and should be carefully monitored and reported on
 | After project effective and throughout project implementation to 2024 | Ministry of Planning, Investment & Economic Development and Ministry of Planning and National Development Somaliland Central Statistics Department | * Within the specified timeframe and throughout Project implementation
 |
| **ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT** |
| This standard is not relevant for the Project |
| **ESS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL RESOURCES** |
| This standard is not relevant for the Project |
| **ESS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL COMMUNITIES** |
| This standard is not relevant for the Project |
| **ESS 8: CULTURAL HERITAGE** |
| This standard is not relevant for the Project |
| **ESS 9: FINANCIAL INTERMEDIARIES** |
| This standard is not relevant for the Project |
| **ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE** |
| 10.1 | **STAKEHOLDER ENGAGEMENT PLAN (SEP)**: Consistent with the ESS10, prepare, disclose and implement the Stakeholder Engagement Plan (*SEP*), including the project grievance mechanism. Establish, maintain and operate a grievance mechanism (GM) to ensure reception and timely response to any complaints made about the Project (including those from members of the communities, and other stakeholders), as described in the SEP | Disclosure of the SEP following the clearance by the Bank prior to commencement of the project. GM to be established prior to commencement of Project activities and will be maintained and operated throughout Project implementation. | PIU  | * Ongoing implementation and monitoring.
 |
| 10.2 | Conduct stakeholder consultations to validate and seek the views of stakeholders on SEP and LMP. These instruments shall be duly updated and disclosed, following the public consultations.  | As soon as PIUs are fully staffed (prior to project effectiveness) and trained.  |  | * Prior to commencement of project
 |
| **Capacity Support**  |
| **Specify Training to be provided** | **Specify Targeted Groups and Timeframe for Delivery** | **Specify Training Completed** |
| As example, training may be provided in:* ESF in general
* Preparation of ES instruments, SEP, LMP
* Gender Based Violence (GBV)
* GRM
* Labor management
* Stakeholder engagement
 | Targeted groups include the following. Timeframe TBD.* PIU
* Enumerators
* Affected communities
 | The Bank staff and consultants are providing trainings on relevant safeguards topics to targeted groups on an ongoing basis. |