## Procurement Method & Thresholds
Proposed Poverty Alleviation and Agriculture Development Demonstration in Poor Areas Project
Procurement Plan
1. Project information
Country: China
Borrower: The People's Republic of China
Project Name: Poverty Alleviation and Agriculture Development Demonstration in Poor Areas Project
Project No.: P133326
Loan No.：
Project Implementing Agency (PIA): Foreign Capital Project Mangement Center, Office of Poverty Reduction and Development, Guizhou Province
2. Bank's approval date of the procurement plan: [original: May 13, 2015; Revision 1: xxxx; ]
3. Date of General Procurement Notice: xxxxxx
4. Period covered by this procurement plan: 2015-2019
5. Reference to (if any) Project Operational/Procurement Mannual: Yes
6. Short list comprising entirely of national consultant: Short list of consultants for services, estimated to cost less than US$500,000 equivalent per contract, may comprise entirely of national consultants in accoedance with the provisions of paragraph 2.7 of the Consultant Guidelines.
Procurement Method and Prior Review Threshold of The World Bank
Procurement Category | Prior Review Threshold(US$ 000) | Procurement Method | Prior Review Threshold(US$ 000)
1. Civil Works | ≥40,000 | ICB | All Contracts
| <40,000 | NCB | ≥10,000 and first NCB works contract by each province irrespective of value
| No Threshold | DC | ≥200
| <200 | Shopping | N/A
2. Goods, IT Systems and Non-Consulting Services | ≥10,000 | ICB | All Contracts
| <10,000 | NCB | ≥10,000 and first NCB goods contract by each province irrespective of value
| No Threshold | DC | ≥200
| <100 | Shopping | N/A
3. Consultants | No Threshold | QCBS/QBS | All Contracts
| <300 | CQ) | first contract for each province
|  | Individual consultants | Only in exceptional cases e.g. long term TA
|  | Single Source Seletion (Firm) | ≥100
|  | Single Source Seletion (Individual) | ≥50

## Works,Goods & Non-Con. Services
Proposed Poverty Alleviation and Agriculture Development Demonstration in Poor Areas Project
Procurement Plan
Contract No. and Name of Contract |  | Contract Description | Contract Cost Estimate |  | The Bank's financing |  | Procurement Method | 资格预审 | Bank Review (Prior/Post) | Expected Date of Issuing | Expected Date of Bid Opening | Expected Contract Signing | Expected Starting Date of Contract | ExpectedConstruction Duration(months) | Remarks（is there any pilot engineering listed in?）
|  |  | CNY | USD | CNY | USD
1 | 2 | 3 | 4 | 5 |  |  | 6 | 7 | 7 | 8 | 9 | 10 | 11 | 12 | 13
I. Civil Works
GZXS-GC-01-01 | Cooperative office building in Xishui County | To build one new office building (100 ㎡ of brick-concrete structure) for the Qianbei grey goat professional cooperative in Liangcun Town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZXS-GC-01-02 | Cooperative office building in Xishui County | To build one new office building (100 ㎡ of brick-concrete structure) for the Qianbei grey goat professional cooperative in Shuanglong Town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZXS-GC-01-03 | Cooperative office building in Xishui County | To build one new office building (100 ㎡ of brick-concrete structure) for the Qianbei grey goat professional cooperative in Taolin Town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZXS-GC-01-04 | Cooperative office building in Xishui County | To build one new office building (100 ㎡ of brick-concrete structure) for the Qianbei grey goat professional cooperative in Erli Town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4
GZXS-GC-01-05 | Cooperative office building in Xishui County | To build one new office building (100 ㎡ of brick-concrete structure) for the Qianbei grey goat professional cooperative in Guandian Town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4
GZXS-GC-01-06 | Cooperative office building in Xishui County | To build one new office building (100 ㎡ of brick-concrete structure) for the Qianbei grey goat professional cooperative in Yongan Town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4
GZXS-GC-01-07 | Cooperative office building in Xishui County | To build one new office building (200 ㎡ of brick-concrete structure) for the rural tourism professional cooperative in Xianyuan Town | 30 | 4.918 | 30 | 4.918 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZXS-GC-02-01 | Road hardening in Xishui County | Hardening road, 3000 M, concrete surface, 3 meters wide and 0.15 meters thick from Lannicao to Zhongshanping in Tianqiao villiage of Yongan Town | 90 | 14.7541 | 45.2503 | 7.4181 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 7
GZXS-GC-02-02 | Road hardening in Xishui County | Hardening road, 2000 M, concrete surface, 3 meters wide and 0.15 meters thick from Lannicao to Yougouping in Xiaogang villiage of Yongan Town | 60 | 9.8361 | 30.1669 | 4.9454 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 7
GZXS-GC-02-03 | Road hardening in Xishui County | Hardening road, 2000 M, concrete surface, 3 meters wide and 0.15 meters thick from Ganxiqiao to Tutang in Xianfeng villiage of Taolin Town | 60 | 9.8361 | 30.1669 | 4.9454 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZXS-GC-02-04 | Road hardening in Xishui County | Hardening road, 3000 M, concrete surface, 3 meters wide and 0.15 meters thick from Zhongjiawan group to Shitoutian highway Zhongjiawan villiage of Erli Town | 90 | 14.7541 | 45.2503 | 7.4181 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZXS-GC-02-05 | Road hardening in Xishui County | Hardening road, 2200 M, concrete surface, 3 meters wide and 0.15 meters thick from Heitao to Shanjian for Shanjian highway in Shuanglong Town | 66 | 10.8197 | 33.1835 | 5.4399 | Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 8
GZXS-GC-02-06 | Road hardening in Xishui County | Hardening road, 2800 M, concrete surface, 3 meters wide and 0.15 meters thick from Meichang to Qingshuzi for Qingshuzi highway in Shuanglong Town | 84 | 13.7705 | 42.2336 | 6.9235 | Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 8
GZXS-GC-02-07 | Road hardening in Xishui County | Hardening road, 3000 M, concrete surface, 3 meters wide and 0.15 meters thick from Zhuanfang and Datian to be paved to HH in Xiaozhang village of Shuanglong Town | 90 | 14.7541 | 45.2503 | 7.4181 | Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 8
GZXS-GC-02-08 | Road hardening in Xishui County | Hardening road, 1000 M, concrete surface, 3 meters wide and 0.15 meters thick to be paved to group in Sanyuan village group of Xianyuan Town | 30 | 4.918 | 15.0834 | 2.4727 | Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 8
GZXS-GC-02-09 | Road hardening in Xishui County | Hardening road, 1500 M, concrete surface, 3 meters wide and 0.15 meters thick to be paved to village group in Chinese Yew base of Xianyuan Town | 45 | 7.377 | 22.6251 | 3.709 | Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 8
GZXS-GC-03-01 | Production footpath in Xishui County | Hardening road, 5000 M, concrete surface, 1.2 meters wide and 0.1 meter thick to be paved to HH in Runnan village of Yongan Town | 40 | 6.5574 | 20.1112 | 3.2969 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZXS-GC-03-02 | Production footpath in Xishui County | Hardening road, 8000 M, concrete surface, 1.2 meters wide and 0.1 meter thick to be paved to HH for Qianbei grey goat breed project in Taolin Town | 64 | 10.4918 | 32.178 | 5.2751 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZXS-GC-03-03 | Production footpath in Xishui County | Hardening road, 4000 M, concrete surface, 1.2 meters wide and 0.1 meter thick to be paved to HH in Houtian village of Liangcun Town | 32 | 5.2459 | 16.089 | 2.6375 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZXS-GC-03-04 | Production footpath in Xishui County | Hardening road, 3000 M, concrete surface, 1.2 meters wide and 0.1 meter thick to be paved to HH in Zhongjianwan group of Zhongjiawan village of Erli Town | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZXS-GC-03-05 | Production footpath in Xishui County | Hardening road, 4000 M, concrete surface, 1.2 meters wide and 0.1 meter thick to be paved to HH in Dazhang village of Xianyuan Town | 32 | 5.2459 | 16.089 | 2.6375 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZXS-GC-03-06 | Production footpath in Xishui County | Hardening road, 3000 M, concrete surface, 1.2 meters wide and 0.1 meter thick to be paved to HH in Hecun village of Guandian Town | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZXS-GC-03-07 | Production footpath in Xishui County | Hardening road, 3000 M, concrete surface, 1.2 meters wide and 0.1 meter thick to be paved to HH in Huangtao village of Guandian Town | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZXS-GC-03-08 | Production footpath in Xishui County | Hardening road, 4000 M, concrete surface, 1.2 meters wide and 0.1 meter thick to be paved to Qianbei grey goat breed HH in Heba village of Shuanglong Town | 32 | 5.2459 | 16.089 | 2.6375 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZXS-GC-03-09 | Industrial road in Xishui County (Rural tourism) | 400 meters slab road (1.5 metres wide) in thousand years old Chinese yew site and old gingko tree site of rural tourism scenery spots | 32 | 5.2459 | 16.089 | 2.6375 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 8
GZXS-GC-04-01 | Water conservancy enginnering in Xinshui County | To build 4 dringking water engineering in 4 villages of Guandian Town, 1 storage pond of 100M3, installation fo main pipeline of 5600 M with 75PP-R and 25PP-R pipeline of 1200 M to HH per each village. | 40 | 6.5574 | 20.1112 | 3.2969 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 8
GZXS-GC-04-02 | Water conservancy enginnering in Xinshui County | To build 2 dringking water engineering in 2 villages (xiaogou village and Xinglongtai village) of Liangcun Town, 2 storage ponds of 150M3, installation of pipeline 3000 M with Φ50PP-R, Φ32PP-R pipeline of 2000 M and Φ25PP-R pipelin 6000 M to HH , total pipeline installation of 11000 M | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 8
GZXS-GC-05-01 | Waste water treatment in Xishui County | To build 60 waste water treatment facilities for rural tourism. | 30 | 4.918 | 15.0834 | 2.4727 | Shopping |  | Post | 2015.12. | 2016.1. | 2016.2. | 2016.3. | 8
GZXS-GC-06-01 | Village toilets in Xishui County (Rural tourism) | To build 10 slots squatting public toilets in Xianyuan Town (1 for Yangjiu village and 1 for Dazhang village) | 50 | 8.1967 | 25.1391 | 4.1212 | Shopping |  | Post | 2015.12. | 2016.1. | 2016.2. | 2016.3. | 8
GZXS-GC-07-01 | Pavilion in Xishui County (Rurtal tourism) | To build one pavilion with two floor and hexagon in Xianyuan Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.12. | 2016.1. | 2016.2. | 2016.3. | 8
GZXS-GC-08-01 | Obervation platforms in Xishui County (Rural tourism) | Rural tourism obervation plateform of 90 square meters with wood-plastic structure, set up wood-plastic guardrails of 51 meters long | 11 | 1.8033 | 5.5306 | 0.90665 | Shopping |  | Post | 2015.12. | 2016.1. | 2016.2. | 2016.3. | 8
GZCS－GC－01-01 | Office building of Dendrobium and Black bone chicken cooperative in Hongxing villiage of Chishui city | To build 200 ㎡ of office building with brick concrete structure in Hongxing village of Shipu Town, Dendrobium cooperative 100 ㎡and Black bone chicken cooperative 100 ㎡, two floor with strip foundation under wall. | 30 | 4.918 | 30 | 4.918 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZCS－GC－01-02 | Office building of Dendrobium and Black bone chicken cooperative in Hongwei villiage of Chishui city | To build 200 ㎡ of office building with brick concrete structure in Hongwei village of Changqi Town, Dendrobium cooperative 100 ㎡and Black bone chicken cooperative 100 ㎡, two floor with strip foundation under wall. | 30 | 4.918 | 30 | 4.918 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZCS－GC－01-03 | Office building of Dendrobium and Black bone chicken cooperative in Wuqi villiage of Chishui city | To build 200 ㎡ of office building with brick concrete structure in Wuqi village of Changqi Town, Dendrobium cooperative 100 ㎡and Black bone chicken cooperative 100 ㎡, two floor with strip foundation under wall. | 30 | 4.918 | 30 | 4.918 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZCS－GC－01-04 | Office building of Dendrobium and Black bone chicken cooperative in Pingtan villiage of Chishui city | To build 200 ㎡ of office building with brick concrete structure in Pingtan village of Baiyun Town, Dendrobium cooperative 100 ㎡and Black bone chicken cooperative 100 ㎡, two floor with strip foundation under wall. | 30 | 4.918 | 30 | 4.918 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZCS－GC－01-05 | Office building of Dendrobium and Black bone chicken cooperative in Fushun villiage of Chishui city | To build 200 ㎡ of office building with brick concrete structure in Fushun village of Wanglong Town, Dendrobium cooperative 100 ㎡and Black bone chicken cooperative 100 ㎡, two floor with strip foundation under wall. | 30 | 4.918 | 30 | 4.918 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZCS－GC－02-01 | Dendrobium industrial production roads in Hongxing village of Chishui city | To build 5 km of industrial road in the Dendrobium production base in Hongxing village of Shipu Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－02-02 | Dendrobium industrial production roads in Hongxing village of Chishui city赤水市红卫村石斛产业生产道路 | To build 5 km of industrial road in the Dendrobium production base in Hongwei village of Changqi Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－02-03 | 赤水市五七村石斛产业生产道路 | To build 5 km of industrial road in the Dendrobium production base in Wuqi village of Changqi Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－02-04 | Dendrobium industrial production roads in Pingtan village of Chishui city | To build 5 km of industrial road in the Dendrobium production base in Pingtan village of Baiyun Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－02-05 | Dendrobium industrial production roads in Fushun village of Chishui city | To build 5 km of industrial road in the Dendrobium production base in Fushun village of Wanglong Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－03-01 | Dendrobium industrial irrigation equipment in Hongxing village of Chishui city | To build 300 mu of the Dendrobium base irrigation equipment in Hongxing village of Shipu Town (including piping net and irrigation facilities). | 16.5 | 2.7049 | 8.2959 | 1.36 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－03-02 | Dendrobium industrial irrigation equipment in Hongwei village of Chishui city | To build 300 mu of the Dendrobium base irrigation equipment in Hongwei village of Changqi Town (including piping net and irrigation facilities). | 16.5 | 2.7049 | 8.2959 | 1.36 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－03-03 | Dendrobium industrial irrigation equipment in Wuqi village of Chishui city | To build 300 mu of the Dendrobium base irrigation equipment in Wuqi village of Changqi Town (including piping net and irrigation facilities). | 16.5 | 2.7049 | 8.2959 | 1.36 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－03-04 | Dendrobium industrial irrigation equipment in Pingtan village of Chishui city | To build 300 mu of the Dendrobium base irrigation equipment in Pingtan village of Baiyun Town (including piping net and irrigation facilities). | 16.5 | 2.7049 | 8.2959 | 1.36 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－03-05 | Dendrobium industrial irrigation equipment in Fushun village of Chishui city | To build 300 mu of the Dendrobium base irrigation equipment in Fushun village of Wanglong Town (including piping net and irrigation facilities). | 16.5 | 2.7049 | 8.2959 | 1.36 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－04-01 | Water pond of the Dendrobium industrial irrigation equipment in Hongxing village of Chishui city | To build 4 water storage ponds with 40~60 cubic meters cubage of brick concrete structure in Hongxing village of Shipu Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－04-02 | Water pond of the Dendrobium industrial irrigation equipment in Hongwei village of Chishui city | To build 4 water storage ponds with 40~60 cubic meters cubage of brick concrete structure in Hongwei village of Changqi Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 5
GZCS－GC－04-03 | Water pond of the Dendrobium industrial irrigation equipment in Wuqi village of Chishui city | To build 4 water storage ponds with 40~60 cubic meters cubage of brick concrete structure in Wuqi village of Changqi Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 5
GZCS－GC－04-04 | Water pond of the Dendrobium industrial irrigation equipment in Pingtan village of Chishui city | To build 4 water storage ponds with 40~60 cubic meters cubage of brick concrete structure in Pingtan village of Baiyun Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 5
GZCS－GC－04-05 | Water pond of the Dendrobium industrial irrigation equipment in Fushun village of Chishui city | To build 4 water storage ponds with 40~60 cubic meters cubage of brick concrete structure in Fushun village of Wanglong Town. | 20 | 3.2787 | 10.0556 | 1.6485 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 5
GZCS－GC－05-01 | Water source abstraction works of the water pond of the Dendrobium industrial irrigation equipment in Hongxing village of Chishui city | To build water source abstraction works matched for 4 water storage ponds in Hongxing village of Shipu Town. | 2 | 0.32787 | 1.0056 | 0.16485 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 5
GZCS－GC－05-02 | Water source abstraction works of the water pond of the Dendrobium industrial irrigation equipment in Hongwei village of Chishui city | To build water source abstraction works for 4 water storage ponds in Hongwei village of Changqi Town. | 2 | 0.32787 | 1.0056 | 0.16485 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 5
GZCS－GC－05-03 | Water source abstraction works of the water pond of the Dendrobium industrial irrigation equipment in Wuqi village of Chishui city | To build water source abstraction works matched for 4 water storage ponds in Wuqi village of Changqi Town. | 2 | 0.32787 | 1.0056 | 0.16485 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 5
GZCS－GC－05-04 | Water source abstraction works of the water pond of the Dendrobium industrial irrigation equipment in Pingtan village of Chishui city | To build water source abstraction works matched for 4 water storage ponds in Pingtan village of Baiyun Town. | 2 | 0.32787 | 1.0056 | 0.16485 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 5
GZCS－GC－05-05 | Water source abstraction works of the water pond of the Dendrobium industrial irrigation equipment in Fushun village of Chishui city | To build water source abstraction works matched for 4 water storage ponds in Fushun village of Wanglong Town. | 2 | 0.32787 | 1.0056 | 0.16485 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 5
GZCS－GC－06-01 | To build bio-gas tank matched for Black bone chicken feeding in Hongxing village of Chishui city. | To build 5 bio-gas tanks in Hongxing village of Shipu Town. | 17.5 | 2.8689 | 8.7987 | 1.4424 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZCS－GC－06-02 | To build bio-gas tank matched for Black bone chicken feeding in Hongwei village of Chishui city. | To build 5 bio-gas tanks in Hongwei village of Changqi Town. | 17.5 | 2.8689 | 8.7987 | 1.4424 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZCS－GC－06-03 | To build bio-gas tank matched for Black bone chicken feeding in Wuqi village of Chishui city. | To build 5 bio-gas tanks in Wuqi village of Changqi Town. | 17.5 | 2.8689 | 8.7987 | 1.4424 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZCS－GC－06-04 | To build bio-gas tank matched for Black bone chicken feeding in Pingtan village of Chishui city. | To build 5 bio-gas tanks in Pingtan village of Baiyun Town. | 17.5 | 2.8689 | 8.7987 | 1.4424 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZCS－GC－06-05 | To build bio-gas tank matched for Black bone chicken feeding in Fushun village of Chishui city. | To build 5 bio-gas tanks in Fushun village of Wanglong Town. | 17.5 | 2.8689 | 8.7987 | 1.4424 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZCS－GC－07-01 | Water pond and water source abstraction works for Black bone chicken in Hongxing village of Chishui city | To build 5 water ponds and the matched water source abstraction works for Black bone chicken in Hongxing village of Shipu Town. | 25 | 4.0984 | 12.5695 | 2.0606 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZCS－GC－07-02 | Water pond and water source abstraction works for Black bone chicken in Hongwei village of Chishui city | To build 5 water ponds and the matched water source abstraction works for Black bone chicken in Hongwei village of Changqi Town. | 25 | 4.0984 | 12.5695 | 2.0606 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 6
GZCS－GC－07-03 | Water pond and water source abstraction works for Black bone chicken in Wuqi village of Chishui city | To build 5 water ponds and the matched water source abstraction works for Black bone chicken in Wuqi village of Changqi Town. | 25 | 4.0984 | 12.5695 | 2.0606 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 6
GZCS－GC－07-04 | Water pond and water source abstraction works for Black bone chicken in Pingtan village of Chishui city | To build 5 water ponds and the matched water source abstraction works for Black bone chicken in Pingtan village of Baiyun Town. | 25 | 4.0984 | 12.5695 | 2.0606 | Shopping |  | Post | 2015.12. | 2015.13. | 2016.2. | 2016.3. | 6
GZCS－GC－07-05 | Water pond and water source abstraction works for Black bone chicken in Fushun village of Chishui city | To build 5 water ponds and the matched water source abstraction works for Black bone chicken in Fushun village of Wanglong Town. | 25 | 4.0984 | 12.5695 | 2.0606 | Shopping |  | Post | 2015.12. | 2015.13. | 2016.2. | 2016.3. | 6
GZCS－GC－08-01 | Production road for Black bone chicken industry in Hongxing village of Chishui city. | To build cement hardening road of 800 m in Hongxing village of Shipu Town. | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 6
GZCS－GC－08-02 | Production road for Black bone chicken industry in Hongwei village of Chishui city. | To build cement hardening road of 800 m in Hongwei village of Changqi Town. | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 6
GZCS－GC－08-03 | Production road for Black bone chicken industry in Wuqi village of Chishui city. | To build cement hardening road of 800 m in Wuqi village of Changqi Town. | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 6
GZCS－GC－08-04 | Production road for Black bone chicken industry in Pingtan village of Chishui city. | To build cement hardening road of 800 m in Pingtan village of Baiyun Town. | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 6
GZCS－GC－08-05 | Production road for Black bone chicken industry in Fushun village of Chishui city. | To build cement hardening road of 800 m in Fushun village of Wanglong Town. | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 6
GZTZ－GC－01－01 | Cooperative office building in Tongzi County | Office building with brick-concrete structure and the strip foundation under wall for rural tourism industrial association in Huaqiu town. | 30 | 4.918 | 30 | 4.918 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZTZ－GC－01－02 | Cooperative office building in Tongzi County | Office building with brick-concrete structure and the strip foundation under wall for Huaqiu native chicken industrial cooperative in Huaqiu town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZTZ－GC－01－03 | Cooperative office building in Tongzi County | Office building for rural tourism industrial association in Fengshui town. | 30 | 4.918 | 30 | 4.918 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZTZ－GC－01－04 | Cooperative office building in Tongzi County | Office building for Huaqiu native chicken industrial cooperation in Fengshui town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZTZ－GC－01－05 | Cooperative office building in Tongzi County | Office building for rural tourism industrial association in Rongguang town. | 30 | 4.918 | 30 | 4.918 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4
GZTZ－GC－01－06 | Cooperative office building in Tongzi County | Office building for Huaqiu native chicken industrial cooperative in Rongguang town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4
GZTZ－GC－01－07 | Cooperative office building in Tongzi County | Office building for rural tourism industrial association in Gaoqiao town. | 30 | 4.918 | 30 | 4.918 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZTZ－GC－01－08 | Cooperative office building in Tongzi County | Office building for Huaqiu native chicken industrial cooperative in Gaoqiao town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZTZ－GC－02—01 | Tourism highway hardening in Tongzi County | 6 km in Lejing village of Huaqiu town | 315 | 51.6393 | 165.8343 | 27.186 | NCB |  | Prior | 2015.10. | 2015.11. | 2016.1. | 2016.2. | 8
GZTZ－GC－02—02 | Tourism highway hardening in Tongzi County | 4 km in Jiangyan village and Pingzi village of Fengshui town | 200 | 32.7869 | 100.5562 | 16.4846 | NCB |  | Post | 2015.10. | 2015.11. | 2016.1. | 2016.2. | 8
GZTZ－GC－02—03 | Tourism highway hardening in Tongzi County | 3 km in Daqing village and Zhailang village of Rongguang town | 150 | 24.5902 | 75.4172 | 12.3635 | NCB |  | Post | 2015.10. | 2015.11. | 2016.1. | 2016.2. | 8
GZTZ－GC－02—04 | Tourism highway hardening in Tongzi County | 3 km in Zhailang village of Gaoqiao town | 150 | 24.5902 | 75.4172 | 12.3635 | NCB |  | Post | 2015.10. | 2015.11. | 2016.1. | 2016.2. | 8
GZTZ－GC－03-01 | Village rural tourism road and Huaiqu native chicken industrial road in Tongzi county | 2 km in Zhailang village of Gaoqiao town | 60 | 9.8361 | 30.1669 | 4.9454 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZTZ－GC－03-02 | Village rural tourism road and Huaiqu native chicken industrial road in Tongzi county | 2 km in Huaqiu town | 60 | 9.8361 | 30.1669 | 4.9454 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 8
GZTZ－GC－04—01 | Footpath road hardening in Tongzi county | 22 km in Lejing village of Huaqiu town | 176 | 28.8525 | 88.4895 | 14.5065 | NCB |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 8
GZTZ－GC－04—02 | Footpath road hardening in Tongzi county | A total of 12 km in Jianyan village and Pingzi village of Fengshui town | 96 | 15.7377 | 48.267 | 7.9126 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 8
GZTZ－GC－04—03 | Footpath road hardening in Tongzi county | A total of 10 km in Daqing village and Yuanmu village of Rongguang town | 80 | 13.1148 | 40.2225 | 6.5938 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 8
GZTZ－GC－04—04 | Footpath road hardening in Tongzi county | 10 km in Zhialng village of Gaoqiao town | 80 | 13.1148 | 40.2225 | 6.5938 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 8
GZTZ－GC-05—01 | Safety drinking water construction in Tongzi county | 10 sets in Lejing village of Huaqiu town | 116 | 19.0164 | 58.3226 | 9.5611 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZTZ－GC-05—02 | Safety drinking water construction in Tongzi county | A total of 3 sets in Jianyan village and Pingzi village of Fengshui town | 34.8 | 5.7049 | 17.4968 | 2.8683 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZTZ－GC-05—03 | Safety drinking water construction in Tongzi county | A total of 3 stes in Daqing village and Yuanmu village of Rongguang town | 34.8 | 5.7049 | 17.4968 | 2.8683 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZTZ－GC-06—01 | Waste water treatment facility construction in Tongzi county | To build one set of living waste water treatment facility in Lejing village of Huaqiu town. | 50 | 8.1967 | 25.1391 | 4.1212 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZTZ－GC-06—02 | Waste water treatment facility construction in Tongzi county | To build one set of living waste water treatment facility in Pingzi village of Fengshui town. | 50 | 8.1967 | 25.1391 | 4.1212 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZTZ－GC-06—03 | Waste water treatment facility construction in Tongzi county | To build one set of living waste water treatment facility in Yuanmu village of Rongguang town. | 50 | 8.1967 | 25.1391 | 4.1212 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZTZ－GC-06—04 | Waste water treatment facility construction in Tongzi county | To build one set of living waste water treatment facility in Zhailang village of Gaoqiao town. | 50 | 8.1967 | 25.1391 | 4.1212 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZTZ－GC-07—01 | Recreational square construction in Tongzi county | 6000m² in Lejing village of Huaqiu town | 60 | 9.8361 | 30.1669 | 4.9454 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZTZ－GC-07—02 | Recreational square construction in Tongzi county | 6900m² in Yuanmu village of Rongguang town | 69 | 11.3115 | 34.6919 | 5.6872 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZTZ－GC-08 | Fitness equipment and cultural package matched with the recreational square construction in Tongzi county. | Two sets in Lejing village of Huaqiu town and the estimation will be RMB 290000 yuan and one set in Daqing village of Rongguang town and the estimation will be RMB 145000 yuan. | 43.5 | 7.1311 | 21.871 | 3.5854 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZTZ－GC-09 | Fishing pavilion in Tongzi county | 6 in Zhailang village of Gaoqiao town | 12 | 1.9672 | 6.0334 | 0.98908 | Community Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZTZ－GC-10 | Fishing platform construction in Tongzi county | A total of 200 ㎡ in Zhailang village of Gaoqiao town and it will be implemented in different spots. | 5.38 | 0.88197 | 2.705 | 0.44344 | Community Shopping |  | Post | 2016.2. | 2016.3. | 2016.4. | 2016.5 | 3
GZTZ－GC-11 | Fishing foot path greening in Tongzi county | 8 km in Zhailang village of Gaoqiao town | 32 | 5.2459 | 16.089 | 2.6375 | Community Shopping |  | Post | 2015.11 | 2015.12 | 2016.1 | 2016.2 | 2
GZTZ－GC-12 | Garbage treatment pool in Tongzi county | 120m²in Lejing village of Huaqiu town, 64m² in Yuanmu village of Rongguang town, 64m²in Pingzi village of Fengshui town and 64m²in Zhailang village of Gaoqiao. | 15.6 | 2.5574 | 7.8434 | 1.2858 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 2
GZTZ－GC-13 | Public toilet construction in Tongzi county | 105 m²in Lejing village of Huaqiu town, 55m² in Yuanmu village of Rongguang town, 50 m²in Daqing village, 70m²in Pingzi village of Fengshui and 40m² in Jiangyan village with a total of 320m². | 59.52 | 9.7574 | 29.9255 | 4.9058 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 2
GZTZ－GC-14 | Parking area construction in tourism spot of Tongzi county | 1200m²in Lejing village of Huaqiu town, 900m² in Yuanmu village of Rongguang town, 900m²in Pingzi village of Fengshui town and 900 m²in Zhailang village of Gaoqiao. | 101.5 | 16.6393 | 51.0323 | 8.3659 | NCB |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZTZ－GC-15 | Manure treatment ponds for native chicken feeding in Tongzi county | 12 ponds for Huaqiu town breeading base, 6 ponds for Fengshui breeding base and 3 ponds for Rongguan breeding base. | 31.5 | 5.1639 | 15.8376 | 2.5963 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZTZ－GC-16 | Water ponds construction for native chicken feeding in Tongzi county | 6 ponds for Huaqiu town breeading base, 4 ponds for Fengshui breeding base and 5 ponds for Rongguan breeding base. | 75 | 12.2951 | 37.7086 | 6.1817 | Shopping |  | Post | 2015.11 | 2015.12 | 2016.1 | 2016.2 | 6
GZDF-GC-01-01 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for rhizoma gastrodiae cooperative in Longong village of Yangchang town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZDF-GC-01-02 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for rhizoma gastrodiae cooperative in Tongjing village of Yangchang town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZDF-GC-01-03 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for Radix Salviae Miltiorrhizae cooperative in Xintian village of Yangchang town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZDF-GC-01-04 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for Radix Salviae Miltiorrhizae cooperative in Bijiao village of Maochang town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZDF-GC-01-05 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for rhizoma gastrodiae cooperative in Haiba village of Jianwenge town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZDF-GC-01-06 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for hot pepper cooperative in Shiguan village of Dafang town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4
GZDF-GC-01-07 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for hot pepper cooperative in Jiulong village of Niuchang town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4
GZDF-GC-01-08 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for hot pepper cooperative in Xinfeng village of Machang town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4
GZDF-GC-01-09 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for hot pepper cooperative in Fale village of Lihua town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZDF-GC-01-10 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for potato cooperative in Gaochao village of Lutang town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZDF-GC-01-11 | Cooperative office building construction in Dafang county | One office building of 100 ㎡ with brick-concrete structure for potato cooperative in Niuchang village of Lutang town. | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZDF-GC-02-01 | Industrial road in Dafang county | 4 km for Tianba group of Tianba village of Jianwenge town. | 200 | 32.7869 | 100.5562 | 16.4846 | NCB |  | Post | 2015.10. | 2015.11. | 2016.1. | 2016.2. | 8
GZDF-GC-02-02 | Industrial road in Dafang county | Industrial roads of 6 km for Yingpan group of Xintian village of Yangchang town. | 300 | 49.1803 | 150.8343 | 24.7269 | NCB |  | Post | 2015.10. | 2015.11. | 2016.1. | 2016.2. | 8
GZDF-GC-02-03 | Industrial road in Dafang county | Industrial roads of 3.8 km for Zhoujiazhai group of Bijiao village of Maochang town. | 190 | 31.1475 | 95.5284 | 15.6604 | NCB |  | Post | 2015.10. | 2015.11. | 2016.1. | 2016.2. | 8
GZDF-GC-02-04 | Industrial road in Dafang county | Industrial roads of 6.2 km for the 1st group of Jiulong village of Niuchang town. | 310 | 50.8197 | 155.8621 | 25.5512 | NCB |  | Post | 2015.10. | 2015.11. | 2016.1. | 2016.2. | 8
GZDF-GC-02-05 | Industrial road in Dafang county | Industrial roads of 4.2 km of Xinfeng village of Machang town. | 210 | 34.4262 | 105.584 | 17.3089 | NCB |  | Post | 2015.10. | 2015.11. | 2016.1. | 2016.2. | 8
GZDF-GC-02-06 | Industrial road in Dafang county | Industrial roads of 2.2 km for Chenjiazhai of Qiaoshang village of Machang town. | 110 | 18.0328 | 55.3059 | 9.0665 | Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 6
GZDF-GC-02-07 | Industrial road in Dafang county | Industrial roads of 4.6 km of Fale village of Lihua town. | 230 | 37.7049 | 115.6396 | 18.9573 | NCB |  | Post | 2015.12. | 2016.1. | 2016.2. | 2016.3. | 6
GZDF-GC-02-08 | Industrial road in Dafang county | Industrial roads of 2 km for the Yingchang group of Changchun village of Lihua town. | 100 | 16.3934 | 50.2781 | 8.2423 | Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 6
GZDF-GC-02-09 | Industrial road in Dafang county | Industrial roads of 4 km for the Fangzhuba group of Gaochao village of Lutang town. | 200 | 32.7869 | 100.5562 | 16.4846 | NCB |  | Post | 2015.12. | 2016.1. | 2016.2. | 2016.3. | 6
GZDF-GC-03-01 | Footpath in Dafang county | Footpath of 3 km in Haiba village of Wenge town. | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 3
GZDF-GC-03-02 | Footpath in Dafang county | Footpath of 5 km in Fangjing village of Niuchang town. | 40 | 6.5574 | 20.1112 | 3.2969 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 3
GZDF-GC-03-03 | Footpath in Dafang county | Footpath of 10 km in Jiulong village | 80 | 13.1148 | 40.2225 | 6.5938 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 3
GZDF-GC-03-04 | Footpath in Dafang county | Footpath of 5 km in Legong village | 40 | 6.5574 | 20.1112 | 3.2969 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 3
GZDF-GC-03-05 | Footpath in Dafang county | Footpath of 3 km in Xintian village of Yangchang town | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 3
GZDF-GC-03-06 | Footpath in Dafang county | Footpath of 5 km in Xinfeng village of Machang town | 40 | 6.5574 | 20.1112 | 3.2969 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 3
GZDF-GC-03-07 | Footpath in Dafang county | Footpath of 4 km in Qiaoshang village of Machang town | 32 | 5.2459 | 16.089 | 2.6375 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 3
GZDF-GC-03-08 | Footpath in Dafang county | Footpath of 2.25 km in Gaochao village of Lutang town | 18 | 2.9508 | 9.0501 | 1.4836 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 3
GZDF-GC-03-09 | Footpath in Dafang county | Footpath of 2 km in Niuchang village of Lutang town | 16 | 2.623 | 8.0445 | 1.3188 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 3
GZDF-GC-04-01 | Irrigation and drainage canal in Dafang county | Irrigation and drainage canal of 5 km in Fangjing village of Niuchang town | 40 | 6.5574 | 20.1112 | 3.2969 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZDF-GC-04-02 | Irrigation and drainage canal in Dafang county | Irrigation and drainage canal of 1 km in Jiulong village of Niuchang town | 8 | 1.3115 | 4.0222 | 0.65938 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZDF-GC-04-03 | Irrigation and drainage canal in Dafang county | Irrigation and drainage canal of 5 km in Legong village of Niuchang town | 40 | 6.5574 | 20.1112 | 3.2969 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZDF-GC-04-04 | Irrigation and drainage canal in Dafang county | Irrigation and drainage canal of 6 km in Xinfeng village of Machang town | 48 | 7.8689 | 24.1335 | 3.9563 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZDF-GC-04-05 | Irrigation and drainage canal in Dafang county | Irrigation and drainage canal of 3 km in Qiaoshang village of Machang town | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 6
GZDF-GC-04-06 | Irrigation and drainage canal in Dafang county | Irrigation and drainage canal of 1 km in Changchun village of Lihua town | 8 | 1.3115 | 4.0222 | 0.65938 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 6
GZDF-GC-04-07 | Irrigation and drainage canal in Dafang county | Irrigation and drainage canal of 3 km in Datang village of Lihua town | 24 | 3.9344 | 12.0667 | 1.9782 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 6
GZDF-GC-04-08 | Irrigation and drainage canal in Dafang county | Irrigation and drainage canal of 2 km in Gaochao village of Lutang town | 16 | 2.623 | 8.0445 | 1.3188 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 6
GZDF-GC-04-09 | Irrigation and drainage canal in Dafang county | Irrigation and drainage canal of 2 km in Niuchang village of Lutang town | 16 | 2.623 | 8.0445 | 1.3188 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 6
GZDF-GC-05 | Potato storage and cold store equipment in Dafang county | To build 500 ㎡ of potato storage warehouse and purchase a set of cold storage equipment in Dafang town. | 180 | 29.5082 | 90.5006 | 14.8362 | NCB |  | Prior | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 5
GZZJ-GC-01-01 | Bamboo fungus industrial cooperative office building in Zhijin county | Office building of 100 ㎡ with brick-concrete structure and strip foundation under wall, one floor in Baima village of Xiongjiachang town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZZJ-GC-01-02 | Bamboo fungus industrial cooperative office building in Zhijin county | Office building of 100 ㎡ with brick-concrete structure and strip foundation under wall, one floor in Nuochong village of Xiongjiachang town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZZJ-GC-01-03 | Bamboo fungus industrial cooperative office building in Zhijin county | Office building of 100 ㎡ with brick-concrete structure and strip foundation under wall, one floor in Hongxing village of Heitu town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZZJ-GC-01-04 | Bamboo fungus industrial cooperative office building in Zhijin county | Office building of 100 ㎡ with brick-concrete structure and strip foundation under wall, one floor in Muli village of Heitu town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZZJ-GC-01-05 | Bamboo fungus industrial cooperative office building in Zhijin county | Office building of 100 ㎡ with brick-concrete structure and strip foundation under wall, one floor in Machang village of Guiguo town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4 | Yes
GZZJ-GC-01-06 | Tea industrial cooperative office building in Zhijin county | Office building of 100 ㎡ with brick-concrete structure and strip foundation under wall, one floor in Maochang village of Guiguo town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4
GZZJ-GC-01-07 | Tea industrial cooperative office building in Zhijin county | Office building of 100 ㎡ with brick-concrete structure and strip foundation under wall, one floor in Chahe village of Guiguo town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZZJ-GC-01-08 | Tea industrial cooperative office building in Zhijin county | Office building of 100 ㎡ with brick-concrete structure and strip foundation under wall, one floor in Qimo village of Guiguo town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZZJ-GC-01-09 | Tea industrial cooperative office building in Zhijin county | Office building of 100 ㎡ with brick-concrete structure and strip foundation under wall, one floor in Xinzhai village of Baini town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZZJ-GC-01-10 | Potato industrial cooperative office building in Zhijin county | Office building of 100 ㎡ with brick-concrete structure and strip foundation under wall, one floor in Longjiaba village of Huaqi town | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 4
GZZJ-GC-02-01 | Tractor roads in Zhijin county | Tractor road of 2 km with 3.5 meters of width for tea project in Chahe village and Qimo village of Guiguo town | 60 | 9.8361 | 30.1669 | 4.9454 | Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 5
GZZJ-GC-02-02 | Tractor roads in Zhijin county | Tractor road of 3 km with 3.5 meters of width for tea project in Qianjin village and Sanhe village of Baini town | 90 | 14.7541 | 45.2503 | 7.4181 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 6
GZZJ-GC-03-01 | Production roads in Zhijin county | Production road of 4 km for tea project in Chahe village of Guiguo town and production road of 8 km for Bamboo fungus project in Machang village and Maochang village of Guiguo town with 1.2 meters of width | 96 | 15.7377 | 48.267 | 7.9126 | Shopping |  | Post | 2015.8. | 2015.9. | 2015.10. | 2015.11. | 4
GZZJ-GC-03-02 | Production roads in Zhijin county | Production road of 8 km for Bamboo fungus project in Hongxing village and Muli village of Heitu town with 1.2 meters of width | 64 | 10.4918 | 32.178 | 5.2751 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 4
GZZJ-GC-03-03 | Production roads in Zhijin county | Production road of 12 km for Bamboo fungus project in Baima village, Nuochong village and Taojiadong village of Xiongjiachang town with 1.2 meters of width | 96 | 15.7377 | 48.267 | 7.9126 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 4
GZZJ-GC-03-04 | Production roads in Zhijin county | Production road of 8 km for tea project in Qianjin village and Xinzhai village of Baini town with 1.2 meters of width | 64 | 10.4918 | 32.178 | 5.2751 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 4
GZZJ-GC-04-01 | Water ponds in Zhijin county | 10 ponds in Chahe village and 10 ponds in Qimo village of Guiguo town for tea project and 50 cubic meters per each with a total of 1000 cubic meters | 110 | 18.0328 | 55.3059 | 9.0665 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 5
GZZJ-GC-04-02 | Water ponds in Zhijin county | 10 ponds in Qianjin village and 10 ponds in Xinzhai village of Baini town for tea project and 50 cubic meters per each with a total of 1000 cubic meters | 110 | 18.0328 | 55.3059 | 9.0665 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 5
GZZJ-GC-05-01 | Bamboo fungus irrigation equipment in Zhijin county | Bamboo fungus irrigation pipeline and its matched equipment of 15 km in Taojiadong village, Nuochong village and Baima village of Xiongjiachang town | 45 | 7.377 | 22.6251 | 3.709 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 4
GZZJ-GC-05-02 | Bamboo fungus irrigation equipment in Zhijin county | Bamboo fungus irrigation pipeline and its matched equipment of 10 km in Hongxing village and Muli village of Heitu town | 30 | 4.918 | 15.0834 | 2.4727 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 4
GZZJ-GC-05-03 | Bamboo fungus irrigation equipment in Zhijin county | Bamboo fungus irrigation pipeline and its matched equipment of 10 km in Machang village and Maochang village of Guiguo town | 30 | 4.918 | 15.0834 | 2.4727 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 4
GZZJ-GC-05-04 | Tea spraying and irrigation equipment in Zhijin county | Bamboo fungus irrigation pipeline and its matched equipment of 60 km in Chahe village and Qimo village of Guiguo town and Qianjin village and Xinzhai village of Baini town | 30 | 4.918 | 15.0834 | 2.4727 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 6
GZZJ-GC-06-01 | Potato storage warehouse in Zhijin county | One in Longjiaba village of Huaqi town with an area of 750 ㎡ and the outside wall will be brick-concrete structure and the roof wiil be equipped with steel structure and tiled. | 112.5 | 18.4426 | 56.5629 | 9.2726 | Shopping |  | Post | 2015.12. | 2016.1. | 2016.2. | 2016.3. | 6
GZZJ-GC-06-02 | Potato storage warehouse in Zhijin county | One in Donghong village of Guiguo town with an area of 750 ㎡ and the outside wall will be brick-concrete structure and the roof wiil be equipped with steel structure and tiled. | 112.5 | 18.4426 | 56.5629 | 9.2726 | Shopping |  | Post | 2015.12. | 2016.1. | 2016.2. | 2016.3. | 6
GZZJ-GC-07-01 | Agricultural products trading market in Zhijin county | One in Guiguo town for Bamboo fungus project with an area of 500 ㎡, hardening ground, rain-proof roof covered and the facilities include stalls, dustbins and road lamps,etc. | 50 | 8.1967 | 25.1391 | 4.1212 | Shopping |  | Post | 2016.4. | 2016.4. | 2016.5. | 2016.6. | 6
GZZJ-GC-07-02 | Agricultural products trading market in Zhijin county | One in Heitu town for Bamboo fungus project with an area of 500 ㎡, hardening ground, rain-proof roof covered and the facilities include stalls, dustbins and road lamps, etc. | 50 | 8.1967 | 25.1391 | 4.1212 | Shopping |  | Post | 2016.4. | 2016.4. | 2016.5. | 2016.6. | 6
GZZJ-GC-08-01 | Bamboo fungus cold storage warehouse in Zhijin county | One in Guiguo town to be constructed with middle and small size standard. | 100 | 16.3934 | 50.2781 | 8.2423 | Shopping |  | Post | 2016.3. | 2016.4. | 2016.5. | 2016.6. | 6
GZZJ-GC-08-02 | Bamboo fungus cold storage warehouse in Zhijin county | One in Heitu town to be constructed with middle and small size standard. | 100 | 16.3934 | 50.2781 | 8.2423 | Shopping |  | Post | 2016.3. | 2016.4. | 2016.5. | 2016.6. | 6
Total of Works |  |  | 8655.6 | 1418.9508 | 4739.702 | 777.0003
II. Goods and Non-Consulting Services
GZSJ-HW-01 | Office equipment of provincial PMO and city-class PMO | To purchase 7 sets of notebook PC, 7 sets of desktop PC and printer, 4 sets of photocopies, 4 sets of projectors, 9 sets of digital camera, 3 sets of digital video and 5 sets of scanners. | 46.6 | 7.6393 | 46.6 | 7.6393 | Shopping |  | Post | 2015.8 | 2015.9. | 2015.10. | 2015.11. | 2
GZXS-HW-01-01 | Office equipment of Xishui county | Each cooperative of the 7 cooperatives will purchase one set of desktop PC, one set of printer and one set of photocopier. | 10.5 | 1.7213 | 10.5 | 1.7213 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 3
GZXS-HW-01-02 | Office equipment of Xishui county | Each cooperative of the 7 cooperatives will purchase one set of office furniture, desks and chairs and file cabinets. | 18.9 | 3.0984 | 18.9 | 3.0984 | Community Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 3 | Yes | 4 sets of cooperative office furniture had been listed in the pilot engeering.
GZXS-HW-02-01 | Office equipment of Xishui county | The industrial incubation centre will pruchase one set of equipment including PC, printer, photocopier and office furniture. | 15 | 2.459 | 15 | 2.459 | Shopping |  | Post | 2015.8 | 2015.9. | 2015.10. | 2015.12. | 3
GZXS-HW-03-01 | Office equipment of Xishui county | The county PMO will purchase one set of office equipment (including one set of notebook PC, 12 sets of desktop PC and printer, one set of photocopier, 2 sets of camera, one set of digital video and one set of scanner.) | 17 | 2.7869 | 17 | 2.7869 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 3
GZXS-HW-04-01 | A rural tourism exhibition hall of Xishui county | Equipped with facilities and agricultural products and special products in the 100 ㎡ of exhibition hall (faciltities and commodity) | 15 | 2.459 | 15 | 2.459 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 6
GZXS-HW-05-01 | Garbage truck of Xishui county | one garbage truck for rural tourism project in Xianyuan town | 15 | 2.459 | 15 | 2.459 | Shopping |  | Post | 2015.8 | 2015.9. | 2015.10. | 2015.12. | 4
GZCS－HW－01 | Office equipment of Chishui municiple PMO | Purchase one set of notebook PC, 8 sets of desktop PC and printer, one set of photocopier, one set of projector, 2 sets of digital camera, one set of digital video and one set of scanner. | 16.2 | 2.6557 | 16.2 | 2.6557 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 3
GZCS－HW－02 | Coopertive office equipment of Chishui municipality | Purchase 10 sets of desktop PC and printer, photocopier and office furniture,etc. | 42 | 6.8852 | 42 | 6.8852 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 3 | Yes | 10 sets of cooperative office furniture had been listed in the pilot engeering.
GZCS－HW－03 | Office equipment of the industrial incubation centre of Chishui municipality | Purchase one set of desktop PC and printer, photocopier and office desks and chairs and furniture,etc. | 15 | 2.459 | 15 | 2.459 | Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 2
GZCS－HW－04 | Inspection and test instroments and equipment of traditional Chinese medicine of Chishui municipality | Including PH meter, Alkali burette, ultraviolet spectrophotometer, digtal dsplay thermostat water bath, fast moisture tester, electronic analytical balance,etc. | 38.65 | 6.3361 | 38.65 | 6.3361 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.2. | 2016.3. | 3
GZTZ-HW-01-01 | Cooperative office equipment of Tongzi county | 8 cooperatives, each cooperative purchases one set | 12 | 1.9672 | 12 | 1.9672 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 2
GZTZ-HW-01-02 | Desks, chairs and file cabinets of Tongzi county cooperative offices | 8 cooperatives, each cooperative purchases one set | 21.6 | 3.541 | 21.6 | 3.541 | Community Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 1 | Yes | 4 sets of cooperative office furniture had been listed in the pilot engeering.
GZTZ-HW-02 | Office equipment of the industrial incubation centre of Tongzi county | Purchaes one set | 15 | 2.459 | 15 | 2.459 | Shopping |  | Post | 2015.8 | 2015.9. | 2015.10. | 2015.11. | 2
GZTZ-HW-03 | Office equipment of Tongzi county PMO | Purchaes one set | 16.6 | 2.7213 | 16.6 | 2.7213 | Shopping |  | Post | 2015.8 | 2015.9. | 2015.10. | 2015.11. | 4
GZTZ-HW-04 | Solar powered road lights in Tongzi county project area | Purchase 100 sets for Lejing village of Huaqiu town | 213 | 34.918 | 107.0924 | 17.5561 | NCB |  | Prior | 2015.8 | 2015.9. | 2015.10. | 2015.11. | 2
GZTZ-HW-05 | Dust recycle boxes for Tongzi county rpoject area | Purchaes 420 boxes | 11.76 | 1.9279 | 5.9127 | 0.9693 | Community Shopping |  | Post | 2015.10. | 2015.11. | 2015.12. | 2016.1. | 2
GZDF-HW-01 | Cooperative office equipment of Dafang county | 11 cooperatives, each cooperative will purchase one set of desktop PC, printer, photocopier and office desks and chairs,etc. | 46.2 | 7.5738 | 46.2 | 7.5738 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 2 | Yes | 5 sets of cooperative office furniture had been listed in the pilot engeering.
GZDF-HW-02 | Office equipment of the industrial incubation centre of Dafang county | The industrial incubation centre will pruchase one set of equipment including PC, printer, photocopier and office furniture. | 15 | 2.459 | 15 | 2.459 | Shopping |  | Post | 2015.9. | 2015.10. | 2015.11. | 2015.12. | 2
GZDF-HW-03 | Office equipment of Dafang county PMO for Proposed Poverty Alleviation and Agriculture Development Demonstration in Poor Areas Project loaned by World Bank | one set of notebook PC, 10 sets of desktop PC and printer, one set of photocopier. One set of projector, 2 set of digital camera and one set of scanner. | 17.8 | 2.918 | 17.8 | 2.918 | Shopping |  | Post | 2015.8 | 2015.9. | 2015.10. | 2015.11. | 2
GZZJ-HW-01-01 | Cooperative office equipment of Zhijin county | 10 sets of desktop PC, photocopiers,office charis, desks and file cabinets, etc. | 42 | 6.8852 | 42 | 6.8852 | Shopping |  | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 2 | Yes | 5 sets of cooperative office furniture had been listed in the pilot engeering.
GZZJ-HW-02-01 | Public service office equipment of Zhijin county | The industrial incubation centre will pruchase one sets of desktop PC, 2 sets of printer, one set of photocopier, 2 sets of digital camera and office desks, chairs and file cabinets, etc. | 15 | 2.459 | 15 | 2.459 | Shopping |  | Post | 2015.8 | 2015.9. | 2015.10. | 2015.11. | 2
GZZJ-HW-03-01 | Office equipment for Zhijin institutional structure construction | one set of notebook PC, 7 sets of desktop PC and printer, one set of photocopier, one set of projector, 2 sets of digital camera, one set of digital video and one set of scanner. | 15.4 | 2.5246 | 15.4 | 2.5246 | Shopping |  | Post | 2015.8 | 2015.9. | 2015.10. | 2015.11. | 2
Total of Goods |  |  | 691.21 | 113.3131 | 579.4551 | 94.9926
GZXS-FZX-01 | Market system construction of Xishui county | Market system: brand registration, quality authentication and safety test for Qainbei grey goat. | 28 | 4.5902 | 28 | 4.5902 | DC | 单一来源的选择(DC) | Post | 2015.7. | 2015.8. | 2015.9. | 2015.10. | 12
GZTZ-FZX-01 | Identification and authentication for Huaqiu native chicken of Tongzi county | Brand authentication, quality system establishment for Huaiqu native chicken in Tongzi county | 70 | 11.4754 | 70 | 11.4754 | DC | 单一来源的选择(DC) | Post | 2015.11. | 2015.12. | 2016.1. | 2016.2. | 6
GZZJ-FZX-01 | Food safety test of Zhijin county | Procurement of a qualified appraisal institue to carry out food safety examination for Bamboo fungus and tea. | 30 | 4.918 | 30 | 4.918 | DC | 单一来源的选择(DC) | Post | 2016.6. | 2016.7. | 2016.8. | 2016.9. | 6
Total of Non-Consulting Services |  |  | 128 | 20.9836 | 128 | 20.9836
Contract coding description:
1. The contract number will be composed of "province and county names" (abbr. lettere of Chinese phonetic transcription)--"procurement category" (abbr. lettere of Chinese phonetic transcription)—“procurement content number”—“contract number under the procurement content item”.
2.“Abbr. phonetic transcription of province and county names”:“GZSJ”means Guizhou provincial level, “GZXS”means Xishui county of Guizhou, “GZCS”means Chishui municipality of Guizhou, “GZTZ”means Tongzi county of Guizhou, “GZDF”means Dafang county of Guizhou and “GZZJ”means Zhijin county of Guizhou.
3.“Abbr. of Chinese phonetic transcription for procurement category: "GC”means engineering, “HW”means goods,“FZX”means non consultation and “ZX”means consultation.
4.“Procurement content number”is the specific procurement content number under the procurement category and the number will be double digits.
5.“The contract package number under a procurement content”shall be based on the procurement content to carry out a numbering by dividing package and the number will be double digits. （If there is not any subproject package under the item, there is not any subpackage number.）
Note on I3: 不要，写在说明中

## Consulting Services
Proposed Poverty Alleviation and Agriculture Development Demonstration in Poor Areas Project
Procurement Plan
Contract No. | Brief Description of Sevices | Contract Cost Estimate |  | The Bank's financing |  | Selection Method | Bank Review (Prior/Post) | Selection Schedule |  |  |  | Remarks
|  | CNY | USD | CNY | USD |  |  | Selection Process |  |  | Contract Implementation Duration
[8 empty] | Expected Inviting for Proposals | Expected Receipt of Proposals | Expected Contract Award Date
GZXS-ZX-01 | Cooperative facilitator hired (salary for facilitator） | 18 | 2.9508 | 18 | 2.9508 | IC | Post | 2015.8. | 2015.9. | 2015.10. | 18
GZXS-ZX-02 | Agricultural research, technology transfer: to carry out refinement and rejuvenescence resear for Qianbei grey goat | 30 | 4.918 | 30 | 4.918 | SSS | Post | 2015.10. | 2015.11. | 2015.12. | 18 | Only one management and technical deaprtment in the county can provide this kind of service.
GZXS-ZX-03 | Consulting and technical assistment | 12 | 1.9672 | 12 | 1.9672 | CQS | Prior | 2015.9. | 2015.10. | 2015.11. | 60
GZCS-ZX-01 | salary of 4 facilitators for 18 months for dendrobium and black bone chicken industries in Chishui | 18 | 2.9508 | 18 | 2.9508 | IC | Post | 2015.8. | 2015.9. | 2015.10. | 18
GZCS-ZX-02 | To establish a public service platform of Dendrobium nobile in the industrial incubation centre and cooperate with enterprises to provide public service for cooperatives, planters and enterprises in several sectors, sush as plantation technology, pest prevention and treatment and dendrobium marketing trend and so on. | 10 | 1.6393 | 10 | 1.6393 | SSS | Post | 2015.10. | 2015.11. | 2015.12. | 3 | Only one management and technical deaprtment in the county can provide this kind of service.
GZCS-ZX-03 | To carry out the industrial incubation and development research for Dendrobium nobile and Chishui black bone chicken industries in the national wide to provide the industrial develoment report,research achievements or feasibility study and to provide technical support for the industries' development and strengthening and these research result should be up to the national advanced level. | 4 | 0.65574 | 4 | 0.65574 | CQS | Post | 2015.10. | 2015.11. | 2015.12. | 12
GZTZ-ZX-01 | Salary 4 facilitators for 2 years for rural toruism industry and Huaqiu native chicken breeding industry in Tongzi. | 24 | 3.9344 | 24 | 3.9344 | IC | Post | 2015.8. | 2015.9. | 2015.10. | 24
GZTZ-ZX-02 | Technology consulting and technical assistance in 2015 in Tongzi county | 6 | 0.98361 | 6 | 0.98361 | CQS | Prior | 2015.8. | 2015.9. | 2015.10. | 10 | Only one management and technical deaprtment in the county can provide this kind of service.
GZDF-ZX-01 | To hire facilitators of 12 person/time, of which rhizoma gastrodiae 3 person/time, the root of red-rooted salvia 3 person/time, hot pepper 3 person/time and potato 3 person/TIEM. | 36 | 5.9016 | 36 | 5.9016 | IC | Post | 2015.8. | 2015.9. | 2015.10. | 18
GZZJ-ZX-01 | Based on the local variety advantage in Bsmboo fungus and tea to provide program and feasibility study for brand-making. | 30 | 4.918 | 30 | 4.918 | CQS | Post | 2016.3. | 2016.4. | 2016.5. | 12
GZZJ-ZX-02 | To carry out the industrial incubation and development research for bamboo fungus, tea and potato industries in the national wide to provide the industrial develoment report,research achievements or feasibility study. | 8 | 1.3115 | 8 | 1.3115 | CQS | Post | 2015.8. | 2015.9. | 2015.10. | 9
GZZJ-ZX-03 | To carry out the tehnical service in the fields of the cooperative management, industrial technology and market development for the 3 industries of bamboo fungus, tea and potato in the national wide. | 20 | 3.2787 | 20 | 3.2787 | CQS | Post | 2015.10. | 2015.11. | 2015.12. | 14
GZZJ-ZX-04 | To hire 6 cooperative facilitators and to pay salary for a year and a half | 27 | 4.4262 | 27 | 4.4262 | IC | Post | 2015.8. | 2015.9. | 2015.10. | 18
GZSJ-ZX-01 | Project management software | 30 | 4.918 | 30 | 4.918 | DC | Post | 2015.8. | 2015.9. | 2015.10. | 3
Total |  | 273 | 44.7541 | 273 | 44.7541
Remarks: QCBS/QBS：Selection based on Quality and Cost; CQS:Selection based on Consultant's Qualification; IC: Individual Consultant