## Procurement Plan Cover
PROCUREMENT PLAN
LAND REGISTRY AND CADASTRE MODERNIZATION PROJECT
Revision No: 4.0
I. General
1. Project Information
|  | Country |  |  | : | Turkey
|  | Borrower |  |  | : | Republic of Turkey
|  | Project Name |  |  | : | Land Registry and Cadastre Modernization Project
|  | Loan No |  |  | : | 7537-TU
|  | Implementing Agency |  |  | : | General Directorate of Land Registry and Cadastre (TKGM)
| 2. Bank's Approval Date of the Procurement Plan: |  |  |  |  | Original: March 17, 2008; Revision 1: June 18, 2010
Revision 1.1: October 04, 2010; Revision 2: 04 March 2011
Revision 3.0: 06 June 2012; Revison 4.0: 08 March 2013
| 3. Date of General Procurement Notice: |  |  |  |  | 2008-10-22
| 4. Period Covered with this procurement plan: |  |  |  |  | 01 January 2012 - 31 December 2014
| 5. Loan Closing Date: |  |  |  |  | 31 December 2014
II. Goods and Technical Services
1. Prior Review Threshold : Procurement decisions subject to Prior Review by the Bank as stated in Appendix 1 to the
Procurement Guidelines.
|  |  | Procurement Method | Procurement Method Threshold |  | Prior Review Threshold
|  |  | International Competitive Bidding (ICB) | Default Method (No procurement method threshold) |  | All Goods contracts valued ≥ $1,000,000 and irrespective of their value first ICB contract for Goods
|  |  |  | Default Method (No procurement method threshold) |  | All Works contracts valued ≥ $5,000,000 and irrespective of its value first ICB contract for Works
|  |  |  | Default Method (No procurement method threshold) |  | All Technical Services bid packages (more than one slice) in total valued ≥ $15,000,000 and irrespective of its value first ICB contract for Technical Services
|  |  | National Competitive Bidding (NCB) | Contracts valued < $1,000,000 - Goods |  | First NCB contract for Goods
|  |  |  | Contracts valued < $15,000,000 - Works |  | All Works contracts valued ≥ $5,000,000 and irrespective of its value first contract for Works
|  |  |  | Bid packages (more than one slice) valued in total < $20,000,000 - Technical Services |  | All Technical Services bid packages (more than one slice) in total valued ≥ $15,000,000 and irrespective of its value first contract for Technical Services
|  |  | Shopping | Contracts valued <$ 100,000 - Goods |  | First contract of each category
Contracts valued < $ 100,000 - Works
Contracts valued < $ 100,000 - Logistic services for workshops and similar events
|  |  | Direct Contracting | No threshold |  | All contracts are subject to prior review
III. Selection of Consultants
1. Prior Review Threshold : Selection decisions subject to Prior Review by the Bank as stated in Appendix 1 to the
Consultant Guidelines
|  |  | Selection Method | Selection Method Threshold |  | Prior Review Threshold
|  |  | Quality and Cost Based Selection (QCBS) | Default Method (No selection method threshold) |  | Contracts valued ≥$ 350,000 and | Irrespective of contract amount (i) first contract of QCBS package; and (ii) first package of each other selection methods subject to prior review
|  |  | Least Cost Selection (LCS) | No selection method threshold |  | Contracts valued ≥$ 350,000 and
|  |  | Quality Based Selection (QBS) | No selection method threshold |  | Contracts valued ≥$ 350,000 and
|  |  | Selection Based on Consultants Qualification (CQS or CQ) | Contracts valued <$ 200,000
|  |  | Single Source Selection of Firms (SSS) | No selection method threshold |  | All contracts are subject to prior review
|  |  | Individual Consultants (IC) | No selection method threshold |  | Contracts valued ≥ $ 100,000 and,
the first individual consultant contract and all single source individual contracts are subject to Bank's prior review irrespective of contract amount. ToRs for individual consultant contracts are all subject to prior review by the Bank.
The selection of any audit, procurement or legal consultants financed by the project, even those are below
prior review threshold, shall be sent to the Bank for prior review.
2. Short list comprising entirely of national consultants: Short list of consultants for services estimated to cost less
than US$ 300,000 equivalent per contract, may comprise entirely of national consultants in accordance with provisions
of paragraph 2.7 of the Consultant Guidelines.
IV. Any Other Special Procurement Arrangements:
In accordance with the Bank's general policy on financing from the loan account with reference to the loan closing date,
the Bank will finance eligible expenditures that are payable only for such goods, works and services that are included
in the Project and delivered, performed and completed on or before the closing date of the Loan, and in accordance with
the provisions of respective contract. The Bank's no-objection to the procurement plan is subject to the above financing policy
and TKGM's insuring, prior to signing of such contracts, availability of funds from TKGM's own or other resources as may be
required for goods to be delivered or works to be performed or services to be completed after the Loan closing date of the Project.
V. Procurement Packages with Methods and Time Schedule
- The estimated costs in the attached tables (sheets) include all the taxes (including VAT).
- The Cadastre Renovation NCB Contract package TS.2 -Group 1 (19 Slices with a total cost of US$23.399,866 equivalent)
was agreed by the Bank on an exceptional basis without setting a precedent. The Bank prior reviewed the master bidding
documents and also the Bid Evaluation Report.
- The Cadastre Renovation NCB Contract package TS.3 -Group 1 (16 Slices with a total cost of US$14,121,898 equivalent)
was agreed by the Bank on an exceptional basis without setting a precedent. The Bank prior reviewed the master bidding
documents and also the Bid Evaluation Report.
- The details (number of contract slices, estimated cost of each slice, location etc.) of procurement packages of TS.14;
and TS.20 shall be furnished to the Bank and Bank's concurrence shall be obtained on the procurement
packaging, method and time schedule before initiating the procurements.

## Procurement Tables ($)
PROCUREMENT PACKAGES WITH METHOD AND TIME SCHEDULE (Procurement Plan Revision No: 4.0, Period: 01 Jan 2012 - 31 Dec 2014)
Land Registry and Cadastre Modernization Project, LN: 7537-TU
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Ref. No. |  | Description |  | Type | Number of contracts /slices |  | Estimated Cost(US$) (5), (8) |  |  | Procurement Method | Review by Bank Prior/ Post (1), (2), (3) | Expected Bid-Open. Date/ Proposal submission date | Expected contract signing date | Expected Contract Completion date (4)
Sub Component | Item |  |  | 6: Cost of Slice; 7: Total; 8: BF; 9: Euro Equivalent
G | GOODS
5 | G.1 | Financial Management System Software |  | G | 1 |  | 6423.4426 | 6423.4426 | 4271.19 | S | Prior | 2010-05-20 | 2010-06-08 | 2010-07-08
2.3 & 1.2 | G.2 | Database Server, Storage Hardware and IT equipments for Base Mapping & IT Equipments related with Data Consolidation System |  | G | 1 |  | 2017000 | 2017000 | 1521777.0117 | ICB | Prior | 2013-05-20 | 2013-08-03 | 2013-12-31
3.3 | G.3 | Furniture, Equipment and Hardware for video conferancing facilities |  | G | 1 |  | 2643660.3514 | 2643660.3514 | 1978868.2599 | ICB | Prior | 2013-08-05 | 2013-10-19 | 2014-11-13
2.2 | G.4 | Furniture, equipment, hardware, software for two Model Offices |  | G | 1 |  | 950000 | 950000 | 723973.1978 | NCB | Prior | 2014-03-06 | 2014-05-25 | 2014-12-21
4.2 | G.5 | Property Valuation Software and Equipment |  | G | 1 |  | 95000 | 95000 | 71110.6798 | S | Post | 2013-08-20 | 2013-08-25 | 2013-08-30
|  | Sub-Total |  | 7: 5712083.794; 8: 5712083.794; 9: 4300000.3392
W | WORKS
2.2 | W.1.1 | Construction of Bursa Region Directorate Building |  | W | 1 | 17033682.4252 | 17033682.4252 | 17033682.4252 | 11326339.8 | ICB | Prior | 2011-01-28 | 2011-03-25 | 2012-07-06
2.2 | W.1.2 | Construction of two Model Office Building |  | W | Multiple |  | 8694936.8215 | 8694936.8215 | 7623659.9418 | NCB | Prior | 2013-10-12 | 2013-11-11 | 2014-11-06
|  | Sub-Total |  | 7: 25728619.2467; 8: 25728619.2467; 9: 18949999.7418
TS | TECHNICAL SERVICES
1.1 | TS.1-17 | Cadastre Renovation Works |  | 4: TS; 5: Multiple; 7: 134076096.0972; 9: 99697394.4503
1.1 | TS.1 | Cadastral Renovation works tenders in 2009
|  | Cadastre Renovation Works in Kocasinan | KYS-KCS | TS | 1 |  | 1315677.3047 | 1315677.3047 | 873342.08 | NCB | Post (1) | 2009-06-17 | 2009-08-31 | 2011-02-15
|  | Cadastre Renovation Works in Kelikgazi | KYS-MLK | TS | 1 |  | 1170182.5573 | 1170182.5573 | 718658.49 | NCB | Post (1) | 2009-06-17 | 2009-08-27 | 2011-02-16
|  | Cadastre Renovation Works in Selcuklu | KNY-SLC | TS | 1 |  | 669775.8667 | 669775.8667 | 514541.28 | NCB | Post (1) | 2009-05-20 | 2009-07-29 | 2011-03-29
|  | Cadastre Renovation Works in Meram | KNY-MRM | TS | 1 |  | 781843.7471 | 781843.7471 | 563542.49 | NCB | Post (1) | 2009-05-20 | 2009-08-11 | 2011-03-22
|  | Cadastre Renovation Works in Karatay | KNY-KRT | TS | 1 |  | 669255.88 | 669255.88 | 509911.97 | NCB | Post (1) | 2009-05-20 | 2009-07-30 | 2011-05-24
|  | Cadastre Renovation Works in Adana SEYHAN | ADN-SYH | TS | 1 |  | 443539.1237 | 443539.1237 | 291499.12 | NCB | Post (1) | 2009-05-20 | 2009-07-29 | 2011-05-24
|  | Cadastre Renovation Works in Antalya Merkez | ANT-MRK1 | TS | 1 |  | 956065.1067 | 956065.1067 | 619171.33 | NCB | Prior | 2009-05-18 | 2009-07-27 | 2011-05-11
|  | Cadastre Renovation Works in Antalya Merkez | ANT-MRK2 | TS | 1 |  | 585775.6 | 585775.6 | 404618.33 | NCB | Prior | 2009-05-18 | 2009-07-27 | 2011-05-11
|  | Cadastre Renovation Works in Aksaray | AKS-AGC | TS | 1 |  | 1325967.0227 | 1325967.0227 | 892336.28 | NCB | Post (1) | 2009-06-17 | 2009-08-26 | 2011-07-19
|  | Cadastre Renovation Works in Sorgun | YZG-SRG | TS | 1 |  | 1077451.1167 | 1077451.1167 | 669410.01 | NCB | Post (1) | 2009-06-17 | 2009-08-25 | 2011-01-10
|  | Cadastre Renovation Works in Usak Merkez | USK-MRK | TS | 1 |  | 589929.9867 | 589929.9867 | 454957.56 | NCB | Post (1) | 2009-06-17 | 2009-08-26 | 2011-04-19
1.1 | TS.2 | Group-01 Cadastral Renovation works tenders in 2010
|  | Cadastre Renovation Works in POLATLI | ANK-PLT | 6: 805939.8986; 13: 2010-05-17; 14: 2011-12-12
|  | Cadastre Renovation Works in Cankiri MERKEZ | CNR-MRK | 6: 1127113.7795; 13: 2010-06-01; 14: 2011-09-24
|  | Cadastre Renovation Works in KAZAN | ANK-KZN | 6: 1199074.2223; 13: 2010-05-17; 14: 2011-10-19
|  | Cadastre Renovation Works in ELDİVAN | CNR-EDN | 6: 1034253.1492; 13: 2010-05-27; 14: 2011-09-24
|  | Cadastre Renovation Works in DODURGA | CRM-DDR | 6: 1186109.6183; 13: 2010-05-17; 14: 2011-10-06
|  | Cadastre Renovation Works in Ş.KOÇHİSAR | ANK-SKH | 6: 1634925.7806; 13: 2010-05-18; 14: 2011-10-14
|  | Cadastre Renovation Works in GÖLBAŞI | ANK-GLB | 6: 1257215.991; 13: 2010-05-20; 14: 2012-04-17
|  | Cadastre Renovation Works in AYAŞ | ANK-AYS | 6: 2380293.8254; 13: 2010-05-14; 14: 2011-10-12
|  | Cadastre Renovation Works in GÜDÜL | ANK-GDL | 4: TS; 5: 19; 6: 663815.2321; 13: 2010-05-18; 14: 2011-11-21
|  | Cadastre Renovation Works in Sivas MERKEZ | SVS-MRK |  |  | 705001.8472 | 20277137.7109 | 20277137.7109 | 15178116.28 | NCB | Post (1), (7) | 2010-01-22 | 2010-05-20 | 2011-09-16
|  | Cadastre Renovation Works in Amasya MERKEZ | AMS-MRK | 6: 1817975.1769; 13: 2010-05-17; 14: 2012-04-09
|  | Cadastre Renovation Works in Çorum MERKEZ | CRM-MRK | 6: 782529.9368; 13: 2010-05-18; 14: 2011-12-16
|  | Cadastre Renovation Works in İSKİLİP | CRM-ISK | 6: 551507.1614; 13: 2010-05-13; 14: 2012-03-15
|  | Cadastre Renovation Works in AKDAĞMADENİ | YZG-AKD | 6: 510725.8588; 13: 2010-05-14; 14: 2012-05-03
|  | Cadastre Renovation Works in YERKÖY | YZG-YRK | 6: 999099.464; 13: 2010-05-17; 14: 2011-10-17
|  | Cadastre Renovation Works in ALADAĞ | ADN-SYH II | 6: 486482.9482; 13: 2010-05-10; 14: 2012-03-27
|  | Cadastre Renovation Works in MERKEZ | OSM-MRK | 6: 815003.6883; 13: 2010-05-17; 14: 2012-02-09
|  | Cadastre Renovation Works in ANAMUR | MRS-ANM | 6: 1230565.5462; 13: 2010-05-17; 14: 2011-10-28
|  | Cadastre Renovation Works in ERDEMLİ | MRS-SLF | 6: 1089504.5862; 13: 2010-05-17; 14: 2011-11-16
1.1 | TS.3 | Group-02 Cadastral Renovation works tenders in 2010
|  | Cadastre Renovation Works in KULA | MNS-KUL | 6: 878599.6955; 13: 2010-07-07; 14: 2012-01-05
|  | Cadastre Renovation Works in İNEGÖL | BRS-ING | 6: 484910.9811; 13: 2010-06-23; 14: 2011-08-22
|  | Cadastre Renovation Works in AYVALIK | BLK-AYV | 6: 753899.9545; 13: 2010-06-18; 14: 2011-12-31
|  | Cadastre Renovation Works in ÇAN | CNK-CAN | 6: 990696.8203; 13: 2010-06-30; 14: 2011-08-08
|  | Cadastre Renovation Works in NİLÜFER | BRS-NLF | 6: 509014.4056; 13: 2010-06-30; 14: 2011-12-22
|  | Cadastre Renovation Works in DURSUNBEY | BLK-DRS | 6: 455602.9397; 13: 2010-06-29; 14: 2011-10-28
|  | Cadastre Renovation Works in LAPSEKİ | CNK-LPS | 6: 853133.2992; 13: 2010-06-30; 14: 2011-11-22
|  | Cadastre Renovation Works in AYVACIK | CNK-AYC |  |  | 692979.312 | 12056828.9266 | 12056828.9266 | 9024940.01 | NCB | Post (1), (7) | 2010-04-22 | 2010-06-21 | 2011-11-20
|  | Cadastre Renovation Works in KARAMAN MERKEZ | KRM-MRK | 4: TS; 5: 16; 6: 798361.8407; 13: 2010-07-06; 14: 2011-12-04
|  | Cadastre Renovation Works in AKŞEHİR | KNY-AKS | 6: 1221141.3717; 13: 2010-07-02; 14: 2011-11-15
|  | Cadastre Renovation Works in KULU | KNY-KLU | 6: 293149.5496; 13: 2010-06-23; 14: 2011-10-25
|  | Cadastre Renovation Works in MUT | MRS-MUT | 6: 610344.3032; 13: 2010-06-29; 14: 2011-11-05
|  | Cadastre Renovation Works in KADİRLİ | OSM-KDR | 6: 1295788.4812; 13: 2010-06-30; 14: 2012-02-09
|  | Cadastre Renovation Works in TEPEBAŞI | ESK-TPB | 6: 892579.9254; 13: 2010-07-01; 14: 2011-10-31
|  | Cadastre Renovation Works in FETHİYE | MGL-FTH | 6: 622137.5634; 13: 2010-07-02; 14: 2011-11-24
|  | Cadastre Renovation Works in OSMANCIK | CRM-OSM | 6: 704488.4834; 13: 2010-07-08; 14: 2011-11-04
1.1 | TS.4 | Group 03 Cadastral Renovation works tenders in 2010
|  | Cadastral Renovation works in KRK-YHN |  | 6: 703610.5667; 13: 2010-12-23; 14: 2012-05-31
|  | Cadastral Renovation works in TRB-BSK |  | 6: 462835.2816; 13: 2010-12-03; 14: 2012-01-16
|  | Cadastral Renovation works in GRS-MRK |  | 6: 701304.7246; 13: 2010-12-23; 14: 2012-06-04
|  | Cadastral Renovation works in ORD-UNY |  | 6: 553554.7519; 13: 2010-12-15; 14: 2011-12-28
|  | Cadastral Renovation works in SMS-TKE |  | TS | 12 | 285386.864 | 6561852.1103 | 6561852.1103 | 4911765.9387 | NCB | Prior | 2010-10-07 | 2010-12-09 | 2011-12-08
|  | Cadastral Renovation works in ORD-MRK |  | 6: 1057227.2587; 13: 2010-12-17; 14: 2012-08-08
|  | Cadastral Renovation works in NVS-KOZ |  | 6: 501189.7054; 13: 2010-12-08; 14: 2012-05-18
|  | Cadastral Renovation works in HTY-ANT |  | 6: 487678.9535; 13: 2010-12-16; 14: 2012-02-14
|  | Cadastral Renovation works in BLK-MRK |  | 6: 466082.8318; 13: 2010-12-21; 14: 2012-04-27
|  | Cadastral Renovation works in CNK-BIG |  | 6: 357878.1982; 13: 2010-12-06; 14: 2012-03-07
|  | Cadastral Renovation works in BRS-OSM |  | 6: 426136.6537; 13: 2010-12-02; 14: 2012-02-12
|  | Cadastral Renovation works in YZG-MRK |  | 6: 558966.3202; 13: 2010-12-01; 14: 2012-02-13
1.1 | TS.5 | Group 04 Cadastral Renovation works tenders in 2010
|  | Cadastral Renovation works in ANK-AYS II |  | 6: 349019.9704; 13: 2011-03-01; 14: 2012-05-23
|  | Cadastral Renovation works in ANT-KUM |  | 6: 300507.2567; 13: 2011-02-21; 14: 2012-04-06
|  | Cadastral Renovation works in TRB-MRK |  | 6: 1019106.1311; 13: 2011-03-01; 14: 2012-08-31
|  | Cadastral Renovation works in TRB-AKC |  | TS | 7 | 1125060.6716 | 4683804.8186 | 4683804.8186 | 3505984.68 | NCB | Prior | 2010-12-30 | 2011-03-01 | 2012-05-02
|  | Cadastral Renovation works in ERC-UZM |  | 6: 497848.6658; 13: 2011-02-15; 14: 2012-06-16
|  | Cadastral Renovation works in BNG-MRK |  | 6: 505476.6747; 13: 2011-03-02; 14: 2012-12-19
|  | Cadastral Renovation works in YZG-BGZ |  | 6: 886785.4483; 13: 2011-03-01; 14: 2012-06-01
Cadastral Renovation works tenders in 2011
1.1 | TS.6 | Group 05 Cadastral Renovation works tenders in 2011
|  | Cadastral Renovation works in CNR-MRK II |  | 6: 621468.3676; 13: 2011-11-04; 14: 2013-04-07
|  | Cadastral Renovation works in IST-CTL |  | 6: 802965.7622; 13: 2011-12-01; 14: 2013-05-02
|  | Cadastral Renovation works in GRS-TRB |  | 6: 414131.0778; 13: 2011-11-01; 14: 2013-01-03
|  | Cadastral Renovation works in SMS-BFR |  | 6: 692024.0757; 13: 2011-11-01; 14: 2012-11-29
|  | Cadastral Renovation works in KRK-LLB |  | TS | 10 | 396322.4541 | 7069291.4681 | 7069291.4681 | 5291601.2827 | NCB | Prior | 2011-08-23 | 2011-11-16 | 2013-03-19
|  | Cadastral Renovation works in AFY-SLT |  | 6: 585946.4768; 13: 2011-11-16; 14: 2013-03-19
|  | Cadastral Renovation works in DNZ-MRK |  | 6: 915713.1676; 13: 2011-11-18; 14: 2013-03-22
|  | Cadastral Renovation works in BRT-MRK |  | 6: 1114557.2; 13: 2011-11-23; 14: 2013-03-19
|  | Cadastral Renovation works in SVS-SUH |  | 6: 906004; 13: 2011-11-16; 14: 2013-03-12
|  | Cadastral Renovation works in TKT-ERB |  | 6: 620158.8865; 13: 2011-11-03; 14: 2013-01-04
1.1 | TS.7 | Group 06 Cadastral Renovation works tenders in 2011
|  | Cadastral Renovation works in IZM-CSM |  | 6: 325388.1892; 13: 2012-01-16; 14: 2013-03-21
|  | Cadastral Renovation works in ANT-ELM |  | 6: 783628.3049; 13: 2012-01-17; 14: 2013-05-14
|  | Cadastral Renovation works in NGD-ULK |  | 6: 570603.9892; 13: 2012-01-20; 14: 2013-06-20
|  | Cadastral Renovation works in KHM-MRK |  | 6: 424142.3892; 13: 2012-01-10; 14: 2013-03-09
|  | Cadastral Renovation works in TKD-MRT |  | 6: 427098.1297; 13: 2012-01-10; 14: 2013-05-12
|  | Cadastral Renovation works in ESK-TPB II |  | 6: 683736.9676; 13: 2012-01-30; 14: 2013-04-04
|  | Cadastral Renovation works in KTH-TVS |  | TS | 12 | 339042.0649 | 6930021.8086 | 6930021.8086 | 5187353.281 | NCB | Prior | 2011-11-14 | 2012-01-16 | 2013-03-20
|  | Cadastral Renovation works in MGL-BDR |  | 6: 816036.973; 13: 2012-01-20; 14: 2013-06-03
|  | Cadastral Renovation works in USK-BNZ |  | 6: 605622.5622; 13: 2012-01-20; 14: 2013-03-25
|  | Cadastral Renovation works in KST-MRK |  | 6: 795405.4703; 13: 2012-01-20; 14: 2013-05-24
|  | Cadastral Renovation works in SVS-MRK II |  | 6: 596665.0227; 13: 2012-01-11; 14: 2013-05-11
|  | Cadastral Renovation works in TKT-ZLE |  | 6: 562651.7459; 13: 2012-01-24; 14: 2013-05-27
Cadastral Renovation works tenders in 2012
1.1 | TS.8 | Group 07 Cadastral Renovation works tenders in 2012
|  | Cadastral Renovation works in ANK-GDL II |  | 6: 827778.9297; 13: 2012-04-30; 14: 2013-09-15
|  | Cadastral Renovation works in CNR-IGZ |  | 6: 389081.0811; 13: 2012-04-20; 14: 2013-07-01
|  | Cadastral Renovation works in AYD-CNE |  | 6: 639818.9622; 13: 2012-04-20; 14: 2013-08-31
|  | Cadastral Renovation works in ERZ-KRC |  | 6: 427357.7297; 13: 2012-04-20; 14: 2013-09-22
|  | Cadastral Renovation works in IGD-MRK |  | 6: 541578.5405; 13: 2012-04-30; 14: 2013-09-22
|  | Cadastral Renovation works in SMS-CNK |  | 6: 496845.187; 13: 2012-04-18; 14: 2013-08-23
|  | Cadastral Renovation works in NGD-BOR |  | TS | 14 | 405032.1297 | 6906999.2496 | 6906999.2496 | 5170120.125 | NCB | Prior | 2012-01-31 | 2012-04-30 | 2013-08-30
|  | Cadastral Renovation works in KHM-ELB |  | 6: 263612.6378; 13: 2012-04-20; 14: 2013-08-19
|  | Cadastral Renovation works in MLT-MRK |  | 6: 448537.4541; 13: 2012-04-30; 14: 2013-09-01
|  | Cadastral Renovation works in KTH_SMV |  | 6: 357839.7838; 13: 2012-04-20; 14: 2013-06-24
|  | Cadastral Renovation works in KTH-HSR |  | 6: 603371.6324; 13: 2012-04-30; 14: 2013-07-03
|  | Cadastral Renovation works in ZNG-MRK |  | 6: 425898.7395; 13: 2012-05-10; 14: 2013-07-12
|  | Cadastral Renovation works in YZG-SRG II |  | 6: 603807.0907; 13: 2012-05-11; 14: 2013-09-10
|  | Cadastral Renovation works in CRM-MRK II |  | 6: 476439.3514; 13: 2012-04-20; 14: 2013-08-20
1.1 | TS.9 | Group 08 Cadastral Renovation works tenders in 2012
|  | Cadastral Renovation works in CNR-MRK III |  | 6: 716665.6649; 13: 2012-07-05; 14: 2013-11-04
|  | Cadastral Renovation works in IZM-MND |  | 6: 399560.7568; 13: 2012-06-29; 14: 2013-11-01
|  | Cadastral Renovation works in BLK-MRK II |  | 6: 355642.4324; 13: 2012-07-06; 14: 2013-09-09
|  | Cadastral Renovation works in ANT-MNV |  | 6: 508750.9405; 13: 2012-07-05; 14: 2013-09-06
|  | Cadastral Renovation works in ISP-EGR |  | 6: 280626.9622; 13: 2012-07-19; 14: 2013-09-20
|  | Cadastral Renovation works in AMS-TAS |  | 6: 741260.0541; 13: 2012-07-05; 14: 2013-10-29
|  | Cadastral Renovation works in KYS-TMZ |  | TS | 13 | 297186.5081 | 6931052.1081 | 6931052.1081 | 5188124.4947 | NCB | Prior | 2012-05-08 | 2012-06-25 | 2013-11-24
|  | Cadastral Renovation works in KHR-KMN |  | 6: 804726.8324; 13: 2012-07-09; 14: 2013-12-10
|  | Cadastral Renovation works in KRL-BBS |  | 6: 545059.8595; 13: 2012-07-05; 14: 2013-11-03
|  | Cadastral Renovation works in AFY-MRK |  | 6: 351368.9189; 13: 2012-07-04; 14: 2013-09-06
|  | Cadastral Renovation works in KST-TAS |  | 6: 573761.9243; 13: 2012-06-29; 14: 2013-09-02
|  | Cadastral Renovation works in SVS-ZRA |  | 6: 674625.1351; 13: 2012-07-17; 14: 2013-11-16
|  | Cadastral Renovation works in TKT-TRH |  | 6: 681816.1189; 13: 2012-07-24; 14: 2013-11-25
1.1 | TS.10 | Group 09 Cadastral Renovation works tenders in 2012
|  | Cadastral Renovation works in MNS-ALH |  | 6: 536629.5568; 13: 2012-09-26; 14: 2014-01-19 | 480
|  | Cadastral Renovation works in AKS-MRK |  | 6: 750669.4378; 13: 2012-10-04; 14: 2014-02-26 | 510
|  | Cadastral Renovation works in ANT-GZP |  | 6: 623586.627; 13: 2012-10-02; 14: 2014-02-24 | 510
|  | Cadastral Renovation works in ISP-SKC |  | 6: 440500.3784; 13: 2012-09-14; 14: 2013-11-08 | 420
|  | Cadastral Renovation works in GMH-KLT |  | 6: 784998.5081; 13: 2012-10-05; 14: 2014-01-28 | 480
|  | Cadastral Renovation works in RZE-MRK |  | 6: 385123.2973; 13: 2012-09-13; 14: 2013-11-07 | 420
|  | Cadastral Renovation works in KYS-SRZ |  | 6: 456470.5622; 13: 2012-09-14; 14: 2014-01-07 | 480
|  | Cadastral Renovation works in HTY-ANT II |  | TS | 16 | 629321.427 | 9406683.8162 | 9406683.8162 | 7041217.6909 | NCB | Post(1b) | 2012-07-23 | 2012-10-04 | 2013-11-28 | 420
|  | Cadastral Renovation works in KHM-AFN |  | 6: 670277.6324; 13: 2012-10-10; 14: 2014-02-02 | 480
|  | Cadastral Renovation works in BTS_MRK |  | 6: 409115.5676; 13: 2012-09-17; 14: 2014-02-09 | 510
|  | Cadastral Renovation works in BLC-MRK |  | 6: 870183.6649; 13: 2012-10-18; 14: 2014-02-10 | 480
|  | Cadastral Renovation works in AFY-CBR |  | 6: 441914.4649; 13: 2012-09-26; 14: 2014-01-19 | 480
|  | Cadastral Renovation works in USK-MRK II |  | 6: 480473.6757; 13: 2012-09-26; 14: 2014-01-19 | 480
|  | Cadastral Renovation works in ZNG-ERG |  | 6: 366935.3514; 13: 2012-09-13; 14: 2013-11-07 | 420
|  | Cadastral Renovation works in YZG-BGZ II |  | 6: 1082127.6108; 13: 2012-09-24; 14: 2014-02-16 | 510
|  | Cadastral Renovation works in CRM-MRK III |  | 6: 478356.0541; 13: 2012-10-04; 14: 2014-01-27 | 480
1.1 | TS.11 | Group 10 Cadastral Renovation works tenders in 2012
|  | Cadastral Renovation works in ANK-KZN II |  | 6: 922349.2324; 13: 2012-11-28; 14: 2014-04-22 | 510
|  | Cadastral Renovation works in KRK-KSN |  | 6: 412560.8486; 13: 2012-11-28; 14: 2014-04-22 | 510
|  | Cadastral Renovation works in KNY-ERG |  | 6: 278714.7881; 13: 2012-11-30; 14: 2014-04-24 | 510
|  | Cadastral Renovation works in KNY-ERG II |  | 6: 872234.3135; 13: 2012-11-19; 14: 2014-04-13 | 510
|  | Cadastral Renovation works in KRM-MRK II |  | 6: 569158.0108; 13: 2012-11-19; 14: 2014-04-13 | 510
|  | Cadastral Renovation works in ANT-KAS |  | 6: 1086282.1676; 13: 2012-11-13; 14: 2014-03-08 | 480
|  | Cadastral Renovation works in TRB-VKR |  | 4: TS; 5: 14; 6: 872114.7253; 13: 2012-11-14; 14: 2014-01-08 | 420
|  | Cadastral Renovation works in BYB-MRK |  |  |  | 474224.1405 | 9410333.9134 | 9410333.9134 | 7043949.9109 | NCB | Post | 2012-10-01 | 2012-11-27 | 2014-04-21 | 510
|  | Cadastral Renovation works in AMS-MRK II |  | 6: 596253.3622; 13: 2012-11-13; 14: 2014-01-07 | 420
|  | Cadastral Renovation works in ORD-UNY II |  | 6: 819249.7622; 13: 2012-12-30; 14: 2014-04-24 | 480
|  | Cadastral Renovation works in SNP-MRK |  | 6: 760038.6378; 13: 2012-11-29; 14: 2014-03-24 | 480
|  | Cadastral Renovation works in SMS-CRS |  | 6: 717747.4378; 13: 2012-11-28; 14: 2014-04-22 | 510
|  | Cadastral Renovation works in HTY-ANT III |  | 6: 566106.5946; 13: 2012-11-19; 14: 2014-01-13 | 420
|  | Cadastral Renovation works in ESK-ODZ |  | 6: 463299.8919; 13: 2012-11-27; 14: 2014-01-21 | 420
1.1 | TS.12 | Group 11 Cadastral Renovation works tenders in 2012
|  | Cadastral Renovation works in CNR-YPR |  | 6: 1174313.0378; 13: 2013-02-28; 14: 2014-07-23 | 510
|  | Cadastral Renovation works in IZM-MDN II |  | 6: 857700.5405; 13: 2013-03-05; 14: 2014-07-28 | 510
|  | Cadastral Renovation works in KRS-MRK |  | 6: 1018292.1622; 13: 2013-03-01; 14: 2014-07-24 | 510
|  | Cadastral Renovation works in TRB-MRK II |  | 6: 431913.8054; 13: 2013-02-13; 14: 2014-06-08 | 480
|  | Cadastral Renovation works in GRS-MRK II |  | 6: 588779.1784; 13: 2013-02-27; 14: 2014-06-22 | 480
|  | Cadastral Renovation works in KHR-MCR |  | 4: TS; 5: 12; 6: 586962.731; 13: 2013-02-12; 14: 2014-07-07 | 510
|  | Cadastral Renovation works in MRS-ADZ |  |  |  | 898127.3405 | 8531412.8716 | 8531412.8716 | 6386048.0924 | NCB | Post | 2012-12-17 | 2013-02-28 | 2014-07-23 | 510
|  | Cadastral Renovation works in MUS-MRK |  | 6: 280083.2054; 13: 2013-02-19; 14: 2014-06-14 | 480
|  | Cadastral Renovation works in BLC-INH |  | 6: 283559.7405; 13: 2013-02-26; 14: 2014-06-21 | 480
|  | Cadastral Renovation works in DNZ-CVR |  | 6: 747101.4368; 13: 2013-02-28; 14: 2014-07-23 | 510
|  | Cadastral Renovation works in MGL-BDR II |  | 6: 1081669.2605; 13: 2013-02-27; 14: 2014-07-22 | 510
|  | Cadastral Renovation works in TKT-ZLE II |  | 6: 582910.4324; 13: 2013-02-19; 14: 2014-06-14 | 480
Cadastral Renovation works tenders in 2013
1.1 | TS.13 | Group 12 Cadastral Renovation works tenders in 2013
|  | Cadastral Renovation works in ANK-CBK |  | 6: 1988059.8536; 13: 2013-05-13; 14: 2014-10-05 | 510
|  | Cadastral Renovation works in ANK-SCN |  | 6: 1935871.328; 13: 2013-05-13; 14: 2014-10-05 | 510
|  | Cadastral Renovation works in SKY-GYV |  | 6: 559210.9389; 13: 2013-05-13; 14: 2014-09-05 | 480
|  | Cadastral Renovation works in AYD-MRK |  | 6: 684558.5737; 13: 2013-05-13; 14: 2014-09-05 | 480
|  | Cadastral Renovation works in CNK-BIG II |  | 6: 871018.014; 13: 2013-05-13; 14: 2014-09-05 | 480
|  | Cadastral Renovation works in YLV-CNR |  | 4: TS; 5: 14; 6: 842389.963; 13: 2013-05-13; 14: 2014-09-05 | 480
|  | Cadastral Renovation works in BRD-MRK |  |  |  | 504023.2086 | 14954197.9784 | 14954197.9784 | 11193717.7242 | NCB | Post | 2013-03-14 | 2013-05-13 | 2014-09-05 | 480
|  | Cadastral Renovation works in ERC-MRK |  | 6: 708809.7672; 13: 2013-05-13; 14: 2014-09-05 | 480
|  | Cadastral Renovation works in IGD-MRK II |  | 6: 1262293.0027; 13: 2013-05-13; 14: 2014-09-05 | 480
|  | Cadastral Renovation works in RZE-MRK II |  | 6: 676398.2564; 13: 2013-05-13; 14: 2014-10-05 | 510
|  | Cadastral Renovation works in MGL-BDR II |  | 6: 1241361.4083; 13: 2013-05-13; 14: 2014-09-05 | 480
|  | Cadastral Renovation works in ADN-CYH |  | 6: 589806.6957; 13: 2013-05-13; 14: 2014-10-05 | 510
|  | Cadastral Renovation works in BTS-TTN |  | 6: 925442.9709; 13: 2013-05-13; 14: 2014-10-05 | 510
|  | Cadastral Renovation works in CRM-MRK III |  | 6: 2164953.9975; 13: 2013-05-13; 14: 2014-10-05 | 510
1.1 | TS.14 | Group 13 Cadastral Renovation works tenders in 2013 |  | TS | 5 |  | 10771016.0046 | 10771016.0046 | 8062466 | NCB | Post | 2013-05-13 | 2013-07-12 | 2014-12-04
1.2 | TS.15-20 | Base Mapping Including Ortophoto and Vector Maps in Throughout the Country |  | 4: TS; 5: Multiple; 7: 5169177.5758; 8: 5169177.5758; 9: 5775938.9305
#REF!
1.2 | TS.15 | Base Mapping including Ortophoto and Vector Maps in 2009
1.2 | TS.15.1 | Base Mapping including Ortophoto and Vector Maps in ADANA-1 |  | TS | 1 |  | 605371.845 | 605371.845 | 403581.23 | NCB | Post (1b) | 2009-05-01 | 2009-07-28 | 2011-02-10
1.2 | TS.15.2 | Base Mapping including Ortophoto and Vector Maps in IZMIR 1 |  | TS | 1 |  | 549727.305 | 549727.305 | 366484.87 | NCB | Post (1b) | 2009-05-01 | 2009-07-28 | 2011-01-11
1.2 | TS.16 | Base Mapping including Ortophoto and Vector Maps Group-1 in 2010
|  | Base Mapping including Ortophoto and Vector Maps in ESKISEHIR |  | 6: 356501.6; 13: 2010-08-10; 14: 2012-12-12
|  | Base Mapping including Ortophoto and Vector Maps in ADANA-2 |  | TS | 4 | 313885.8213 | 1428364.3547 | 1428364.3547 | 885228.3985 | NCB | Prior | 2010-06-28 | 2010-08-18 | 2012-06-13
|  | Base Mapping including Ortophoto and Vector Maps in ANTALYA |  | 6: 339840; 13: 2010-08-16; 14: 2012-02-16
|  | Base Mapping including Ortophoto and Vector Maps in CORUM-1 |  | 6: 418136.9333; 13: 2010-08-17; 14: 2012-04-17
1.2 | TS.17 | Base Mapping including Ortophoto and Vector Maps Group-2 in 2011
|  | Base Mapping including Ortophoto and Vector Maps in SINOP |  | 6: 225576.6667; 13: 2011-06-30; 14: 2013-01-18
|  | Base Mapping including Ortophoto and Vector Maps in SAMSUN |  | TS | 3 | 297964.16 | 751658.4267 | 751658.4267 | 499806.1219 | NCB | Post | 2011-05-09 | 2011-06-30 | 2013-01-05
|  | Base Mapping including Ortophoto and Vector Maps in ELBISTAN |  | 6: 228117.6; 13: 2011-06-30; 14: 2012-02-02
1.2 | TS.18 | Planned Base Mapping Tenders Group-3 in 2012
|  | Base Mapping including Ortophoto and Vector Maps in Edirne |  | 6: 230524.8; 13: 2012-09-03; 14: 2013-06-30
|  | Base Mapping including Ortophoto and Vector Maps in Sivas |  | TS | 4 | 184932.2222 | 1834055.6444 | 1834055.6444 | 1372852.0382 | NCB | Post | May 07, 2012 | 2012-08-24 | 2013-06-20
|  | Base Mapping including Ortophoto and Vector Maps in Divrigi |  | 6: 767321.2222; 13: 2012-08-31; 14: 2013-06-27
|  | Base Mapping including Ortophoto and Vector Maps in Trabzon |  | 6: 651277.4; 13: 2012-08-29; 14: 2013-06-25
1.2 | TS.19 | Planned Base Mapping Tenders Group-4 in 2013
|  | Base Mapping including Ortophoto and Vector Maps in ADANA |  | 6: 834746.3514; 13: 2013-07-07; 14: 2014-02-02
|  | Base Mapping including Ortophoto and Vector Maps in UŞAK |  | TS | 2 | 832495.4216 | 1667241.773 | 1667241.773 | 1247986.2719 | NCB | Post | May 07, 2013 | 2013-07-07 | 2014-02-02
0
1.2 | TS.20 | Planned Base Mapping Tenders Group-5 in 2013 |  | TS | Multiple |  | 1335945.6033 | 1335945.6033 | 1000000 | NCB | Post | 2013-11-01 | 2014-01-30 | 2014-08-28
4.2 | TS.21-22 | Pilot Implementation - Technical Services for the collection of Pilot Data |  | 4: TS; 5: Multiple; 7: 837193.0234; 8: 837193.0234; 9: 626667
#REF!
4.2 | TS.21 | Pilot Implementation - Technical Services for Data Collection for the pilot implementation area in Fatih and Mamak Region |  | TS | 2 |  | 195000 | 195000 | 145964.0269 | S | Post (1b) | 2013-05-01 | 2013-05-31 | 2013-07-30
4.2 | TS.22 | Pilot Implementation - Technical Services for Data Collection for the pilot implementation in Throughout the Country |  | TS | 1 |  | 642193.0234 | 642193.0234 | 480702.9731 | NCB | Post (1b) | 2013-10-01 | 2013-10-31 | 2014-02-28
|  | Sub-Total |  | 7: 140082466.6964; 8: 140082466.6964; 9: 106099999.8808
CS | CONSULTING SERVICES
2.2 | CS.1 | Design and Supervision of Bursa Regional Directorate Building |  | CS | 1 |  | 925120 | 925120 | 615147.2837 | QCBS | Prior | August 2009 | 2010-01-05 | 2013-07-06
2.2 | CS.2 | Construction Supervision of Two Model Offices |  | CS | 1 |  | 577964.7344 | 577964.7344 | 432625.9489 | QCBS | Prior | 2013-02-14 | 2013-06-14 | 2014-12-06
3.3 | CS.3 | Training Consultant for Project Management 2012 |  | CS | 1 |  | 17859.4595 | 17859.4595 | 8479.29 | IC | Prior | July 2012 | 2012-10-05 | 2012-10-08
3.3 | CS.4 | Training Consultant for Project Management 2013 |  | CS | 1 |  | 17860.0973 | 17860.0973 | 8054.26 | SSS | Prior | Feb 2013 | 2013-02-07 | 2013-02-10
4.2 | CS.5 | International Valuation Consultants |  | CS | 2 |  | 268450 | 268450 | 200943.8104 | IC | Prior | June 2012 | 2012-10-15 | 2014-01-31
4.2 | CS.6 | Database & Statistical Economical Analyzes of Valuation Consultant |  | CS | 1 |  | 47597.0958 | 47597.0958 | 35628.0193 | IC | Post | July 2013 | September 2013 | December 2014
5 | CS.7 | Consultant services, Social and Economic Assessment |  | CS | 2 |  | 200000 | 200000 | 149706.6943 | CQS | Prior | April 2013 | 2013-05-01 | August 2014
5 | CS.8 | Consultants services, base line and follow up surveys |  | CS | 2 |  | 236000 | 236000 | 176653.8992 | CQS | Post | July 2013 | September 2013 | December 2014
5 | CS.9 | TA to PMU (procurement specialist, disbursement specialist, financial management specalist, monitoring and evaluation specialist and other individual consultants required by the PMU and other TKGM technical units) |  | CS | Multiple |  | 2590860.2679 | 2590860.2679 | 1722761 | IC | Prior | Jan 2010 | September 2010 | December 2014
|  | Sub-Total |  | 7: 4881711.6548; 8: 4881711.6548; 9: 3350000.2059
TR | TRAININGS AND WORKSHOPS
1.1 | TR.1.1 | Workshop for Evaluation of Cadastre Renovation Works |  | TR | 1 |  | 144625.52 | 144625.52 | 95530.45 | NCB | Prior | April 04, 2011 | April 15, 2011 | April 30, 2011
1.1 | TR.1.2 | Planning and Training Workshops 2012 for Renovation Works |  | TR | 1 |  | 154489.01 | 154489.01 | 118837.7 | NCB | Prior | March 25, 2012 | April 10, 2012 | April 30, 2012
1.1 | TR.1.3 | Planning and Training Workshops 2013 for Renovation Works |  | TR | 1 |  | 531031.86 | 531031.86 | 397495.1216 | NCB | Post | March 19, 2013 | April 10, 2013 | April 30, 2013
1.1 | TR.1.4 | Planning and Training Workshops 2014 for Renovation Works |  | TR | 1 |  | 219819.1615 | 219819.1615 | 164542 | NCB | Post | March 15, 2014 | April 10, 2014 | April 30, 2014
4.1 | TR.2.1 | Preperation meeting for Consultation Workshop of Property Valuation and Registration |  | TR | 1 |  | 19880.2065 | 19880.2065 | 14881 | S | Prior | March 03,2011 | March 10, 2011 | March 20, 2011
4.1 | TR.2.2 | Fact Finding Conference within the context of property valuation |  | TR | 1 |  | 99710 | 99710 | 79109.2724 | S | Prior | 2012-07-05 | 2012-10-03 | 2012-10-13
4.1 | TR.2.3 | Consultation Workshop related with policy development of property valuation |  | TR | 1 |  | 354000 | 354000 | 264980.8489 | NCB | Post | July 2013 | September 2013 | September 2013
3.3 | TR.3.1-3.5 | International Study visits within the context of modernization of TKGM |  | TR | 5 |  | 250000 | 250000 | 163261.3678 | S | Post | October 2013 | October 2013 | August 2014
4.1 | TR.4.1-4.3 | International Study visits within the context of policy development in the field of property valuation |  | TR | 3 |  | 285000 | 285000 | 213332.0393 | S | Post | April 2012 | April 2012 | September 2014
2.3 | TR. 5 | International Study visits related with development of Data Consolidation System |  | TR | 1 |  | 90000 | 90000 | 67368.0124 | S | Post | August 2013 | September 2013 | October 2013
3.3 | TR. 6 | International visits to International Seminars related with the context of TKMP |  | TR | 1 |  | 95000 | 95000 | 71110.6798 | S | Post | July 2013 | September 2013 | December 2013
1.1 | TR. 7 | International Congress related with policy development in the field of Turkish Cadastre Implementations |  | TR | 1 |  | 350000 | 350000 | 259551.715 | NCB | Post | September 2013 | October 2013 | December 2013
|  | Sub-Total |  | 7: 2593555.758; 8: 2593555.758; 9: 1910000.2072
OC | OPERATING COST
5 | OC.1.1-1.5 | Incremental operating cost |  | OC | 5 |  | 526500 | 526500 | 390000 | OC | Post | April 2008 |  | December 2014
|  | Sub-Total |  | 7: 526500; 8: 526500; 9: 390000
|  | TOTAL GOODS |  | 7: 5712083.794; 8: 5712083.794; 9: 4300000.3392
|  | TOTAL WORKS |  | 7: 25728619.2467; 8: 25728619.2467; 9: 18949999.7418
|  | TOTAL TECHNICAL SERVICES |  | 7: 140082466.6964; 8: 140082466.6964; 9: 106099999.8808
|  | TOTAL CONSULTING SERVICES |  | 7: 4881711.6548; 8: 4881711.6548; 9: 3350000.2059
|  | TOTAL TRAINING AND WORKSHOPS |  | 7: 2593555.758; 8: 2593555.758; 9: 1910000.2072
|  | TOTAL OPERATING COST |  | 7: 526500; 8: 526500; 9: 390000
|  | UNALLOCATED |  | 7: 0.4361; 8: 0.4361; 9: -0.37496
|  | GRAND TOTAL |  | 7: 179524937.5859; 8: 179524937.5859; 9: 135000000
|  | GRAND TOTAL (US$ million)(€ million) (5)(8) |  | 7: 179.5249; 8: 179.5249; 9: 135
Notes:
| (1) | Irrespective of its estimated cost the first package of each category (i.e. NCB works, technical services and Goods) is subject to prior review.
| (1a) | These two NCB Packages were reviewed as prior review contracts for NCB technical services category in accordance with note (1).
| (1b) | Only bidding document was reviewed by WB for these tenders.
| (2) | The first package of each shopping (i.e goods, small works and logistic services) is subject to prior review and rest of the Shopping packages are subject to post review.
| (3) | Irrespective of its value first package of any QCBS and first package of each other selection procedure is subject to prior review.
| (4) | Expected contract completion date does not include the defects liability/warranty period.
| (5) | For Contracts till October, 2011 1 € = 1.5039 US$ (rate as of Feb 29, 2008 in the PAD), For Contracts after November, 2012 1 € = 1.3359 US$ (Ministry of Development Reference Currency Rate for 2012)
| (7) | The bid evaluation report of these procurements will be prior reviewed by the Bank.
| (8) | The Bank shall not finance any expenditure due to any contract exceeding the Loan amount and exceeding the Loan closing date. TKGM shall finance the Contracts exceeding the Loan amount and Loan duration from its own resources.
| Types: |  | Procurement Methods:
| G: | Goods | NCB: | 4: National Competitive Bidding; 9: Procurement initiated
| W: | Works | ICB: | 4: International Competitive Bidding; 9: Contract Awarded
| TS: | Technical Services | S: | 4: Shopping; 9: Contract Signed
| CS: | Consulting Services | QCBS: | 4: Quality and Cost Based Selection; 9: Contract Completed
| TR: | Training | CQS: | 4: Selection Based on Consultant's Qualifications
| OC: | Operating Cost | IC: | 4: Individual Consultant
|  |  | OC: | 4: Operating Cost

## -
| Original Cost / Allocation (US$) | Original Cost/Allocation (Euro) 1.5039 USD = 1 Euro | Current Cost/Allocation (Euro) | Difference (Euro)
1. Cadastre and Land Registry Renovations and Updating | 175.39 | 116624034 | 107095400.3674 | 9528633.6326 | 107094100.3954
1.1 Cadastre Renovation |  | 108616374 | 100733351.4369 | 7883022.5631 | 101469624.7524
1.2 Base Mapping |  | 6271521 | 6362048.9305 | -90527.9305 | 5624475.6431
1.3 Supervision and Quality Control |  | 1736139 | 0 | 1736139 | 0
2. Improved Service Delivery | 19.35 | 9729370 | 21724780.1847 | -11995410.1847 | 21724781.0239
2.1 Cadastre Integration Consultancy Support |  | 196156 | 0 | 196156 | 0
2.2 Model Office Construction /Renovation |  | 9533214 | 20721746.1723 | -11188532.1723 | 20721746.1723
2.3 Integration of E-cadastre into the NSDI |  | 0 | 1003035.0124 | -1003035.0124 | 1003034.8516
3. Human Resources and Institutional Development | 6.02 | 2432343 | 0 | 2432343 | 2250480.8592
3.1. Human Resources Development Strategy |  | 313851 | 0 | 313851 | 0
3.2 Business Planning and Strategic Planning |  | 941552 | 0 | 941552 | 0
3.3. Training and Study Visits |  | 1176940 |  | 1176940 | 2250480.8592
4. Property Valuation | 4.96 | 3295432 | 1506652.6701 | 1788780.3299 | 1506652.6701
4.1. Policy Development |  | 470776 | 572303.1606 | -101527.1606 | 572303.1606
4.2. Pilot Implementation |  | 1184786 | 934349.5095 | 250436.4905 | 934349.5095
4.3. Capacity Building |  | 1639870 | 0 | 1639870 | 0
5. Project Management | 2.2 | 1468821 | 2443392.7835 | -974571.7835 | 2423985.4426
6. Unallocated | 2.18 | 1450000 | 0 | 1450000 | 0
Total | 210.1 | 135000000 | 132770226.0057 |  | 135000000.3913

## Sayfa1
1.3359 | 1.5 | 1.7354 | 100 | 43.1332
Geçici Kabul Euro Yapılan Ödeme
2984 | 0.99741 | 0.74853 | 43.1034 | 40.4613
7100 | 8378 |  | 4271.19
1175847.4576 | 1387500 | 750000 | 0.9387
4000000 | 4720000 | 2551351.3514
650000 | 1000000
100000 | 118000 | 63783.7838 | 6508451.2422 | 0.3392
|  | 50000.3392 | 16772051.872 | -0.25816
679952 | 23817248 | 28104352.64 | 17031080.8218 | 7404817.7486
12787452 | 15089193.36 | 26243 | 4593834 | -1250000.2582
5051134.44 | 11073271.8182 | 12453619.2467 | 2.4105 | 17031080.8218
109787286 | 163345260 | 2681521.9219 | 1250
10089891.5497 | 12184910.99 | 15174187.9015
0
1672471.15 | 1973515.957 |  | 873342.08
1487520.2 | 1755273.836 |  | 718658.49
851410 | 1004663.8 |  | 514541.28
993869.17 | 1172765.6206 |  | 563542.49
850749 | 1003883.82 |  | 509911.97
563820.92 | 665308.6856 |  | 291499.12
1215337 | 1434097.66 |  | 619171.33
744630 | 878663.4 |  | 404618.33
1685551.3 | 1988950.534 |  | 892336.28
1369641.25 | 1616176.675 |  | 669410.01
749911 | 884894.98 | 43.9112 | 454957.56
12184910.99 | 51.8152 | 9585463.3121
| 1026052 | 53165086.8785
1091004.4 | 1287385.192 | 14139.2965 | 603272.99 | 603272.99
1684688.3 | 1987932.194 | 19773.926 | 843682.39 | 843682.39
1841342.6 | 2172784.268 | 21036.3899 | 897547.19 | 897547.19
1449848.9 | 1710821.702 | 18144.7921 | 774173.1 | 774173.1
1652274 | 1949683.32 | 20808.9407 | 887842.75 | 887842.75
2373552 | 2800791.36 | 28682.9084 | 1223796.67 | 1223796.67
1855766.35 | 2189804.293 | 22056.4209 | 941068.25 | 941068.25
3389627 | 3999759.86 | 41759.5408 | 1781729.6 | 1781729.6
1053467 | 1243091.06 | 11645.8813 | 496887.92 | 496887.92
1128568.7 | 1331711.066 | 12368.4535 | 527717.48 | 527717.48
2575048 | 3038556.64 | 31894.3013 | 1360815.27 | 1360815.27
1131580.2 | 1335264.636 | 13728.5954 | 585749.85 | 585749.85
868062.6 | 1024313.868 | 9675.5642 | 412821.57 | 412821.57
736685.15 | 869288.477 | 8960.1028 | 382295.4 | 382295.4
1500038.5 | 1770045.43 | 17528.0608 | 747859.39 | 747859.39
752333 | 887752.94 | 8534.7886 | 364148.77 | 364148.77
1286714 | 1518322.52 | 14298.3103 | 610057.54 | 610057.54
1503376.8 | 1773984.624 | 21588.8692 | 921119.5 | 921119.5
1633793.5 | 1927876.33 | 19114.1155 | 815530.65 | 815530.65
29507771 |  | 20277137.7109 | 15178116.28 | 15178116.28
1318393.5 | 1555704.33 | 15414.0297 | 657661.28 | 657661.28
680162.53 | 802591.7854 | 8507.2102 | 362972.1 | 362972.1
966898.5 | 1140940.23 | 13226.315 | 564319.35 | 564319.35
1532315 | 1808131.7 | 17380.646 | 741569.73 | 741569.73
827825.35 | 976833.913 | 8930.0773 | 381014.32 | 381014.32
748922.92 | 883729.0456 | 7993.034 | 341034.05 | 341034.05
1303621.4 | 1538273.252 | 14967.2509 | 638598.83 | 638598.83
985469 | 1162853.42 | 12157.5318 | 518718.21 | 518718.21
1241731.94 | 1465243.6892 | 14006.3481 | 597600.56 | 597600.56
1639341.4 | 1934422.852 | 21423.5328 | 914065.19 | 914065.19
477909.6 | 563933.328 | 5142.9746 | 219432.25 | 219432.25
845313 | 997469.34 | 10707.7948 | 456863.14 | 456863.14
1870761.5 | 2207498.57 | 22733.1312 | 969941.05 | 969941.05
1196155 | 1411462.9 | 15659.2969 | 668125.95 | 668125.95
875930 | 1033597.4 | 10914.6941 | 465690.79 | 465690.79
1141761 | 1347277.98 | 12359.4471 | 527333.21 | 527333.21
29507771 | 17652511.64 | 12056828.9266 |  | 9024940.01
490000 | 41919429.9496 | 17652511.64
1112016.5 | 1312179.47 | 12344.045 | 526676.06 | 526676.06
667742.62 | 787936.2916 | 8119.9172 | 346447.7 | 346447.7
1091704.4 | 1288211.192 | 12303.5917 | 524950.06 | 524950.06
918481.14 | 1083807.7452 | 9711.4869 | 414354.26 | 414354.26
446117.91 | 526419.1338 | 5006.7871 | 213621.62 | 213621.62
1466261.3 | 1730188.334 | 18547.8466 | 791369.99 | 791369.99
888425.7 | 1048342.326 | 8792.8018 | 375157.27 | 375157.27
834222 | 984381.96 | 8555.7711 | 365044.02 | 365044.02
719658.7 | 849197.266 | 8176.8918 | 348878.6 | 348878.6
663973.2 | 783488.376 | 6278.5649 | 267883.81 | 267883.81
621735.9 | 733648.362 | 7476.0816 |  | 318977.5487
903505 | 1066135.9 | 9806.4267 | 418405 | 418405
10333844.37 |  |  |  | 4911765.9387
588551.5 | 694490.77 | 6123.1574 | 261253.13 | 261253.13
488907 | 576910.26 | 5272.0571 | 224939.74 | 224939.74
1618474.96 | 1909800.4528 | 17879.0549 | 762835.05 | 762835.05
1734637.9 | 2046872.722 | 19737.9065 | 842145.57 | 842145.57
817622.5 | 964794.55 | 8734.1871 | 372656.39 | 372656.39
1040135 | 1227359.3 | 8868.0118 | 378366.21 | 378366.21
1463196.5 | 1726571.87 | 15557.6394 | 663788.59 | 663788.59
7751525.36 |  |  | 2.3 | 3505984.68
12435263.0143
974336 | 1149716.48 | 621468.3676 |  | 764489.9794
1258887 | 1485486.66 | 802965.7622 |  | 645863.7652
649273.3 | 766142.494 | 414131.0778 |  | 333105.4322
1084953 | 1280244.54 | 692024.0757 | 537334.9 | 537334.9
621353 | 733196.54 | 396322.4541 |  | 318781.1043
918644.9 | 1084000.982 | 585946.4768 |  | 471304.7748
1435652 | 1694069.36 | 915713.1676 |  | 736551.8957
1747399 | 2061930.82 | 1114557.2 |  | 896491.6609
1420430 | 1676107.4 | 906004 |  | 728742.3478
972283 | 1147293.94 | 620158.8865 |  | 498823.4522
11083211.2 | 13078189.216 | 7069291.4681 | 2.2049 | 5931489.3124
510142.5 | 601968.15 | 325388.1892 |  | 261725.2826
1228569.8 | 1449712.364 | 783628.3049 |  | 630309.7235
894591 | 1055617.38 | 570603.9892 |  | 458964.0783
664969 | 784663.42 | 424142.3892 |  | 341158.0087
669603 | 790131.54 | 427098.1297 |  | 343535.4522
1071960.5 | 1264913.39 | 683736.9676 |  | 549962.3435
531549 | 627227.82 | 339042.0649 |  | 272707.7478
1279380 | 1509668.4 | 816036.973 |  | 656377.5652
949493 | 1120401.74 | 605622.5622 |  | 487131.1913
1247034 | 1471500.12 | 795405.4703 |  | 639782.6609
935449.4 | 1103830.292 | 596665.0227 |  | 479926.2139
882123.5 | 1040905.73 | 562651.7459 |  | 452567.7087
10864864.7 | 12820540.346 |  |  | 5574147.9765
#REF!
1297789 | 1531391.02 | 827778.9297 |  | 665822.1826
610000 | 719800 | 389081.0811 |  | 312956.5217
1003106 | 1183665.08 | 639818.9622 |  | 514636.9913
670010 | 790611.8 | 427357.7297 |  | 343744.2609
849085 | 1001920.3 | 541578.5405 |  | 435617.5217
778952.2 | 919163.596 | 496845.187 |  | 399636.3461
635008 | 749309.44 | 405032.1297 |  | 325786.713
413291 | 487683.38 | 263612.6378 |  | 212036.2522
703215.5 | 829794.29 | 448537.4541 |  | 360780.1261
561020 | 662003.6 | 357839.7838 |  | 287827.6522
945964 | 1116237.52 | 603371.6324 |  | 485320.6609
667722.6 | 787912.668 | 425898.7395 |  | 342570.7252
946646.71 | 1117043.1178 | 603807.0907 |  | 485670.9208
746960 | 881412.8 | 476439.3514 |  | 383222.9565
10828770.01 |  | 12149782.2937 |  | 5555629.8312
0
1123586 | 1325831.48 | 716665.6649 |  | 576448.4696
626430 | 739187.4 | 399560.7568 |  | 321385.8261
557575 | 657938.5 | 355642.4324 |  | 286060.2174
797618 | 941189.24 | 508750.9405 |  | 409212.713
439966 | 519159.88 | 280626.9622 |  | 225721.687
1162145 | 1371331.1 | 741260.0541 |  | 596230.913
465928 | 549795.04 | 297186.5081 |  | 239041.3217
1261648 | 1488744.64 | 804726.8324 |  | 647280.2783
854543 | 1008360.74 | 545059.8595 |  | 438417.713
550875 | 650032.5 | 351368.9189 |  | 282622.8261
899542 | 1061459.56 | 573761.9243 |  | 461504.1565
1057675 | 1248056.5 | 674625.1351 |  | 542633.2609
1068949 | 1261359.82 | 681816.1189 |  | 548417.313
5574976.6957
841326 | 992764.68 | 536629.5568 |  | 431636.8174
1176897 | 1388738.46 | 750669.4378 |  | 603799.3304
977657 | 1153635.26 | 623586.627 |  | 501580.5478
690615 | 814925.7 | 440500.3784 |  | 354315.5217
1230718 | 1452247.24 | 784998.5081 |  | 631411.8435
603795 | 712478.1 | 385123.2973 |  | 309773.087
715653 | 844470.54 | 456470.5622 |  | 367161.1043
986648 | 1164244.64 | 629321.427 |  | 506193.3217
1050859 | 1240013.62 | 670277.6324 |  | 539136.3565
641410 | 756863.8 | 409115.5676 |  | 329071.2174
1364271 | 1609839.78 | 870183.6649 |  | 699930.3391
692832 | 817541.76 | 441914.4649 |  | 355452.9391
753285 | 888876.3 | 480473.6757 |  | 386467.9565
575280 | 678830.4 | 366935.3514 |  | 295143.6522
1696556 | 2001936.08 | 1082127.6108 |  | 870406.9913
749965 | 884958.7 | 478356.0541 |  | 384764.6522
7566245.6783
1446056 | 1706346.08 | 922349.2324 |  | 741889.6
646811.5 | 763237.57 | 412560.8486 |  | 331842.4217
436968.1 | 515622.358 | 278714.7881 |  | 224183.6339
1367486 | 1613633.48 | 872234.3135 |  | 701579.7739
892324 | 1052942.32 | 569158.0108 |  | 457801.0087
1703069.5 | 2009622.01 | 1086282.1676 |  | 873748.7
1367298.51 | 1613412.2418 | 872114.7253 |  | 701483.5834
743487 | 877314.66 | 474224.1405 |  | 381441.1565
934804 | 1103068.72 | 596253.3622 |  | 479595.0957
1284417 | 1515612.06 | 819249.7622 |  | 658961.7652
1191586 | 1406071.48 | 760038.6378 |  | 611335.4261
1125282 | 1327832.76 | 717747.4378 |  | 577318.5913
887540 | 1047297.2 | 566106.5946 |  | 455346.6087
726360 | 857104.8 | 463299.8919 |  | 372654.2609
14753489.61 |  |  |  | 7569181.626
1841084 | 2172479.12 | 1174313.0378 |  | 944556.1391
1344700 | 1586746 | 857700.5405 |  | 689889.5652
1596475 | 1883840.5 | 1018292.1622 |  | 819061.087
677153 | 799040.54 | 431913.8054 |  | 347408.9304
923086 | 1089241.48 | 588779.1784 |  | 473583.2522
920238.18 | 1085881.0524 | 586962.731 |  | 472122.1967
1408081 | 1661535.58 | 898127.3405 |  | 722406.7739
439113.5 | 518153.93 | 280083.2054 |  | 225284.3174
444564 | 524585.52 | 283559.7405 |  | 228080.6609
1171303.1 | 1382137.658 | 747101.4368 |  | 600929.4165
1695837.4 | 2001088.132 | 1081669.2605 |  | 870038.3183
913885 | 1078384.3 | 582910.4324 |  | 468862.7391
|  |  | 89766602.0061 | 74055162.6338
|  |  | 77583115.2924 | 3527952.6586
1998544.2337
1688909.5762
1608936.5759
654832.9798
1021638.8715
1026362.5353
1412252.457
454208.3743
452052.2735
1415645.9541
2021025.0137
1018218.9083
490000 | #REF!
#REF! | 1485486.66
3263466.6326 | 16317333.163
939998 | 1109197.64 |  | 403581.23
943350 | 1113153 |  | 366484.87
1883348 |  |  | 770066.1
453180 | 534752.4 |  | 206213.22 | 216523.881
399007.4 | 470828.732 |  | 210285.26 | 220799.523
432000 | 509760 |  | 192324.19 | 192324.19
531530 | 627205.4 | 243410.29 | 243410.29 | 255580.8045
1815717.4
286750 | 338365 | 321429.75 | 122161.01 | 128269.0605
378768 | 446946.24 | 340686 | 99173.83 | 104132.5215
289980 | 342176.4 | 473735 | 163730.87 | 171917.4135
955498 |  |  |  | 404318.9955
351648 | 414944.64 | 230524.8 |  | 153284.6599
282100 | 332878 | 184932.2222 |  | 122968.4302
1170490 | 1381178.2 | 767321.2222 |  | 510220.9071
993474 | 1172299.32 | 651277.4 |  | 433058.98
2797712 |  |  |  | 1219532.9772
707412.1622 | 834746.3514 | 834746.3514 |  | 555054.4261
705504.5946 | 832495.4216 | 832495.4216 |  | 553557.6977
| 0 | 0 | 0 | NCB
#REF! | 0
0 | 0
939998 | 1109197.64 |  | 403581.23
943350 | 1113153 |  | 366484.87 | 602795
172777000
850000 | 1003000 | 30478
28000 | 33040 | 17859.4595
28001 | 33041.18 | 17860.0973
227500 | 131093.696 | 268450
82600 | 47597.0958
750000 | 1762500 | 12360140
|  | 7478428.3452 | -49999.7941
95530.45
| 43660 | 37000 | 14881.07
29106.6667
| -1431255.758 | 1162300