## Unit rates_MOE_No contingencies
Contractors (Works) classifications:
|  | JD | US$ | Rounding US$ |  | Expected Signing | 2009-07-01
Category 1 |  | No ceiling |  |  |  | CLOSING | 2015-12-31
Category 2 | < | 5000000 | 7142857.1429 | 7000000
Category 3 | < | 2000000 | 2857142.8571 | 2750000
Category 4 | < | 750000 | 1071428.5714 | 1000000
Category 5 | < | 250000 | 357142.8571 | 350000
|  | School cost US$ (no contingency) | Qty/ctt | Ctt amount
New schools
|  | 750000 | 2 | 1500000 | Cat 3
|  | 750000 | 3 | 2250000 | Cat 3
Extension
|  |  | .5-7 | 1120000 | Cat 3
UNIT COST
|  | Category | cost/M2 (indoor/ outdoor) without contingencies | Sch base cost in US$ (w/o contingencies) | Cost based on unit cost/M2 and on architectural programs (including 20% circulation). No contingencies
|  | Construction of new schools- 1 | 650$/M2 | 750000
450JD/M2
|  | King Abdullah2- Schools of Excellence- 1 | 800$/M2 | 1500000
560JD/M2
|  | Special Education Construction- 1 | 845$/M2 | 1100000
592JD/M2

## PAD Thresholds
(a) Prior Review Thresholds: |  |  | (a) Methods Thresholds: |  |  | Expected Signing | 2009-07-01
| Procurement Method | Prior Review Threshold |  |  |  | CLOSING | 2015-12-31
1 | ICB (Goods) | All |  | Procurement Method | Method Threshold | Updated on 14-Jan-09 |  | Estimated Contract Cost (in USD)
2 | NCB (Goods) | First contract irrespective of the value | 1 | ICB (Goods) | No threshold | Type of Procurement |  | High Risk Implementing Agency | Substantial Risk Implementing Agency | Moderate Risk Implementing Agency | Low Risk Implementing Agency
3 | ICB (Works) | All | 2 | NCB (Goods) | <= US$500,000 | Works, Turnkey and S&I of Plant and Equipment |  | $ 5 million | $ 10 million | $ 15 million | $ 20 million
4 | NCB (Works) | First contract irrespective of the value | 3 | ICB (Works) | No threshold | Goods |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
5 | Shopping (Goods) | First contract irrespective of the value | 4 | NCB (Works) | <= US$4,500,000 | IT Systems, and Non-consulting Services |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
6 | Shopping (Works) | First contract irrespective of the value | 5 | Shopping (Goods) | <= US$50,000 | Consulting Services | Firms | $ 0.2 million | $ 0.5 million | $ 1 million | $ 2 million
7 | Direct contracting | All | 6 | Shopping (Works) | <= US$50,000 |  | Individuals | $ 0.1 million | $ 0.2 million | $ 0.3 million | $ 0.5 million
8 | Innovation Fund | As defined by the operational manual thresholds | 7 | Direct contracting | No threshold
|  |  | 8 | Innovation fund | As defined by the operational manual thresholds |  | 1 | 15 |  | PPR=7% to be reviewd
[7 empty] | 6.6667 | 100
2. Consulting Services |  |  | (b) Methods Thresholds:
Prior Review Threshold:
| Selection Method | Prior Review Threshold |  | Selection Method | Method Threshold
1 | Competitive Methods (Firms) | > = US$200,000 | 1 | QCBS (Firms) | No threshold | Updated on 14-Jan-09 |  | Estimated Contract Cost (in USD)
2 | Government-owned universities and research institutes | All | 2 | CQS, FBS, LCS | <200,000 | Type of Procurement |  | High Risk Implementing Agency | Substantial Risk Implementing Agency | Moderate Risk Implementing Agency | Low Risk Implementing Agency
3 | Single Source (Firms) | All | 3 | Single Source (Firms) | No threshold | Works, Turnkey and S&I of Plant and Equipment |  | $ 5 million | $ 10 million | $ 15 million | $ 20 million
4 | Individual Consultants | > = US$100,000 | 4 | Individual Consultants | No threshold | Goods |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
5 | Governed-owned university professors or scientists from research institutes | All | 5 | Sole Source (Individual) | No threshold | IT Systems, and Non-consulting Services |  | $ 0.5 million | $ 1 million | $ 3 million | $ 5 million
6 | Single Source (Individual) | All | 6 | Innovation fund | As defined by the operational manual thresholds | Consulting Services | Firms | $ 0.2 million | $ 0.5 million | $ 1 million | $ 2 million
7 | Innovation fund | As defined by the operational manual thresholds |  |  |  |  | Individuals | $ 0.1 million | $ 0.2 million | $ 0.3 million | $ 0.5 million

## Sheet 1-C5-WorksNewSch
|  | WORLD BANK- PROCUREMENT PLAN FOR WORKS (New Schools) update23/2/2015 | [5 empty] | UPDATE 2/4/2015
as at [17-May-12]
| Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Names of schools | Governorate | Qty Sch | Unit cost (US$) | Estimated Cost (US$) | Revised Estimated Cost (US$) | Awarded Amount (JOD) | Awarded Amount (US$) | Selection Method | Bank Rev. | Bid. Doc/Specs prep. | Interval | NOL Date | Interval | Invitation Date | Interval | Bid Opening Date | Interval | Evaluation & Recomm. | Interval | NOL Date | Interval | Contract No. | Contract Signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Contract amount JD (original) | Contract amount US $ (original) | Variation Orders Amount US$ | Contract amount US $ (last revised) | Architect/ Consultant's Name | Contractor's Name | Built area of school (M2) | Total area of school (including outdoors) (M2) | Comments | Construction progress rate 30-Apr-14
0 | P | C51 | PWN001 | Works | NewSch 01 | Phase I | That Al-Sawari Basic Co.School | Amman | 1 |  |  |  | 1606625 | 2269244.3503 | NCB | PR | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 9/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Eng.Waheeb Mdanat | Salah Khalaf al hajaj co. |  |  | Implementing stage. Ruins were found and Mof tourism was informed and looking for new site. Two sites identified. Change of design is expected to start 15-Dec-11- Expected VO to be issued on the same contract or re-bidding. Design for 2 months- Contractor signature expected on Jul-2012. | 0%
| R | [8 empty] | 2829729 | 4112829 | 2923200 |  |  |  |  | 2010-11-24 | 14 | 2010-12-08 | 1 | 2010-12-09 | 28 | 2011-01-06 | 28 | 2011-02-03 | 14 | 2011-02-17 | 7 |  | 2011-02-24 | 14 | 2012-07-31 | 366 | 12 | 2013-08-01 | NA | NA |  | 160942.0904 |  |  |  |  | 5048
| A | [15 empty] | 2011-02-27 | 14 | 2011-03-13 | 1 | 2011-03-14 | 28 | 2011-04-11 | [6 empty] | 2011-06-16 | 44 | 2011-07-30 | 365 | 12 |  | NA | 1606625 | 2269244.3503 | [9 empty] | 0
1 | P | C51 | PWN002 | Works | NewSch 02 |  | Maymonah Bint Al-Hareth Basic Co. School | Amman | 1 |  |  |  | 1086972.3 | 1535271.6102 | NCB | PR | 2010-04-16 18:00 |  | 2010-04-16 18:00 | 1 | 2010-04-17 18:00 | 28 | 2010-05-15 18:00 | 28 | 2010-06-12 18:00 |  | 2010-06-12 18:00 | 3 | 8/2011 | 2010-06-15 18:00 | 14 | 2010-06-29 18:00 | 549 | 18 | 2011-12-30 18:00 | NA | NA |  | NA |  | ENG.Waheeb Mdanat | A'akef Abu Hajar Est. for Contracting |  |  | taking over procedure | 99%
| R | [8 empty] | 1283100 |  | 1904000 |  |  |  |  | 2010-11-24 | 14 | 2010-12-08 | 1 | 2010-12-09 | 28 | 2011-01-06 | 28 | 2011-02-03 | 14 | 2011-02-17 | 7 |  | 2011-02-24 | 14 | 2011-08-04 | 366 | 12 | 2012-08-04 | NA | NA |  | NA | 1696213.7 |  |  |  | 2867
| A | [15 empty] | 2011-02-27 | 14 | 2011-03-13 | 1 | 2011-03-14 | 28 | 2011-04-11 | [6 empty] | 2011-06-27 | 38 | 2011-08-04 | 365 | 12 | 2012-08-03 | NA | 1086972.3 | 1535271.6102
| P | C51 | PWN003 | Works | NewSch 03 |  | Sweileh Al-Hai Al-Sharqi Basic Boys School | Amman | 1 |  |  |  | 842245 | 1189611.5819 | NCB | PO | 2011-03-03 |  | 2011-03-03 | 1 | 2011-03-04 | 28 | 2011-04-01 | 28 | 2011-04-29 |  | 2011-04-29 | 3 | 34/2010 | 2011-05-02 | 14 | 2011-05-16 | 549 | 18 | 2012-11-15 | NA | NA |  | NA |  | Allaneha'ieh | Al sakhra al mosharafah |  |  | completed | 99%
2 | R | [8 empty] | 1386206 | 1386206 | 1488960 |  |  |  |  | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-05-01 | 28 | 2011-05-29 | 28 | 2011-06-26 | 14 | 2011-07-10 | 7 |  | 2011-07-17 | 14 | 2011-09-08 | 410 | 13.4426 | 2012-10-22 | NA | NA |  | 92288.1356 | 1281900.47 |  |  |  | 2995
| A | [15 empty] | 2011-04-09 | 14 | 2011-04-23 | 1 | 2011-04-24 | 28 | 2011-05-22 | [6 empty] | 2011-08-09 | 30 | 2011-09-08 | 410 |  | 2012-10-22 | NA | 842245.53 | 1189612.3305
3 | P | C51 | PWN004 | Works | NewSch 04 |  | Kufr Asad Secondary Boys School | Irbid | 1 |  |  |  | 1296340 | 1830988.7006 | NCB | PO | 2011-04-17 18:00 |  | 2011-04-17 18:00 | 1 | 2011-04-18 18:00 | 28 | 2011-05-16 18:00 | 28 | 2011-06-13 18:00 |  | 2011-06-13 18:00 | 3 | 43/2010 | 2011-06-16 18:00 | 14 | 2011-06-30 18:00 | 549 | 18 | 2012-12-30 18:00 | NA | NA |  | NA |  | Eng.Waheeb Mdanat | Economical & Social Est for Militarian Retirees |  |  | Implementing stage expected date of completion 1-Apr-15 | 99%
| R | [8 empty] | 1168538 | 1168538 | 2115000 |  |  |  |  | 2010-11-24 | 14 | 2010-12-08 | 1 | 2010-12-09 | 28 | 2011-01-06 | 28 | 2011-02-03 | 14 | 2011-02-17 | 7 |  | 2011-02-24 | 14 | 2011-08-25 | 450 |  | 2012-11-17 | NA | NA |  | NA | 1830989.096 |  |  |  | 4015
| A | [15 empty] | 2011-02-16 | 14 | 2011-03-02 | 1 | 2011-03-03 | 28 | 2011-03-31 | [6 empty] | 2011-07-28 | 28 | 2011-08-25 | 500 |  | 2013-01-06 | NA | 1296340.28 | 1830989.096
4 | P | C51 | PWN005 | Works | NewSch 05 |  | Zubia Secondary Boys School | Irbid | 1 |  |  |  | 1341878 | 1895307.9096 | NCB | PO | 2012-03-03 |  | 2012-03-03 | 1 | 2012-03-04 | 28 | 2012-04-01 | 28 | 2012-04-29 |  | 2012-04-29 | 3 | 44/2010 | 2012-05-02 | 14 | 2012-05-16 | 549 | 18 | 2013-11-16 | NA | NA |  | NA |  | Eng.Waheeb Mdanat | Ibraheem abo rasheed |  |  | completed | 99%
| R | [8 empty] | 1122713 | 1122713 | 2115000 |  |  |  |  | 2010-11-24 | 14 | 2010-12-08 | 1 | 2010-12-09 | 28 | 2011-01-06 | 28 | 2011-02-03 | 14 | 2011-02-17 | 7 |  | 2011-02-24 | 14 | 2011-08-02 | 500 |  | 2012-12-14 | NA | NA |  | 87707.6271 | 1983015.5367 |  |  |  | 3977
| A | [15 empty] | 2011-02-16 | 14 | 2011-03-02 | 1 | 2011-03-03 | 28 | 2011-03-31 | [6 empty] | 2011-06-23 | 40 | 2011-08-02 | 500 |  | 2012-12-14 | NA | 1341878 | 1895307.9096
5 | P | C51 | PWN006 | Works | NewSch 06 |  | Abd Al-Rahman Bin Awf Basic Co. School | Ma'an | 1 |  |  |  | 864914 | 1221629.9435 | NCB | PO | 2012-04-17 18:00 |  | 2012-04-17 18:00 | 1 | 2012-04-18 18:00 | 28 | 2012-05-16 18:00 | 28 | 2012-06-13 18:00 |  | 2012-06-13 18:00 | 3 | 46/2010 | 2012-06-16 18:00 | 14 | 2012-06-30 18:00 | 549 | 18 | 2013-12-31 18:00 | NA | NA |  | NA |  | Soubh Office | Adnan kreshan office for bledges |  |  | completed | 100%
| R | [8 empty] | 1353670 | 1353670 | 1762500 |  |  |  |  | 2010-11-24 | 14 | 2010-12-08 | 1 | 2010-12-09 | 28 | 2011-01-06 | 28 | 2011-02-03 | 14 | 2011-02-17 | 7 |  | 2011-02-24 | 14 | 2011-07-20 | 350 |  | 2012-07-04 | NA | NA |  | 83790.9605 | 1305422.1751 |  |  |  | 2954
| A | [15 empty] | 2011-02-12 | 14 | 2011-02-26 | 1 | 2011-02-27 | 28 | 2011-03-27 | [6 empty] | 2011-06-15 | 35 | 2011-07-20 | 350 |  | 2012-07-04 | NA | 864914.9 | 1221631.2147
6 | P | C51 | PWN007 | Works | NewSch 7 | Phase II | Kufr Youba Basic Boys School | Irbid | 1 |  |  |  | 1207118 | 1704968.9266 | NCB | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 33/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Al-Dar Al- arabia | Ali al-shagareen est. |  |  | Implementing stage expected date of completion 30-Jun-15 | 82%
| R | [8 empty] | 1168538 | 1168538 | 2026910 |  |  |  |  | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-05-01 | 28 | 2011-05-29 | 28 | 2011-06-26 | 14 | 2011-07-10 | 7 |  | 2011-07-17 | 14 | 2011-11-03 | 450 |  | 2013-01-26 | NA | NA |  | NA | 1704969.435 |  |  |  | 4073
| A | [16 empty] | 0 |  |  | 2011-06-05 |  |  | 0 |  | 0 |  |  |  | 2011-10-17 | 17 | 2011-11-03 | 500 |  | 2013-03-17 | NA | 1207118.36 | 1704969.435
7 | P | C51 | PWN008 | Works | NewSch 8 |  | Sabha Secondary Girls School | Al-Mafraq | 1 |  |  |  | 1092742 | 1543420.904 | NCB | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 30/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Maktab manar | Ahmad abu soied |  |  | taking over procedure | 99%
| R | [8 empty] | 1353670 | 1353670 | 2103750 |  |  |  |  | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-05-01 | 28 | 2011-05-29 | 28 | 2011-06-26 | 14 | 2011-07-10 | 7 |  | 2011-07-17 | 14 | 2011-10-26 | 415 | 13.6066 | 2012-12-14 | NA | NA |  | 42250 | 1585671.845 |  |  |  | 3173
| A | [15 empty] | 2011-05-23 | 14 | 2011-06-06 | 1 | 2011-06-07 | 28 | 2011-07-05 | 28 | 2011-08-02 | 14 | 2011-08-16 | 7 |  | 2011-09-27 | 29 | 2011-10-26 | 415 | 13.6066 | 2012-12-14 | NA | 1092742.666 | 1543421.8446
8 | P | C51 | PWN009 | Works | NewSch 9 |  | Sama Al-Rousan Basic Girls School | Irbid | 1 |  |  |  | 1376240.8 | 1943842.9379 | NCB | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 29/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Al-Dar Al- arabia | Al ta'ani and shdefat |  |  | completed | 100%
| R | [8 empty] | 50 | 1353670 | 2356990 |  |  |  |  | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-05-01 | 28 | 2011-05-29 | 28 | 2011-06-26 | 14 | 2011-07-10 | 7 |  | 2011-07-17 | 14 | 2011-10-15 | 415 | 13.6066 | 2012-12-03 | NA | NA |  | 18509.887 | 1962352.8249 |  |  |  | 2903
| A | [15 empty] | 2011-05-22 | 14 | 2011-06-05 | 1 | 2011-06-06 | 28 | 2011-07-04 | 28 | 2011-08-01 | 14 | 2011-08-15 | 7 |  | 2011-09-05 | 40 | 2011-10-15 | 415 | 13.6066 | 2012-12-03 | NA | 1376240.8 | 1943842.9379
9 | P | C51 | PWN010 | Works | NewSch 10 |  | Majadel Basic Co. School | Al-Tafieleh | 1 |  |  |  | 1113177.62 | 1572284.774 | NCB | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 34/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Madi and partners | Al fakher |  |  | completed | 99%
| R | [8 empty] | 23 | 1353670 | 2125790 |  |  |  |  | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-05-01 | 28 | 2011-05-29 | 28 | 2011-06-26 | 14 | 2011-07-10 | 7 |  | 2011-07-17 | 14 | 2011-10-29 | 500 |  | 2013-03-12 | NA | NA | 1572284.7458 | 12293.7853 | 1584578.5311 |  |  |  | 3260
| A | [16 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 2011-10-10 | 19 | 2011-10-29 | 500 |  | 2013-03-12 | NA | 1113177.6
10 | P | C51 | PWN01+D25 | Works | NewSch 11 |  | Al-Zaytounah Basic Boys School | Al-Mafraq | 1 |  |  |  | 841000.5 | 1187853.8136 | NCB | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 31/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Eng.Waheeb Mdanat | Al-Weshahe for bledges |  |  | completed | 99%
| R | [8 empty] | 1353670 | 1353670 | 1491000 |  |  |  |  | 2011-05-16 | 14 | 2011-05-30 | 1 | 2011-05-31 | 28 | 2011-06-28 | 28 | 2011-07-26 | 14 | 2011-08-09 | 7 |  | 2011-08-16 | 14 | 2011-09-24 | 375 | 12 | 2012-10-03 | NA | NA |  | 187853.1073 | 1375706.9209 |  |  |  | 2360
| A | [15 empty] | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-05-01 | 28 | 2011-05-29 |  |  |  | 0 |  |  | 2011-08-23 | 32 | 2011-09-24 | 375 |  | 2012-10-03 | NA | 841000.5 | 1187853.8136
11 | P | C51 | PWN012 | Works | NewSch 12 |  | Al-Housaynieh Basic.Co School | Maan | 1 |  |  |  | 799950 | 1129872.8814 | NCB | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 32/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Madi and partners | Mansour al agaileh |  |  | completed | 100%
| R | [8 empty] | 1353670 | 1353670 | 1470000 |  |  |  |  | 2011-05-16 | 14 | 2011-05-30 | 1 | 2011-05-31 | 28 | 2011-06-28 | 28 | 2011-07-26 | 14 | 2011-08-09 | 7 |  | 2011-08-16 | 14 | 2011-10-01 | 350 |  | 2012-09-15 | NA | NA |  | 148449.6723 | 1278322.5537 |  |  |  | 2319
| A | [15 empty] | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-05-01 | 28 | 2011-05-29 | 28 | [5 empty] | 2011-09-05 | 26 | 2011-10-01 | 350 |  | 2012-09-15 | NA | 799950 | 1129872.8814
12 | P | C51 | PWN013 | Works | NewSch 13 | phase III | Al-Rabyah Basic Co. School | Al-Mafraq | 1 |  |  |  | 1049922.268 | 1482941.0565 | NCB | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 95/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Eng.Waheeb Mdanat | Ismae'el Audeh Est. |  |  | taking over procedure | 99%
| R | [8 empty] | 1122713 | 1122713 | 2157897 |  |  |  |  | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-05-01 |  | 2011-11-01 | 58 | 2011-11-29 | 14 | 2011-12-13 | 7 |  | 2012-02-14 | 14 | 2012-02-28 | 366 | 12 | 2013-02-28 | NA | NA |  | 105757.0621 | 1588698.119 |  |  |  | 2770
| A | [16 empty] | 0 |  | 1 | 2011-10-05 |  | 2011-11-01 | 28 | 2011-11-29 |  |  |  |  | 2012-02-14 | 14 | 2012-02-28 | 365 | 11.9672 | 2013-02-27 | NA | 1049922.268 | 1482941.0565
| P | C51 | PWN014 | Works | NewSch 14 |  | Hareema Basic Boys School | Irbid | 1 | 1353670 | 1353670 | 2288122 | 1219483.56 | 1722434.4068 | NCB | PO | 2010-03-02 | 14 | 2010-03-16 | 1 | 2010-03-17 |  | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 94/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Eng.Waheeb Mdanat | Nae'l hadad for bledges مؤسسة نائل حداد للمقاولات |  |  | Canceled as a result of WB Objection on re_tendering process
| R | [15 empty] | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-05-01 |  | 2011-10-31 | 58 | 2011-11-29 | 14 | 2011-12-13 | 7 |  | 2011-12-20 | 14 | 2012-01-03 | 366 | 12 | 2013-01-03 | NA | NA |  | NA
| A | [16 empty] | 0 |  | 1 | 2011-09-29 |  | 2011-10-31 | -40847 |  |  |  | 0 |  |  | 14 |  |  | 0 | 0 | 0 |  |  |  | 0
13 | P | C51 | PWN014 | Works | NewSch 14 |  | Mansheyet Bani-Hasan Basic Girls School | Al-Mafraq | 1 |  |  |  |  | 1304500.7486 | NCB | PO | 2010-03-02 | 14 | 2010-03-16 | 1 | 2010-03-17 |  | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 109/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Eng.Waheeb Mdanat | Al- Harraneh Est. |  |  | completed | 99%
| R | [8 empty] | 1353670 | 1353670 | 1911000 | 923586.53 |  |  |  | 2011-05-16 | 14 | 2011-05-30 | 1 | 2011-05-31 |  | 2011-11-30 | 58 | 2011-12-14 | 14 | 2011-12-28 | 7 |  | 2012-01-19 | 14 | 2012-02-02 | 366 | 12 | 2013-02-02 | NA | NA |  | 431600.2825 | 1736101.0311 |  |  |  | 3202
| A | [16 empty] | 0 |  | 1 | 2011-10-25 |  | 2011-11-30 | 14 | 2011-12-14 |  |  |  |  | 2012-01-19 | 19 | 2012-02-07 | 365 | 11.9672 | 2013-02-06 | NA | 923586.53 | 1304500.7486
14 | P | C51 | PWN015 | Works | NewSch 15 |  | That Al-Netaqayn Basic.Co School | Maan | 1 |  |  |  |  | 1161016.9492 | NCB | PO | 2010-03-02 | 14 | 2010-03-16 | 1 | 2010-03-17 |  | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 92/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Dar Al- Takhteet دار التخطيط للاستشارات الهندسية | Mansour al agaileh |  |  | completed | 100%
| R | [8 empty] | 1353670 | 1353670 | 1435000 | 822000 |  |  |  | 2011-05-16 | 14 | 2011-05-30 | 1 | 2011-05-31 |  | 2011-11-27 | 58 | 2011-12-07 | 14 | 2011-12-21 | 7 |  | 2012-02-07 | 14 | 2012-02-21 | 366 | 12 | 2013-02-21 | NA | NA |  | 178617.2316 | 1339634.1808 |  |  |  | 2263
| A | [16 empty] | 0 |  | 1 | 2011-10-18 |  | 2011-11-27 | 10 | 2011-12-07 |  |  |  |  | 2012-02-06 | 20 | 2012-02-26 | 350 | 11.4754 | 2013-02-10 | NA | 822000 | 1161016.9492
15 | P | C51 | PWN016 | Works | NewSch 16 |  | Rufaidah Al-Aslamieh Basic.Co instead of Yajouz Basic Boys School | Amman | 1 |  |  |  |  | 2273639.3644 | NCB | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 120/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Eng.Waheeb Mdanat | Al-Eman Est. |  |  | Implementing Stage | 99%
| R | [8 empty] | 1353670 | 1353670 | 2800000 | 1609736.67 |  |  |  | 2011-05-16 | 14 | 2011-05-30 | 1 | 2011-11-29 | 20 | 2011-12-19 | 28 | 2012-01-02 | 14 | 2012-01-16 | 7 |  | 2012-02-12 | 14 | 2012-02-26 | 366 | 12 | 2013-02-26 | NA | NA |  | 137430.791 | 2411070.1554 |  |  |  | 4917
| A | [16 empty] | 0 |  | 1 | 2011-11-29 |  | 2011-12-19 |  | 2012-01-02 |  |  |  |  | 2012-02-09 | 10 | 2012-02-19 | 415 | 13.6066 | 2013-04-09 | NA | 1609736.67 | 2273639.3644
16 | P | C51 | PWN017 | Works | NewSch 17 |  | Al-Yarout Secondary Boys School | Al-Karak | 1 |  |  |  |  | 1101221.322 | NCB | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 114/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Dar Al- Takhteet دار التخطيط للاستشارات الهندسية | Mekhled al majali company شركة مخلد المجالي /الريف |  |  | completed | 99%
| R | [8 empty] | 2829729 | 4112829 | 2450000 | 779664.696 |  |  |  | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-11-15 |  | 2011-12-11 | 28 | 2011-12-19 | 14 | 2012-01-02 | 7 |  | 2012-01-08 | 14 | 2012-01-22 | 366 | 12 | 2013-01-22 | NA | NA |  | 457822.0339 | 1559043.3559 |  |  |  | 2500
| A | [16 empty] | 0 |  | 1 | 2011-11-15 |  | 2011-12-11 | 8 | 2011-12-19 |  |  |  |  | 2012-01-08 | 35 | 2012-02-12 | 410 | 13.4426 | 2013-03-28 | NA | 779664.696 | 1101221.322
17 | P | C51 | PWN019 | Works | NewSch 18 |  | Banat Al-Hashemeyeh Basic.Co School | Maan | 1 |  |  |  |  | 1200275.7768 | NCB | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 3 | 93/2011 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | NA | NA |  | NA |  | Dar Al- Takhteet دار التخطيط للاستشارات الهندسية | Bassam Farhan Est. |  |  | completed | 99%
| R | [8 empty] | 1353670 | 1353670 | 1533000 | 849795.25 |  |  |  | 2011-05-16 | 14 | 2011-05-30 | 1 | 2011-11-22 | 22 | 2011-12-14 | 19 | 2012-01-02 | 14 | 2012-01-16 | 7 |  | 2012-01-23 | 14 | 2012-02-06 | 366 | 12 | 2013-02-06 | NA | NA |  | 231097.4576 | 1431373.2345 |  |  |  | 2466
| A | [16 empty] | 0 |  | 1 | 2011-11-22 |  | 2011-12-14 | 19 | 2012-01-02 |  |  |  |  | 2012-01-30 | 20 | 2012-02-19 | 350 | 11.4754 | 2013-02-03 | NA | 849795.25 | 1200275.7768
18 | P | C51 | PWN020+D37 |  | NewSch 19 |  | Shkout Basic Boys school | Al Zarqa | 1 |  |  |  |  | 915404.7458 | NCB | PO | 2011-04-16 | 14 | 2011-04-30 | 1 | 2011-05-01 | 28 | 2011-05-29 | 28 | 2011-06-26 | 14 | 2011-07-10 | 7 | 21/2012 | 2011-07-17 | 14 | 2011-07-31 | 366 | 12 | 2012-07-31 | NA | NA |  | NA |  |  | Salim Smaadi/Al-Watar |  |  | Implementing stage expected date of completion 1-JUN-15 | 68%
| R | [8 empty] | 1353670 |  | 1837116 | 648106.56 |  |  |  | 2012-04-23 | 14 | 2012-05-07 | 1 | 2012-05-08 | 28 | 2012-06-05 | 28 | 2012-07-03 | 14 | 2012-07-17 | 7 |  | 2012-07-24 | 14 | 2012-08-07 | 365 | 12 | 2013-08-07 |  |  |  | NA | 915404.75 |  |  |  | 1729
| A | [16 empty] | 14 |  | 1 |  |  | 2012-06-05 | [6 empty] | 2012-08-30 |  | 2012-10-03 | 300 |  | 2013-07-30 |  | 648106.56 | 915404.7458
19 | P | C51 | PWN021 | Works | NewSch 20 | Phase IV | Al- Andalus basic co | Amman | 1 |  |  |  |  | 0 | NCB | PO | 2012-08-01 | 14 | 2012-08-15 | 1 | 2012-08-16 | 28 | 2012-09-13 | 28 | 2012-10-11 | 14 | 2012-10-25 | 7 |  | 2012-11-01 | 14 | 2012-11-15 | 366 | 12 | 2013-11-28 | [5 empty] | صبح للاستشارات الهندسية | Sadeen Cont comp |  |  | Implementing stage | 4%
| R | [8 empty] | 1553672.3164 |  | 2115000 |  |  |  |  | 2014-07-30 | 14 | 2014-08-13 | 1 | 2014-08-14 | 28 | 2014-09-11 | 28 | 2014-10-09 | 14 | 2014-10-23 | 7 |  | 2014-10-30 | 14 | 2014-11-13 | 365 | 12 | 2015-11-13 | [8 empty] | 4200
| A | [36 empty] | 4063838.216 |  | 4063838.216
20 | P | C51 | PWN022 | Works | NewSch 21 |  | Al- Sumaira Bent Qais Basic Girls | Amman | 1 |  |  |  |  | 0 | NCB | PO | 2012-08-01 | 14 | 2012-08-15 | 1 | 2012-08-16 | 28 | 2012-09-13 | 28 | 2012-10-11 | 14 | 2012-10-25 | 7 |  | 2012-11-01 | 14 | 2012-11-15 | 366 | 12 | 2013-11-28 | [5 empty] | صبح للاستشارات الهندسية | Sadeen Cont comp |  |  | Implementing stage | 3%
| R | [8 empty] | 1553672.3164 |  | 2256000 |  |  |  |  | 2014-07-30 | 14 | 2014-08-13 | 1 | 2014-08-14 | 28 | 2014-09-11 | 28 | 2014-10-09 | 14 | 2014-10-23 | 7 |  | 2014-10-30 | 14 | 2014-11-13 | 365 | 12 | 2015-11-13 | [8 empty] | 4800
A
21 | P | C51 | PWN023 | Works | NewSch 22 |  | Ein Al- Bustan Basic Co | Ajlun | 1 |  |  |  |  | 0 | NCB | PO | 2012-08-01 | 14 | 2012-08-15 | 1 | 2012-08-16 | 28 | 2012-09-13 | 28 | 2012-10-11 | 14 | 2012-10-25 | 7 |  | 2012-11-01 | 14 | 2012-11-15 | 366 | 12 | 2013-11-28 | [5 empty] | منار مهندسون مستشارون | Dijla contracting foundation |  |  | Implementing stage expected date of completion 25-Oct-15 | 63%
| R | [8 empty] | 1624293.7853 | 1624293.7853 | 1694915.2542 |  |  |  |  | 2014-05-30 | 14 | 2014-06-13 | 1 | 2014-06-14 | 28 | 2014-07-12 | 28 | 2014-08-09 | 14 | 2014-08-23 | 7 |  | 2014-08-30 | 14 | 2014-09-13 | 365 | 12 | 2015-09-13 |  |  | 3897471.62 | 214689.3 | 4112160.92 |  |  |  | 2500
| A | [15 empty] | 2014-05-12
22 | [6 empty] | Yobla secondary boys | Irbid | 1 |  |  |  |  | 0 | NCB | PO | 2012-08-01 | 14 | 2012-08-15 | 1 | 2012-08-16 | 28 | 2012-09-13 | 28 | 2012-10-11 | 14 | 2012-10-25 | 7 |  | 2012-11-01 | 14 | 2012-11-15 | 366 | 12 | 2013-11-28 | [5 empty] | منار مهندسون مستشارون | Dijla contracting foundation |  |  | Implementing stage expected date of completion 8-Dec-15 | 55%
[10 empty] | 1624293.7853 | 1624293.7853 | 1977401.1299 |  |  |  |  | 2014-05-30 | 14 | 2014-06-13 | 1 | 2014-06-14 | 28 | 2014-07-12 | 28 | 2014-08-09 | 14 | 2014-08-23 | 7 |  | 2014-08-30 | 14 | 2014-09-13 | 365 | 12 | 2015-09-13 | [8 empty] | 3000
2014-05-12
23 | P | C51 | PWN024 | Works | NewSch 23 |  | Khadeja Bent Khuwiled Basic co | Al- Balqa'a | 1 |  |  |  |  | 0 | NCB | PO | 2012-08-01 | 14 | 2012-08-15 | 1 | 2012-08-16 | 28 | 2012-09-13 | 28 | 2012-10-11 | 14 | 2012-10-25 | 7 |  | 2012-11-01 | 14 | 2012-11-15 | 366 | 12 | 2013-11-28 | [5 empty] | منار مهندسون مستشارون | Al Bader Contracting Company |  |  | Implementing stage expected date of completion 18-DEC-15 | 34%
| R | [8 empty] | 2966101.6949 | 2966101.6949 | 2966101.6949 |  |  |  |  | 2014-05-30 | 14 | 2014-06-13 | 1 | 2014-06-14 | 28 | 2014-07-12 | 28 | 2014-08-09 | 14 | 2014-08-23 | 7 |  | 2014-08-30 | 14 | 2014-09-13 | 365 | 12 | 2015-09-13 |  |  |  |  | 2966101.695 |  |  |  | 4500
| A | [15 empty] | 2014-05-12
| P | C51 | PWN026 | Works | NewSch 24 |  | Al- batrawe al-janobe co | Zarqa | 1 |  |  |  |  | 0 | NCB | PO | 2012-08-01 | 14 | 2012-08-15 | 1 | 2012-08-16 | 28 | 2012-09-13 | 28 | 2012-10-11 | 14 | 2012-10-25 | 7 |  | 2012-11-01 | 14 | 2012-11-15 | 366 | 12 | 2013-11-28 | [5 empty] | عمان للاستشارت الهندسية | Ismae'el Al Hersh & Partners |  |  | Implementing stage expected date of completion 22-jun-15 | 82%
24 | R | [8 empty] | 3107344.6328 | 3107344.6328 | 1694915.2542 |  |  |  |  | 2013-11-30 | 14 | 2013-12-14 | 1 | 2013-12-15 | 28 | 2014-01-12 | 28 | 2014-02-09 | 14 | 2014-02-23 | 7 |  | 2014-03-02 | 14 | 2014-03-16 | 365 | 12 | 2015-03-16 |  |  |  |  | 1974442.403 |  |  |  | 4969
| A | [15 empty] | 2014-05-12 | [19 empty] | 1410316.0021
25 | P | C51 | PWN028 | Works | NewSch 26 |  | Jreba basic Co | Zarqa | 1 |  |  |  | 999715.65 | 1412027.7542 | NCB | PO | 2012-08-01 | 14 | 2012-08-15 | 1 | 2012-08-16 | 28 | 2012-09-13 | 28 | 2012-10-11 | 14 | 2012-10-25 | 7 | 141/2013 | 2012-11-01 | 14 | 2012-11-15 | 366 | 12 | 2013-11-28 | [5 empty] | Dar Al- Takhteet دار التخطيط للاستشارات الهندسية | Yousef Bustanji & brother company |  |  | Implementing stage expected date of completion13-Apr-15 | 80%
| R | [8 empty] | 1624293.7853 | 1624293.7853 | 1977401.1299 |  |  |  |  | 2013-11-30 | 14 | 2013-12-14 | 1 | 2013-12-15 | 28 | 2014-01-12 | 28 | 2014-02-09 | 14 | 2014-02-23 | 7 |  | 2014-03-02 | 14 | 2014-03-16 | 365 | 12 | 2015-03-16 |  |  |  | NA | 1412027.754 |  |  |  | 2700
| A | [19 empty] | 2013-11-06 |  | 2013-11-27 |  | 2014-01-18 | [6 empty] | 2014-04-13 | 365 |  |  |  | 999715.65 | 1412027.7542
26 | P | C51 | PWN028 | Works | NewSch 27 |  | Al_ Mallaha basic Co | Der A'lla | 1 |  |  |  | 472401.185 | 667233.3121 | NCB | PO | 2012-08-01 | 14 | 2012-08-15 | 1 | 2012-08-16 | 28 | 2012-08-12 | 28 | 2012-09-09 | 14 | 2012-09-23 | 7 | 81/2012 | 2012-09-30 | 14 | 2012-10-14 | 549 | 18 | 2014-04-28 |  | 472401.185 | 667233.3121 | 0 |  |  | Abo Siam |  |  | Implementing stage expected date of completion30-Jun-15 | 75%
| R | [9 empty] | 861581.9209 | [5 empty] | 2011-11-20 | 14 | 2011-12-04 | 1 | 2011-12-05 | 28 | 2012-01-02 | 28 | 2012-01-30 | 14 | 2012-02-13 | 7 |  | 2012-02-20 | 14 | 2012-03-05 | 365 | 12 | 2013-03-05 |  |  |  |  | 700590.657 |  |  |  | 916
| A | [23 empty] | 2012-09-06 |  |  |  |  | 2013-10-22 |  |  | 240 | 7.8689 | 2013-10-22 |  | 472401.185 | 667233.3121
27 | P | C51 | PWN028 | Works | NewSch 28 |  | Fatima AL-Zahra basic Co. | Zarqa | 1 |  |  |  |  | 0 | NCB | PO | 2012-08-01 | 14 | 2012-08-15 | 1 | 2015-01-04 | 28 | 2012-08-12 | 28 | 2012-09-09 | 14 | 2012-09-23 | 7 |  | 2012-09-30 | 14 | 2012-10-14 | 549 | 18 | 2014-05-04 |  |  | 0 | 0 | 3606685.028 | ENG.Waheeb Mdanat |  |  |  | Implementing stage expected date of completion29-Apr-16 | 1%
| R | [9 empty] | 2824858.7571 | 1974000 |  |  |  |  | 2014-11-20 | 14 | 2014-12-04 | 1 | 2014-12-05 | 28 | 2015-01-02 | 28 | 2015-01-30 | 14 | 2015-02-13 | 7 |  | 2015-02-20 | 14 | 2015-03-06 | 365 | 12 | 2016-03-05 |  |  |  | NA |  |  |  |  | 4200
| A | [19 empty] | 2015-01-04 |  | 2015-02-02 | [10 empty] | 0 |  |  |  | 0
28 | P | C51 | PWN028 | Works | NewSch 29 |  | Porma Secondary schools for girls | Jarash | 1 |  |  |  |  | 0 | NCB | PO | 2012-08-01 | 14 | 2012-08-15 | 1 | 2012-08-16 | 28 | 2012-08-12 | 28 | 2012-09-09 | 14 | 2012-09-23 | 7 |  | 2012-09-30 | 14 | 2012-10-14 | 549 | 18 | 2014-05-04 |  |  | 0 | 0 |  | ENG.Waheeb Mdanat |  |  |  | Implementing stage expected date of completion29-Apr-16 | 1%
| R | [9 empty] | 1836158.1921 | 1833000 |  |  |  |  | 2014-11-20 | 14 | 2014-12-04 | 1 | 2014-12-05 | 28 | 2015-01-02 | 28 | 2015-01-30 | 14 | 2015-02-13 | 7 |  | 2015-02-20 | 14 | 2015-03-06 | 365 | 12 | 2016-03-05 |  |  |  | NA |  |  |  |  | 2500
| A | [19 empty] | 2015-01-04 | 1900-01-28 | 2015-02-02 | [10 empty] | 0 |  |  |  | 0
[40 empty] | CONTRACT AMOUNT |  |  |  |  | uncontract estimated cost |  | 0
47406314.588
TOTAL CONTRACT AMOUNT
60031943.3471
0
Formulas:
Bid. Doc/Specs prep. = [NOL Date]-[Interval]
NOL Date = [Invitation Date]-[Interval]
NOL Date = [Contract Signature Date]-[Interval]
Invitation Date = [Bid Opening Date]-[Interval]
Invitation Date = [NOL Date]+[Interval]
Bid Opening Date = [Evaluation & Recomm.]-[Interval]
Bid Opening Date = [Invitation Date]+[Interval]
Evaluation & Recomm. = [NOL Date]-[Interval]
Evaluation & Recomm. = [Bid Opening Date]+[Interval]
Contract Start Date = [Contract Signature Date]+[Interval]
Completion Date (original) = [Contract Start Date]+[Execution in days]
Completion Date (original) = [Contract Start Date]+[Execution in days]+AJ62
Contract Signature Date = [NOL Date]+[Interval]
Interval = [NOL Date]-[Bid. Doc/Specs prep.]
Interval = [Evaluation & Recomm.]-[Bid Opening Date]
Completion Date (last revision) = [Execution in days]+[Execution in months]
Contract amount US $ (last revised) = [Contract amount JD (original)]+[Variation Orders Amount US$]
Note on AO6: Procurement: Quantity Inc.
Note on AH7: wb232552: May be rebidding
Note on AV8: User: commencement date 18-Sep-11
Note on AV11: Aتم الاستلام الاولي بنواقص بتاريخ 9/9/2014 zmy.Hmaidi:
Note on AO12: Exepected = 14000 JD
Note on AP12: Azmy.Hmaidi: 1281900.47
Note on AV14: User: commencement date 25-Aug-11
Note on AO15: Exepected = 30969 JD
Note on AP15: Azmy.Hmaidi: قيمة العقد مع الاوامر التغيرية
Note on AI16: Procurement: تم تعديل الرقم
Note on AV23: User: commencement date 30-Nov-11
Note on AV26: User: 26-Oct-11 commencement date
Note on AO27: Procurement: Exepected = 3000 JD
Note on AO33: Procurement: Quantity Inc.
Note on AV41: User: 6-Mar-12
Note on Z42: wb232552: to get waiver for financial obligation
Note on AO42: Procurement: Exepected = 135000 JD
Note on AI43: Procurement: الرقم
Note on Z45: wb232552: to get waiver for financial obligation
Note on Z48: wb232552: to get waiver for financial obligation
Note on Z51: wb232552: to get waiver for financial obligation
Note on AI52: Procurement: الرقم
Note on AH55: Procurement: jتم تعديل التاريخ ,l ,ومدة التنفيذ
Note on AI58: Procurement: تم تعديل الرقم
Note on AI61: Procurement: تم تعديل الرقم
Note on AV62: User: commencement date 30-Oct-12
Note on AV65: User: expected date of completion 1-Mar-16
Note on AV68: User: expected date of completion 1-Mar-16
Note on AV71: User: commencement date 15-Oct-14
Note on AN72: Azmy.Hmaidi: مجموع عقود يبلا & عين البستان
Note on AO72: Azmy.Hmaidi: VO IS 152000 JD
Note on AV74: User: commencement date 8-Dec-14
Note on AV77: User: commencement date 24-Seb-14
Note on AV80: User: commencement date 22-jun-14
Note on AV83: User: commencement date 13-Apr-14
Note on AP84: Azmy.Hmaidi: 1412027.754
Note on AV86: User: commencement date 24-Feb-14
Note on AP87: Azmy.Hmaidi: 700590657

## Sheet 2-5 WorkExt
WORLD BANK- PROCUREMENT PLAN FOR WORKS (Extensions)
as at [30-Oct-14]
|  | EXTENSION SCHOOLS |  |  |  | UPDATE 2/4/2015
| Plan vs. Actual | Proc. System Ref. # | SN. # | Comp | Sub-Comp | Location/ Description of Assignment | Names of schools | Qty Sch | Governorate | Bank Rev. | Bid. Doc/Specs prep. | Interval | NOL Date | Interval | Invitation Date | Interval | Bid Opening Date | Interval | Evaluation & Recomm. | Interval | NOL Date | Contract No. | Interval | Contract Signature Date | Interval | Contract Start Date | Execution in days | Execution in months | Completion Date (original) | Completion Date (last revision) | Contract amount JOD (original) | Contract amount US$ (original) | Variation Orders Amount US$ | Contract amount US$ (last revised) | Architect/ Consultant's Name | Contractor's Name | Built area of school (M2) | Total area of school (including outdoors) (M2) | Status | Construction Progress rate 30-Apr-14
1 | P | C51 | PWE001 | Works | Ext. 01 | Phase I | Jawa Secondary Boys School | 4 | Amman | PR | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 16/2012 | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  |  |  |  | 827342.133 |  | Zedan & Murad Hajaj/Al Bedayah for Contracting Construction | 1900 |  | expected date of completion 30-Aug-15 | 62%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2012-03-27 | 28 | 2012-04-29 | 28 | 2012-05-27 | 14 | 2012-06-10 |  | 7 | 2012-06-17 | 14 | 2012-07-01 | 366 | 12 | 2013-07-02
| A | [13 empty] | 2012-03-27 | 33 | 2012-04-29 | [6 empty] | 2012-06-28 |  | 2012-09-09 | 180 | 5.9016 | 2013-03-08
2 | P | C51 | PWE002 | Works | Ext. 02 |  | Azmeileh Secondary Girls School |  |  | PR | 2010-04-16 18:00 |  | 2010-04-16 18:00 | 1 | 2010-04-17 18:00 | 28 | 2010-05-15 18:00 | 28 | 2010-06-12 18:00 |  | 2010-06-12 18:00 |  | 3 | 2010-06-15 18:00 | 14 | 2010-06-29 18:00 | 549 | 18 | 2011-12-30 18:00 | [9 empty] | taking over procedure | 99%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2012-04-29 | 28 | 2012-05-27 | 14 | 2012-06-10 |  | 7 | 2012-06-17 | 14 | 2012-07-01 | 366 | 12 | 2013-07-02
| A | [13 empty] | 2012-03-27 | 33 | 2012-04-29 | [6 empty] | 2012-06-28 |  | 2012-09-09 | 180 | 5.9016 | 2013-03-08
3 | P | C51 | PWE003 | Works | Ext. 03 |  | E'era Secondary Boys School |  | Al-Balqa | PR | 2010-06-01 12:00 |  | 2010-06-01 12:00 | 1 | 2010-06-02 12:00 | 28 | 2010-06-30 12:00 | 28 | 2010-07-28 12:00 |  | 2010-07-28 12:00 |  | 3 | 2010-07-31 12:00 | 14 | 2010-08-14 12:00 | 549 | 18 | 2012-02-14 12:00 | [9 empty] | expected date of completion 30-Jun-15 | 80%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2012-04-29 | 28 | 2012-05-27 | 14 | 2012-06-10 |  | 7 | 2012-06-17 | 14 | 2012-07-01 | 366 | 12 | 2013-07-02
| A | [13 empty] | 2012-03-27 | 33 | 2012-04-29 | [6 empty] | 2012-06-28 |  | 2012-09-09 | 180 | 5.9016 | 2013-03-08
4 | P | C51 | PWE004 | Works | Ext. 04 |  | Somia Basic Co. School |  |  | PO | 2010-07-17 06:00 |  | 2010-07-17 06:00 | 1 | 2010-07-18 06:00 | 28 | 2010-08-15 06:00 | 28 | 2010-09-12 06:00 |  | 2010-09-12 06:00 |  | 3 | 2010-09-15 06:00 | 14 | 2010-09-29 06:00 | 549 | 18 | 2012-03-31 06:00 | [9 empty] | expected date of completion 30-Jun-15 | 75%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2012-04-29 | 28 | 2012-05-27 | 14 | 2012-06-10 |  | 7 | 2012-06-17 | 14 | 2012-07-01 | 366 | 12 | 2013-07-02
| A | [13 empty] | 2012-03-27 | 33 | 2012-04-29 | [6 empty] | 2012-06-28 |  | 2012-09-09 | 180 | 5.9016 | 2013-03-08
5 | P | C51 | PWE005 | Works | Ext. 05 |  | Maymonah Bint Al-Hareth Basic Co. School | 3 | Irbid | PO | 2011-06-02 12:00 |  | 2011-06-02 12:00 | 1 | 2011-06-03 12:00 | 28 | 2011-07-01 12:00 | 28 | 2011-07-29 12:00 |  | 2011-07-29 12:00 | 76/2011 | 3 | 2011-08-01 12:00 | 14 | 2011-08-15 12:00 | 549 | 18 | 2013-02-14 12:00 |  | 445891 | 629789.548 | 116673.7288 |  |  | شركة البركة للمقاولات |  |  | completed | 99%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-07-13 | 28 | 2011-08-10 | 14 | 2011-08-24 |  | 7 | 2011-08-31 | 14 | 2012-02-15 | 366 | 12 | 2013-02-15
| A | [22 empty] | 2012-01-12 |  | 2012-02-15 | 120 | 3.9344 | 2012-06-14
6 | P | C51 | PWE006 | Works | Ext. 06 |  | Al-Huson Basic Co. School |  |  | PO | 2011-07-18 06:00 |  | 2011-07-18 06:00 | 1 | 2011-07-19 06:00 | 28 | 2011-08-16 06:00 | 28 | 2011-09-13 06:00 |  | 2011-09-13 06:00 |  | 3 | 2011-09-16 06:00 | 14 | 2011-09-30 06:00 | 549 | 18 | 2013-04-01 06:00 |  |  |  |  | 746463.2768 | [5 empty] | 99%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-07-13 | 28 | 2011-08-10 | 14 | 2011-08-24 |  | 7 | 2011-08-31 | 14 | 2012-02-15 | 366 | 12 | 2013-02-15
| A | [22 empty] | 2012-01-12 |  | 2012-02-15 | 120 | 3.9344 | 2012-06-14
7 | P | C51 | PWE007 | Works | Ext. 07 |  | Malka Secondary Girls School |  |  | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | [10 empty] | 99%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-07-13 | 28 | 2011-08-10 | 14 | 2011-08-24 |  | 7 | 2011-08-31 | 14 | 2012-02-15 | 366 | 12 | 2013-02-15
| A | [22 empty] | 2012-01-12 |  | 2012-02-15 | 120 | 3.9344 | 2012-06-14 | 2012-05-25
8 | P | C51 | PWE008 | Works | Ext. 08 |  | A'aeshah Al-Ba'ounieh Basic Girls School | 2 | Ajloun | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 38/2011 | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  | 418714.56 | 591404.7458 | 164192.0904 | 755596.8362 | مؤسسة البريق للمقاولات الانشائية | المختصون للتصميم الهندسي | 972 |  | completed | 99%
| R | [9 empty] | 2011-04-30 | 14 | 2011-05-14 | 1 | 2011-05-15 | 28 | 2011-06-12 | 28 | 2011-07-10 | 14 | 2011-07-24 |  | 7 | 2011-07-31 | 14 | 2011-10-08 | 366 | 12 | 2012-10-08
| A | [9 empty] | 2011-04-19 | 14 | 2011-05-03 | 1 | 2011-05-04 | 28 | 2011-06-01 | 28 | 2011-06-29 | 14 | 2011-07-13 |  | 7 | 2011-08-25 | 44 | 2011-10-08 | 180 |  | 2012-04-05 | 2013-05-25
9 | P | C51 | PWE009 | Works | Ext. 09 |  | Al-Faihaa Basic Girls School |  | Jarash | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | [10 empty] | 100%
| R | [9 empty] | 2011-04-30 | 14 | 2011-05-14 | 1 | 2011-05-15 | 28 | 2011-06-12 | 28 | 2011-07-10 | 14 | 2011-07-24 |  | 7 | 2011-07-31 | 14 | 2011-10-08 | 366 | 12 | 2012-10-08
| A | [9 empty] | 2011-04-19 | 14 | 2011-05-03 | 1 | 2011-05-04 | 28 | 2011-06-01 | 28 | 2011-06-29 | 14 | 2011-07-13 |  | 7 | 2011-08-25 | 44 | 2011-10-08 | 230
10 | P | C51 | PWE010 | Works | Ext. 10 |  | Khalid Bin Al-Waleed Secondary Boys School | 4 | Zarqa | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 75/2011 | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  | 595896 | 841661.0169 | 331728.8136 | 1173389.8305 |  | يوسف الدراويش |  |  | completed | 99%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-07-13 | 28 | 2011-08-10 | 14 | 2011-08-24 |  | 7 | 2011-08-31 | 14 | 2012-02-15 | 366 | 12 | 2013-02-15
| A | [22 empty] | 2012-01-10 |  | 2012-02-15 | 170 |  | 2012-08-03
11 | P | C51 | PWE011 | Works | Ext. 11 |  | Maisaloon Basic Co. School |  |  | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | [10 empty] | 100%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-07-13 | 28 | 2011-08-10 | 14 | 2011-08-24 |  | 7 | 2011-08-31 | 14 | 2012-02-15 | 366 | 12 | 2013-02-15
| A | [22 empty] | 2012-01-10 |  | 2012-02-15 | 170 |  | 2012-06-14
12 | P | C51 | PWE012 | Works | Ext. 12 |  | Al-Mkaifteh Secondary Boys School |  | Mafraq | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | [10 empty] | 99%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-07-13 | 28 | 2011-08-10 | 14 | 2011-08-24 |  | 7 | 2011-08-31 | 14 | 2012-02-15 | 366 | 12 | 2013-02-15
| A | [22 empty] | 2012-01-10 |  | 2012-02-15 | 170 |  | 2012-06-14
13 | P | C51 | PWE013 | Works | Ext. 13 |  | Al-Mazra'ah Basic Co. School |  |  | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | [10 empty] | 99%
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-07-13 | 28 | 2011-08-10 | 14 | 2011-08-24 |  | 7 | 2011-08-31 | 14 | 2012-02-15 | 366 | 12 | 2013-02-15
| A | [22 empty] | 2012-01-10 |  | 2012-02-15 | 170 |  | 2012-06-14
| P | C51 | PWE014 | Works | Ext. 14 |  | Um Al-Hasheem Basic Girls School | 2 | Karak | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  |  | 0 | [6 empty] | Canceled as a result of WB Objection on re_tendering process
A
| P | C51 | PWE015 | Works | Ext. 15 |  | Faynan Basic Co. School |  | Aqaba | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-07-13 | 28 | 2011-08-10 | 14 | 2011-08-24 |  | 7 | 2011-08-31 | 14 | 2011-09-14 | 366 | 12 | 2012-09-14
A
| P | C51 | PWE015 | Works | Ext. 16 | Phase II | Mahis Secondary Boys School | 2 | Al-salt | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 60/2011 | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  | 465280 | 657175.1412 |  |  |  | درة عبدالله للمقاولات الانشائية |  |  | Canceled as a result of WB Objection on re_tendering process
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-07-13 | 28 | 2011-08-10 | 14 | 2011-08-24 |  | 7 | 2011-08-31 | 14 | 2011-09-14 | 366 | 12 | 2012-09-14
A
| P | C51 | PWE017 | Works | Ext. 17 |  | Umm Katheer Secondary Boys School |  | Al-Balqa'a | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-07-13 | 28 | 2011-08-10 | 14 | 2011-08-24 |  | 37 | 2011-09-30 | 14 | 2011-10-14 | 366 | 12 | 2012-10-14
A
14 | P | C51 | PWE014 | Works | Ext. 14 |  | Al-Qadesieh Basic Girls School | 2 | Irbid | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 61/2011 | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  | 498527.68 | 704135.1412 | 115467.5141 | 819602.6554 |  | موسى جيوسي وشركاه |  |  | completed | 100%
| R | [9 empty] | 2011-10-30 | 14 | 2011-11-13 | 1 | 2011-11-14 | 28 | 2011-12-12 | 28 | 2012-01-09 | 14 | 2012-01-23 |  | 7 | 2012-01-30 | 14 | 2012-02-20 | 366 | 12 | 2013-02-20
| A | [22 empty] | 2012-01-10 |  | 2012-02-20 | 230 |  | 2012-10-07
15 | P | C51 | PWE015 | Works | Ext. 15 |  | Jdeta Secondary Girls School |  | Al- korah | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | [10 empty] | 100%
| R | [9 empty] | 2011-10-30 | 14 | 2011-11-13 | 1 | 2011-11-14 | 28 | 2011-12-12 | 28 | 2012-01-09 | 14 | 2012-01-23 |  | 7 | 2012-01-30 | 14 | 2012-02-20 | 366 | 12 | 2013-02-20
| A | [22 empty] | 2012-01-10 |  | 2012-02-20 | 230 |  | 2012-08-18
16 | P | C51 | PWE016 | Works | Ext. 16 |  | Al-Tourah Secondary Girls School | 2 | Irbid | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 62/2011 | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  | 322791.88 | 455920.7345 | 31706.2147 | 487626.9492 |  | البركة للمقاولات |  |  | completed | 100%
| R | [9 empty] | 2011-10-30 | 14 | 2011-11-13 | 1 | 2011-11-14 | 28 | 2011-12-12 | 28 | 2012-01-09 | 14 | 2012-01-23 |  | 7 | 2012-01-30 | 14 | 2012-01-21 | 366 | 12 | 2013-01-21
| A | [22 empty] | 2011-12-21 |  | 2012-01-21 | 230 |  | 2012-09-07
17 | P | C51 | PWE017 | Works | Ext. 17 |  | Aqraba Secondary Boys School |  | Irbid | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | [10 empty] | 100%
| R | [9 empty] | 2011-10-30 | 14 | 2011-11-13 | 1 | 2011-11-14 | 28 | 2011-12-12 | 28 | 2012-01-09 | 14 | 2012-01-23 |  | 7 | 2012-01-30 | 14 | 2012-01-21 | 366 | 12 | 2013-01-21
| A | [22 empty] | 2011-12-21 |  | 2012-01-21 | 230 |  | 2012-07-19
18 | P | C51 | PWE018 | Works | Ext. 18 |  | Jubah Secondary Girls School | 2 | Jarash | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 63/2011 | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  | 279568 | 394870.0565 | 21288.1356 | 416158.192 |  | Fadel Henande Foundation |  |  | expected date of completion 30-Jun-15 | 77%
| R | [9 empty] | 2011-10-30 | 14 | 2011-11-13 | 1 | 2011-11-14 | 28 | 2011-12-12 | 28 | 2012-01-09 | 14 | 2012-01-23 |  | 7 | 2012-01-30 | 14 | 2012-02-05 | 366 | 12 | 2013-02-05
| A | [22 empty] | 2011-12-29 |  | 2012-02-05 | 230 |  | 2012-09-22
19 | P | C51 | PWE019 | Works | Ext. 19 |  | Ajloun Secondary Boys School |  | Ajloun | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 230 | 7.541 | 2010-12-31 | [9 empty] | taking over procedure | 99%
| R | [9 empty] | 2011-10-30 | 14 | 2011-11-13 | 1 | 2011-11-14 | 28 | 2011-12-12 | 28 | 2012-01-09 | 14 | 2012-01-23 |  | 7 | 2012-01-30 | 14 | 2012-02-05 | 366 | 12 | 2013-02-05
| A | [22 empty] | 2011-12-29 |  | 2012-02-05 | 180 |  | 2012-08-03
20 | P | C51 | PWE020 | Works | Ext. 20 |  | Al-Mudawarah Secondary Girls School | 2 | Al- Badyah | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 64/2011 | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  | 411483.32 | 581191.1299 | 102687.8531 | 683878.9831 |  | شركة باب الحارة لمقاولات |  |  | completed | 99%
| R | [9 empty] | 2011-12-15 | 14 | 2011-12-29 | 1 | 2011-12-30 | 28 | 2012-01-27 | 28 | 2012-02-24 | 14 | 2012-03-09 |  | 7 | 2012-03-16 | 14 | 2012-04-03 | 366 | 12 | 2013-04-04
| A | [22 empty] | 2012-01-09 |  | 2012-04-03 | 230 |  | 2012-11-19
21 | P | C51 | PWE021 | Works | Ext. 21 |  | Kuthruba Secondary Boys School |  | Al- karak | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 | [10 empty] | 99%
| R | [9 empty] | 2011-12-15 | 14 | 2011-12-29 | 1 | 2011-12-30 | 28 | 2012-01-27 | 28 | 2012-02-24 | 14 | 2012-03-09 |  | 7 | 2012-03-16 | 14 | 2012-04-03 | 366 | 12 | 2013-04-04
| A | [22 empty] | 2012-01-09 |  | 2012-04-03 | 230 |  | 2012-09-30
| P | C51 | PWE022 | Works | Ext. 26 | Phase III | Seil Husban Basic Co. School | 2 | Amman | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 | 119/2011 | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  |  | 0 | [6 empty] | Canceled as a result of WB Objection on re_tendering process
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-12-08 | 28 | 2012-01-05 | 14 | 2012-01-19 |  | 7 | 2012-01-26 | 14 | 2012-02-09 | 366 | 12 | 2013-02-09
| A | [15 empty] | 2011-12-08
| P | C51 | PWE023 | Works | Ext. 29 |  | Al-Ramah Secondary Girls School(instead of Al-Zaytouneh B.CO.School) |  | Amman | PO | 2010-02-02 | 14 | 2010-02-16 | 1 | 2010-02-17 | 28 | 2010-03-17 | 28 | 2010-04-14 | 14 | 2010-04-28 |  | 3 | 2010-05-01 | 14 | 2010-05-15 | 549 | 18 | 2011-11-15 |  |  | 0
| R | [9 empty] | 2011-05-31 | 14 | 2011-06-14 | 1 | 2011-06-15 | 28 | 2011-12-08 | 28 | 2012-01-05 | 14 | 2012-01-19 |  | 7 | 2012-01-26 | 14 | 2012-02-09 | 366 | 12 | 2013-02-09
| A | [15 empty] | 2011-12-08
22 | P | C51 | PWE022 | Works | Ext. 22 |  | Shajrat Al-Durr Basic Girls School | 3 | Amman | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 |  |  |  |  | 1195323.7 | المختصون للتصميم الهندسي | Yousef Bustanji & brother company | 1244 |  | expected date of completion 30-Sep-15 | 26%
| R | [9 empty] | 2014-05-30 | 14 | 2014-06-13 | 1 | 2014-06-14 | 28 | 2014-07-12 | 28 | 2014-08-09 | 14 | 2014-08-23 |  | 7 | 2014-08-30 | 14 | 2014-09-13 | 366 | 12 | 2015-09-14
A
23 | P | C51 | PWE023 | Works | Ext. 23 |  | Al-Zyoud Secondary Girls School |  | Amman | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 | [6 empty] | Yousef Bustanji & brother company | 483 |  |  | 1%
| R | [9 empty] | 2014-05-30 | 14 | 2014-06-13 | 1 | 2014-06-14 | 28 | 2014-07-12 | 28 | 2014-08-09 | 14 | 2014-08-23 |  | 7 | 2014-08-30 | 14 | 2014-09-13 | 366 | 12 | 2015-09-14
A
24 | P | C51 | PWE024 | Works | Ext. 24 |  | Abd Allateef Abden Basic School |  | Amman | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 | [6 empty] | Yousef Bustanji & brother company | 626 |  |  | 27%
| R | [9 empty] | 2014-05-30 | 14 | 2014-06-13 | 1 | 2014-06-14 | 28 | 2014-07-12 | 28 | 2014-08-09 | 14 | 2014-08-23 |  | 7 | 2014-08-30 | 14 | 2014-09-13 | 366 | 12 | 2015-09-14
A
25 | P | C51 | PWE025 | Works | Ext. 25 |  | Daheyat Al-Ameerah Haya Basic Girls School | 3 | Al-Zarqa | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 |  | 647913.6 | 912894.83 |  |  | المختصون للتصميم الهندسي | Mohammad Raje Al Abouini & partner Company | 525 |  | Implementing stage expected date of completion 30-May-15 | 45%
| R | [9 empty] | 2014-05-12 | 14 | 2014-05-26 | 1 | 2014-05-27 | 28 | 2014-06-24 | 28 | 2014-07-22 | 14 | 2014-08-05 |  | 7 | 2014-08-12 | 14 | 2014-08-26 | 366 | 12 | 2015-08-27
A
26 | P | C51 | PWE026 | Works | Ext. 26 |  | Qatr Al-Nada Secondary Boys School |  | Al-Zarqa | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 |  |  |  |  | 915132.2 |  |  | 502 |  |  | 60%
| R | [9 empty] | 2014-05-12 | 14 | 2014-05-26 | 1 | 2014-05-27 | 28 | 2014-06-24 | 28 | 2014-07-22 | 14 | 2014-08-05 |  | 7 | 2014-08-12 | 14 | 2014-08-26 | 366 | 12 | 2015-08-27
A
27 | P | C51 | PWE027 | Works | Ext. 27 |  | Rahbat Rakad Secondary Boys School |  | Al- Mafrraq | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 | [7 empty] | 640 |  |  | 80%
| R | [9 empty] | 2014-05-12 | 14 | 2014-05-26 | 1 | 2014-05-27 | 28 | 2014-06-24 | 28 | 2014-07-22 | 14 | 2014-08-05 |  | 7 | 2014-08-12 | 14 | 2014-08-26 | 366 | 12 | 2015-08-27
A
28 | P | C51 | PWE028 | Works | Ext. 28 |  | Al-Qadesieh Basic co School | 3 | Al- Tafieleh | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 |  | 864432 | 1217964.1 |  |  | مؤسسة الجذور للهندسة | Salem Thyab Tarawneh & sons company | 292 |  | Implementing stage expected date of completion 30-Apr-15 | 90%
| R | [9 empty] | 2014-05-30 | 14 | 2014-06-13 | 1 | 2014-06-14 | 28 | 2014-07-12 | 28 | 2014-08-09 | 14 | 2014-08-23 |  | 7 | 2014-08-30 | 14 | 2014-09-13 | 366 | 12 | 2015-09-14
A
29 | P | C51 | PWE029 | Works | Ext. 29 |  | Al-Qutraneh Basic Co. School |  | Al- karak | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 |  |  |  |  | 1220949.153 |  |  | 416 |  |  | 95%
| R | [9 empty] | 2014-05-30 | 14 | 2014-06-13 | 1 | 2014-06-14 | 28 | 2014-07-12 | 28 | 2014-08-09 | 14 | 2014-08-23 |  | 7 | 2014-08-30 | 14 | 2014-09-13 | 366 | 12 | 2015-09-14
A
30 | P | C51 | PWE030 | Works | Ext. 30 |  | Al-Faihaa Secondary Boys School |  | madaba | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 | [7 empty] | 502 |  |  | 90%
| R | [9 empty] | 2014-05-30 | 14 | 2014-06-13 | 1 | 2014-06-14 | 28 | 2014-07-12 | 28 | 2014-08-09 | 14 | 2014-08-23 |  | 7 | 2014-08-30 | 14 | 2014-09-13 | 366 | 12 | 2015-09-14
A
31 | P | C51 | PWE031 | Works | Ext. 31 |  | Hatem Basic Boys School | 3 | Irbid | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 | [5 empty] | دار االتخطيط للاستشارات الهندسية | Typical comp for engineering & bridges | 204 |  | expected date of completion 31-Oct-15 | 15%
| R | [9 empty] | 2014-06-30 | 14 | 2014-07-14 | 1 | 2014-07-15 | 28 | 2014-08-12 | 28 | 2014-09-09 | 14 | 2014-09-23 |  | 7 | 2014-09-30 | 14 | 2014-10-14 | 366 | 12 | 2015-10-15
A
32 | P | C51 | PWE032 | Works | Ext. 32 |  | Al-Muthanna Bin Harethah Basic Boys School |  | Irbid | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 |  |  |  |  | 657295.9 |  |  | 312 |  |  | 33%
| R | [9 empty] | 2014-06-30 | 14 | 2014-07-14 | 1 | 2014-07-15 | 28 | 2014-08-12 | 28 | 2014-09-09 | 14 | 2014-09-23 |  | 7 | 2014-09-30 | 14 | 2014-10-14 | 366 | 12 | 2015-10-15
A
33 | P | C51 | PWE033 | Works | Ext. 33 |  | Al-Karamah Basic co School |  | Irbid | PO | 2013-06-03 | 14 | 2013-06-17 | 1 | 2013-06-18 | 28 | 2013-07-16 | 28 | 2013-08-13 | 14 | 2013-08-27 |  | 3 | 2013-08-30 | 14 | 2013-09-13 | 549 | 18 | 2015-03-16 | [7 empty] | 204 |  |  | DELETED
| R | [9 empty] | 2014-06-30 | 14 | 2014-07-14 | 1 | 2014-07-15 | 28 | 2014-08-12 | 28 | 2014-09-09 | 14 | 2014-09-23 |  | 7 | 2014-09-30 | 14 | 2014-10-14 | 366 | 12 | 2015-10-15
A
34 | P | C51 | PWE034 | Works | Ext. 34 |  | Maymonah Bint Al-Hareth Basic Co. |  | Ein Al Basha | PO | 2012-05-30 | 14 | 2012-06-13 | 1 | 2012-06-14 | 28 | 2012-07-12 | 28 | 2012-08-09 | 14 | 2012-08-23 |  | 7 | 2013-08-30 | 14 | 2013-09-13 | 365 | 12 | 2014-09-13 |  |  |  |  | 457836.5 | السبيل للاستشارات الهندسية | Banda for construction | 700 |  | has not commenced yet | 1%
| R | [9 empty] | 2014-06-15 | 14 | 2014-06-29 | 1 | 2014-06-30 | 28 | 2014-07-28 | 28 | 2014-08-25 | 14 | 2014-09-08 |  | 7 | 2014-09-15 | 14 | 2014-09-29 | 366 | 12
A
35 | P | C51 | PWE035 | Works | Ext. 35 |  | Al- naserah basic Co |  | Al Kurah | PO | 2012-05-30 | 14 | 2012-06-13 | 1 | 2012-06-14 | 28 | 2012-07-12 | 28 | 2012-08-09 | 14 | 2012-08-23 |  | 7 | 2013-08-30 | 14 | 2013-09-13 | 365 | 12 | 2014-09-13 |  |  |  |  | 644958.3 |  | Al-safade for construction | 700 |  | has not commenced yet | 5%
| R | [9 empty] | 2014-06-30 | 14 | 2014-07-14 | 1 | 2014-07-15 | 28 | 2014-08-12 | 28 | 2014-09-09 | 14 | 2014-09-23 |  | 7 | 2014-09-30 | 14 | 2014-10-14 | 366 | 12
A
36 | P | C51 | PWE036 | Works | Ext. 36 |  | Salem Basic Co |  | Al-mouagar | PO | 2012-05-30 | 14 | 2012-06-13 | 1 | 2012-06-14 | 28 | 2012-07-12 | 28 | 2012-08-09 | 14 | 2012-08-23 |  | 7 | 2013-08-30 | 14 | 2013-09-13 | 365 | 12 | 2014-09-13 |  |  |  |  | 597068.2 |  | Mohamed Raje Alabwini and co. | 900 |  | has not commenced yet | 0%
| R | [9 empty] | 2014-06-30 | 14 | 2014-07-14 | 1 | 2014-07-15 | 28 | 2014-08-12 | 28 | 2014-09-09 | 14 | 2014-09-23 |  | 7 | 2014-09-30 | 14 | 2014-10-14 | 366 | 12
A
37 | P | C51 | PWE037 | Works | Ext. 37 |  | Al_ Hadeetha Basic Boys |  | AlAgwar aljanoubia | PO | 2012-05-30 | 14 | 2012-06-13 | 1 | 2012-06-14 | 28 | 2012-07-12 | 28 | 2012-08-09 | 14 | 2012-08-23 |  | 7 | 2013-08-30 | 14 | 2013-09-13 | 365 | 12 | 2014-09-13 |  |  |  |  | 429937.75 |  | Aymen Al-kasasbeh and co. | 500 |  | has not commenced yet | 0%
| R | [9 empty] | 2014-06-15 | 14 | 2014-06-29 | 1 | 2014-06-30 | 28 | 2014-07-28 | 28 | 2014-08-25 | 14 | 2014-09-08 |  | 7 | 2014-09-15 | 14 | 2014-09-29 | 366 | 12
A
38 | P | C51 | PWE038 | Works | Ext. 38 |  | Ceebawaeeh Basic Boys |  | Zarqa 1 | PO | 2012-05-30 | 14 | 2012-06-13 | 1 | 2012-06-14 | 28 | 2012-07-12 | 28 | 2012-08-09 | 14 | 2012-08-23 |  | 7 | 2013-08-30 | 14 | 2013-09-13 | 365 | 12 | 2014-09-13 | [9 empty] | Under design | DELETED
| R | [9 empty] | 2014-09-30 | 14 | 2014-10-14 | 1 | 2014-10-15 | 28 | 2014-11-12 | 28 | 2014-12-10 | 14 | 2014-12-24 |  | 7 | 2014-12-31 | 14 | 2015-01-14 | 366 | 12
A
39 | P | C51 | PWE039 | Works | Ext. 39 |  | Al_Margab Secondary Boys/ |  | Amman 4 | PO | 2012-05-30 | 14 | 2012-06-13 | 1 | 2012-06-14 | 28 | 2012-07-12 | 28 | 2012-08-09 | 14 | 2012-08-23 |  | 7 | 2013-08-30 | 14 | 2013-09-13 | 365 | 12 | 2014-09-13 |  |  |  |  | 597068.2 | السبيل للاستشارات الهندسية | Mohamed Raje Alabwini and co. | 800 |  | has not commenced yet | 0%
| R | [9 empty] | 2014-07-30 | 14 | 2014-08-13 | 1 | 2014-08-14 | 28 | 2014-09-11 | 28 | 2014-10-09 | 14 | 2014-10-23 |  | 7 | 2014-10-30 | 14 | 2014-11-13 | 366 | 12
A
[33 empty] | contract amount US$ | 12625628.7591
[39 empty] | uncontracted estimated cost |  | 0
Formulas:
Bid. Doc/Specs prep. = [NOL Date]-[Interval]
NOL Date = [Invitation Date]-[Interval]
NOL Date = [Contract Signature Date]-[Interval]
Invitation Date = [Bid Opening Date]-[Interval]
Invitation Date = [NOL Date]+[Interval]
Bid Opening Date = [Evaluation & Recomm.]-[Interval]
Bid Opening Date = [Invitation Date]+[Interval]
Evaluation & Recomm. = [NOL Date]-[Interval]
Evaluation & Recomm. = [Bid Opening Date]+[Interval]
Contract Start Date = [Contract Signature Date]+[Interval]
Completion Date (original) = [Contract Start Date]+[Execution in days]
Contract Signature Date = [NOL Date]+[Interval]
Note on AI5: Procurement: Est. = 29149 JD
Note on AP5: User: commencement date 9-Sep-12
Note on AP8: User: commencement date 9-Sep-12
Note on AP11: User: commencement date 9-Sep-12
Note on AP14: User: commencement date 9-Sep-12
Note on AC31: Procurement: الرقم
Note on AC34: Procurement:
Note on Y53: wb232552: waiting for Fin Obl waiver
Note on AC57: Procurement:
Note on AC60: Procurement:
Note on AC63: Procurement: الرقم
Note on AP67: User: commencement date 5-Feb-12
Note on AP70: User: commencement date 5-Feb-12
Note on AP85: Azmy.Hmaidi: commencement date 10-Feb-15
Note on AP94: User: commencement date 28-Sep-14
Note on AP97: User: commencement date 28-Sep-14
Note on AP100: User: commencement date 28-Sep-14
Note on I103: Azmy.Hmaidi: تم استبدالها بمدرسة فروة
Note on AP103: User: commencement date 29-Sep-14
Note on AP106: User: commencement date 29-Sep-14
Note on AP109: User: commencement date 29-Sep-14
Note on AP112: Azmy.Hmaidi: commencment date 10-Feb-15
Note on AP121: Azmy.Hmaidi: completion date 31-Jan-16 tender no. 244/2014
Note on AP124: Azmy.Hmaidi: completion date 30-Nov-15 tender no. 245/2014
Note on AP127: Azmy.Hmaidi: completion date 31-Mar-16 tender no. 247/2014
Note on AP130: Azmy.Hmaidi: completion date 31-Sep-15 tender no. 246/2014
Note on I133: Procurement: problem
Note on AP136: Azmy.Hmaidi: completion date 31-Mar-16 tender no. 247/2014