## Goods
[14 empty] | NO Objection from Bank for Evaluation of Prequalification Application (Date)** |  |  |  | IRAQ
[11 empty] | Prequalification | [6 empty] | EMERGENCY SOCIAL PROTECTION PROJECT
Plan vs. Actual | packge/Refrence NO. | Description of Goods / Works | Goods / Works / NCS | Estimated Cost (US$) /c | Currency of Estimated Cost | Estimated No. of Lots | Procurement Method | Review By Bank (PRIOR / Post) | method of selection | Domesticaction prefrence (Yes/NO) | preqaulification (Yes/NO) | NO Objection from Bank for Draft Prequalification documents (Date)** | NO Objection from Bank for Evaluation of Prequalification Application (Date)** | preparation of Bid Documents (Date) | Interval /a | WB No Objection Date | Interval /a | Bid Invitation (Date) | Interval /a | Bid Opening (Date) | Interval /a | Evalu- ation & Recomm. | Interval /a | WB No Objec- tion Date | Interval /a | Contract Award Decision(Date) | Interval /a | Contract Signed (Date) | Execution /b | Completion of contract (Date) | Contract Value | Contract Currency | Contract No. | Name,City and Country of Contractor (incl.Zip Code if US) | Expenditure incurred to Date | Comments
B | C | D |  | E |  | F | G | H |  |  |  | I |  | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | [5 empty] | Z
1. GOODS
R | ESPP.G.SH-01/2008 | IT Equipment -Servers & Software/MoLSA | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2006-04-07 | 2 | 2006-04-09 | 18 | 2006-04-27 | 30 | 2006-05-27 | 5 | 2008-06-01 | 4 | 2008-06-05 | 36 | 2008-07-11 | 20 | 2008-07-30 | 75 | 2008-10-13 |  |  | ESPP.G.SH-01/2008 | AL-shurkaa / Baghdad
A |  |  |  | 76291 | USD | [8 empty] | 2006-04-07 | 2 | 2006-04-09 | 18 | 2006-04-27 | 30 | 2006-05-27 | 5 | 2008-06-01 | 4 | 2008-06-05 | 36 | 2008-07-11 | 20 | 2008-07-30 | 75 | 2008-10-13 | 76291 | USD | ESPP.G.SH-01/2008 |  | 76291
R | ESPP.G.SH-02/2008 | IT Equipment -Servers & Software/SSN | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-04-09 | 8 | 2008-04-17 | 8 | 2008-04-25 | 30 | 2008-05-25 | 45 | 2008-07-09 | 7 | 2008-07-16 | 7 | 2008-07-23 | 15 | 2008-08-07 | 75 | 2008-10-21 |  |  | ESPP.G.SH-02/2008 | AL-shurakaa / Baghdad
A |  |  |  | 76291 | USD | [8 empty] | 2008-04-09 | 8 | 2008-04-17 | 8 | 2008-04-25 | 30 | 2008-05-25 | 45 | 2008-07-09 | 7 | 2008-07-16 | 7 | 2008-07-23 | 15 | 2008-08-07 | 75 | 2008-10-21 | 76291 | USD | ESPP.G.SH-02/2008 |  | 76291
R | ESPP.G.SH-03/2011 | IT Equipment -Desktop & Peripherals | Goods | 190000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2011-07-03 | 2 | 2011-07-05 | 77 | 2011-09-20 | 14 | 2011-10-04 | 30 | 2011-11-03 | 13 | 2011-11-16 | 1 | 2011-11-17 | 42 | 2011-12-29 | 45 | 2012-02-12 |  |  | ESPP.G.SH-03/2011 | AL- NABAA / Baghdad
A |  |  |  | 175650 | USD | [8 empty] | 2011-07-03 | 2 | 2011-07-05 | 77 | 2011-09-20 | 14 | 2011-10-04 | 30 | 2011-11-03 | 13 | 2011-11-16 | 1 | 2011-11-17 | 42 | 2011-12-29 | 45 | 2012-02-12 | 175650 | USD | ESPP.G.SH-03/2011 |  | $174,79
R | ESPP.G.SH-04/2007 | IT Equipment -Servers & Software/SPS-MoF | Goods | 147000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2007-11-12 | 7 | 2007-11-19 | 9 | 2007-11-28 | 28 | 2007-12-26 | 43 | 2008-02-07 | 6 | 2008-02-13 | 6 | 2008-02-19 | 40 | 2008-03-30 | 60 | 2008-05-29 |  |  | ESPP.G.SH-04/2007 | IRAQ GLOBAL / Baghdad
A |  |  |  | 261880 | USD | [8 empty] | 2007-11-12 | 7 | 2007-11-19 | 9 | 2007-11-28 | 28 | 2007-12-26 | 43 | 2008-02-07 | 6 | 2008-02-13 | 6 | 2008-02-19 | 40 | 2008-03-30 | 60 | 2008-05-29 | 261880 | USD | ESPP.G.SH-04/2007 |  | 261880
R | ESPP.G.SH-05/2008 | IT Equipment -Desktop & Peripherals/SPS-MoF | Goods | 110000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-06-01 | 3 | 2008-06-04 | 2 | 2008-06-06 | 24 | 2008-06-30 | 45 | 2008-08-14 | 6 | 2008-08-20 | 6 | 2008-08-26 | 15 | 2008-09-10 | 60 | 2008-11-09 |  |  | ESPP.G.SH-05/2008 | AL-shurakaa / Baghdad
|  |  |  | 89848 | USD | [8 empty] | 2008-06-01 | 3 | 2008-06-04 | 2 | 2008-06-06 | 24 | 2008-06-30 | 45 | 2008-08-14 | 6 | 2008-08-20 | 6 | 2008-08-26 | 15 | 2008-09-10 | 60 | 2008-11-09 | 89848 | USD | ESPP.G.SH-05/2008 |  | 89.848
R | ESPP.G.SH-06/2007 | IT Equipment -Servers /Basrah & Najaf | Goods | 140000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2007-11-12 | 7 | 2007-11-19 | 14 | 2007-12-03 | 23 | 2007-12-26 | 20 | 2008-01-15 | 2 | 2008-01-17 | 17 | 2008-02-03 | 56 | 2008-03-30 | 60 | 2008-05-29 |  |  | ESPP.G.SH-06/2007 | IRAQ GLOBAL / Baghdad
A |  |  |  | 162640 | USD | [8 empty] | 2007-11-12 | 7 | 2007-11-19 | 14 | 2007-12-03 | 23 | 2007-12-26 | 20 | 2008-01-15 | 2 | 2008-01-17 | 17 | 2008-02-03 | 56 | 2008-03-30 | 60 | 2008-05-29 | 162640 | USD | ESPP.G.SH-06/2007 |  | 162640
R | ESPP.G.SH-07/2007 | IT Equipment -Software/Basrah & Najaf/Baghdad,K&R | Goods | 108000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2007-11-12 | 7 | 2007-11-19 | 14 | 2007-12-03 | 23 | 2007-12-26 | 20 | 2008-01-15 | 2 | 2008-01-17 | 17 | 2008-02-03 | 56 | 2008-03-30 | 60 | 2008-05-29 |  |  | ESPP.G.SH-07/2007 | IRAQ GLOBAL / Baghdad
A |  |  |  | 136718 | USD | [8 empty] | 2007-11-12 | 7 | 2007-11-19 | 14 | 2007-12-03 | 23 | 2007-12-26 | 20 | 2008-01-15 | 2 | 2008-01-17 | 17 | 2008-02-03 | 56 | 2008-03-30 | 60 | 2008-05-29 | 136718 | USD | ESPP.G.SH-07/2007 |  | 136718
R | ESPP.G.SH-08/2008 | IT Equipment -Desktop & Peripherals/Basrah & Najaf/Baghdad,K&R | Goods | 155000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-06-01 | 3 | 2008-06-04 | 2 | 2008-06-06 | 24 | 2008-06-30 | 45 | 2008-08-14 | 6 | 2008-08-20 | 6 | 2008-08-26 | 15 | 2008-09-10 | 60 | 2008-11-09 |  |  | ESPP.G.SH-08/2008 | AL-shurakaa / Baghdad
A |  |  |  | 99303.05 | USD | [8 empty] | 2008-06-01 | 3 | 2008-06-04 | 2 | 2008-06-06 | 24 | 2008-06-30 | 41 | 2008-08-10 | 1 | 2008-08-11 | 14 | 2008-08-25 | 9 | 2008-09-03 | 75 | 2008-11-14 | 99303.05 | USD | ESPP.G.SH-08/2008 |  | 99303.05
R | ESPP.G.SH-09/2008 | IT Equipment - Peripherals/Basrah & Najaf/Baghdad,K&R | Goods | 196000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-06-01 | 3 | 2008-06-04 | 2 | 2008-06-06 | 24 | 2008-06-30 | 45 | 2008-08-14 | 6 | 2008-08-20 | 6 | 2008-08-26 | 15 | 2008-09-10 | 60 | 2008-11-09 |  |  | ESPP.G.SH-09/2008 | IRAQ GLOBAL / Baghdad
A |  |  |  | 92557 | USD | [8 empty] | 2008-06-01 | 3 | 2008-06-04 | 2 | 2008-06-06 | 24 | 2008-06-30 | 41 | 2008-08-10 | 1 | 2008-08-11 | 7 | 2008-08-18 | 20 | 2008-09-07 | 75 | 2008-11-21 | 92557 | USD | ESPP.G.SH-09/2008 |  | 92.557
R | ESPP.G.SH-10/2007 | IT Equipment -Servers/Baghdad,K&R | Goods | 128000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2007-11-12 | 7 | 2007-11-19 | 14 | 2007-12-03 | 23 | 2007-12-26 | 20 | 2008-01-15 | 2 | 2008-01-17 | 17 | 2008-02-03 | 56 | 2008-03-30 | 60 | 2008-05-29 |  |  | ESPP.G.SH-10/2007 | IRAQ GLOBAL / Baghdad
A |  |  |  | 132640 | USD | [8 empty] | 2007-11-12 | 7 | 2007-11-19 | 14 | 2007-12-03 | 23 | 2007-12-26 | 20 | 2008-01-15 | 2 | 2008-01-17 | 17 | 2008-02-03 | 56 | 2008-03-30 | 60 | 2008-05-29 | 132640 | USD | ESPP.G.SH-10/2007 |  | 132640
R | ESPP.G.SH-11/2008 | IT Equipment -Servers, Sofware, Peripherals & Desktop /Erbil | Goods | 253000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-04-09 | 7 | 2008-04-16 | 11 | 2008-04-27 | 30 | 2008-05-27 | 79 | 2008-08-14 | 4 | 2008-08-18 | 7 | 2008-08-25 | 15 | 2008-09-09 | 75 | 2008-11-23 |  |  | ESPP.G.SH-11/2008 | AL-shurakaa / Baghdad
A |  |  |  | 154720 | USD | [8 empty] | 2008-04-09 | 7 | 2008-04-16 | 11 | 2008-04-27 | 30 | 2008-05-27 | 79 | 2008-08-14 | 4 | 2008-08-18 | 7 | 2008-08-25 | 9 | 2008-09-03 | 75 | 2008-11-17 | 154720 | USD | ESPP.G.SH-11/2008 |  | 151.409
R | ESPP.G.SH-12/2008 | IT Equipment -Servers & Sofware/Salah Aldeen | Goods | 151099.75 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-04-09 | 7 | 2008-04-16 | 11 | 2008-04-27 | 30 | 2008-05-27 | 79 | 2008-08-14 | 4 | 2008-08-18 | 7 | 2008-08-25 | 15 | 2008-09-09 | 75 | 2008-11-23 |  |  | ESPP.G.SH-12/2008 | AL-shurakaa / Baghdad
A |  |  |  | 118975.66 | USD | [8 empty] | 2008-04-09 | 7 | 2008-04-16 | 11 | 2008-04-27 | 30 | 2008-05-27 | 79 | 2008-08-14 | 4 | 2008-08-18 | 7 | 2008-08-25 | 9 | 2008-09-03 | 75 | 2008-11-17 | 118975.66 | USD | ESPP.G.SH-12/2008 |  | 119.285
R | ESPP.G.SH-13/2008 | IT Equipment -Peripherals & Desktop/Salah Aldeen | Goods | 64000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-04-09 | 7 | 2008-04-16 | 11 | 2008-04-27 | 30 | 2008-05-27 | 79 | 2008-08-14 | 4 | 2008-08-18 | 7 | 2008-08-25 | 15 | 2008-09-09 | 75 | 2008-11-23 |  |  | ESPP.G.SH-13/2008 | AL- NABAA / Baghdad
A |  |  |  | 29058 | USD | [8 empty] | 2008-04-09 | 7 | 2008-04-16 | 11 | 2008-04-27 | 30 | 2008-05-27 | 79 | 2008-08-14 | 4 | 2008-08-18 | 7 | 2008-08-25 | 22 | 2008-09-16 | 75 | 2008-11-30 | 29058 | USD | ESPP.G.SH-13/2008 |  | 29.205
R | Sub-total |  |  | 1902099.75 | USD
A | Sub-total |  |  | 1606571.71 | USD | [29 empty] | 946245.354
R | ESPP.G.SH-CONN-01/2008 | Baghdad K & R, Najaf and Basrah/ Connectivity Equipments |  | 195000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-10-20 | 9 | 2008-10-29 | 8 | 2008-11-06 | 12 | 2008-11-18 | 7 | 2008-11-25 | 7 | 2008-12-02 | 1 | 2008-12-03 | 15 | 2008-12-18 | 75 | 2009-03-03 |  |  | ESPP.G.SH-CONN-01/2008 | AL- NABAA / Baghdad
A |  |  |  | 157983 | USD | [8 empty] | 2008-10-20 | 9 | 2008-10-29 | 8 | 2008-11-06 | 12 | 2008-11-18 | 7 | 2008-11-25 | 7 | 2008-12-02 | 1 | 2008-12-03 | 15 | 2008-12-18 | 75 | 2009-03-03 | 157983 | USD | ESPP.G.SH-CONN-01/2008 |  | 157.984
R | ESPP.G.SH-CONN-06/2010 | Supply And Installation of PTP Wireless towers (MOLSA-HQ, Karah & Russafa) and wireless Internet (MOLSA-HQ, Karkh & Rusafa) | Goods | 11000 | USD |  | SH | POST | SH | NO | NO | NA | NA | I: 2010-08-30; O: 2010-09-03; P: 7; Q: 2010-09-10; U: 2010-11-07; V: 1; W: 2010-11-08; X: 30; Y: 2010-12-08 |  |  | ESPP.G.SH-CONN-06/2010 | AL- NABAA / Baghdad
A |  |  |  | 10990 | USD | [8 empty] | I: 2010-09-22; O: 2010-09-03; Q: 2010-09-03; U: 2010-11-07; V: 1; W: 2010-11-08; X: 30; Y: 2010-12-08 | 10990 | USD | ESPP.G.SH-CONN-06/2010 |  | 10990
R | ESPP.G.SH-CONN-07/2011 | Supply And Installation of PTP Wireless towers for (Najaf& Basra) | Goods | 10000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2011-01-06 |  |  | 7 | 2011-01-13 | 18 | 2011-01-19 | 7 | 2011-01-26 |  |  | 7 | 2011-02-01 |  | 2011-02-01 | 30 | 2011-03-03 |  |  | ESPP.G.SH-CONN-07/2011 | ERTH LINK/ Baghdad
A |  |  |  | 5360 | USD | [8 empty] | 2011-01-06 |  |  |  | 2011-01-13 | 18 | 2011-01-19 | 7 | 2011-01-26 |  |  | 7 | 2011-02-01 |  | 2011-02-01 | 30 | 2011-03-03 | 5360 | USD | ESPP.G.SH-CONN-07/2011 |  | 5360
R | ESPP.G.SH-CONN-08/2011 | Supply And Installation of PTP Wireless towers for Erbil,Dohuk,Sylaimania) | Goods | 10000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2011-04-05 |  |  | 7 | 2011-04-12 | 5 | 2011-04-17 | 1 | 2011-08-18 |  |  | 3 | 2011-04-21 |  | 2011-04-21 | 30 | 2011-05-21 |  |  | ESPP.G.SH-CONN-08/2011 | ERTH LINK/ Baghdad
A |  |  | Goods | 8040 | USD |  | SH | Post | SH |  |  |  |  | 2011-04-05 |  |  | 7 | 2011-04-12 | 5 | 2011-04-17 | 1 | 2011-04-18 |  |  | 3 | 2011-04-21 | 0 | 2011-04-21 | 70 | 2011-06-30 | 8040 | USD | ESPP.G.SH-CONN-08/2011 |  | 8040
R | ESPP.G.SH-CONN.09/2011 | Supply And Installation of PTP Wireless towers for (six governorates) (Karbala,Babil,Muthana,Diwaneya,kirkuk,diyala ) | Goods | 50000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2011-11-13 |  |  | 7 | 2011-11-20 | 4 | 2011-11-24 | 18 | 2011-12-12 |  |  | 2 | 2011-12-14 | 6 | 2011-12-20 | 45 | 2012-02-03 |  |  | ESPP.G.SH-CONN.09/2011 | ERTH LINK/ Baghdad
A |  |  |  | 18480 | USD | [8 empty] | 2011-11-13 |  |  | 7 | 2011-11-20 | 4 | 2011-11-24 | 18 | 2011-12-12 |  |  | 2 | 2011-12-14 | 6 | 2011-12-20 | 45 | 2012-02-03 | 18480 | USD | ESPP.G.SH-CONN.09/2011 |  | 18480
R | ESPP.G.SH-CONN-10/2012 | Supply And Installation of PTP Wireless towers for (six governorates) (Wassit,Mosel,Anbar,Salahedeen,Thiqar,Missan ) | Goods | 50000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 03/19/2012 |  |  | 38 | 2012-04-26 | 7 | 2012-05-03 | 5 | 2012-05-08 |  |  | 2 | 2012-05-10 | 3 | 2012-05-13 | 45 | 2012-06-27 |  |  | ESPP.G.SH-CONN-10/2012 | ERTH LINK/ Baghdad
A |  |  |  | 18480 | USD |  | SH | POST | SH |  |  |  |  | I: 2012-04-19; M: 2012-04-26; O: 2012-05-03; Q: 2012-05-17; U: 2012-07-15; W: 2012-07-24; Y: 2012-07-30 | 18480 | USD | ESPP.G.SH-CONN-10/2012 |  | 18480
R | ESPP.G.SH-SERV.01/2009 | Connectivety Servises for Baghdad K&R, Najaf & Basra | Goods | 120000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2009-06-21 | 12 | 2009-02-02 | 10 | 2009-02-12 | 10 | 2009-02-22 | 2 | 2009-02-24 | 3 | 2009-02-27 | 2 | 2009-03-01 | 3 | 2009-03-04 | 75 | 2009-05-18 |  |  | ESPP.G.SH-SERV.01/2009 | AL- NABAA / Baghdad
A |  |  |  | 90000 | USD |  |  | POST | [5 empty] | 2009-04-08 |  |  | 12 | 2009-04-20 | 6 | 2009-04-26 | 3 | 2009-04-29 |  |  | 6 | 2009-05-05 | 2 | 2009-03-07 | 90 | 2009-08-05 | 90000 | USD | ESPP.G.SH-SERV.01/2009 |  | 90000
R | ESPP.G.SH-SERV.02/2011 | Connectivety Servises for (H.Q) | Goods | 6000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2011-01-06 |  |  | 7 | 2011-01-15 | 4 | 19/1/2011 | 7 | 2011-01-26 |  |  | 7 | 2011-02-01 |  | 2011-02-01 | 30 | 2011-03-03 |  |  | ESPP.G.SH-SERV.02/2011 | ERTH LINK/ Baghdad
A |  |  |  | 4500 | USD |  | SH | POST | SH |  |  |  |  | I: 2011-01-06; L: 7; M: 2011-01-15; N: 4; O: 19/1/2011; P: 7; Q: 2011-01-26; T: 7; U: 2011-02-01; W: 2011-02-01 | 4500 | USD | ESPP.G.SH-SERV.02/2011 |  | 4331.25
R | ESPP.G.SH-SERV.03/2011 | Supply Wireless Internet Service (erbil) | Goods | 1500 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2011-03-27 |  |  | 7 | 2011-04-04 | 3 | 2011-04-07 |  | 2011-04-07 |  |  | 7 | 2011-04-14 |  | 2011-04-14 | 30 | 2011-05-14 |  |  | ESPP.G.SH-SERV.03/2011 | ERTH LINK/ Baghdad
A |  |  |  | 1000 | USD |  | SH | POST | SH |  |  |  |  | I: 2011-03-27; L: 7; M: 2011-04-04; N: 3; O: 2011-04-07; Q: 2011-04-07; T: 7; U: 2011-04-14; W: 2011-04-14 | 1000 | USD | ESPP.G.SH-SERV.03/2011 |  | 1000
R | ESPP.G.SH-SERV.04/2011 | Connectivety Servises for (H.Q) | Goods | 14000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2011-05-07 |  |  | 7 | 2011-05-17 | 6 | 2011-05-23 | 2 | 2011-05-25 |  |  | 7 | 2011-06-03 | 10 | 2011-06-13 | 2 | 2011-06-15 |  |  | ESPP.G.SH-SERV.04/2011 | ERTH LINK/ Baghdad
A |  |  |  | 10500 | USD |  | SH | POST | SH |  |  |  |  | 2011-05-07 |  |  | 7 | 17/5/2011 | 6 | 2011-05-23 | 2 | 2011-05-25 |  |  | 7 | 2011-06-03 | 10 | 2011-06-13 | 2 | 2011-06-15 | 10500 | USD | ESPP.G.SH-SERV.04/2011 |  | 10181.25
R | ESPP.G.SH-SERV.05/2011 | Connectivety Servises for (H.Q) | Goods | 10000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2011-12-19 |  |  | 3 | 2011-12-22 | 7 | 2011-12-29 | 5 | 2012-01-03 |  |  | 0 | 2012-01-03 | 42 | 2012-02-14 | 180 | 2012-08-12 |  |  | ESPP.G.SH-SERV.05/2011 | Baghdad
A |  |  |  | 7200 | USD |  | SH | POST | SH |  |  |  |  | 2011-12-19 |  |  | 3 | 2011-12-22 | 7 | 2011-12-29 | 5 | 2012-01-03 |  |  | 0 | 2012-01-03 | 42 | 2012-02-14 | 180 |  | 7200 | USD | ESPP.G.SH-SERV.05/2011
R | ESPP.G.SH-SERV.6/2012 | Supply Wireless Internet Service for 9 sites | Goods | 32500 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2012-03-19 |  |  | 38 | 2012-04-26 | 7 | 2012-05-03 | 5 | 2012-05-08 |  |  | 2 | 2012-05-10 | 7 | 2012-05-17 | 45 | 2012-07-01 |  |  | ESPP.G.SH-SERV.6/2012 | ERTH LINK / Baghdad
A |  |  |  | 2700 | USD | [8 empty] | I: 2012-04-16; M: 2012-04-29; O: 2012-05-03; Q: 2012-05-14; U: 2012-05-14; W: 2012-05-15; Y: 2012-07-15 | 2700 | USD | ESPP.G.SH-SERV.6/2012 |  |  | Internet service for three governortes
R | ESPP.G.SH-SERV.7/2012 | Supply Wireless Internet Service for 9 sites including HQ | Goods | 50000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2012-07-01 |  |  | 3 | 2012-07-04 | 7 | 2012-07-11 | 5 | 2012-07-16 |  |  | 0 | 2012-07-16 | 20 | 2012-08-05 | 240 | 2013-04-02 |  |  | ESPP.G.SH-SERV.7/2012 | NEW CORE / Baghdad
A |  |  |  | 39780 | USD |  | SH | POST | SH |  |  |  |  | I: 2012-08-22; M: 2012-08-29; O: 2012-09-02; Q: 2012-09-04; U: 2012-09-09; W: 2012-09-13 | 39780 | USD | ESPP.G.SH-SERV.7/2012
R | Sub-total |  |  | 560000 | USD | [27 empty] | Sub-total
A | Sub-total |  |  | 375013 | USD | [25 empty] | 375013 | USD | Sub-total |  | 167020.484
R | ESPP.G.SH-14/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Kerbala | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-04-10 | 7 | 2008-04-17 | 44 | 2008-05-31 | 30 | 2008-06-30 | 41 | 2008-08-10 | 1 | 2008-08-11 | 7 | 2008-08-18 | 15 | 2008-09-02 | 75 | 2008-11-16 |  |  | ESPP.G.SH-14/2008 | IRAQ GLOBAL / Baghdad
A |  |  |  | 125492.54 | USD | [8 empty] | 2008-04-10 | 7 | 2008-04-17 | 44 | 2008-05-31 | 30 | 2008-06-30 | 41 | 2008-08-10 | 1 | 2008-08-11 | 7 | 2008-08-18 | 20 | 2008-09-07 | 75 | 2008-11-21 | 125492.54 | USD | ESPP.G.SH-14/2008 |  | 125492.54
R | ESPP.G.SH-15/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Hilla | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-04-10 | 7 | 2008-04-17 | 44 | 2008-05-31 | 30 | 2008-06-30 | 41 | 2008-10-08 | 6 | 2008-10-14 | 5 | 2008-10-19 | 4 | 2008-10-23 | 75 |  |  |  | ESPP.G.SH-15/2008 | IRAQ GLOBAL / Baghdad
A1 |  |  |  | 119826 | USD | [8 empty] | Q: 2008-10-08; R: 6; S: 2008-10-14; T: 5; U: 2008-10-19; V: 4; W: 2008-10-23; X: 75; Y: 2009-01-06 | 119826 | USD | ESPP.G.SH-15/2008 |  | 119826
R | ESPP.G.SH-16/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Muthanna | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-04-10 | 7 | 2008-04-17 | 44 | 2008-05-31 | 30 | 2008-06-30 | 41 | 2008-08-10 | 1 | 2008-08-11 | 7 | 2008-08-18 | 15 | 2008-09-02 | 75 | 2008-11-16 |  |  | ESPP.G.SH-16/2008 | IRAQ GLOBAL / Baghdad
A |  |  |  | 125492.54 | USD | [8 empty] | 2008-04-10 | 7 | 2008-04-17 | 44 | 2008-05-31 | 30 | 2008-06-30 | 41 | 2008-08-10 | 1 | 2008-08-11 | 7 | 2008-08-18 | 20 | 2008-09-07 | 75 | 2008-11-21 | 125492.54 | USD | ESPP.G.SH-16/2008 |  | 125590
R | ESPP.G.SH-17/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Missan | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-04-10 | 7 | 2008-04-17 | 44 | 2008-05-31 | 30 | 2008-06-30 | 41 | 2008-08-10 | 1 | 2008-08-11 | 7 | 2008-08-18 | 15 | 2008-09-02 | 75 | 2008-11-16 |  |  | ESPP.G.SH-17/2008 | IRAQ GLOBAL / Baghdad
A |  |  |  | 125577.66 | USD | [8 empty] | 2008-04-10 | 7 | 2008-04-17 | 44 | 2008-05-31 | 30 | 2008-06-30 | 41 | 2008-08-10 | 1 | 2008-08-11 | 7 | 2008-08-18 | 20 | 2008-09-07 | 75 | 2008-11-21 | 125577.66 | USD | ESPP.G.SH-17/2008 |  | 125590
R | ESPP.G.SH-18/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Thi-Qar | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 30 | 2008-12-05 | 7 | 2008-12-12 | 7 | 2008-12-19 | 15 | 2009-01-03 | 75 | 2009-03-19 |  |  | ESPP.G.SH-18/2008 | AL- NABAA / Baghdad
A |  |  |  | 139945 | USD | [8 empty] | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 14 | 2008-11-19 | 23 | 2008-12-12 | 5 | 2008-12-17 | 54 | 4-Feb-09 | 75 | 2009-04-20 | 139945 | USD | ESPP.G.SH-18/2008 |  | 139946
R | ESPP.G.SH-19/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Diwaniyah | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 30 | 2008-12-05 | 7 | 2008-12-12 | 7 | 2008-12-19 | 15 | 2009-01-03 | 75 | 2009-03-19 |  |  | ESPP.G.SH-19/2008 | AL- NABAA / Baghdad
A |  |  |  | 139595 | USD | [8 empty] | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 14 | 2008-11-19 | 23 | 2008-12-12 | 5 | 2008-12-17 | 54 | 4-Feb-09 | 75 | 2009-04-20 | 139595 | USD | ESPP.G.SH-19/2008 |  | 139596
R | ESPP.G.SH-20/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Wassit | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 30 | 2008-12-05 | 7 | 2008-12-12 | 7 | 2008-12-19 | 15 | 2009-01-03 | 75 | 2009-03-19 |  |  | ESPP.G.SH-20/2008 | AL- NABAA / Baghdad
A |  |  |  | 139946 | USD | [8 empty] | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 14 | 2008-11-19 | 23 | 2008-12-12 | 5 | 2008-12-17 | 54 | 2009-02-04 | 75 | 2009-04-20 | 139946 | USD | ESPP.G.SH-20/2008 |  | 139946
R | ESPP.G.SH-21/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Anbar | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 30 | 2008-12-05 | 7 | 2008-12-12 | 7 | 2008-12-19 | 15 | 2009-01-03 | 75 | 2009-03-19 |  |  | ESPP.G.SH-21/2008 | AL- NABAA / Baghdad
A |  |  |  | 139890 | USD | [8 empty] | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 14 | 2008-11-19 | 23 | 2008-12-12 | 5 | 2008-12-17 | 54 | 2009-02-04 | 75 | 2009-04-20 | 139890 | USD | ESPP.G.SH-21/2008 |  | 139890
R | ESPP.G.SH-22/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Mousil | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 30 | 2008-12-05 | 7 | 2008-12-12 | 7 | 2008-12-19 | 15 | 2009-01-03 | 75 | 2009-03-19 |  |  | ESPP.G.SH-22/2008 | AL- NABAA / Baghdad
A |  |  |  | 139867 | USD | [8 empty] | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 14 | 2008-11-19 | 23 | 2008-12-12 | 5 | 2008-12-17 | 54 | 2009-02-04 | 75 | 2009-04-20 | 139867 | USD | ESPP.G.SH-22/2008 |  | 139867
R | ESPP.G.SH-23/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Sulaymaniyah | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 30 | 2008-12-05 | 7 | 2008-12-12 | 7 | 2008-12-19 | 15 | 2009-01-03 | 75 | 2009-03-19 |  |  | ESPP.G.SH-23/2008 | AL- NABAA / Baghdad
A |  |  |  | 139945 | USD | [8 empty] | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 14 | 2008-11-19 | 23 | 2008-12-12 | 5 | 2008-12-17 | 54 | 2009-02-04 | 75 | 2009-04-20 | 139945 | USD | ESPP.G.SH-23/2008 |  | 139946
R | ESPP.G.SH-24/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Dahuk | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 30 | 2008-12-05 | 7 | 2008-12-12 | 7 | 2008-12-19 | 15 | 2009-01-03 | 75 | 2009-03-19 |  |  | ESPP.G.SH-24/2008 | AL- NABAA / Baghdad
A |  |  |  | 139945 | USD | [8 empty] | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 14 | 2008-11-19 | 23 | 2008-12-12 | 5 | 2008-12-17 | 54 | 2009-02-04 | 75 | 2009-04-20 | 139945 | USD | ESPP.G.SH-24/2008 |  | 139946
R | ESPP.G.SH-25/2008 | IT Equipment -Servers, Software,Desktop & Peripherals/Kerkuk | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 30 | 2008-12-05 | 7 | 2008-12-12 | 7 | 2008-12-19 | 15 | 2009-01-03 | 75 | 2009-03-19 |  |  | ESPP.G.SH-25/2008 | AL- NABAA / Baghdad
A |  |  |  | 139946 | USD | [8 empty] | 2008-09-24 | 13 | 2008-10-07 | 2 | 2008-10-09 | 27 | 2008-11-05 | 14 | 2008-11-19 | 23 | 2008-12-12 | 5 | 2008-12-17 | 54 | 2009-02-04 | 75 | 2009-04-20 | 139946 | USD | ESPP.G.SH-25/2008 |  | 139946
R | ESPP.G.SH-26/2009 | IT Equipment -Servers, Software,Desktop & Peripherals/Diyala | Goods | 130000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2009-05-22 | 3 | 2009-05-29 | 6 | 2009-06-04 | 18 | 2009-06-22 | 76 | 2009-09-06 | 4 | 2009-09-10 | 5 | 2009-09-15 | 15 | 2009-09-30 | 45 | 2009-11-14 |  |  | ESPP.G.SH-26/2009 | AL- NABAA / Baghdad
A |  |  |  | 131205.89 | USD | [8 empty] | 2009-05-26 | 3 | 2009-05-29 | 6 | 2009-06-04 | 18 | 2009-06-22 | 76 | 6-Seb-09 | 4 | 10-Seb-09 | 5 | 15-Seb-09 |  | 2009-11-24 | 75 | 2010-02-15 | 131205.89 | USD | ESPP.G.SH-26/2009 |  | 131.206
R | ESPP.G.SH-27/2011 | IT Equipment -Smart Card Printers/Governorates* | Goods | 190000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2011-07-03 | 2 | 2011-07-05 | 77 | 2011-09-20 | 14 | 2011-10-04 | 30 | 2011-11-03 | 13 | 2011-11-16 | 1 | 2011-11-17 | 27 | 2011-12-14 | 45 | 2012-01-28 |  |  | ESPP.G.SH-27/2011 | NEW CORE / Baghdad
A |  |  |  | 138796 | USD | [8 empty] | 2011-07-03 | 2 | 2011-07-05 | 77 | 2011-09-20 | 14 | 2011-10-04 | 30 | 2011-11-03 | 13 | 2011-11-16 | 1 | 2011-11-17 | 27 | 2011-12-14 | 45 | 2012-01-28 | 138796 | USD | ESPP.G.SH-27/2011 |  | 138796
R | ESPP.G.SH-28/2009 | Line Printers for Governorates | Goods | 100000 | USD |  | SH | post | SH | NO | NO | NA | NA | 2011-10-01 | 4 |  |  | 2011-10-05 | 13 | 2011-10-18 | 32 | 2011-11-20 |  |  | 5 | 2011-11-25 | 5 | 2011-11-30 | 45 | 2012-01-15 |  |  | ESPP.G.SH-28/2009 | URUK .co / Baghdad
A |  |  |  | 110241 | USD | [8 empty] | 2011-09-29 |  |  | 5 | 2011-10-05 | 13 | 2011-10-18 | 57 | 2011-12-11 | 1 | 2011-12-15 | 4 | 2011-12-19 | 29 | 2012-01-17 | 45 | 2012-05-03 | 110241 | USD | ESPP.G.SH-28/2009 |  | 110241
R | ESPP.G.SH-29/2012 | Disaster Recovery | Goods | 150000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2012-05-13 | 6 | 2012-05-19 | 2 | 2012-05-21 | 15 | 2012-06-05 | 15 | 2012-06-20 | 6 | 2012-06-26 | 10 | 2012-07-06 | 10 | 2012-07-16 | 45 | 2012-08-30 |  |  | ESPP.G.SH-29/2012 | AL- NABAA / Baghdad
A |  |  |  | 145000 | USD |  | SH | PRIOR | SH |  |  |  |  | I: 2012-10-03; K: 2012-10-13; M: 2012-10-16; O: 2012-11-05; Q: 2012-09-12; S: 2012-12-21; U: 2012-12-30; W: 2012-01-27; Y: 2012-04-10 | 145000 | USD | ESPP.G.SH-29/2012
R | ESPP.G.SH-30/2012 | Monitoring & Equipment Software | Goods | 120000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2012-05-13 | 6 | 2012-05-19 | 2 | 2012-05-21 | 15 | 2012-06-05 | 15 | 2012-06-20 | 6 | 2012-06-26 | 10 | 2012-07-06 | 10 | 2012-07-16 | 45 | 2012-08-30 |  |  | ESPP.G.SH-30/2012 | AL- NABAA / Baghdad
A |  |  |  | 98800 | USD |  | SH | POST | SH |  |  |  |  | I: 2012-07-18; M: 2012-07-25; O: 2012-08-08; Q: 2012-09-04; U: 2012-09-09; W: 2012-09-18 | 98800 | USD | ESPP.G.SH-30/2012
R | ESPP.G.SH-31/2012 | Help Desk Equipment | Goods | 60000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2013-02-15 |  |  | 7 | 2013-02-22 | 13 | 2013-03-07 | 7 | 2013-03-14 |  |  | 7 | 2013-03-21 | 5 | 2013-03-26 | 45 | 2013-05-10 |  |  | ESPP.G.SH-31/2012 | Under Awarding
[31 empty] | 60000 | USD | ESPP.G.SH-31/2012
R | ESPP.G.SH-32/2012 | Servers, pc, ups | Goods | 80000 | USD |  | SH | POST | SH | NO | NO | NA | NA | I: 2012-12-19 |  |  | ESPP.G.SH-32/2012 | Under Awarding
A | [30 empty] | 80000 | USD | ESPP.G.SH-32/2012
R | ESPP.G.SH-34/2012 | Monitoring Cameras | Goods | 195000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2012-02-28 | 22 | 2012-03-21 | 39 | 2012-04-29 | 16 | 2012-05-15 | 10 | 2012-07-18 | 7 | 2012-07-25 | 10 | 2012-08-04 | 10 | 2012-08-14 | 75 | 2012-10-28 |  |  | ESPP.G.SH-34/2012 | MASAR AL-REEM / Baghdad
A |  |  |  | 178000 | USD |  | SH | PRIOR | SH |  |  |  |  | I: 2012-02-28; K: 2012-03-22; M: 2012-04-30; O: 2012-05-26; Q: 2012-07-18; S: 2012-07-21; U: 2012-07-24; W: 2012-08-08 | 178000 | USD | ESPP.G.SH-34/2012
R | ESPP.G.SH-Int/2008 | Internet Equipments- Connection/PMO & SPS | Goods | 28000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2008-06-28 |  | 2008-06-28 |  | 2008-06-25 | 7 | 2008-07-02 | 29 | 2008-07-31 | 6 |  | 0 | 2008-08-06 | 19 | 2008-08-25 | 10 | 2008-09-04 |  |  | ESPP.G.SH-Int/2008 | AL- NABAA / Baghdad
A |  |  |  | 25460 | USD | [8 empty] | 2008-06-28 |  |  |  | 2008-06-25 |  | 2008-07-02 | 29 | 2008-07-31 | 6 |  |  | 2008-08-06 | 19 | 2008-08-25 | 10 | 2008-09-04 | 25460 | USD | ESPP.G.SH-Int/2008 |  | 25460
R | ESPP.G.SH-Gen01/2010 | Generators/Baghdad,K&R, Najaf and Basrah | Goods | 75000 | USD |  | SH | POST | SH | NO | NO | NA | NA | 2010-08-05 |  |  |  | 2010-08-12 | 3 | 2010-08-15 | 1 | 2010-09-16 |  |  |  | 2010-09-24 | 10 | 2010-10-04 | 60 | 2010-12-04 |  |  | ESPP.G.SH-Gen01/2010 | Baghdad
A |  |  |  | 90000 | USD | [8 empty] | I: 2010-08-05; M: 2010-08-12; O: 2010-08-15; P: 1; Q: 2010-09-16; U: 2010-09-24; V: 10; W: 2010-10-04; X: 60; Y: 2010-12-04 | 90000 | USD | ESPP.G.SH-Gen01/2010 |  | 90000
R | ESPP.G.SH-Gen02/2009 | Generators/All Gvernorates | Goods | 195000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 28-M ay-09 | 6 | 2009-06-03 | 1 | 2009-06-04 | 18 | 2009-06-22 | 106 | 2009-10-06 | 22 | 2009-10-28 | 4 | 2009-11-01 | 15 | 2009-11-16 | 75 | 2010-06-30 |  |  | ESPP.G.SH-Gen02/2009 | NAWAER AL-KHEIR / Baghdad
A |  |  |  | 194850 | USD |  | SH | PRIOR | SH |  |  |  |  | 2009-05-28 | 6 | 2009-06-03 | 1 | 2009-06-04 | 18 | 2009-06-22 | 106 | 2009-10-06 | 7 | 2009-10-28 | 4 | 2009-11-01 | 23 | 2009-11-24 | 78 | 2010-02-10 | 194850 | USD | ESPP.G.SH-Gen02/2009 |  | 194.85
R | ESPP.G.SH-AC/2010 | Air Coditions/All Gvernorates | Goods | 60000 | USD |  | SH | POST | SH | NO | NO | NA | NA | I: 2010-08-05; M: 2010-08-12; O: 2010-08-12; P: 4; Q: 2010-08-16; U: 2010-08-24; W: 2010-09-01; X: 75; Y: 2010-11-15 |  |  | ESPP.G.SH-AC/2010 | CRAFT AL-RUBAI / Baghdad
A | ESPP.G.SH-AC/2010 | Air Coditions/All Gvernorates |  | 37170 | USD |  | SH | POST | SH |  |  |  |  | I: 2010-08-05; M: 2010-08-12; O: 2010-08-12; P: 4; Q: 2010-08-16; U: 2010-08-24; W: 2010-09-01; X: 75; Y: 2010-11-15 | 37170 | USD | ESPP.G.SH-AC/2010 |  | 37170
R | ESPP.G.SH-EQ/2012 | IT Equipment and Software | Goods | 75000 | USD |  | SH | Post | SH | NO | NO | NA | NA | 2012-03-19 |  |  | 41 | 2012-04-29 | 16 | 2012-05-15 | 10 | 2012-05-25 |  |  | 5 | 2012-05-30 | 10 | 2012-06-09 | 45 | 2012-07-24 |  |  | ESPP.G.SH-EQ/2012 | SOOR ZUHAL / Baghdad
A1 |  |  |  |  | USD |  | SH | Post | SH |  |  |  |  | I: 2012-03-19; K: 2012-04-22; M: 2012-04-29; O: 2012-05-15; Q: 2012-06-26; U: 2012-12-30; W: 2013-01-27 | 41900 | USD | ESPP.G.SH-EQ/2012 | SOOR ZUHAL / Baghdad |  | Re-tendered
A2 |  |  |  | $ 41.900 | USD |  | SH | post | SH |  |  |  |  | I: 2012-07-05; K: 2012-04-22; M: 2012-07-25; O: 2012-08-08; Q: 2012-08-26; S: 2012-12-24; U: 2012-12-30; W: 2013-01-27; Y: 2012-04-10 | 41900 | USD | ESPP.G.SH-EQ/2012 | SOOR ZUHAL / Baghdad
R | ESPP.G.SH.EQ(PENSION)/2012 | SUPPLY OF IT EQUIPMENT-SERVERS,UPS,AND PERIPHERALS FOR PENSION(BAGHDAD) | Goods | 165000 | USD |  | SH | PRIOR | SH | NO | NO | NA | NA | 2012-01-24 | 8 | 2012-02-01 | 7 | 2012-02-08 | 14 | 2012-02-22 | 15 | 2012-04-25 | 5 | 2012-04-30 | 7 | 2012-05-07 | 9 | 2012-05-16 | 45 | 2012-06-30 |  |  | ESPP.G.SH.EQ(PENSION)/2012 | SOOR ZUHAL / Baghdad
A |  |  |  | 171150 | USD |  | SH | PRIOR | SH |  |  |  |  | 2012-01-24 | 8 | 2012-02-01 | 7 | 2012-02-12 | 14 | 2012-02-22 | 15 | 2012-04-25 | 5 | 2012-05-01 | 7 | 2012-07-15 | 9 | 2012-07-30 |  |  | 171150 | USD | ESPP.G.SH.EQ(PENSION)/2012 |  | 171150 | NBP has not informed the PMO of the actual completion date
R | ESPP.G.SH.Fire System/2012 | Fire Fighting System, all Centers | Goods | 80000 | USD |  | SH | Post | SH | NO | NO | NA | NA | 2012-08-01 | 8 |  | 7 | 2012-08-08 | 14 | 2012-08-22 | 15 | 2012-09-06 | 5 |  | 7 | 2012-09-13 | 9 | 2012-09-22 | 45 | 2012-11-06 |  |  | ESPP.G.SH.Fire System/2012 | Under Awarding
A | [32 empty] | ESPP.G.SH.Fire System/2012
R | Sub-total |  |  | 3263000 | USD
A | Sub-total |  |  | 2936182.53 | [30 empty] | 2188724.596
R | Total Revised |  |  | 5725099.75 | USD
A | Total Actual |  |  | 4917767.24 | USD | [29 empty] | 2355774.285
Grant Total:Actual
| Notes: | All cost figures are totals including contingencies
| /* | First 3 packages are subject to prior review
| ICB = | International Competitive Bidding (in accordance with section 2 of the Guidelines)
| NCB = | National Competitive Bidding (in accordance with section 3.3 of the Guidelines)
| SH = | Shopping (in accordance with section 3.5 of the Guidelines)
| NA = | Not applicable
| * | For 13 Governorates:Kerbala, Hilla, Muthana, Missan, Thi-Qar, Diwaniyah, Wassit, Anbar, Mousl, Sulaymaniyah, Dahuk, Kerkuk and Diyala

## Consultants' Services
IRAQ
EMERGENCY SOCIAL PROTECTION PROJECT
Plan vs. Actual | Procurement System Ref. # | Location/ Description of Assignment | Estimated Cost (US$) | Selection Method | Review by Bank Prior / Post | Type of Counsultant (Firm / Individual) | RFP Final Draft to be forwarded to the bank (Date) | No objection from Bank for TOR (Date)** | No objection from Bank for RFP (Date)** | Adverti- sement for EOI Date | Interval /a | TOR / Shortlist to be Finalised (Date) | Interval /a | No objection from Bank for Shortlist (Date)** | Interval /a | RFP Issued (Date) | Interval /a | prposal Submission Deadline(Date) | Interval /a | Technical Evaluation Date | Interval /a | No objection by the Bank to Evaluation Report (Date ) ** | Interval /a | Final Evaluation Date | Interval /a | No Objection Date | Interval /a | No objection by the Bank (Technical/ # combined/ Draft contract / Final Contract) (Date)** | Interval /a | Contract Signed( Date) | Execution /b | Services Completion Date | Contract Value | Contract Currency | Contract No. | Name,City and Country of Contractor (incl.Zip Code if US) | Expenditure incurred to Date | Comments
B | C | D | E | F | G |  |  |  |  | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | Z | AA | AB | AC | AD | [5 empty] | AE
2. CONSULTANTS' SERVICES
R | ESPP.C.SSN.IND-01 | Social Safety Net-International Consultant | 150000 | IC | PRIOR | Individual | 2008-04-23 | 2008-04-29 | 2008-04-29 | 2008-01-24 | 90 | 2008-04-23 | 6 | 2008-04-29 | 1 | 2008-04-30 | 15 | 2008-05-15 |  |  |  |  | 62 | 2008-07-16 |  | 2008-07-16 | 7 | 2008-07-23 | 4 | 2008-07-27 | 490 | 2009-11-29 |  |  | ESPP.C.SSN.IND-01 | MUSA SHTEWI / BAGHDAD |  | Contract was cancelled
A |  |  | 5360 | [6 empty] | 2008-01-24 | 90 | 2008-04-23 | 6 | 2008-04-29 | 1 | 2008-04-30 | 15 | 2008-05-15 |  |  |  |  | 62 | 2008-07-16 | 7 | 2008-07-23 | 7 | 2008-07-30 | 4 | 2008-08-03 | 490 | 2009-12-06 | 5360 | USD |  |  | 5360 | Contract was terminated
R | ESPP.C.SSN.IND-02 | Social Safety Net-Local Consultant | 20000 | IC | PRIOR | Firm | 2008-03-31 | 2008-05-05 | 2008-05-05 | 2008-01-24 | 102 | 2008-05-05 | 0 | 2008-05-05 |  | 2008-05-05 | 10 | 2008-05-15 | 84 |  |  |  |  | 2008-08-07 |  | 2008-08-07 | 1 | 2008-08-08 | 3 | 2008-08-11 | 490 | 2009-12-14 |  |  | ESPP.C.SSN.IND-02 | KAFAAT AL RAFDIAN / BAGHDAD
A |  |  | 1524 | [6 empty] | 2008-01-24 | 102 | 2008-05-05 | 0 |  |  | 2008-05-05 | 10 | 2008-05-15 | 84 |  |  |  |  | 2008-08-07 | 4 | 2008-08-11 | 1 | 2008-08-12 | 3 | 2008-08-15 | 490 | 2009-12-18 | 1524 | USD |  |  | 1524 | Contract was terminated
R | ESPP.C.CQS.SSN-03 | Social Safety Net Survey Firm | 200000 | CQS | PRIOR | Firm | 2010-03-10 | 2010-03-17 | 2010-03-17 | 2008-01-24 | 74 | 2008-04-07 | 9 | 2008-04-16 | 4 | 2008-04-20 | 15 | 2008-05-05 | 0 | 0 |  |  | 78 | 2008-07-22 | 1 | 2008-07-23 | 8 | 2008-07-31 | 15 | 2008-08-15 | 490 | 2009-12-18 |  |  | ESPP.C.CQS.SSN-03 | KAFAAT AL RAFDIAN / BAGHDAD
A2 |  |  | 172700 | [6 empty] | X: 2010-04-13; Z: 2010-03-25; AB: 2010-03-25; AD: 2010-12-31 | 172700 | USD |  |  | 172700 | TOR Modified to complete the Social Safety Net-International Consultan tasks. The consultant submitted the final report in April 2011 in three languages (Arabic, English, & Kurdish) and is being discussed by the PMO and SSN
R | ESPP.C.CQS.PSSA | Product Support and Services Agreement for SSN Informatiom System | 198000 | CQS | PRIOR | Firm | 2012-10-05 | 2012-10-05 | 2012-10-05 | 2012-02-29 | 15 | 2012-05-10 | 7 | 2012-08-03 | 20 | 2012-08-08 | 29 | 2012-09-20 | 10 | 2012-09-30 | 7 | 2012-10-07 | 15 | 2012-10-22 | 3 | 2012-10-25 | 3 | 2012-10-28 | 3 | 2012-10-31 | 300 | 2013-08-27 |  |  | ESPP.C.CQS.PSSA | PRIMUS COMPANY
A |  |  |  | CQS | PRIOR |  |  |  |  | H: 2012-02-29; J: 2012-05-10; L: 2012-08-03; N: 2012-08-08; P: 2012-09-20 | [5 empty] | The technical and financial proposals were received and are still under evaluation
R | ESPP.C.QCBS-03 | Pension System Survey and Data Base Development | 368000 |  |  | Firm | 2007-07-09 | 2007-07-23 | 2007-07-23 | 2006-05-15 | 306 | 2007-03-17 | 11 | 2007-03-28 | 4 | 2007-04-01 | 43 | 2007-05-14 | 56 | 2007-07-09 | 14 | 2007-07-23 | 217 | 2008-02-25 | 16 | 2008-03-12 | 10 | 2008-03-22 | 9 | 2008-03-31 | 510 | 2009-08-23 |  |  | ESPP.C.QCBS-03 | Data mention
A |  |  | 100218 | [6 empty] | 2006-05-15 | 306 | 2007-03-17 | 11 | 2007-03-28 | 4 | 2007-04-01 | 43 | 2007-05-14 | 56 | 2007-07-09 | 14 | 2007-07-23 | 217 | 2008-02-25 | 16 | 2008-03-12 | 10 | 2008-03-22 | 9 | 2008-03-31 | 910 | 2011-06-30 | 100218 | USD |  |  | 100218 | Commitment reduced due to contract termination on June 30, 2011
P | ESPP.C.IND-02 | Project Management Office-Project Manager | 45000 | IC | PRIOR | Individual |  |  |  | X: 2006-11-14; Z: 2006-11-14; AB: 2006-11-14; AC: 778; AD: 2008-12-31 |  |  | ESPP.C.IND-02 | Maki Al Rubei'ai CONTRACT
A |  |  | 30221 | [6 empty] | X: 2006-11-14; Z: 2006-11-14; AB: 2006-11-14; AC: 778; AD: 2008-12-31 | 30221 | USD |  |  | 30221
R1 | ESPP.C.LCS.AUDIT | Project management Office - External Auditor | 135000 | LCS | POST | Firm | 2007-11-29 | 2007-12-03 | 2007-12-03 | H: 2012-01-02; U: 71; V: 2012-03-13; W: 7; X: 2012-03-20; Y: 3; Z: 2012-03-23; AA: 11; AB: 2012-04-03; AC: 272; AD: 2012-12-31 |  |  | ESPP.C.LCS.AUDIT | TALAL ABO GAZALA
A1 |  |  | 115000 | [29 empty] | 115000 | USD |  |  | 115000
R | ESPP.C.IND-04 | Project Manager (Mr. Maki Al Rubei'ai) | 14000 | SSS | PRIOR | Individual |  |  |  | L: 2010-06-20; X: 2010-07-01; Z: 2010-07-01; AB: 2010-07-01; AD: 2011-02-28 |  |  | ESPP.C.IND-04 | EXTENDING Maki Al Rubei'ai CONTRACT
A |  |  | 13559.322 |  |  |  | 2006-11-23 | 2006-12-17 | 2006-12-17 | L: 2010-06-20; X: 2010-07-01; Z: 2010-07-01; AB: 2010-07-01; AD: 2011-02-28 | 13559.322 | USD |  |  | 13559.322
R | ESPP.C.IND-data.01-106 | Data Entry Staff | 100000 | IC | POST | Firm |  |  |  | H: 2011-01-01; J: 2011-01-01; Z: 2011-03-01; AB: 2011-03-01; AD: 2011-03-01 |  |  | ESPP.C.IND-data.01-106
A |  |  | 110811 | [6 empty] | Z: 2011-03-01; AB: 2011-03-01 | 110811 | USD |  |  | 110811 | Salaries up to 29-2-2012
R | Sub-total |  | 1185000 | [31 empty] | Sub-total
A | Sub-total |  | 542509.322 | [31 empty] | Sub-total |  | 549393.322
| 3.Training | [33 empty] | 3.Training
R | ESPP.C.CQS-TS | Training of designing a Microsoft SQL server and CISCO | 134000 | CQS | PRIOR | Firm | 2007-05-29 | 2007-05-29 | 2007-05-29 | 2007-05-01 | 10 | 2007-05-11 | 18 | 2007-05-29 | 1 | 2007-05-30 | 20 | 2007-06-19 | 90 | 2007-09-17 | 1 | 2007-09-18 |  | 2007-09-18 | 0 | 2007-09-18 | 12 | 2007-09-30 | 0 | 2007-09-30 | 115 | 2008-01-23 |  |  | ESPP.C.CQS-TS | ACADEMY COMPANY
A |  |  | 60480 |  |  |  | 2007-05-29 | 2007-05-29 | 2007-05-29 | 2007-05-01 | 10 | 2007-05-11 | 18 | 2007-05-29 | 1 | 2007-05-30 | 20 | 2007-06-19 | 90 | 2007-09-17 | 1 | 2007-09-18 |  | 2007-09-18 | 0 | 2007-09-18 | 12 | 2007-09-30 |  | 2007-09-30 | 115 | 2008-01-23 | 60480 | USD |  |  | 60480
R | ESPP.C.CQS-TP | Training of designing a Microsoft ORACLE | 123000 | CQS | PRIOR | Firm | 2007-05-29 | 2007-05-29 | 2007-05-29 | 2007-05-01 | 10 | 2007-05-11 | 18 | 2007-05-29 | 1 | 2007-05-30 | 6 | 2007-06-05 | 90 | 2007-09-03 | 9 | 2007-09-12 | 0 | 2007-09-12 | 0 | 2007-09-12 | 18 | 2007-09-30 | 0 | 2007-09-30 | 119 | 2008-01-27 |  |  | ESPP.C.CQS-TP | ORACLE COMPANY
A |  |  | 47800 |  |  |  | 2007-05-29 | 2007-05-29 | 2007-05-29 | 2007-05-01 | 10 | 2007-05-11 | 18 | 2007-05-29 | 1 | 2007-05-30 | 6 | 2007-06-05 | 90 | 2007-09-03 | 9 | 2007-09-12 | 0 | 2007-09-12 | 0 | 2007-09-12 | 18 | 2007-09-30 | 0 | 2007-09-30 | 123 | 2008-01-31 | 47800 | USD |  |  | 47800
R | ESPP.C.CQS.Prog. | TRAINING COURSES OF PROGRAMMERS SNN | 195000 | CQS | POST | Firm | 2012-12-23 | 2012-12-27 | 2012-12-27 | 2012-05-01 | 10 | 2012-05-11 | 11 | 2012-05-22 | 3 | 2012-05-25 | 20 | 2012-06-14 | 12 | 2012-06-26 | 3 | 2012-06-29 | 4 | 2012-07-03 | 7 | 2012-07-10 | 7 | 2012-07-17 | 17 | 2012-08-03 | 120 | 2012-12-01 |  |  | ESPP.C.CQS.Prog.
A | [9 empty] | H: 2012-08-07; J: 2012-09-24 | [5 empty] | Under evaluation
R | ESPP.C.CQS.Eng. | TRAINING COURSES OF ENGINEERS SNN | 195000 | CQS | POST |  | 2012-12-23 | 2012-12-27 | 2012-12-27 | 2012-05-01 | 10 | 2012-05-11 | 11 | 2012-05-22 | 3 | 2012-05-25 | 20 | 2012-06-14 | 12 | 2012-06-26 | 3 | 2012-06-29 | 4 | 2012-07-03 | 7 | 2012-07-10 | 7 | 2012-07-17 | 17 | 2012-08-03 | 60 | 2012-10-02 |  |  | ESPP.C.CQS.Eng.
A | [9 empty] | H: 2012-08-07; J: 2012-09-24 | [5 empty] | Under evaluation
R | ESPP.C.IND-02 | Learning Visit (ANKARAL) | 150000 | IC | Post | [29 empty] | ESPP.C.IND-02
A |  |  | 23462 | [6 empty] | H: 2012-01-09 | 23462 | USD |  |  | 23462
R | ESPP.C.IND-03 | Learning Visit (Lebanon) |  | IC | Post | [29 empty] | ESPP.C.IND-03
A |  |  | 18657 | [6 empty] | H: 2012-06-04 | 18657 | USD |  |  | 18657
R | ESPP.C.IND-04 | Learning Visit (Gorgia) |  | IC | Post | [29 empty] | ESPP.C.IND-04
A |  |  | 33518 | [6 empty] | H: 2012-11-11 | 33518 | USD |  |  | 33518
R | ESPP.C.IND-05 | Learning Visit (Indonesia) |  | IC | Post | [29 empty] | ESPP.C.IND-05
A |  |  | 41256 | [6 empty] | H: 2012-06-25 | 41256 | USD |  |  | 41256 | Learning visit to ANKARA (Group 1)
P | Sub-total |  | 257000 | [31 empty] | Sub-total
R | Sub-total |  | 540000 | [31 empty] | Sub-total
A | Sub-total |  | 149536 | [31 empty] | Sub-total |  | 225173
R | Total Revised |  | 1725000 | [31 empty] | Total Revised
A | Total Actual |  | 692045.322 | [31 empty] | Total Actual |  | 774566.322
Note on AK21: green: