## consultancy
Ethiopia
Arbaminch City Administration
Urban Local Government Development Project (ULGDP)
IDA Credit No |  | 4456-ET
Procurement Plan Consultancy EFY 2004 (20011/12)
Item no | Loan #: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  | Contract Implementation
| Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
|  | IC | Lumpsum | 14770.6997 | Post
1 | Consultancy Service for EIA Market and Drainage Line and Cuvert |  |  |  |  | Plan | 2011-12-20 |  | 2012-01-02 | 2012-01-16 | 2012-01-23 | NA | Plan | 2012-01-30 | 2012-02-29 | 2012-03-12 | NA | 2012-03-19 | 2012-03-26 | 2012-04-02 | Plan | 2012-04-09 | NA |  | 2012-04-16 | 2012-04-25 |  | 2012-05-07 | 2012-07-11 | 2012-08-10
[6 empty] | Rev | 2012-11-01 |  | 2012-11-12 | 2012-11-27 | 2012-12-04 | NA | Rev | NA | NA | NA | NA | NA | NA | 2013-02-06 | Plan | 2013-02-11 | NA |  | 2013-02-18 | 2013-02-25 |  | 2013-03-07 | 2013-05-15 | 2013-06-10
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual
2 | Design for Public park, | LCS | lumpsum | 28090.2033 |  | Plan | 2012-11-01 |  | 2012-11-12 | 2012-11-27 | 2012-12-04 | NA | Rev | 2012-12-10 | 2013-01-09 | 2013-01-21 | NA | 2013-01-29 | 2013-02-01 | 2013-02-06 | Plan | 2013-02-11 | NA |  | 2013-02-18 | 2013-02-25 |  | 2013-03-07 | 2013-05-15 | 2013-06-10
[6 empty] | Rev | [6 empty] | Rev
[6 empty] | Actual | [6 empty] | Actual
3 | Consultancy Service revenue enhancement | LCS | lumpsum | 14045.1 |  | Plan | 2012-12-20 |  | 2013-01-02 | 2013-01-16 | 2013-01-23 | NA | Plan | 2013-01-30 | 2013-03-01 | 2013-03-13 | NA | 2013-03-20 | 2013-03-27 | 2013-04-03 | Plan | 2013-04-10 | NA |  | 2013-04-17 | 2013-04-26 |  | 2013-05-02 | 2013-07-30 | 2013-08-28
[6 empty] | Rev | [6 empty] | Rev
[6 empty] | Actual | [6 empty] | Actual
4 | Consultancy Service external Audit | LCS | lumpsum | 14045.1 |  | Plan | 2012-12-20 |  | 2013-01-02 | 2013-01-16 | 2013-01-23 | NA | Plan | 2013-01-30 | 2013-03-01 | 2013-03-13 | NA | 2013-03-20 | 2013-03-27 | 2013-04-03 | Plan | 2013-04-10 | NA |  | 2013-04-17 | 2013-04-26 |  | 2013-05-02 | 2013-07-30 | 2013-08-28
[6 empty] | Rev | [6 empty] | Rev
[6 empty] | Actual | [6 empty] | Actual
| Total Cost |  |  | 70951.1029

## Works 2004
ETHIOPIA
Urban Local Government : ARBAMINCH CITY ADMINSTRATION
Urban Local Government Development Project (ULGDP)
IDA Credit No. 4456-ET
Procurement Plan - Civil Works EEY 2004 ( 2011/12)
Basic Data | [9 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | SPN Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation
S/N | Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB/ Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount in US$ | Date Contract Award | Date Contract Signature | Advance Mobilisation Payment | Substantial completion | Final Completion | Final cost
[10 empty] | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | 1 wk | 1.5-3 wks
1 | Cobblestone Road
1.1 | Sikela Old Market Enterance -Assa Tera /phase 3 | ULGDP/ARBA/CB0030/2004 | 3 | BOQ | NCB | 262689 | Post | Post | Plan | 2011-12-07 | N/A | 2011-12-14 | 2011-12-14 | 2012-01-13 | 2012-01-24 | NA | 228,881.99 | 2012-01-31 | 2012-02-08 | 2012-02-29 | 2012-04-30 | 2013-04-30
[9 empty] | Revised | [11 empty] | 2012-12-31 | 2013-12-31
[9 empty] | Actual | 2011-12-07 |  | 2012-01-16 | 2012-01-16 | 2012-02-15 | 2012-02-20 |  |  | 2012-02-27 | 2012-03-14 | 2012-03-19
| Sikela Old Market Enterance -Teka Work Bet/phase 3 |  | Lot 1 |  |  | 87563 | [10 empty] | 76293.03
| Teka Work Bet - Gudeta Dabi Wefecho Bet phase 3 |  | Lot 2 |  |  | 87563 | [10 empty] | 76297.08
| Gudata Wefecho Bet to Assa Tera / phase 3 |  | Lot 3 |  |  | 87563 | [10 empty] | 76291.88
2 | Konso Adebabay to Sikela Primary School/phase 3 | ULGDP/ARBA/CB0031/2004 |  | BOQ | CPP/LCB | 85896 | Post | Post | Plan | 2011-12-05 | N/A | NA | 2011-12-12 | 2011-12-26 | 2012-01-02 | NA | 83377.94 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-03-30 | 2013-03-29
[9 empty] | Revised | [11 empty] | 2012-10-30 | 2013-10-30
[9 empty] | Actual | 2011-12-05 |  | NA | 2012-02-13 | 2012-03-01 | 2012-03-04 |  |  | 2012-03-09 | 2012-03-14 | 2012-03-19
3 | Infront of Nechsar Sub City to Kairo Hotel phase 3 | ULGDP/ARBA/CB0032/2004 |  | BOQ | CPP/LCB | 85897 | Post | post | Plan | 2011-12-05 | N/A | NA | 2011-12-12 | 2011-12-26 | 2012-01-02 | NA | 85971.0849 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-03-30 | 2013-03-29
[9 empty] | Revised | [11 empty] | 2012-10-30 | 2013-10-30
[9 empty] | Actual | 2011-12-05 |  | NA | 2012-02-13 | 2012-03-01 | 2012-03-04 |  |  | 2012-03-09 | 2012-03-14 | 2012-03-19
4 | Mesiqued to Debube Merab Sinodos /phase 3 | ULGDP/ARBA/CB/0033 /2004 |  | BOQ | CPP/LCB | 85897 | Post | post | Plan | 2011-12-05 | N/A | NA | 2011-12-12 | 2011-12-26 | 2012-01-02 | NA | 84682.1936 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-03-30 | 2013-03-29
[9 empty] | Revised | [11 empty] | 2012-10-30 | 2013-10-30
[9 empty] | Actual | 2011-12-05 |  | NA | 2012-02-13 | 2012-03-01 | 2012-03-04 |  |  | 2012-03-09 | 2012-03-14 | 2012-03-19
5 | Hailu Getaneh to FM phase 3 | ULGDP/ARBA/CB/0034/ 2004 |  | BOQ | CPP/LCB | 73647.58 | Post | post | Plan | 2011-12-12 | N/A | N/A | 2011-12-19 | 2012-01-02 | 2012-01-09 | NA | 72476.87 | 2012-01-16 | 2012-01-23 | 2012-02-06 | 2012-05-30 | 2013-05-30
[9 empty] | Revised | [11 empty] | 2012-10-30 | 2013-10-30
[9 empty] | Actual | 2011-12-05 |  | NA | 2012-02-13 | 2012-03-01 | 2012-03-04 |  |  | 2012-03-09 | 2012-03-14 | 2012-03-19
6 | Yetnebersh School - Highland Rendez vous Curve phase 3 | ULGDP/ARBA/CB/0035/2004 |  | BOQ | CPP/LCB | 80897 | Post | post | Plan | 2011-12-12 | N/A | N/A | 2011-12-19 | 2012-01-02 | 2012-01-09 | NA | 79785.5885 | 2012-01-16 | 2012-01-23 | 2012-02-06 | 2012-05-30 | 2013-05-30
[9 empty] | Revised | [11 empty] | 2012-10-30 | 2013-10-30
[9 empty] | Actual | 2011-12-05 |  | NA | 2012-02-13 | 2012-03-01 | 2012-03-04 |  |  | 2012-03-09 | 2012-03-14 | 2012-03-19
7 | Agip - Bahile Museum / phase 3 | ULGDP/ARBA/CB0036/2004 | 4 | BOQ | NCB | 329484 | Post | post | Plan | 2011-12-07 | N/A | 2011-12-14 | 2011-12-14 | 2012-01-13 | 2012-01-24 |  | 311645.22 | 2012-01-31 | 2012-02-08 | 2012-02-29 | 2012-04-30 | 2013-04-30
[9 empty] | Revised | [11 empty] | 2012-12-31 | 2013-12-31
[9 empty] | Actual | 2011-12-07 | N/A | 2012-01-16 | 2012-01-16 | 2012-02-15 | 2012-02-20 |  |  | 2012-03-09 | 2012-03-14 | 2012-03-19
| Agip - Aroge Kuteba / phase 3 |  | Lot 1 |  |  | 82371 | [10 empty] | 77874.38
| Korkoro Sefer - Assa Corporation /phase 3 |  | Lot 2 |  |  | 82371 | [10 empty] | 77857.66
| Chamo Secondary School - Chamo Primary School / phase 3 |  | Lot 3 |  |  | 82371 | [10 empty] | 77991
| Secha Condominium -Bahile Museum / phase 3 |  | Lot 4 |  |  | 82371 | [10 empty] | 77922.18
Gravel Road
8 | Nechsar SC: Wehaminch Kebele -Yetenebereshe phase 1 | ULGDP/ ARBA/GR001/2004 |  | BOQ | NCB | 177248.3959 | Post | Post | Plan | 2011-12-13 | N/A | 2011-12-23 | 2011-12-23 | 2012-01-23 | 2012-02-07 | NA | 129737.5542 | 2012-02-15 | 2012-03-01 | 2012-03-21 | 2012-09-21 | 2013-09-23
[9 empty] | Revised | [11 empty] | 2012-11-30 | 2013-11-30
[9 empty] | Actual | 2011-12-13 |  | 2012-06-17 | 2012-06-17 | 2012-08-01 | 2012-08-14 |  |  | 2012-08-24 | 2012-08-31 | 2012-09-05
9 | Sikella SC: Gurba Kebele/ TEVT - Infront of Memere Ziruhun House phase 1 | ULGDP/ ARBA/GR002/2004 |  | BOQ | NCB | 180000 | Post | Post | Plan | 2011-12-13 | N/A | 2011-12-23 | 2011-12-23 | 2012-01-23 | 2012-02-07 | NA | 129737.55 | 2012-02-15 | 2012-03-01 | 2012-03-21 | 2012-09-21 | 2013-09-23
[9 empty] | Revised | [11 empty] | 2012-11-30 | 2013-11-30
[9 empty] | Actual | 2011-12-13 |  | 2012-06-17 | 2012-06-17 | 2012-08-01 | 2012-08-14 |  |  | 2012-08-24 | 2012-08-31 | 2012-09-05
10 | Neachsar SC: Tehadiso Meakele - Edeget Ber Kebelle - Sikella Primary School | ULGDP/ ARBA/GR003/2004 |  | BOQ | NCB | 163668.77 | Prior | Prior | Plan | 2011-01-16 | N/A | 2012-02-15 | 2012-02-15 | 2012-03-19 | 2012-04-02 | NA | 129737.55 | 2012-04-09 | 2012-04-23 | 2012-05-14 | 2012-10-15 | 2013-10-15
[9 empty] | Revised | [11 empty] | 2012-11-30 | 2013-11-30
[9 empty] | Actual | 2011-12-13 |  | 2012-06-17 | 2012-06-17 | 2012-08-01 | 2012-08-14 |  |  | 2012-08-24 | 2012-08-31 | 2012-09-05
11 | Abaya SC: Weze from the Asphat road to Weze Kebele Adminstration/ phase1 | ULGDP/ ARBA/GR/004/2004 |  | BOQ | NCB | 175324.81 | Post | Post | Plan | 2011-01-16 | N/A | 2012-02-15 | 2012-02-15 | 2012-03-19 | 2012-04-02 | NA | 129737.55 | 2012-04-09 | 2012-04-23 | 2012-05-14 | 2012-10-15 | 2013-10-15
[9 empty] | Revised | [11 empty] | 2012-11-30 | 2013-11-30
[9 empty] | Actual | 2011-12-13 |  | 2012-06-17 | 2012-06-17 | 2012-08-01 | 2012-08-14 |  |  | 2012-08-24 | 2012-08-31 | 2012-09-05
12 | Secha SC : Road from Amarech Hotel to Red Cross /phase 1 | ULGDP/ ARBA/GR/0005/2004 |  | BOQ | NCB | 190000 | Prior | Prior | Plan | 2011-01-16 | N/A | 2012-02-15 | 2012-02-15 | 2012-03-19 | 2012-04-02 | NA | 129737.55 | 2012-04-09 | 2012-04-23 | 2012-05-14 | 2012-11-15 | 2013-11-15
[9 empty] | Revised |  |  | 2013-01-08 | 2013-01-08 | 2013-02-11 | 2013-02-25 |  |  | 2013-03-05 | 2013-03-15 | 2013-03-25 | 2013-11-18 | 2014-11-18
[9 empty] | Actual | 2011-12-13
13 | Drainage | ULGDP/ARBA/DR/2004 | 3 | BOQ | NCB | 265079.31 | Post | Post | Plan | 2011-12-05 | N/A | 2011-12-08 | 2011-12-08 | 2012-01-12 | 2012-01-30 | NA |  | 2012-02-10 | 2012-02-28 | 2012-03-08 | 2012-06-14 | 2013-06-14
| Nechsar SC, Wehaminch Kebelle Yetenebersh Wehaminch/ and Drainage line construction Edeget Ber Kebelle near to Belaye Badebo House Nechsar/ Edegete Ber |  | I |  |  | 90080 |  |  | Revised |  |  | 2013-01-08 | 2013-01-08 | 2013-02-11 | 2013-02-25 |  |  | 2013-03-05 | 2013-03-15 | 2013-03-25 | 2013-12-17 | 2014-12-17
[9 empty] | Actual | 2011-12-05
Actual
[9 empty] | Plan | 2010-12-31 | N/A | 2011-12-08 | 2011-12-08 | 2012-01-12 | 2012-01-30 | NA |  | 2012-02-10 | 2012-02-28 | 2012-03-08 | 2012-06-14 | 2013-06-14
Revised
Actual
| Culvert/ Mini Bridge infront of Belaye Badebo Resident Nechsar / Edeget Ber - former 04 Kebelle Back Side Way to Arbaminch Hospital -Satdium to Arbaminch Jill Abaya |  | II |  |  | 88624.17
| Culvert/ Mini Bridge Secha back Omo Holo -Secha Back of Fishery Corporation - Sikela Cemetery Way |  | III |  |  | 86375.14
Market Development
14 | Market Development | ULGDP/ARBA/Cob1/Ex2 |  | BOQ | NCB | 163941 | Post | Post | Plan | Dec 30/09 | N/A | 2010-01-10 | Jan 10/10 | 2010-03-05 | 2010-03-15 |  | 169 704.68 | 2010-03-30 | 2010-04-05 | 2010-04-26 | 2010-12-31 | 2011-12-31
[9 empty] | Revised | [8 empty] | 2011-01-30 | 2011-02-20 | 2011-02-28 | 2013-02-15 | 2014-02-15
[9 empty] | Actual | 2010-03-15 | N/A | 2010-08-03 | 2010-08-03 | 2010-09-03 | 2010-11-30 |  |  | 2011-12-20 | 2011-01-05 | 2011-01-15
15 | Market Development | ULGDP/ARBA/market/ phase II |  | BOQ | NCB | 564034.74 | Post | Post | Plan | 2011-12-30 | N/A | 2012-01-06 | 2012-01-10 | 2012-02-10 | 2012-03-05 | NA | 605610.3361 | 2012-03-15 | 2012-04-05 | 2012-04-26 | 2013-05-10 | 2014-05-09
[9 empty] | Revised | [11 empty] | 2013-08-30 | 2014-08-29
[9 empty] | Actual | 2011-12-30 |  | 2012-06-17 | 2012-06-17 | 2012-08-01 | 2012-08-14 |  |  | 2012-08-24 | 2012-08-31 | 2012-09-05
Total
16 | Cluster Shade | ULGDP/ARBA/shade/ phase I |  | BOQ | NCB | 177248.3959 | Post | Post | Plan | 2011-12-30 | N/A | 2012-01-06 | 2012-01-10 | 2012-02-10 | 2012-03-05 | NA |  | 2012-03-15 | 2012-04-05 | 2012-04-26 | 2013-05-10 | 2014-05-09
[9 empty] | Revised |  |  | 2013-01-10 | 2013-01-10 | 2013-02-14 | 2013-02-25 | NA |  | 2013-03-08 | 2013-03-13 | 2013-03-18 | 2013-11-13 | 2014-11-13
[9 empty] | Actual | 2011-12-30
| Total |  |  |  |  | 177248.3959
* The price was revised due to cahnge in type of market shade

## works 2005
ETHIOPIA
Urban Local Government : ARBAMINCH CITY ADMINSTRATION
Urban Local Government Development Project (ULGDP)
IDA Credit No. 4456-ET
Procurement Plan - Civil Works EEY 2005 ( 2012/13)
Basic Data | [9 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | SPN Advert | Bidding Period |  | Plan vs. Actual | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation
S/N | Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Nat Press | Bid Invitation Date | Bid Closing-Opening |  | Submission Bid Eval Rpt | No-objection Date | Contract Amount in US$ | Date Contract Award | Date Contract Signature | Advance Mobilisation Payment | Substantial completion | Final Completion | Final cost
[10 empty] | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to |  | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | 1 wk | 1.5-3 wks
1 | Cobblestone Road
1.1 | Soma hotel-Secha market | ULGDP/ARBA/CB0041/2005 |  | BOQ | CPP/LCB | 195000 | Post | post | Plan | 2012-10-26 | N/A | 2012-11-02 | 2012-11-02 | 2012-11-19 |  | 2012-11-26 | NA |  | 2012-12-03 | 2012-12-11 | 2012-12-18 | 2013-02-14 | 2014-02-14
Revised
Actual
1.2 | Abeba hotel-beruhi tesfa KG and Agip Cobble Remain | ULGDP/ARBA/CB0042/2005 |  | BOQ | CPP/LCB | 100000 | Post | post | Plan | 2012-10-26 | N/A | 2012-11-02 | 2012-11-02 | 2012-11-19 |  | 2012-11-26 | NA |  | 2012-12-03 | 2012-12-11 | 2012-12-18 | 2013-02-14 | 2014-02-14
Revised
Actual
1.3 | Interances (Stastics back &front of block, Trade &Indestery, Fish cor, Preparatory school, Amarech hotel,Ahemed shop) | ULGDP/ARBA/CB0043/2005 |  | BOQ | CPP/LCB | 80000 | Post | post | Plan | 2012-10-26 | N/A | 2012-11-02 | 2012-11-02 | 2012-11-19 |  | 2012-11-26 | NA |  | 2012-12-03 | 2012-12-11 | 2012-12-18 | 2013-02-14 | 2014-02-14
Revised
Actual
1.4 | Back side of Abi hotel-Dell fana hole | ULGDP/ARBA/CB0044/2005 |  | BOQ | CPP/LCB | 93000 | Post | post | Plan | 2012-10-26 | N/A | 2012-11-02 | 2012-11-02 | 2012-11-19 |  | 2012-11-26 | NA |  | 2012-12-03 | 2012-12-11 | 2012-12-18 | 2013-02-14 | 2014-02-14
Revised
Actual
1.5 | Dell fana hole-Sikela market | ULGDP/ARBA/CB/0045 /2005 |  | BOQ | CPP/LCB | 86000 | Post | post | Plan | 2012-11-05 | N/A | 2012-11-20 | 2012-11-20 | 2012-12-05 |  | 2012-12-14 | NA |  | 2012-12-19 | 2012-12-27 | 2013-01-03 | 2013-03-04 | 2014-03-04
Revised
Actual
1.6 | Gudata Wefecho Bete-ELPA cobble | ULGDP/ARBA/CB/0046/ 2004 |  | BOQ | CPP/LCB | 86000 | Post | post | Plan | 2012-11-05 | N/A | 2012-11-20 | 2012-11-20 | 2012-12-05 |  | 2012-12-14 | NA |  | 2012-12-19 | 2012-12-27 | 2013-01-03 | 2013-03-04 | 2014-03-04
Revised
Actual
1.7 | Stadium Cobble near to taxi fermata -Chat tera cobble | ULGDP/ARBA/CB/0047/2004 |  | BOQ | CPP/LCB | 89000 | Post | post | Plan | 2012-11-05 | N/A | 2012-11-20 | 2012-11-20 | 2012-12-05 |  | 2012-12-14 | NA |  | 2012-12-19 | 2012-12-27 | 2013-01-03 | 2013-03-04 | 2014-03-04
Revised
Actual
1.8 | Sikela primary school-TVET | ULGDP/ARBA/CB0048/2005 |  | BOQ | CPP/LCB | 86000 | Post | post | Plan | 2012-11-05 | N/A | 2012-11-20 | 2012-11-20 | 2012-12-05 |  | 2012-12-14 | NA |  | 2012-12-19 | 2012-12-27 | 2013-01-03 | 2013-03-04 | 2014-03-04
Revised
Actual
1.9 | Aserat building-Chat tera | ULGDP/ARBA/CB0049/2005 |  | BOQ | CPP/LCB | 98000 | Post | post | Plan | 2012-11-20 | N/A | 2012-12-03 | 2012-12-03 | 2012-12-18 |  | 2012-12-25 | NA |  | 2013-01-02 | 2013-01-11 | 2013-01-18 | 2013-03-14 | 2014-03-14
Revised
Actual
1.1 | Back side of bus station and interance | ULGDP/ARBA/CB0050/2005 |  | BOQ | CPP/LCB | 112000 | Post | post | Plan | 2012-11-20 | N/A | 2012-12-03 | 2012-12-03 | 2012-12-18 |  | 2012-12-25 | NA |  | 2013-01-02 | 2013-01-11 | 2013-01-18 | 2013-03-14 | 2014-03-14
Revised
Actual
1.11 | Out let of bus station-Chat tera | ULGDP/ARBA/CB0051/2005 |  | BOQ | CPP/LCB | 110000 | Post | post | Plan | 2012-11-20 | N/A | 2012-12-03 | 2012-12-03 | 2012-12-18 |  | 2012-12-25 | NA |  | 2013-01-02 | 2013-01-11 | 2013-01-18 | 2013-03-14 | 2014-03-14
Revised
Actual
1.12 | opposite of bus station out let-To nech sar lamerot hotel | ULGDP/ARBA/CB0052/2005 |  | BOQ | CPP/LCB | 89000 | Post | post | Plan | 2012-11-20 | N/A | 2012-12-03 | 2012-12-03 | 2012-12-18 |  | 2012-12-25 | NA |  | 2013-01-02 | 2013-01-11 | 2013-01-18 | 2013-03-14 | 2014-03-14
Revised
Actual
| Sub total |  |  |  |  | 1224000
2 | Market Development(new) | ULGDP/ARBA/market/ phase III |  | BOQ | NCB | 617984.4717 | Post | Post | Plan | 2013-01-01 | NA | 2013-01-08 | 2013-01-08 | 2013-02-11 |  | 2013-02-25 |  |  | 2013-03-05 | 2013-03-15 | 2013-03-25 | 2013-11-18 | 2014-11-18
Revised
Actual
3 | Street light | ULGDP/ARBA/ST/ phase I |  | BOQ | NCB | 333574.5 | Post | Post | Plan | 2013-01-01 | NA | 2013-01-08 | 2013-01-08 | 2013-02-11 |  | 2013-02-25 |  |  | 2013-03-05 | 2013-03-15 | 2013-03-25 | 2013-11-18 | 2014-11-18
Revised
Actual
| Sub total |  |  |  |  | 951558.9717