## Front Page
Procurement Plan
Grant name: | Agriculture Commercialization Project, H9640-TJ
Country: | Tajikistan
Prepared by: | Agriculture Commercialization Project
Date: | 22-June-2015 | Approved by: | Sandra Broka
Updated: | 2012-12-07 | Update approved: | 15-Dec-2015
|  | Approved by: | Sandra Broka
Updated: | 2016-02-24 | Update approved: | 2016-02-25
|  | Approved by: | Sandra Broka
Updated: | 2016-05-06 | Update approved:
|  | Approved by: | Sandra Broka

## Thresholds
Procurement Plan
Grant name: | Agriculture Commercialization Project, H9640-TJ
Country: | Tajikistan
Prepared by: | Agriculture Commercialization Project
ECA Regional procurement maximum prior/post review thresholds :
Contracts for procurement of works – USD 5 million;
Contracts for procurement of goods and non-consulting services – USD 0.5 million;
Contracts for consulting services with firms – USD 0.2 million;
Contracts for consulting services with individual experts – USD 0.1 million.

## IC
TAJIKISTAN
Agriculture Commercialization Project (ACP)
PROCUREMENT PLAN - CONSULTANT SERVICES IC - FOR PERIOD 1 MARCH 2015 - 31 DECEMBER 2016
(Date of PP: 22 JUNE 2015; Update No.3; Date of WB NOL: _____)
(Дата ПЗ: 15 декабря 2015 г.; Обновление №3; Дата одобрения ВБ: ______2016 г.)
# | Contract Description | Ref. No. | Plan/ Actual | Total Bid Est. ('000 US$) | Selection method | WB Review (Prior/Post) | Date of sending RFP (including TOR) to WB | Date of WB's no objection | Issuance of RFP/Request for Expressions of Interest | Date of Proposal Submission/(EOI) | Evaluation report | Date of WB's no objection for ER | Draft contract | WB's no objection to Draft Contract | Date of Contract Signing | Contract Signature Date | Contract Completion Date | Consultant | Comments | Status | Paid to date, ('000) US$ | Costs ('000), US$ | Costs ('000), SDR
№п/п | Описание контракта | №контракта | План/ факт | Бюджет ('000 US$) | Метод закупки | Обзор Банка (предваритель-ный / последующий) | Дата отправки ППП (включая ТЗ) ВБ | Дата одобрения ВБ | ППП/ Запрос на выражение заинтересован-ности | Дата подачи предложений/ ВЗ | Оценочный отчет | Дата одобрения банка на ОО | Проект контракта | Дата одобрение банка на проект контракта | Дата подписание контракта | Дата подписания контракта | Дата завершения контракта | Консультант | Комментарии | Статус | Оплачено, ('000) US$ | Расходы ('000), US$ | Расходы ('000), SDR
1 | FM Consultant | AED/PMU/SSS/2015-01 | P | 28600 | SSS | Prior | 2015-03-03 | 2015-03-13 | NA | NA | NA | NA | 2015-05-22 | 2015-03-13 | 2015-03-13 | 2016-03-13 | 2016-03-13 | Firdavs Satorov | The WB provided retro-active NOB. Amendment #1 valued at 13000USD was signed on 14 March 2016 | ongoing/действующий
|  |  | A | 28600 |  |  | 2015-03-03 | 2015-03-13 | NA | NA | NA | NA | 2015-05-25 | 2015-05-28 | 2015-03-13 | 2016-03-13 | 2016-12-31
2 | Deputy Director (re-tender) | AED/PMU/IC/2016-01 | P | 12600 | IC | Prior | 2015-03-02 | 2015-03-09 | 2016-01-01 | 2016-01-29 | 2016-02-06 | 2016-02-16 | 2016-02-20 | 2016-02-29 | 2016-03-05 |  | 2016-12-31 |  |  | ongoing/действующий
|  |  | A |  |  |  | 2015-07-23 | 2015-07-24 | 2016-01-07 | 2016-01-29 | 2016-04-18 | 2016-04-19 | 2016-04-20 | 2016-04-22 | 2016-04-22 |  | 2016-12-31 | Husseyn Karimov
3 | VC Consultants on meat and diary | AED/PMU/SSS/2015-02 | P | 14400 | SSS | Prior | 2015-03-03 | 2015-03-13 | NA | NA | NA | NA | 2015-05-22 | 2015-03-13 | 2015-03-13 | 2016-03-13 | 2016-03-13 |  | (официальное одобрение на 2,25 месяца было получено 5 января 2016 года) | completed/закончен
|  |  | A | 10097 |  |  | 2015-03-03 | 2015-03-13 | NA | NA | NA | NA | 2015-05-25 | 2015-05-28 | 2016-01-04 |  | 2016-01-05 | Nosirjon Sattorov
4 | VC Consultants on fruit and vegetables | AED/PMU/SSS/2015-03 | P | 14400 | SSS | Prior | 2015-03-03 | 2015-03-13 | NA | NA | NA | NA | 2015-05-22 | 2015-03-13 | 2015-03-13 | 2016-03-13 | 2016-03-13 |  | The WB provided retro-active NOB | completed/закончен
|  |  | A | 12700 |  |  | 2015-03-03 | 2015-03-13 | NA | NA | NA | NA | 2015-05-25 | 2015-05-28 | 2015-03-13 |  | 2016-02-01 | Nazira Zevarshoeva
5 | Translator Consultant | AED/PMU/IC/2015-03 | P | 16200 | IC | Post | 2015-03-18 | 2015-03-25 | 2015-03-29 | 2015-04-12 | 2015-04-22 | NA | NA | NA | 2015-06-05 | 2016-05-13 | 2016-06-05 |  |  | ongoing/действующий
|  |  | A | 10800 |  |  | 2015-04-09 | 2015-04-13 | 2015-03-11 | 2015-03-23 | 2015-04-22 | NA | NA | NA | 2015-06-05 | 2016-05-13 | 2016-06-05 | Izatulloi Sunatullo
6 | M and E Consultant | AED/PMU/IC/2015-01 | P | 19000 | IC | Post | 2015-03-11 | 2015-03-18 | 2015-03-22 | 2015-04-05 | 2015-05-01 | 2015-05-10 | 2015-05-22 | 2015-05-13 | 2015-05-25 | 2016-05-13 | 2016-05-13 |  |  | ongoing/действующий
|  |  | A | 12000 |  |  | 2015-03-11 | 2015-05-20 | 2015-03-11 | 2015-03-23 | 2015-04-30 | 2015-05-18 | 2015-05-20 | 2015-05-20 | 2015-05-22 | kk | 2016-05-22 | Umed Kasymov
7 | IT Consultant | AED/PMU/IC/2015-02 | P | 19000 | IC | Post | 2015-03-26 | 2015-04-02 | 2015-04-05 | 2015-04-19 | 2015-05-01 | NA | NA | NA | 2015-05-25 | 2016-05-13 | 2016-05-13 |  |  | ongoing/действующий
|  |  | A | 12000 |  |  | 2015-04-09 | 2015-04-13 | 2015-04-02 | 2015-04-15 | 2015-04-24 | NA | NA | NA | 2015-05-25 |  | 2016-05-25 | Shukhrat Barkhonov
8 | Environmental Consultant | AED/PMU/IC/2015-04 | P | 15200 | IC | Post | 2015-03-11 | 2015-03-18 | 2015-03-21 | 2015-04-04 | 2015-04-01 | NA | NA | NA | 2015-04-20 | 2016-05-13 | 2016-05-13 |  |  | ongoing/действующий
|  |  | A | 9600 |  |  | 2015-04-09 | 2015-04-13 | 2015-04-02 | 2015-04-15 | 2015-04-30 | NA | NA | NA | 2015-05-28 |  | 2016-05-28 | Rahim Nosirov
9 | Procurement Consultant | AED/PMU/SSS/2015-04 | P | 3035 | SSS | Prior | 2015-03-03 | 2015-03-13 | NA | NA | NA | NA | 2015-05-22 | 2015-03-13 | 2015-03-13 | 2016-03-13 | 2016-03-13 |  | The WB provided retro-active NOB | completed/закончен
|  |  | A | 3035 |  |  | 2015-03-03 | 2015-03-13 | NA | NA | NA | NA | 2015-05-25 | 2015-05-28 | 2015-03-13 |  | 2015-05-30 | Khurshed Karimov
10 | Procurement Consultant | AED/PMU/IC/2015-13 | P | 18000 | IC | Post | 2015-03-03 | 2015-03-13 | NA | NA | 2015-06-20 | 2015-06-20 | 2015-06-26 | 2015-07-01 | 2015-07-10 | 2016-05-13 | 2016-05-13 |  |  | ongoing/действующий
|  |  | A | 12000 |  |  | 2015-03-03 | 2015-03-13 | NA | NA | 2015-06-22 | 2015-06-22 | 2015-07-02 | 2015-07-02 | 2015-07-08 |  | 2016-07-08 | Khursheda Rakhmatulloeva
11 | Clerk Consultant | AED/PMU/IC/2015-06 | P | 7200 | IC | Post | 2015-03-20 | 2015-03-27 | 2015-03-30 | 2015-04-13 | NA | NA | NA | NA | 2015-05-05 | 2016-05-13 | 2016-05-13 |  |  | ongoing/действующий
|  |  | A | 4800 |  |  | 2015-04-09 | 2015-04-13 | 2015-04-02 | 2015-04-15 | 2015-05-04 | NA | NA | NA | 2015-05-28 |  | 2016-05-28 | Jahongir Gafurov
12 | Disbursement Consultant | AED/PMU/IC/2015-05 | P | 13300 | IC | Post | 2015-03-11 | 2015-03-18 | 2015-03-21 | 2015-04-04 | 2015-05-06 | NA | NA | NA | 2015-06-05 | 2016-06-13 | 2016-06-13 |  |  | ongoing/действующий
|  |  | A | 8400 |  |  | 2015-04-09 | 2015-04-13 | 2015-04-02 | 2015-04-15 | 2015-05-06 | NA | NA | NA | 2015-06-01 |  | 2016-06-01 | Nazira Abdullaeva
13 | Field Officer in Sughd Oblast | AED/PMU/IC/2015-10 | P | 15200 | IC | Post | 2015-05-25 | 2015-06-01 | 2015-06-02 | 2015-06-28 | 2015-07-10 | NA | NA | NA | 2015-09-01 | 2016-08-24 | 2016-09-01 |  |  | ongoing/действующий
|  |  | A | 9600 |  |  | 2015-06-25 | 2015-07-03 | 2015-07-08 | 2015-07-27 | 2015-08-05 | NA | NA | NA | 2015-09-01 | 2016-08-24 | 2016-09-01 | Kahhor Ochilov
14 | Field Officer in RRS | AED/PMU/IC/2015-11 | P | 15200 | IC | Post | 2015-05-25 | 2015-06-01 | 2015-06-02 | 2015-06-28 | 2015-07-10 | NA | NA | NA | 2015-09-01 | 2016-08-24 | 2016-09-01 |  |  | ongoing/действующий
|  |  | A | 9600 |  |  | 2015-06-25 | 2015-07-03 | 2015-07-08 | 2015-07-27 | 2015-08-05 | NA | NA | NA | 2015-09-01 | 2016-08-24 | 2016-09-01 | Tagoibek Hasanov
15 | Field Officer in Khatlon | AED/PMU/IC/2015-12 | P | 15200 | IC | Post | 2015-05-25 | 2015-06-01 | 2015-06-02 | 2015-06-28 | 2015-07-10 | NA | NA | NA | 2015-09-01 | 2016-08-24 | 2016-09-01 |  |  | ongoing/действующий
|  |  | A | 9600 |  |  | 2015-06-25 | 2015-07-03 | 2015-07-08 | 2015-07-27 | 2015-08-05 | NA | NA | NA | 2015-09-01 | 2016-08-24 | 2016-09-01 | Alizoda Zafari Ahmadjon
16 | Administrator Consultant | AED/PMU/IC/2015-07 | P | 9500 | IC | Post | 2015-03-20 | 2015-03-27 | 2015-03-30 | 2015-04-13 | 2015-05-06 | NA | NA | NA | 2015-06-01 | 2016-04-23 | 2015-06-01 |  |  | ongoing/действующий
|  |  | A | 9500 |  |  | 2015-04-09 | 2015-04-13 | 2015-04-02 | 2015-04-15 | 2015-05-06 | NA | NA | NA | 2015-06-01 |  | 2016-12-31 | Hasan Abdulakov | Amendment #1 valued at 8000 USD was signed on 01 September 2015
17 | Social Issues Consultant | AED/PMU/IC/2015-14 | P | 13600 | IC | Post | 2015-05-26 | 2015-06-02 | 2015-06-05 | 2015-06-19 | 2015-06-20 | NA | NA | NA | 2015-07-15 | 2016-07-08 | 2016-07-08 |  |  | ongoing/действующий
|  |  | A | 9600 |  |  | 2015-05-27 | 2015-06-04 | 2015-06-25 | 2015-07-13 | 2015-07-30 | NA | NA | NA | 2015-08-03 |  | 2016-08-03 | Abduhalim Karimov
18 | Training Coordinator | AED/PMU/IC/2016-02 | P | 9000 | IC | Post | 2016-01-03 | 2016-01-17 | 2016-01-01 | 2016-01-29 | 2016-02-06 | NA | NA | NA | 2016-03-05 |  | 2016-12-31 |  |  | ongoing/действующий
|  |  | A |  |  |  | 2015-11-24 | 2015-12-29 | 2016-01-07 | 2016-01-25 | 2016-03-30 | 2016-04-04 | NA | NA | 2016-04-22 |  | 2016-12-31 | Melikov Kurbonali
19 | Institutional Development Consultant | AED/PMU/SSS/2016-01 | P | 9000 | SSS | Prior | 2016-02-05 | 2016-02-15 | NA | NA | NA | NA | NA | NA | 2016-03-13 | NA | 2016-12-31 |  |  | ongoing/действующий
|  |  | A | 10800 |  |  | 2016-03-24 | 2016-03-31 | NA | NA | NA | NA | NA | NA | 2016-03-15 |  | 2016-12-31 | Nosirjon Sattorov | The WB provided retro-active NOB. Parttime contract.
20 | VC Consultant on fruit and vegetables | AED/PMU/IC/2016-03 | P | 9000 | IC | Post | 2016-06-01 | 2016-04-10 | 2016-04-14 | 2016-05-10 | 2016-05-16 | 2016-05-26 | 2016-07-01 | 2016-06-10 | 2016-06-16 | 2016-03-13 | 2016-12-31 |  |  | идет процесс отбора
|  |  | A |  |  |  | 2015-07-23: 2016-03-24; 2015-07-24: 2016-04-12; 2016-01-07: 2016-04-21; 2016-01-29: 2016-05-30
21 | VC Consultant on fruit and vegetables | AED/PMU/IC/2016-06 | P | 9000 | SSS | Prior | 2016-06-01 | 2016-04-10 | 2016-04-14 | 2016-05-10 | 2016-05-16 | 2016-05-26 | 2016-07-01 | 2016-06-10 | 2016-06-16 | 2016-03-13 | 2016-12-31 |  |  | идет процесс отбора
|  |  | A |  |  |  | 2015-07-23: 2016-03-24; 2015-07-24: 2016-04-12; 2016-01-07: 2016-04-21; 2016-01-29: 2016-05-30
22 | Translator Consultant | AED/PMU/IC/2016-04 | P | 7200 | IC | Post | 2016-04-01 | 2016-04-13 | 2016-04-20 | 2016-05-10 | NA | NA | NA | NA | 2016-06-10 | 2016-05-13 | 2016-12-31 |  |  | идет процесс отбора
|  |  | A |  |  |  | 2015-07-23: 2016-04-12; 2015-07-24: 2016-04-13; 2016-01-07: 2016-04-20; 2016-01-29: 2016-05-23
23 | Social Issues Consultant | AED/PMU/IC/2016-05 | P | 6400 | IC | Post | 2016-04-01 | 2016-04-13 | 2016-04-20 | 2016-05-10 | NA | NA | NA | NA | 2016-06-01 | 2016-07-08 | 2016-12-31 |  |  | идет процесс отбора
|  |  | A |  |  |  | 2015-07-23: 2016-04-12; 2015-07-24: 2016-04-13; 2016-01-07: 2016-04-20; 2016-01-29: 2016-05-16
Formulas:
Date of WB's no objection = [Дата отправки ППП (включая ТЗ) ВБ]+7

## Goods
Agriculture Commercialization Project (ACP)
PROCUREMENT PLAN - GOODS - FOR PERIOD MARCH 2013, DECEMBER 31, 2016
(Date of PP: 22 JUNE 2015; Update No.3; Date of WB NOL: _____)
(Дата ПЗ: 15 декабря 2015 г.; Обновление №3; Дата одобрения ВБ: ______2016 г.)
# | Description | Ref. # | Total Bid Est. ('000 US$) * | Selection method | WB Review (Prior/Post) | Plan/ Actual | Date of Draft BD (specification) to WB | Date of WB's no objection to BD | Date of invitation to Bids | Date of bid opening/ Quotation Submission | Bid Evaluation Report | Date of WB NOB for ER | Contract Signing Date | Contract Completion Date | Supplier | Comments
№ | Описание контракта | № контракта | Бюджет ('000 US$) * | Метод закупки | Обзор Банка (предваритель-ный / последующий) | План/ факт | Дата отправки проекта ТД (специфика-ции) ВБ | Дата одобрения ВБ на ТД | Дата объявления | Дата вскрытия/ Подача котировок | Оценочный отчет | Дата одобрения ВБ на ОО | Дата подписания контракта | Дата завершения контракта | Поставщик | Комментарий
1 | Procurement of office equipment (for AED PMU, regional offices) | ACP/PMU/G/SH/2015-03 | 45000 | SH | Prior | P | 2015-06-08 | 2015-06-22 | 2015-06-25 | 2015-07-09 | 2015-07-23 | 2015-08-02 | 2015-08-05 | 2015-09-16 | LLC "Parviz and K" | Completed
|  |  | 53098 |  |  | A | 2015-07-07 | 2015-07-13 | 2015-07-16 | 2015-07-31 | 2015-08-21 | 2015-08-24 | 2015-08-28 | 2015-10-08
2 | Procurement of office furniture (for AED PMU, regional offices) | ACP/PMU/G/SH/2015-04 | 30000 | SH | Post | P | 2015-06-15 | 2015-06-29 | 2015-07-02 | 2015-07-16 | 2015-07-30 | 2015-08-09 | 2015-08-12 | 2015-09-23 | LLC "Sorbon Service Prokat" | Completed
|  |  | 29796.9713 |  |  | A | NA | NA | 2015-07-23 | 2015-08-06 | NA | NA | 2015-08-10 | 2015-10-10
3 | Procurement of vehicles (for AED PMU, MOF PMU, regional offices) | ACP/PMU/G/NCB/2015-01 | 214000 | NCB | Prior | P | 2015-07-01 | 2015-07-15 | 2015-07-18 | 2015-08-15 | 2015-09-12 | 2015-09-22 | 2015-09-25 | 2015-11-24 | LLC "BPM" | Ongoing. Контракт заключен на общую сумму 1359300 TJS . На данный момент оплачено 1223370 TJS (163514,06USD), 90% контрактной стоимости.
|  |  | 203942.9266 |  |  | A | 2015-09-15 | 2015-09-18 | 2015-09-23 | 2015-10-22 | 2015-11-05 | 2015-11-18 | 2015-11-20 | 2016-02-28
4 | Procurement of equipment for TAU | ACP/PMU/G/SH/2016-01 | 40000 | SH | Post | P | 2016-09-15 | 2016-09-25 | 2016-10-15 | 2016-11-14 | 2016-11-28 | 2016-11-29 | 2016-12-19 | 2017-02-27 |  | This procurement (items, quantity etc.) to be guided by international partners (western college and university)
A
5 | Procurement of equipment for Agrarian colleges | ACP/PMU/G/SH/2016-02 | 90000 | SH | Post | P | 2016-09-15 | 2016-09-25 | 2016-10-15 | 2016-11-14 | 2016-11-28 | 2016-11-29 | 2016-12-19 | 2017-02-27 |  | This procurement (items, quantity etc.) to be guided by international partners (western college and university)
A
6 | Procurement of equipment for TAJSTAT | AED/PMU/G/SH/2016-03 | 30000 | SH | Post | P | 2016-03-15 | 2016-03-29 | 2016-04-01 | 2016-04-15 | 2016-04-29 | 2016-05-09 | 2016-05-12 | 2016-06-23 |  | Planned procurement of tablets, server, notebooks, UPS for TAJSTAT
[6 empty] | A | 2016-05-05 | 2016-05-06
7 | Procurement of office equipment (for MOF PMU) | ACP/PMU/G/SH/2015-01 | 21000 | SH | Prior | P | 2015-06-08 | 2015-06-22 | 2015-06-25 | 2015-07-09 | 2015-07-23 | 2015-08-02 | 2015-08-05 | 2015-09-16 | A-Khaem LLC | Completed
|  |  | 21035 |  |  | A | 2015-10-23 | 2015-10-23 | 2015-10-24 | 2015-11-09 | 2015-11-17 | 2015-12-15 | 2015-12-16 | 2016-01-05
8 | Procurement of office furniture (for MOF PMU) | ACP/PMU/G/SH/2015-02 | 28000 | SH | Post | P | 2015-06-08 | 2015-06-22 | 2015-06-25 | 2015-07-09 | 2015-07-23 | 2015-08-02 | 2015-08-05 | 2015-09-16 | PA Imperia LLC | Completed
|  |  | 26381.4255 |  |  | A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-07-23 | 2015-09-18
Formulas:
Date of WB's no objection to BD = [Date of Draft BD (specification) to WB]+14
Date of invitation to Bids = [Date of WB's no objection to BD]+3
Дата вскрытия/ Подача котировок = [Date of invitation to Bids]+14
Bid Evaluation Report = [Дата вскрытия/ Подача котировок]+14
Date of WB NOB for ER = [Bid Evaluation Report]+10
Contract Signing Date = [Date of WB NOB for ER]+3
Contract Completion Date = [Contract Signing Date]+42

## Works
TAJIKISTAN
Agriculture Commercialization Project (ACP)
PROCUREMENT PLAN - WORKS - FOR PERIOD MARCH 2013, DECEMBER 31, 2016
(Date of PP: 22 JUNE 2015; Update No.3; Date of WB NOL: _____)
(Дата ПЗ: 15 декабря 2015 г.; Обновление №3; Дата одобрения ВБ: ______2016 г.)
# | Description | Ref. # | BASIC DATA | Selection method | Total Bid Est. ('000 US$) * | WB Review (Prior/Post) | Plan/ Actual | Date of Draft BD to WB | Date of WB's no objection to BD | Date of invitation to Bids | Date of bid opening/ Quotation Submission | Bid Evaluation Report | Date of WB NOB for ER | WB's no objection to Draft Contract | Contract Signing Date | Contract Completion Date | Supplier | Comments
№ | Описание контракта | № контракта | Isuue # of Invitation for Bds | Метод закупки | Бюджет ('000 US$) * | Обзор Банка (предваритель-ный / последующий) | План/ факт | Дата отправки проекта ТД ВБ | Дата одобрения ВБ на ТД | Дата объявления | Дата вскрытия/ Подача котировок | Оценочный отчет | Дата одобрения ВБ на ОО | Дата одобрение банка на проект контракта | Дата подписания контракта | Дата завершения контракта | Подрядчик | Комментарий
1 | Office renovation (for AED PMU Dushanbe office ) | ACP/PMU/W/SH/2015-01 |  | SH | 25000 | Prior | P | 2015-07-01 | 2015-07-15 | 2015-07-18 | 2015-08-01 | 2015-08-15 | 2015-08-25 | 2015-08-28 | 2015-08-31 | 2015-10-30 | LLC "Mizrob" | Completed
[5 empty] | 23580 |  | A | 2015-07-23 | 2015-07-25 | 2015-07-28 | 2015-08-07 | 2016-08-12 | 2015-08-12 | 2015-08-12 | 2015-08-13 | 2015-09-28
2 | Premises renovation in Bokhtar Agrarian college | ACP/PMU/W/SH/2016-03 |  | SH | 20000 | Post | P | 2016-06-01 | 2016-06-11 | 2016-06-14 | 2016-06-28 | 2016-07-12 | 2016-07-19 | 2016-07-29 | 2016-08-01 | 2016-11-09 |  | This procurement to be guided by international partner (western college)
A
3 | Premises renovation in Mastcho Agrarian college | ACP/PMU/W/SH/2016-04 |  | SH | 20000 | Post | P | 2016-06-01 | 2016-06-11 | 2016-06-14 | 2016-06-28 | 2016-07-12 | 2016-07-19 | 2016-07-29 | 2016-08-01 | 2016-11-09 |  | This procurement to be guided by international partner (western college)
A
4 | Office renovation (for AED PMU Dushanbe office new building ) | ACP/PMU/W/DC/2016-01 |  | DC | 18000 | Prior | P | NA | NA | NA | NA | NA | NA | NA | 2016-05-10 | 2016-07-01
A
5 | MOF PIU office renovation | ACP/PMU/W/SH/2015-03 |  | SH | 12000 | Post | P | 2016-05-01 | 2016-05-15 | 2016-05-18 | 2016-06-01 | 2016-06-15 | 2016-06-25 | 2016-06-28 | 2016-07-01 | 2016-08-30
A
Formulas:
Date of WB's no objection to BD = [Date of Draft BD to WB]+14
Date of invitation to Bids = [Date of WB's no objection to BD]+3
Дата вскрытия/ Подача котировок = [Date of invitation to Bids]+14
Bid Evaluation Report = [Дата вскрытия/ Подача котировок]+14
Date of WB NOB for ER = [Bid Evaluation Report]+10
WB's no objection to Draft Contract = [Date of WB NOB for ER]+3
Contract Signing Date = [WB's no objection to Draft Contract]+3
Contract Completion Date = [Contract Signing Date]+60

## QCBS_CQS
TAJIKISTAN
Agriculture Commercialization Project (ACP)
PROCUREMENT PLAN - CONSULTANT SERVICES (QCBS,LCS,CQS) - FOR PERIOD MARCH 2013, DECEMBER 31, 2016
(Date of PP: 22 JUNE 2015; Update No.3; Date of WB NOL: _____)
(Дата ПЗ: 15 декабря 2015 г.; Обновление №3; Дата одобрения ВБ: ______2016 г.)
# | Description | Ref. No. | Selection method | Estimated cost ('000 US$) | Review by the Bank | Plan/Actual | Date of sending TOR to WB | WB's No TOR | RFP Issued | Date of Proposal Submission | Date of sending Short List ER | WB's no objection to Short List ER | Date of sending Technical ER | WB's no objection to Technical ER | Combined technical & financial ER | Draft Contract | WB's no objection to Draft Contract | Contract Signature Date | Contract Completion Date | Comments | Status
№п/п | Описание контракта | №контракта | Метод закупки | Бюджет ('000 US$) | Обзор Банка (предваритель-ный / последующий) | План/факт | Дата отправки ТЗ ВБ | Одобрение ВБ на ТЗ | Запрос на подачу предложений | Дата подачи предложений | Оценочный отчет | Дата одобрения банка на ОО | Оценочный отчет | Дата одобрения банка на ОО | Итегриро-ванный техни-ческий и финансовый ОО | Проект контракта | Дата одобрение банка на проект контракта | Дата подписания контракта | Дата завершения контракта | Комментарии | Статус
1 | Baseline survey consultancy (Local consultant company or NGO) | AED/PMU/CQS/2015-01 | CQS | 65000 | Prior | P | 2015-11-17 | 2015-11-17 | 2015-10-23 | 2015-11-23 | 2015-11-30 | 2016-02-07 | 2016-02-14 | 2016-02-21 | 2016-02-28 | 2016-03-06 | 2016-03-13 | 2016-03-20 | 2016-05-29 | Ждем одобрение банка на проект к-та | Ongoing
[6 empty] | A | 2015-11-17 | 2015-11-17 | 2015-10-23 | 2015-11-23 | 2015-12-09 | 2016-02-24 | 2016-03-16 | 2016-03-31 | NA | 2016-05-05
2 | Grievance Redress Mechanism Development | AED/PMU/CQS/2015-02 | CQS | 94500 | Post | P | 2015-07-25 | 2015-08-08 | 2015-08-11 | 2015-08-25 | 2016-03-01 | 2016-03-11 | 2016-03-21 | 2016-03-31 | 2016-04-10 | 2016-04-20 | 2016-04-30 | 2016-05-10 | 2016-07-01 | контракт подписан с ООО "Ориён" | Ongoing
|  |  |  | 93829.4195 |  | A | 2015-11-23 | 2015-11-24 | 2015-11-26 | 2015-12-08 | NA | NA | NA | NA | NA | NA | NA | 2016-04-18 | 2017-01-31
3 | International VCD Service Provider | AED/PMU/QCBS/2015-01 | QCBS | 1440000 | Prior | P | 2015-08-21 | 2015-09-04 | 2015-09-07 | 2015-09-21 | 2015-09-28 | 2016-02-20 | 2016-03-18 | 2016-03-25 | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-22 |  | ОО и ППП отправлен на одобрение банка | Ongoing
[6 empty] | A | 2015-10-20 | 2015-10-20 | 2015-08-24 | 2015-09-15 | 2016-05-06
4 | National VCD-SP | AED/PMU/QCBS/2015-02 | QCBS | 300000 | Prior | P | 2016-08-01 | 2016-08-08 | 2016-08-11 | 2016-09-01 | 2016-09-15 | 2016-09-29 | 2016-10-09 | 2016-10-19 | 2016-10-29 | 2016-11-08 | 2016-11-18 | 2016-11-28
A
5 | Training Service Provider in Khatlon | AED/PMU/CQS/2015-03 | CQS | 175000 | Prior | P | 2016-08-01 | 2016-08-08 | 2016-08-11 | 2016-09-01 | 2016-09-15 | 2016-09-29 | 2016-10-09 | 2016-10-19 | 2016-10-29 | 2016-11-08 | 2016-11-18 | 2016-11-28
A
6 | Training SP in Sughd | AED/PMU/CQS/2015-04 | CQS | 150000 | Prior | P | 2016-08-01 | 2016-08-08 | 2016-08-11 | 2016-09-01 | 2016-09-15 | 2016-09-29 | 2016-10-09 | 2016-10-19 | 2016-10-29 | 2016-11-08 | 2016-11-18 | 2016-11-28
A
7 | Training SP in RRS | AED/PMU/CQS/2015-05 | CQS | 150000 | Prior | P | 2016-08-01 | 2016-08-08 | 2016-08-11 | 2016-09-01 | 2016-09-15 | 2016-09-29 | 2016-10-09 | 2016-10-19 | 2016-10-29 | 2016-11-08 | 2016-11-18 | 2016-11-28
A
8 | Consulting services on alignment of the current regulatory environment for fertilizer and agricultural chemicals with international standards | AED/PMU/CQS/2016-01 | CQS | 20000 | Post | P | 2016-09-01 | 2016-09-08 | 2016-09-11 | 2016-10-02 | 2016-10-16 | 2016-10-30 | 2016-11-09 | 2016-11-19 | 2016-11-29 | 2016-12-09 | 2016-12-19 | 2016-12-29 | 2017-03-09
A
9 | Consulting services on impact of current tax policy on farm input use | AED/PMU/CQS/2016-02 | CQS | 20000 | Post | P | 2016-11-01 | 2016-11-08 | 2016-11-11 | 2016-12-02 | 2016-12-16 | 2016-12-30 | 2017-01-09 | 2017-01-19 | 2017-01-29 | 2017-02-08 | 2017-02-18 | 2017-02-28 | 2017-05-09
A
10 | Design of a MIS database and establishment of the public-private partnership for/with TAJSTAT | AED/PMU/CQS/2016-03 | CQS | 101000 | Post | P | 2016-06-01 | 2016-06-08 | 2016-06-11 | 2016-07-02 | 2016-07-16 | 2016-07-30 | 2016-08-09 | 2016-08-19 | 2016-08-29 | 2016-09-08 | 2016-09-18 | 2016-09-28
A
11 | Training for TAJSTAT enumerators | AED/PMU/CQS/2016-05 | CQS | 15000 | Post | P | 2016-03-01 | 2016-03-08 | 2016-03-11 | 2016-04-01 | 2016-04-15 | 2016-04-29 | 2016-05-09 | 2016-05-19 | 2016-05-29 | 2016-06-08 | 2016-06-18 | 2016-06-28 | 2016-07-08
A
12 | Technical Advisory Services Service Provider (TASSP) | AED/PMU/QCBS/2016-01 | QCBS | 300000 | Prior | P | 2016-09-01 | 2016-09-08 | 2016-09-11 | 2016-10-02 | 2016-10-16 | 2016-10-30 | 2016-11-09 | 2016-11-19 | 2016-11-29 | 2016-12-09 | 2016-12-19 | 2016-12-29
A
13 | Curriculum Modernization – Tajikistan Agrarian University and Vocational Agricultural Colleges | AED/PMU/CQS/2016-04 | CQS | 228000 | Prior | P | 2016-06-01 | 2016-06-08 | 2016-06-11 | 2016-07-02 | 2016-07-16 | 2016-07-30 | 2016-08-09 | 2016-08-19 | 2016-08-29 | 2016-09-08 | 2016-09-18 | 2016-09-28 |  |  | Ongoing
[6 empty] | A |  | 2016-04-24 | 2016-05-05 | 2016-05-31
14 | Training on integrated production management for apricot | AED/PMU/CQS/2015-06 | CQS | 20000 | Post | P | 2015-11-01 | 2015-11-15 | 2015-11-24 | 2015-11-30 | 2015-12-01 | 2016-01-25 | NA | NA | NA | NA | 2016-02-01 | 2016-02-25 | 2016-04-30 | Заключен контракт с НПО "Зарзамин" | Ongoing
|  |  |  | 12445.8532 |  | A | 2015-11-03 | 2015-11-10 | 2016-01-27 | 2016-02-03 | 2015-12-28 | 2016-01-07 | NA | NA | NA | NA | 2016-02-09 | 2016-02-10 | 2016-04-20
15 | Training on integrated production management for early tomato | AED/PMU/CQS/2016-08 | CQS | 20000 | Post | P | 2016-02-09 | 2016-02-09 | 2016-02-22 | 2016-03-03 | 2016-03-17 | NA | NA | NA | NA | NA | NA | 2016-04-01 | 2016-04-15 | Идет процесс оценки предложения | Ongoing
[6 empty] | A | 2016-02-09 | 2016-02-10
16 | Audit | ACP/PMU/LCS/2016-01 | LCS | 3500 | Prior | P | Hired by the State Committee on Investments as "Block audit"
A
17 | International Consultant (credit lines) | MOF/PMU/IC/2015-11 | IC | 45000 | Prior | P | 2015-06-08 | 2015-06-15 | 2015-06-19 | 2015-07-03 | NA | NA | NA | NA | NA | NA | 2015-07-19 | 2015-07-22 | Sep-15 | Nergui Sandagjav | Amendment #2
|  |  |  | 40445 |  | A | 2015-03-24 | 2015-07-07 | 2015-07-08 | N/A | N/A | N/A | N/A | N/A | 2015-08-18 | 2015-08-18 | 2015-09-25 | 2015-10-04 | 2015-11-26
18 | International Bank training consulting firm | MOF/PMU/CQS/2015-01 | CQS | 120000 | Prior | P | 2015-09-14 | 2015-09-21 | 2015-09-24 | 2015-10-08 | 2015-10-15 | 2015-10-22 | 2015-11-22 | 2015-11-29 | 2015-12-06 | 2015-12-06 | 2015-12-13 | 2015-12-16 | 2017-01-14 | Frankfurt School of Finance and Management | Ongoing
[6 empty] | A | 2015-07-20 | 2015-11-25 | 2015-11-30 | 2015-12-18 | N/A | N/A | N/A | N/A | 2016-01-07 | 2016-01-07 | 2016-04-15 | 2016-04-15 | 2016-12-31
19 | Environment and Social Training | MOF/PMU/CQS/2016-01 | CQS | 30000 | Post | P | 2016-01-25 | 2016-02-01 | 2016-02-04 | 2016-02-18 | 2016-02-08 | 2016-02-15 | NA | NA | NA | NA | 2016-03-19 | 2016-03-22 | 2018-06-20 | ООО "Менеджмент Эдвайзер" | Ongoing
[6 empty] | A | 2015-07-08 | 2015-11-25 | 2015-11-30 | 2015-12-18 | N/A | N/A | N/A | N/A | 2016-01-07 | 2016-01-07 | 2016-03-18 | 2016-03-25 | 2016-12-31
20 | Participating Financial Institution (PFI for trainings) | MOF/PMU/CQS/2015-02 | CQS | 45000 | Post | P | 2015-08-10 | 2015-08-17 | 2015-08-21 | 2015-09-04 | 2015-09-11 | 2015-09-18 | NA | NA | NA | NA | 2015-10-21 | 2015-10-24 | 2016-10-23 | ООО "БДО" | Ongoing
[6 empty] | A | 2015-08-24 | 2015-11-25 | 2015-11-30 | 2015-12-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-03-10 | 2016-12-31
Formulas:
Date of sending Short List ER = [Date of Proposal Submission]+7
Date of sending Technical ER = [WB's no objection to Short List ER]+7
Combined technical & financial ER = [WB's no objection to Technical ER]+7
Draft Contract = [Combined technical & financial ER]+7
WB's no objection to Draft Contract = [Draft Contract]+7
WB's no objection to Draft Contract = [RFP Issued]+30
Contract Completion Date = [Contract Signature Date]+70
WB's No TOR = [Date of sending TOR to WB]+14
RFP Issued = [WB's No TOR]+3
Date of Proposal Submission = [RFP Issued]+14
WB's no objection to Short List ER = [Date of sending Short List ER]+10
WB's no objection to Technical ER = [Date of sending Technical ER]+7
Contract Signature Date = [WB's no objection to Draft Contract]+7