## PP
Procurement Plan
2014-07-17
IDF Grant P132661
Youth Inclusion and Social Accountability Project (YISAP)
Period Covered by this PP: May 2014- Apr 2016
Package No. | Description of Assignment/ Location | No. of Packages/ Consultants | Category | Selection Method | Review | Adverti- | Expected | Contract | Start | Comple-
|  |  | (goods / non-consulting services, |  | by Bank | sement | Proposal/Qut. | Award | Date | tion
|  |  | consulting services) |  | Prior / | for EOI/ITQ | Submission | Date |  | Date
[5 empty] | Post | Date | Date
Component 1: Promoting Youth Involvement in Local Development
1.1 | Action plan grant | 1 | _ | _ | Prior | 03/16/2015 (GM); 07/23/2015 (TTM) | 03/31/2015 (GM); 08/03/2015 (TTM) | 04/13/2015 (GM); 08/17/2015 (TTM) | 04/20/2015 (GM); 08/24/2015 (TTM) | 12/31/2015 (GM); 03/31/2016 (TTM)
1.1.a | Action plan grants | 4 |  |  | Post | 03/16/2015 (GM); 07/23/2015 (TTM) | 03/31/2015 (GM); 08/03/2015 (TTM) | 04/13/2015 (GM); 08/17/2015 (TTM) | 04/20/2015 (GM); 08/24/2015 (TTM) | 12/31/2015 (GM); 03/31/2016 (TTM)
1.2 | Experts fee for Active Citizenship Workshop |  | CS | IC | Post | 2/9/2015 (GM); 06/08/2015 (TTM) | 02/20/2015 (GM); 06/19/2015 (TTM) | 02/27/2015 (GM); 06/26/2015 (TTM) | 03/09/2015 (GM); 07/13/2015 (TTM) | 03/12/2015 (GM); 07/16/2015 (TTM)
1.3 | Printing materials for Youth Outreach Campaign |  | G | SH | Post | 08/18//2014 (GM); 12/22/2014 (TTM) | 08/25/2014 (GM); 12/29//2015 (TTM) | 08/29/2014 (GM); 01/01/2015 (TTM) | 09/01/2014 (GM); 01/05/2015 (TTM) | 10/31/2015 (GM); 02/27/2015 (TTM)
1.4 | “Purchase” of media for Social Media Campaign |  | CS | CQ | Post | 12/15/2014 (GM); 04/13/2015 (TTM) | 12/23/2014 (GM); 04/22/2015 (TTM) | 12/30/2014 (GM); 04/28/2015 (TTM) | 01/05/2015 (GM); 05/04/2015 (TTM) | 02/27/2015 (GM); 06/30/2015 (TTM)
1.5 | Trainer fee for Social Innovation Camp |  | CS | IC | Post | 12/15/2014 (GM); 04/13/2015 (TTM) | 12/26/2014 (GM); 04/24/2015 (TTM) | 01/05/2015 (GM); 05/04/2015 (TTM) | 01/14/2015 (GM); 05/13/2015 (TTM) | 01/16/2015 (GM); 05/15/2015 (TTM)
1.6 | Social Media/IT expert | 1 | CS | IC | Post | 2014-08-08 | 2014-08-08 | 2014-09-08 | 2014-09-08 | 2016-04-01
1.7 | Trainer fee for Capacity Building of Youth Committee/Local Authorities |  | CS | IC | Post | 10/24/2014 (GM); 04/20/2015 (TTM) | 10/24/2014 (GM); 04/20/2015 (TTM) | 11/24/2014 (GM); 05/20/2015 (TTM) | 11/24/2014 (GM); 05/20/2015 (TTM) | 02/27/2015 (GM); 08/28/2015 (TTM)
1.8 | Printing related to Visibility actions/Publicity of Action Plan |  | G | SH | Post | 02/19/2015 (GM); 06/15/2015 (TTM) | 02/19/2015 (GM); 06/15/2015 (TTM) | 04/20/2015 (GM); 08/24/2015 (TTM) | 04/20/2015 (GM); 08/24/2015 (TTM) | 12/31/2015 (GM); 03/31/2016 (TTM)
1.9 | Purchase of media for Visibility actions/Publicity of Action Plan |  | G | SH | Post | 02/19/2015 (GM); 06/15/2015 (TTM) | 02/19/2015 (GM); 06/15/2015 (TTM) | 03/19/2015 (GM); 07/15/2015 (TTM) | 03/19/2015 (GM); 07/15/2015 (TTM)
1.10 | Project Manager - 100% | 1 | CS | IC | Post | 2014-04-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2016-04-01
1.11 | Project Coordinator (1) - 100% | 1 | CS | IC | Post | on the base of need
1.12 | Kakheti Field Coordinator (1) - 100% | 1 | CS | IC | Post | 2014-07-21 | 2014-08-01 | 2014-08-14 | 2014-08-18 | 2016-04-01
1.13 | Field Officer - 100% | 1 | CS | IC | Post |  |  | 2014-06-16 | 2014-06-15 | 2016-04-29
1.14 | Translator | 1 | CS | IC | Post | throughout project implementation
1.15 | Operational costs directly related to Component 1 (transport costs, accomodation) |  | NA | NA | NA | throughout project implementation
1.16 | Operational costs for trainings, workshops, meetings (expenses for refreshment, rent of venue,...) |  | NA | NA | NA | throughout project implementation
Component 2. Monitoring the Links between Young People's Participation in Social Accountability and Youth Inclusion
2.1 | MoE Expert for Baseline and Final Survey/Evaluation | 1 | CS | IC | Post | 2014-07-10 | 2014-08-04 | 2014-09-10 | 2014-09-10 | 2016-04-29
2.2 | Survey collectors | 9 | CS | AP | Post | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-09-10 | 2016-02-25
2.3 | Operational costs for trainings, workshops, meetings (low value expenses for refreshment, rent of venue, transportation...) |  | NA | NA |  | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-09-10 | 2016-02-25
Component 3. Project Management
3.1 | Country Director (salary & per diem) 15% | 1 | CS | AP | Post | 2014-06-04 | 2014-06-01 | 2014-08-04 | 2014-09-10 | 2016-04-29
3.2 | Project audit | 1 | CS | LCS | Post | 2015-11-01 | 2015-12-01 | 2016-08-01 | 2016-08-01 | 2016-10-01
3.3 | Finance Consultant | 1 | CS | IC | Prior | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2016-04-29
3.4 | Procurement Consultant | 1 | CS | IC | Post | 2014-06-01 | 2014-06-01 | 2014-06-01 | 2014-06-01 | 2016-04-29
3.5. | IT assets for staff (notebook, printer, data projector, ...) | 5 | G | SH | Post | 2014-07-01 | 2014-07-01 | 2014-07-01 | 2014-07-01 | 2014-07-01
3.6 | Operational costs (office costs, transportation, accomodation, salary of supporting staff from Georgia and HQ, etc.) |  | NA | NA | NA | throughout project implementation
Grand Total:
Note on D9: horjan01: This part wasnt in WB template - to make it more simple I will skip it alsoin excel version
Note on F23: horjan01: in case of goods will be SH, company CQ, person IC
Note on C24: horjan01: inles mentioned in proposal
Note on C25: horjan01: unless mentioned in proposal
Note on C27: horjan01: unless mentioned in proposal
Note on C29: horjan01: PIN procurement rules will be used
Note on C30: horjan01: PIN procurement rules will be used
Note on D33: horjan01: max.
Note on C36: horjan01: unless mentioned in proposal
Note on C41: horjan01: PIN procurement rules will be used