## Rural goods
| Procurement of Goods | [9 empty] | 16.91
| Organisation: | Oromia Water Resources Bureau | [15 empty] | 17.3499
| Project/Programme: | MDTF (IDA/DFID) | [6 empty] | REVISED!!
Loan #:
S. No | Description* |  | BASIC DATA |  | Procurement Method | Pre-or Post Qual. | Prior or Post Review | Plan vs. Actual | Draft Bid Documents, including specs and quantities, draft SPN |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  | Date Contract Signature |  | Contract Implementation
|  | Package Number | Lot Number | Estimated Amount in US $ |  |  |  |  | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway National Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award |  | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
List of Contracts
A | Regional Level
1 | Procurement of 38 Generators | OWRB/EME/ MDTF/01/1 /2010 |  | 441000 | NCB | Post | post | Plan | 2010-08-20 | NA | NA | 2010-09-17 | 2010-10-17 | 2010-11-01 | NA | Plan |  | 2010-09-15 | 2010-11-27 | NA | 2011-04-05 | 2011-04-15
[8 empty] | Actual | 2010-09-10 |  |  | 2010-10-31 | 2010-12-29 | 2011-01-17 |  | Actual |  | 2011-09-15 | 2011-10-31 | NA | 2012-02-28 | 2012-03-29
2 | Procurement of 41 Submersible/Surface Pumps | OWRB/EME/ MDTF/02/ 1/2010 |  | 487876.9959 | NCB | Post | post | Plan | 2010-08-20 | NA | NA | 2010-09-17 | 2010-10-17 | 2010-11-01 | NA | Plan |  | 2010-11-17 | 2010-11-27 | NA | 2011-04-05 | 2011-04-15
[8 empty] | Actual | 2010-09-10 |  |  | 2010-10-31 | 2010-12-29 | 2011-01-17 |  | Actual | 319092.0409 | 2011-01-27 | 2011-02-05 | NA | 2011-08-10 | 2011-09-15
3 | Procurement of 34 Generators | OWRB/EME/ MDTF/01/ 2010-Lot 1 |  | 431126.4042 | NCB | Post | post | Plan | 2011-04-01 | NA | NA | 2011-04-16 | 2011-05-21 | 2011-05-31 | NA | Plan |  | 2010-11-17 | 2010-11-27 | NA | 2011-04-05 | 2011-04-15
[8 empty] | Rev. Plan | [7 empty] | Rev.plan |  |  | 2012-02-15 | NA | 2012-05-15 | 2012-06-14
[8 empty] | Revised | [11 empty] | NA | 2012-10-11 | 2012-10-31
[8 empty] | Actual | 2011-10-12 | NA | NA | 2011-10-15 | 2011-11-22 | 2011-12-27 |  | Actual | 477435.0284 | 2012-01-24 | 2012-05-30 |  | 2012-09-27 | 2012-10-07
4 | Procurement of 40 Submersible/Surface Pumps | OWRB/EME/ MDTF/02/2010- Lot 2 |  | 345823.3189 | NCB | Post | post | Plan | 2011-04-01 | NA | NA | 2011-04-16 | 2011-05-21 | 2011-05-31 | NA | Plan |  | 2010-11-17 | 2010-11-27 | NA | 2011-04-05 | 2011-04-15
[8 empty] | Revised | [12 empty] | 2012-07-19 | 2012-07-29
[8 empty] | Actual | 2011-10-12 |  |  | 2011-10-15 | 2011-11-22 | 2011-12-27 |  | Actual | 312231.7708 | 2012-01-24 | 2012-02-20
5 | Office furnitures and equipments | OWRB/MDTF/ OF/01/ 2010 |  | 13701.034 | NS | Post | post | Plan | 2010-10-01 | NA | NA | 2010-10-16 | 2010-10-26 | 2010-11-01 | NA | Plan |  | 2010-11-15 | 2010-11-17 | NA | 2011-11-24 | 2011-11-25
[8 empty] | Actual | 2011-09-10 |  |  | 2011-09-19 | 2011-09-30 | 2011-10-08 |  | Actual | 13701.034 | 2011-10-15 | 2011-11-18 |  | 2010-12-30 | 2011-01-10
6 | Procurment of surveying equipment (2 total station) | OWRB/MDTF/ SE/03/ 2010 |  | 28176.8185 | NS | Post | post | Plan | 2010-10-01 | NA | NA | 2010-10-16 | 2010-10-26 | 2010-11-01 | NA | Plan |  | 2010-11-15 | 2010-11-17 | NA | 2010-11-24 | 2010-11-25
[8 empty] | Actual | 2010-10-17 |  |  | 2010-10-19 | 2011-11-23 | 2011-12-20 |  | Actual |  | 2011-12-22 | 2011-12-25 |  | 2010-12-30
7 | Office furnitures & equipments | OWRB/MDTF/ OF/02/ 2010 |  | 4554 | NS | Post | post | Plan | 2011-03-01 | NA | NA | 2011-03-15 | 2011-04-15 | 2011-04-25 | NA | Plan |  | 2011-04-27 | 2011-05-07 | NA | 2011-08-06 | 2011-08-10
[8 empty] | Actual | 2011-04-20 |  |  | 2011-05-04 | 2011-06-05 | 2011-06-15 |  | Actual | 4554 | 2011-06-20 | 2011-06-30 |  | 2011-07-26 | 2011-07-28
B | Woreda Level
1 | Pocket GPS (84 units) | OWRB/MDTF/ GPS/07/ 2010 |  | 61596.6884 | NCB | Post | post | Plan | 2010-10-01 | NA | NA | 2010-10-16 | 2010-10-26 | 2010-11-01 | NA | Plan |  | 2010-11-15 | 2010-11-17 | NA | 2010-11-24 | 2010-11-25
[8 empty] | Actual | 2010-10-01 |  |  | 2010-10-19 | 2010-12-19 | 2011-01-20 |  | Actual | 61145.4009 | 2011-04-23 | 2011-04-25 |  | 2011-08-15 | 2011-09-16
2 | Hand Pumps (400) | OWRB/HP/ MDTF/04/ 2010 |  | 340731.17 | NCB | Post | post | Plan | 2011-03-01 | NA | NA | 2011-03-15 | 2011-04-15 | 2011-04-25 | NA | Plan |  | 2011-04-27 | 2011-05-07 | NA | 2011-08-06 | 2011-08-10
[8 empty] | Actual | [5 empty] | 2011-11-04 |  | Actual | 230146.5789 | 2011-11-07 | 2011-11-14 |  | 2012-03-13 | 2012-04-12
3 | Water Qaulity Test Kits (84 units) | OWRB/MDTF/WQTK/06/2010 |  | 149024.246 | NCB | Post | post | Plan | 2010-10-01 | NA | NA | 2010-10-30 | 2010-11-30 | 2010-12-15 | NA | Plan |  | 2011-01-01 | 2011-01-01 | NA | 2011-04-11 | 2011-04-20
[8 empty] | Actual | 2010-10-01 |  |  | 2010-10-19 | 2010-12-19 | 2011-01-20 |  | Actual | 104534.6083 | 2011-04-25 | 2011-04-25 |  | 2011-08-21 | 2011-09-25
4 | Maintenance Tool Kits (Pipe Wrench, Cutter, Treader, …etc) 84 sets | OWRB/MDTF/MTK/05/2010 |  | 248373.7433 | NCB | Post | post | Plan | 2011-07-01 | NA | NA | 2011-07-15 | 2011-08-15 | 2011-08-25 | NA | Plan |  | 2011-08-27 | 2012-02-23 | NA | 2012-04-23 | 2012-05-23
[8 empty] | Revised | [10 empty] | 2012-05-30 |  | 2012-10-11 | 2012-10-31
[8 empty] | Actual | 2011-08-05 |  |  | 2011-10-13 | 2011-11-21 | 2011-12-27 |  | Actual | 97992.4956 | 2012-01-24 | 2012-02-20 |  | 2012-06-19 | 2012-06-29
Formulas:
Contract Implementation = 120+[Date Contract Signature]
Contract Implementation = [Date Contract Signature]+120
Inspection Final Acceptance = 30+[Contract Implementation]
Inspection Final Acceptance = [Contract Implementation]+10
Bid Closing-Opening = [Bidding Period]+38
Date Contract Award = [Date Contract Signature]-([Date Contract Signature, row above]-[Date Contract Award, row above])

## Rural Works
Procurement Plan Works
Country/Organization: Oromia National Rgional State Water, Mineral & Energy Bureau | [16 empty] | 1USD= | 17.3499 | birr
Project/Programmed: IDA-DFID (MDTF) | [12 empty] | REVISED!!!
Loan #:
Description* | Package Number | Basic Data | [5 empty] | Plan vs. Actual | Draft Bid Documents, including specs and quantities, draft SPN |  | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Plan vs. Actual | Contract Finalization |  |  | Contract Implementation
|  | Lot Number | Lump sum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre/Post Qualification | Prior or Post Review |  | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway National Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date |  | Contract Amount in US$ | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
List of Contracts
I. Deep Wells drilling (60 DWs)
A. Completed projects (26 DWs) | [8 empty] | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks |  |  | 1 wk | 1.5-3 wks
Drilling of 6 deep wells (Borena & Guji) | ORWB/MDTF/DW/001/ 2008 |  | BOQ | NCB | 155096.0118 | Post | Post | Plan | 2009-04-08 | 2009-04-16 |  | 2009-04-26 | 2009-06-10 | 2009-07-15 | 2009-07-28 | Plan |  | 2009-07-20 | 2009-07-27 |  | 2009-09-09 | 2009-09-09 |  | 0
[8 empty] | Actual | 2009-02-11 | 2009-02-19 |  | 2009-03-01 | 2009-05-30 | 2009-09-25 | 2009-09-30 | Actual | 96967.37 | 07-Oct-09 | 2009-10-20 |  | 2010-12-20 | 2011-12-20
Drilling of 2 deep wells (East & West Hararge) | ORWB/MDTF/DW/002/ 2008 |  | BOQ | NCB | 51698.6706 | Post | Post | Plan | 2009-04-08 | 2009-04-16 |  | 2009-04-26 | 2009-06-10 | 2009-07-15 | 2009-07-28 | Plan |  | 2009-07-20 | 2009-07-27 |  | 2009-09-09 | 2009-09-09
[8 empty] | Actual | 2009-02-11 | 2009-02-19 |  | 2009-03-01 | 2009-05-30 | 2009-09-25 | 2009-09-30 | Actual | 52904.2819 | 7-Oct-10 | 2009-10-20 |  | 2011-01-16 | 2012-01-16
Drilling of 5 deep wells (S.W Showa & E/Wollega) | ORWB/MDTF/RDW/001/ 2009 |  | BOQ | NCB | 103397.3412 | Post | Post | Plan | 2009-11-02 | 2009-11-10 |  | 2009-11-20 | 2009-12-21 | 2010-01-01 | 2010-01-14 | Plan |  | 2010-01-08 | 2010-01-15 |  | 2010-04-15 | 2011-04-15
[8 empty] | Actual | 2009-11-25 | 2009-12-03 |  | 2009-12-13 | 2010-01-13 | 2010-01-15 | 2010-02-01 | Actual | 75441.7605 | 2010-02-08 | 2010-02-18 |  | 2010-06-18 | 2011-06-18
Drilling of 4 Deep wells (Arsi & Bale) | ORWB/MDTF/DW/001/ 2008 |  | BOQ | NCB | 77548.0059 | Post | Post | Plan | 2009-03-15 | 2009-03-23 |  | 2009-04-02 | 2009-05-17 | 2009-06-21 | 2009-07-04 | Plan |  | 2009-07-20 | 2009-07-27 |  | 2009-09-09 | 2010-09-09
[8 empty] | Actual | 2009-02-11 | 2009-02-19 |  | 2009-03-01 | 2009-05-30 | 2009-09-25 | 2009-09-30 | Actual | 111447.8758 | 7-Oct-10 | 2010-10-17 |  | 2011-02-14 | 2012-02-14
Drilling of one deep well in Akaki (Abasamu'el) | ORWB/MDTF/DW/001/ 2007 |  | BOQ | NCB | 25849.3353 | Post | Post | Plan | 2009-03-15 | 2009-03-23 |  | 2009-04-02 | 2009-05-17 | 2009-06-21 | 2009-07-04 | Plan |  | 2009-06-26 | 2009-07-03 |  | 2009-08-02 | 2010-08-02
[8 empty] | Actual | 2009-02-16 | 2009-02-24 |  | 2009-03-06 | 2009-04-05 | 2009-04-30 | 2009-05-12 | Actual | 25327.03 | 2009-05-19 | 2009-05-29 |  | 2009-09-26 | 2010-09-26
Drilling of 3 deep wells (W/Shoa, Nono & Chelia) | OWRB/MDTF/DW/04/1/ 2010 |  | BOQ | NCB | 48415.2646 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2010-07-20 | 2010-07-25 |  | 2010-08-26 | 2010-10-26 | 2010-11-10 | 2010-11-15 | Actual | 769440.7601 | 6-Dec-10 | 2010-12-31 |  | 2011-01-10 | 2012-01-10
Drilling of 2 deep wells (Guji) | OWRB/MDTF/DW/06/1/2/ 2010 |  | BOQ | NCB | 48415.2646 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-05-05 | 2011-05-27 | 2011-08-01 | 2011-08-10 | Actual | 41163.6378 | 27-May-11 | 22-Sep-11 |  | 2011-12-08 | 2011-12-08
Drilling of 1 deep well ( W/ Wellega, Kiltu Kara) | OWRB/MDTF/DW/01/1/2010 |  | BOQ | NCB | 24207.6323 | Post | Post | Plan | 2010-10-30 | 2010-11-15 |  | 2010-11-25 | 2010-12-25 | 2011-01-10 | 2011-01-25 | Plan |  | 2011-01-30 | 2011-02-07 |  | 2011-08-07 | 2012-03-01
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-12 | 2011-03-14 | 2011-03-30 | 2011-05-16 | Actual | 32661.9558 | 23-May-11 | 28-Jun-11 |  | 2011-09-09 | 2012-09-08
Drilling of 2 deep wells (Jimma & West Wellega) | OWRB/MDTF/DW&SW/ 01/ 2008 |  | BOQ | NCB | 48415.2646 | Post | Post | Plan | 2009-04-08 | 2009-04-16 |  | 2009-04-26 | 2009-06-10 | 2009-07-15 | 2009-07-28 | Plan |  | 2009-07-20 | 2009-07-27 |  | 2009-09-15 | 2010-09-15
[8 empty] | Actual | 2009-02-11 | 2009-02-19 |  | 2009-03-01 | 2009-03-30 | 2009-05-05 | 2009-04-30 | Actual | 20012.1038 | 07-May-09 | 2009-06-09 |  | 2011-05-12 | 2012-05-11
B. Ongoing projects (30 DWs)
Drilling of 8 deep wells (Ilu Aba Bora & Jima) | OWRB/MDTF/DW/02/ 2/2010 |  | BOQ | NCB | 145245.7939 | Post | Post | Plan | 2010-10-30 | 2010-11-15 |  | 2010-11-25 | 2010-12-25 | 2011-01-10 | Jan25,11 | Plan |  | 2011-01-30 | 2011-02-07 |  | 2011-08-07 | 2012-08-06
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-13 | 2011-03-14 | 2011-03-30 | 2011-03-31 | Actual | 195220.6257 | 23-May-11 | 30-Jun-11 |  | 2011-10-28 | 2012-10-27
Drilling of 8 deep wells (Borena) | OWRB/MDTF/DW/06/1/1/ 2010 |  | BOQ | NCB | 193661.0586 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-04-06 | 2012-04-05
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-05-05 | 2011-05-27 | 2011-08-01 | 2011-08-10 | Actual | 207007.1585 | 15-Aug-11 | 01-Sep-11 |  | 2011-06-20 | 2012-06-19
Drilling of 10 deep wells (N/Shoa, W/Shoa, SW/Shoa) | OWRB/MDTF/DW/04/2/ 2010 |  | BOQ | NCB | 217868.6909 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-12 | 2011-03-14 | 2011-03-30 | 2011-03-31 | Actual | 375646.6752 | 23-May-11 | 28-Jun-11 |  | 2011-10-26 | 2012-10-25
Drilling of 4 deep ( & shallow) wells (W/Hararge & E/Hararge) | OWRB/MDTF/DW/02/3/ 2010 |  | BOQ | NCB | 96830.5293 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-08-07 | 2012-08-06
[8 empty] | Actual | 20-Jan-11 | 25-Jan-11 |  | 01-Dec.11 | 28-Dec-11 | 2012-01-05 | 2012-01-08 | Actual | 207845.2902 | 03-Feb-12 | 2012-02-13 |  | 2012-06-12 | 2013-06-12
C. New (4DW)
Drilling of 4 deep wells | OWRB/MDTF/DW/01/2012 |  | BOQ | NCB | 96830.5293 | Post | Post | Plan | 2012-04-15 | 2012-04-16 |  | 2012-04-20 | 2012-05-25 | 2012-06-01 | 2012-06-02 | Plan |  | 2012-06-07 | 2012-06-17 |  | 2012-10-15 | 2013-10-15
[8 empty] | Revised | 20-Jan-11 | 25-Jan-11 |  | 2012-08-10 | 2012-09-09 | 2012-09-29 | 2012-10-04 |  |  | 2012-10-11 | 2012-10-21 |  | 2013-01-19 | 2014-01-19
Actual
II. Shallow Wells drilling & construction (270 SHW)
A. Completed projects (163 SHWs)
Drilling of 10 Shallow wells (IluAba Bora, Jima) | OWRB/MDTF/SHW/01/1/ 2010 |  | BOQ | NCB | 44957.0315 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-10-05 | 2010-11-05 | 2010-11-15 | 2010-12-05 | Plan |  | 2010-12-10 | 2010-12-20 |  | 2011-06-20 | 2012-06-19
[8 empty] | Actual | 2010-07-20 | 2010-07-25 |  | 2010-08-26 | 2010-10-26 | 2010-11-10 | 2010-11-15 | Actual | 53916.026 | 2010-12-06 | 2010-12-17 |  | 2011-10-11 | 2012-10-10
Drilling of 12 Shallow wells (Guji; Odo Shakiso) | OWRB/MDTF/SHW/03/2/2010 |  | BOQ | NCB | 69128.5081 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-10-05 | 2010-11-05 | 2010-11-15 | 2010-12-05 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2010-07-20 | 2010-07-25 |  | 2010-08-26 | 2010-10-26 | 2010-11-10 | 2010-11-15 | Actual | 69712.275 | 2010-12-06 | 2010-12-29 |  | 2011-07-15 | 2012-07-14
Drilling of 9 Shallow wells (Guji; Girja, Dama) | OWRB/MDTF/SHW/03/4 2010 |  | BOQ | NCB | 40461.3283 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-10-05 | 2010-11-05 | 2010-11-15 | 2010-12-05 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2010-07-20 | 2010-07-25 |  | 2010-08-26 | 2010-10-26 | 2010-11-10 | 2010-11-15 | Actual | 58584.3002 | 2010-12-06 | 2010-12-31 |  | 2011-10-21 | 2012-10-20
Drilling of 7 shallow wells (Bako & Mida Kegn) | OWRB/MDTF/DW&SW/01/2008 |  | BOQ | NCB | 35672 | Post | Post | Plan | 2009-03-15 | 2009-03-23 |  | 2009-04-02 | 2009-05-17 | 2009-06-21 | 2009-06-22 | Plan |  | 2009-07-20 | 2009-07-27 |  | 2009-09-15 | 2010-09-15
[8 empty] | Actual | 2009-02-11 | 2009-02-19 |  | 2009-03-01 | 2009-03-30 | 2009-05-05 | 2009-05-15 | Actual | 24442.4464 | 07-may-09 | 2009-06-09 |  | 2009-07-10 | 2010-07-10
Drilling of 18 Shallow wells ( South West Shoa, Woliso) | OWRB/MDTF/SHW/06/2/ 2010 |  | BOQ | NCB | 80922.6566 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-12 | 2011-03-14 | 2011-03-30 | 2011-04-20 | Actual | 99702.5919 | 9-Jun-11 | 14-Jul-11 |  | 2011-11-05 | 2012-11-04
Drilling of 18 Shallow wells ( SW/ West Shoa, Ameya) | OWRB/MDTF/SHW/06/1 2010 |  | BOQ | NCB | 80922.6566 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-12 | 2011-03-14 | 2011-03-30 | 2011-04-20 | Actual | 99702.5919 | 9-Jun-11 | 14-Jul-11 |  | 2011-10-08 | 2012-10-07
Drilling of 23 Shallow wells (I/A/Bora, Jima) | OWRB/MDTF/SHW/01/2/ 2010 |  | BOQ | NCB | 94409.7661 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-10-05 | 2010-11-05 | 2010-11-15 | 2010-12-05 | Plan |  | 2010-12-10 | 2010-12-20 |  | 2011-06-20 | 2012-06-19
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-12 | 2011-03-14 | 2011-03-24 | 2011-04-20 | Actual | 170811.1142 | 9-Jun-11 | 14-Jul-11 |  | 2011-10-18 | 2012-10-17
Drilling of 20 Shallow wells (West Shoa; Nono) | OWRB/MDTF/SHW/09/2/ 2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-12 | 2011-03-14 | 2011-03-30 | 2011-04-20 | Actual | 96739.0878 | 24-May-11 | 09-Jun-11 |  | 2011-12-15 | 2012-12-14
Drilling of 13 Shallow wells (Guji - Liban, Adola & Wadera) | OWRB/MDTF/SHW/03/1 /2010 |  | BOQ | NCB | 58444.1409 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-10-05 | 2010-11-05 | 2010-11-15 | 2010-12-05 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2010-07-20 | 2010-07-25 |  | 2010-08-26 | 2010-10-26 | 2010-11-10 | 2010-11-15 | Actual | 67570.7007 | 2010-12-06 | 2010-12-31 |  | 2011-11-25 | 2012-11-24
Drilling of 21 Shallow wells (Mulo, Degem, Berek, Gimbichu, Aleltu) | OWRB/MDTF/SHW/05/1/ 2010 |  | BOQ | NCB | 85418.3598 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-10-05 | 2010-11-05 | 2010-11-15 | 2010-12-05 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2010-07-20 | 2010-07-25 |  | 2010-08-26 | 2010-10-26 | 2010-11-10 | 2010-11-15 | Actual | 84569.5652 | 2010-12-06 | 2010-12-17 |  | 2011-06-24 | 2012-06-23
Drilling of 9 Shallow wells (Borena- Moyale, D/Dawa, B/Hora, Arero, Abaya) | OWRB/MDTF/SHW/03/3/2010 |  | BOQ | NCB | 40461.3283 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-10-05 | 2010-11-05 | 2010-11-15 | 2010-12-05 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-12 | 2011-03-14 | 2011-03-30 | 2010-11-15 | Actual | 85170.0874 | 2010-12-06 | 9-Jun-11 |  | 2011-09-10 | 2012-09-09
Drilling of 3 shallow wells (Jimma, E & W Wellega) | OWRB/MDTF/DW&SW/ 01/ 2008 |  | BOQ | NCB | 13487.1094 | Post | Post | Plan | 2009-04-08 | 2009-04-16 |  | 2009-04-26 | 2009-06-10 | 2009-07-15 | 2009-07-20 | Plan |  | 2009-07-20 | 2009-07-27 |  | 2009-09-15 | 2010-09-15
[8 empty] | Actual | 2009-02-11 | 2009-02-19 |  | 2009-03-01 | 2009-03-30 | 2009-05-05 | 2009-05-15 | Actual | 12016.4381 | 07-May-09 | 2009-06-09 |  | 2010-05-20 | 2011-05-20
B.Ongoing (85 shallow Wells)
Drilling of 20 Shallow wells ( South West Shoa; Goro, Wonchi & Tole) | OWRB/MDTF/SHW/06/3/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2012-04-07 | 2013-04-07
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-12 | 2011-03-14 | 2011-03-30 | 2011-04-20 | Actual | 121488.4236 | 27-May-11 | 9-Jun-11 |  | 2011-10-07 | 2012-10-06
Drilling of 19 Shallow wells (North Shoa & west Shoa, OSZSF) | OWRB/MDTF/SHW/05/2/ 2010 |  | BOQ | NCB | 85418.3598 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2012-04-07 | 2013-04-07
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-12 | 2011-03-14 | 2011-03-30 | 2011-04-20 | Actual | 131954.6107 | 27-May-11 | 22-Jun-11
Drilling of 10 Shallow wells (W/Arsi & Bale) | OWRB/MDTF/SHW/02/1/ 2010 |  | BOQ | NCB | 50720.7534 | Post | Post | Plan | 2010-10-30 | 2010-11-15 |  | 2010-11-25 | 2010-12-25 | 2011-01-10 | 2011-01-25 | Plan |  | 2011-01-30 | 2011-02-07 |  | 2012-04-07 | 2013-04-07
[8 empty] | Actual | 20-Jan-11 | 25-Jan-11 |  | 2011-05-05 | 2011-05-27 | 2011-08-01 | 2011-08-10 | Actual | 104223.0791 | 27-May-11 | 22-Sep-11
Drilling of 20 Shallow wells (East & West Wollega) | OWRB/MDTF/SHW/07/1/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-30 | 2010-11-15 |  | 2010-11-25 | 2010-12-25 | 2011-01-10 | 2011-01-25 | Plan |  | 2011-01-30 | 2011-02-07 |  | 2012-04-07 | 2013-04-07
[8 empty] | Actual | 2011-01-20 | 2011-01-25 |  | 2011-02-12 | 2011-03-14 | 2011-03-30 | 2011-04-20 | Actual | 107041.4239 | 24-May-11 | 09-Jun-11
Drilling of 13 Shallow wells (West Shoa, E/Wollega) | OWRB/MDTF/SHW/09/1/ 2010 |  | BOQ | NCB | 58444.1409 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-10-05 | 2010-11-05 | 2010-11-15 | 2010-12-05 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-06-07 | 2012-06-06
[8 empty] | Actual | 2010-07-20 | 2010-07-25 |  | 2010-08-26 | 2010-10-26 | 2010-11-10 | 2010-11-15 | Actual | 57677.9693 | 2010-12-06 | 2010-12-17 |  | 2011-06-28 | 2012-06-27
Drilling of (deep &) 3 shallow wells (W/Hararge & E/Hararge) | OWRB/MDTF/DW/02/3/ 2010 |  | BOQ | NCB | 13487.1094 | Post | Post | Plan | 2010-08-30 | 2010-09-15 |  | 2010-09-25 | 2010-10-25 | 2010-11-10 | 2010-11-25 | Plan |  | 2010-11-30 | 2010-12-07 |  | 2011-08-07 | 2012-08-06
[8 empty] | Actual | 20-Jan-11 | 25-Jan-11 |  | 01-Dec.11 | 28-Dec-11 | 2012-01-05 | 2012-01-08 | Actual |  | 03-Feb-12 | 2012-02-13 |  | 2012-06-12 | 2013-06-12
C.New projects (22 shallow Wells)
Drilling of 10 Shallow wells | OWMEB/MDTF/SHW/01/ 2012 |  | BOQ | NCB | 44957.0315 | Post | Post | Plan | 2012-04-15 | 2012-04-16 |  | 2012-04-20 | 2012-05-25 | 2012-06-01 | 2012-06-02 | Plan |  | 2012-06-07 | 2012-06-17 |  | 2012-10-15 | 2013-10-15
[8 empty] | Revised | 2012-06-29 |  | 7/14/2012 | 2012-07-29 | 2012-08-28 | 2012-09-12 | 2012-09-22 |  |  | 2012-09-19 | 2012-10-09 |  | 2013-02-06 | 2014-02-06
[8 empty] | Actual | [7 empty] | Actual
Drilling of 12 Shallow wells | OWMEB/MDTF/SHW/02/ 2012 |  | BOQ | NCB | 53948.4377 | Post | Post | Plan | 2012-04-15 | 2012-04-16 |  | 2012-04-20 | 2012-05-25 | 2012-06-01 | 2012-06-02 | Plan |  | 2012-06-07 | 2012-06-17 |  | 2012-10-15 | 2013-10-15
[8 empty] | Revised | 2012-06-29 | 2012-07-19 | 7/14/2012 | 2012-07-29 | 2012-08-28 | 2012-09-12 | 2012-09-22 |  |  | 2012-09-19 | 2012-10-09 |  | 2013-02-06 | 2014-02-06
[8 empty] | Actual | [7 empty] | Actual
III. Rural Pipe System (137RPS)
A. Completed Projects (17 RPS)
Hopha (Geba Arba) water supply projects | OWRB/CWC/002/1/39/2007 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2008-12-16 | 2008-12-21 | - | 2008-04-26 | 2008-06-10 | 2008-06-30 | 2008-07-15 | Plan |  | 2008-07-23 | 2008-08-03 |  | 2009-02-14 | 2010-02-14
[8 empty] | Actual | 2009-07-12 | 2009-07-17 | - | 2008-11-20 | 2009-01-04 | 2009-01-24 | 2009-02-08 | Actual | 61416.5074 | 2009-02-17 | 2009-02-27 |  | 2009-11-26 | 2010-11-26
Koma & Gishe Luchine water supply projects | OWRB/CWC/MDTF/001/1/2008 |  | BOQ | NCB | 179828.1258 | Post | Post | Plan | 2008-12-16 | 2008-12-21 | - | 2009-04-26 | 2009-06-10 | 2009-06-30 | 2009-07-15 | Plan |  | 2009-07-23 | 2009-08-03 |  | 2009-12-13 | 2010-12-13
[8 empty] | Actual |  |  | - | 2009-03-01 | 2009-03-30 | 2009-04-08 | 2009-05-01 | Actual | 110997.8877 | 2009-05-19 | 2009-06-01 |  | 2010-03-08 | 2011-03-08
Debel water supply project | OWRB/CWC/MDTF/001/2/2008 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2008-12-16 | 2008-12-21 | - | 2009-04-26 | 2009-06-10 | 2009-06-30 | 2009-07-15 | Plan |  | 2009-07-23 | 2009-08-03 |  | 2010-02-03 | 2011-02-03
[8 empty] | Actual | 2008-10-14 | 2008-10-19 | - | 2009-02-22 | 2009-04-08 | 2009-04-28 | 2009-05-13 | Actual | 65429.5264 | 2009-05-22 | 2009-06-01 |  | 2010-03-10 | 2011-03-10
Anfera water supply project | OWRB/MDTF/CWC/01/3/ 2008 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2008-12-16 | 2008-12-21 | - | 2009-04-26 | 2009-06-10 | 2009-06-30 | 2009-07-15 | Plan |  | 2009-07-23 | 2009-08-03 |  | 2010-02-03 | 2011-02-03
[8 empty] | Actual | 2009-11-10 | 2009-11-14 | - | 2009-03-01 | 2009-03-30 | 2009-04-08 | 2009-05-01 | Actual | 100729.9973 | 2009-05-13 | 2009-06-01 |  | 2009-11-18 | 2010-11-18
Hidha Korma water supply project | OWRB/CWC/MDTF/001/5/ 2008 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2008-12-16 | 2008-12-21 | - | 2009-04-26 | 2009-06-10 | 2009-06-30 | 2009-07-15 | Plan |  | 2009-07-23 | 2009-08-03 |  | 2010-02-03 | 2011-10-11
[8 empty] | Actual | 2009-11-10 | 2009-11-14 | - | 2010-08-19 | 2010-09-16 | 2010-10-06 | 2010-10-08 | Actual | 115046.7484 | 2010-11-19 | 2010-12-27 |  | 2011-07-10 | 2012-07-09
Wayu water supply project | OWRB/MDTF/CWC/01/3/ 2009 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2009-09-16 | 2009-09-20 | - | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-21 | Plan |  | 2010-01-29 | 2010-02-03 |  | 2010-07-02 | 2011-07-02
[8 empty] | Actual | 2009-11-10 | 2009-11-14 | - | 2009-12-27 | 2010-02-10 | 2010-03-02 | 2010-03-17 | Actual | 76220.6491 | 2010-03-20 | 2010-03-30 |  | 2010-10-11 | 2011-10-11
Halako Wabe water supply project | OWRB/MDTF/CWC/01/7/ 2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 | - | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-21 | Plan |  | 2010-01-29 | 2010-02-03 |  | 2010-07-02 | 2011-07-02
[8 empty] | Actual | 2009-06-12 | 2009-06-16 | - | 2009-07-29 | 2009-09-12 | 2009-10-02 | 2010-02-25 | Actual | 71804.9044 | 2010-02-28 | 2010-03-10 |  | 2010-09-21 | 2011-09-21
Bole Roge water supply project | OWRB/MDTF/CWC/01/08/ 2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 | - | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-21 | Plan |  | 2010-01-29 | 2010-02-03 |  | 2010-07-02 | 2011-07-02
[8 empty] | Actual | 2009-06-12 | 2009-06-16 | - | 2009-07-29 | 2009-09-12 | 2009-10-02 | 2009-10-17 | Actual | 80388.6092 | 2009-10-20 | 2009-10-30 |  | 2010-09-21 | 2011-09-21
Damu Dhinbiba water supply project | OWRB/MDTF/CWC/01/9/ 2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 | - | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-21 | Plan |  | 2010-01-29 | 2010-02-03 |  | 2010-10-11 | 2011-10-11
[8 empty] | Actual | 2009-06-12 | 2009-06-16 | - | 2009-07-29 | 2009-09-12 | 2009-10-02 | 2010-03-17 | Actual | 124133.0734 | 2010-03-20 | 2010-03-30 |  | 2010-10-31 | 2011-10-31
Kelo Water Supply project | ORWRB/MDTF/CWC/007/2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 | - | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-21 | Plan |  | 2010-01-29 | 2010-02-03 |  | 2010-05-13 | 2011-05-13
[8 empty] | Actual | 2009-06-12 | 2009-06-16 | - | 2009-07-29 | 2009-09-12 | 2009-10-02 | 2009-10-17 | Actual | 53770.0678 | 2009-10-23 | 2009-10-30 |  | 2010-06-11 | 2011-06-11
Gaba Robi Water Supply project | ORWRB/MDTF/CWC/006/2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 | - | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-21 | Plan |  | 2010-01-29 | 2010-02-03 |  | 2010-05-13 | 2011-05-13
[8 empty] | Actual | 2009-06-12 | 2009-06-16 | - | 2009-07-29 | 2009-09-12 | 2009-10-02 | 2009-10-17 | Actual | 55379.2604 | 2009-10-23 | 2009-10-30 |  | 2010-07-22 | 2011-07-22
Fulo Romso WSP (Borena, Dire) | OWRB/MDTF/RPS/03/ 2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-08-20 | 2010-09-05 | - | 2010-09-15 | 2010-10-15 | 2010-10-30 | 2010-11-15 | Plan |  | 2010-11-20 | 2010-11-27 |  | 2011-07-04 | 2012-07-03
[8 empty] | Actual | 2010-09-13 | 2010-09-29 | - | 2010-10-09 | 2010-11-08 | 2010-11-23 | 2010-12-09 | Actual | 108635.3627 | 2010-12-16 | 2010-12-21 |  | 2011-08-22 | 2012-08-21
Lege Sure WSP (Borena; Moyale) | OWRB/MDTF/RPS/63/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-08-20 | 2010-09-05 | - | 2010-09-15 | 2010-10-15 | 2010-10-30 | 2011-11-15 | Plan |  | 2010-11-20 | 2010-11-27 |  | 2011-05-27 | 2012-05-26
[8 empty] | Actual | 2010-09-13 | 2010-09-29 | - | 2010-10-09 | 2010-11-08 | 2010-11-23 | 2011-12-09 | Actual | 163185.1993 | 2010-12-16 | 2010-12-21 |  | 2011-08-13 | 2012-08-12
Dheru Denfile WSP (Borena; Dugda Dawa) | OWRB/MDTF/RPS/65/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-08-20 | 2010-09-05 |  | 2010-09-15 | 2010-10-15 | 2010-10-30 | 2011-11-15 | Plan |  | 2010-11-20 | 2010-11-27 |  | 2011-07-04 | 2012-07-03
[8 empty] | Actual | 2010-09-13 | 2010-09-29 |  | 2010-10-09 | 2010-11-08 | 2010-11-23 | 2011-12-09 | Actual | 34917.8514 | 2010-12-16 | 2010-12-21 |  | 2011-04-20 | 2012-04-19
Lencha Lajo water supply project | OWRB/MDTF/CWC/01/11/ 2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-21 | Plan |  | 2010-01-29 | 2010-02-03 |  | 2010-07-02 | 2011-07-02
[8 empty] | Actual | 2009-11-17 | 2009-11-21 |  | 2010-01-03 | 2010-02-17 | 2010-03-09 | 2010-03-24 | Actual | 178634.6521 |  | 2010-04-06 |  | 2010-10-18 | 2011-10-18
Tusha supply project | ORWRB/MDTF/CWC/009/2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-21 | Plan |  | 2010-01-29 | 2010-02-03 |  | 2010-05-13 | 2011-05-13
[8 empty] | Actual | 2009-06-12 | 2009-06-16 |  | 2009-07-29 | 2009-09-12 | 2009-10-02 | 2009-10-17 | Actual | 50745.3086 | 2009-10-20 | 2009-10-30 |  | 2010-02-27 | 2011-02-27
B. On going projects (110 RPS)
Jarso Silase water supply projects | OWRB/CWC/002/1/2007 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2008-12-16 | 2008-12-21 |  | 2009-04-26 | 2009-06-10 | 2009-06-30 | 2009-07-05 | Plan |  | 2009-07-13 | 2009-08-03 |  | 2010-02-14 | 2011-02-14
[8 empty] | Actual | 2006-10-23 | 2006-10-28 |  | 2007-03-03 | 2007-04-17 | 2007-05-07 | 2007-05-12 | Actual | 75920.5362 | 2007-05-31 | 2007-06-10 |  | 2007-10-08 | 2008-10-07
Goda Arba & Ilala Jeba water supply projects | OWRB/CWC/MDTF/001/4/2008 |  | BOQ | NCB | 179828.1258 | Post | Post | Plan | 2008-12-16 | 2008-12-21 |  | 2009-04-26 | 2009-06-10 | 2009-06-30 | 2009-07-05 | Plan |  | 2009-07-13 | 2009-08-03 |  | 2010-02-03 | 2011-02-03
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2006-10-23 | 2006-10-28 |  | 2007-03-03 | 2007-04-17 | 2007-05-07 | 2007-05-12 | Actual | 124332.3832 | 2012-04-28 | 2012-05-08
Geba Gudina water supply projects | OWRB/MDTF/CWC/001/5/2008 |  | BOQ | NCB | 43804.2871 | Post | Post | Plan | 2008-12-16 | 2008-12-21 |  | 2009-04-26 | 2009-06-10 | 2009-06-30 | 2009-07-05 | Plan |  | 2009-07-24 | 2009-08-03 |  | 2010-02-03 | 2011-02-03
[8 empty] | Revised plan | [12 empty] | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2006-10-23 | 2006-10-28 |  | 2009-03-01 | 2009-03-30 | 2009-04-08 |  | Actual | 15409.1845 | 2012-04-28 | 2012-05-08
Mariga Abeyi water supply project | OWRB/MDTF/CWC/01/1/ 2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-11 | Plan |  | 2010-01-19 | 2010-02-03 |  | 2012-11-19 | 2013-11-19
[8 empty] | Revised plan | [12 empty] | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 156822.7898 | 2012-04-28 | 2012-05-08
Bili Malima water supply project | OWRB/MDTF/CWC/01/2/ 2009 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-11 | Plan |  | 2010-01-19 | 2010-02-03 |  | 2010-07-02 | 2011-07-02
[8 empty] | Revised plan | [12 empty] | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 40884.3267 | 2012-04-28 | 2012-05-08
Haro Kono water supply project | OWRB/MDTF/CWC/01/9/ 2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-11 | Plan |  | 2010-01-19 | 2010-02-03 |  | 2010-08-17 | 2011-08-17
[8 empty] | Revised plan | [12 empty] | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 92724.0595 | 2012-04-28 | 2012-05-08
Didibe Abado water supply project | OWRB/MDTF/CWC/01/6/ 2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-11 | Plan |  | 2010-01-19 | 2010-02-03 |  | 2010-07-02 | 2011-10-18
[8 empty] | Revised plan | [12 empty] | 2012-09-11 | 2013-09-11
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 112816.4681 | 2012-04-28 | 2012-05-14
Obenso Jello | ORWRB/MDTF/CWC/001/2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-11 | Plan |  | 2010-01-19 | 2010-02-03 |  | 1900-07-13 | 1901-07-13
[8 empty] | Revised plan | [10 empty] | 2012-05-08 |  | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 112362.5295 | 2012-04-28
Tulu Hofi supply project | ORWRB/MDTF/CWC/002/2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-11 | Plan |  | 2010-01-19 | 2010-02-03 |  | 1900-07-13 | 1901-07-13
[8 empty] | Revised plan | [10 empty] | 2012-05-08 |  | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 87108.9292 | 2012-04-28
Garbi Goba supply project | ORWRB/MDTF/CWC/003/2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-11 | Plan |  | 2010-01-19 | 2010-02-03 |  | 1900-07-13 | 1901-07-13
[8 empty] | Revised plan | [10 empty] | 2012-05-08 |  | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 83001.3112 | 2012-04-28
Soka supply project | ORWRB/MDTF/CWC/004/2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-11 | Plan |  | 2010-01-19 | 2010-02-03 |  | 1900-07-13 | 1901-07-13
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-04-20 | 2013-04-20
[8 empty] | Revised plan | [10 empty] | 2012-05-08 |  | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual |  | 2012-04-28
Sefera Dayu supply project | ORWRB/MDTF/CWC/005/2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-11 | Plan |  | 2010-01-19 | 2010-02-03 |  | 1900-07-13 | 1901-07-13
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-04-15 | 2013-04-15
[8 empty] | Revised plan | [10 empty] | 2012-05-08 |  | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 122075.6454 | 2012-04-28
Bola Roge supply project | ORWRB/MDTF/CWC/008/2009 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2009-09-16 | 2009-09-20 |  | 2009-11-02 | 2009-12-17 | 2010-01-06 | 2010-01-11 | Plan |  | 2010-01-19 | 2010-02-03 |  | 1900-07-13 | 1901-07-13
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-05-15 | 2013-05-15
[8 empty] | Revised plan | [10 empty] | 2012-05-08 |  | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 80388.6092 | 2012-04-28
Abasamu'el water supply project | OWRB/MDTF/RPS/01/ 2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-08-20 | 2010-09-05 |  | 2010-09-15 | 2010-10-15 | 2010-10-30 | 2010-11-04 | Plan |  | 2010-11-20 | 2010-11-27 |  | 2011-05-27 | 2012-05-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Revised plan | [10 empty] | 2012-05-08 |  | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 72643.4377 | 2012-04-28 |  |  | 2011-05-26
Kufa Kas water supply project | OWRB/MDTF/RPS/02/ 2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-08-20 | 2010-09-05 |  | 2010-09-15 | 2010-10-15 | 2010-10-30 | 2010-11-04 | Plan |  | 2010-11-20 | 2010-11-27 |  | 2011-05-27 | 2012-05-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-04-15 | 2013-04-15
[8 empty] | Revised plan | [10 empty] | 2012-05-08 |  | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-28 | 2012-01-01 |  | 2012-02-13 | 2012-03-29 | 2012-04-18 |  | Actual | 107487.8818 | 2012-04-28
Haleyo, Guro gudo & Jallo | OWRB/CWC/MDTF/04/ 2010 |  | BOQ | NCB | 107487.8881 | Post | Post | Plan | 2008-12-16 | 2008-12-21 |  | 2009-04-26 | 2009-06-10 | 2009-06-30 | 2009-07-05 | Plan |  | 2009-07-13 | 2009-08-03 |  | 2010-02-03 | 2011-10-11
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-05-30 | 2013-05-30
|  |  | BOQ | NCB | 85591.2714 |  |  | Actual | 2010-04-10 | 2010-04-15 |  | 2010-08-19 | 2010-09-16 | 2010-10-06 |  | Actual | 131882.495 | 2010-11-05 | 2010-11-22
Hinde WSP (East Wollega; Ebantu) | OWRB/MDTF/RPS/15/2010 |  | BOQ | NCB | 131882.495 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan | 0 | 2011-01-20 | 2011-01-27 |  | 2011-07-27 | 2012-07-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-05-30 | 2013-05-30
[8 empty] | Actual | 2010-09-28 | 2010-10-14 |  | 2010-10-24 | 2010-11-23 | 2010-12-08 | 2010-12-13 | Actual | 109508.2496 | 2010-12-21
0
Korke WSP ( South West Shoa, Weliso) | OWRB/MDTF/RPS/20/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2011-07-27 | 2012-07-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  | 2011-02-07 |  | 2012-05-20 | 2013-05-20
[8 empty] | Actual | 2010-11-12 | 2010-11-28 |  | 2010-12-08 | 2011-01-07 | 2011-01-22 | 2011-01-27 | Actual | 46388.227 | 2011-01-31
Sombo-Disasa & Fechase WSPs ( West Shoa, Bako-Tibe) | OWRB/MDTF/RPS/22/2010 |  | BOQ | NCB | 179828.1258 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2011-07-27 | 2012-07-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2010-08-23 | 2010-09-08 |  | 2010-09-18 | 2010-10-19 | 2010-11-01 | 2010-11-06 | Actual | 86920.3442 | 2010-11-22 | 2010-12-12
Tose & Goben WSPs ( West Shoa, Cheliya) | OWRB/MDTF/RPS/23/2010 |  | BOQ | NCB | 129395.5585 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2011-07-27 | 2012-07-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-05-20 | 2013-05-20
[8 empty] | Actual | 2010-08-23 | 2010-09-08 |  | 2010-09-18 | 2010-10-19 | 2010-11-01 | 2010-11-06 | Actual | 82309.9695 | 2010-11-22 | 2010-12-12
Chimo Negelle WSP (Arsi, Sude) | OWRB/MDTF/RPS/55/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-03-20 | 2011-03-27 |  | 2011-10-08 | 2012-10-07
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-30 | 2013-06-30
[8 empty] | Actual | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Actual | 215786.5463 | 2010-11-08 | 2010-11-12
Tedecha/Teji WSP (Arsi, Amigna) | OWRB/MDTF/RPS/56/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-03-20 | 2011-03-27 |  | 2011-05-26 | 2012-05-25
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-25 | 2013-06-25
[8 empty] | Actual | 2010-08-22 | 2010-09-07 |  | 2010-09-17 | 2010-10-17 | 2010-11-01 | 2010-11-06 | Actual | 94992.1314 | 2010-11-08 | 2010-11-12
Wacho Mishirge WSP (Bale; Goba) | OWRB/MDTF/RPS/57/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-03-20 | 2011-03-27 |  | 2011-10-27 | 2012-10-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-04-30 | 2013-04-30
[8 empty] | Actual | 2010-08-22 | 2010-09-07 |  | 2010-09-17 | 2010-10-17 | 2010-11-01 | 2010-11-06 | Actual | 75175.4696 | 2010-11-08 | 2010-11-12
Hache WSP (Borena; Bule Hora) | OWRB/MDTF/RPS/64/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-08-20 | 2010-09-05 |  | 2010-09-15 | 2010-10-15 | 2010-10-30 | 2010-11-04 | Plan |  | 2010-11-20 | 2010-11-27 |  | 2011-05-26 | 2012-05-25
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 58450.134 | 2010-11-08 | 2010-11-12
Buro Fincha'a WSP (OSZSF; Sebeta-Hawas) | OWMEB/MDTF/RPS/53/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-12-20 | 2011-01-05 |  | 2011-01-15 | 2011-02-15 | 2011-03-02 | 2011-03-07 | Plan |  | 2011-03-20 | 2011-03-27 |  | 2011-10-08 | 2012-10-07
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-25 | 2013-06-25
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 78978.3515 | 2011-06-22 | 2010-11-12
Abebe Silase WSP (SW/Shoa; Tole) | OWMEB/MDTF/RPS/48/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-12-20 | 2011-01-05 |  | 2011-01-15 | 2011-02-15 | 2011-03-02 | 2011-03-07 | Plan |  | 2011-03-20 | 2011-03-27 |  | 2011-10-08 | 2012-10-07
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 37726.7644 | 2011-08-10 | 2011-08-10
Abado Lemen WSP (SW/Shoa; Weliso) | OWMEB/MDTF/RPS/49/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-12-20 | 2011-01-05 |  | 2011-01-15 | 2011-02-15 | 2011-03-02 | 2011-03-07 | Plan |  | 2011-03-20 | 2011-03-27 |  | 2012-01-02 | 2013-01-01
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 35483.6172 | 2011-06-12 | 2011-06-21
Hereri/Terara WSP (West Shoa; Abuna Gindeberet) | OWMEB/MDTF/RPS/24/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-03 | 2013-01-02
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 57944.1317 | 2011-06-12 | 2011-06-22
Chando WSP (W/Shoa; Nono) | OWMEB/MDTF/RPS/50/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-12-20 | 2011-01-05 |  | 2011-01-15 | 2011-02-15 | 2011-03-02 | 2011-03-07 | Plan |  | 2011-03-20 | 2011-03-27 |  | 2012-01-04 | 2013-01-03
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 27788.9198 | 2011-06-12 | 2011-06-23
Wine WSP (W/Shoa; Tikur Inchini) | OWMEB/MDTF/RPS/51/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-12-20 | 2011-01-05 |  | 2011-01-15 | 2011-02-15 | 2011-03-02 | 2011-03-07 | Plan |  | 2011-03-20 | 2011-03-27 |  | 2012-03-13 | 2013-03-13
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 52297.3222 | 2011-06-12 | 2011-08-31
Wakene WSP (N/Shoa; Debre Libanos) | OWMEB/MDTF/RPS/52/2010 |  | BOQ | NCB | 92253.1 | Post | Post | Plan | 2010-12-20 | 2011-01-05 |  | 2011-01-15 | 2011-02-15 | 2011-03-02 | 2011-03-07 | Plan |  | 2011-03-20 | 2011-03-27 |  | 2011-12-29 | 2012-12-28
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 82866.3358 | 2011-06-12 | 2011-06-17
Setema WSP (Jima; Setema) | OWMEB/MDTF/RPS/26/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-05 | 2013-01-04
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 74517.2376 | 2011-06-12 | 2011-06-24
Addis Limat WSP (Jima; Limu Kosa) | OWMEB/MDTF/RPS/27/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-05 | 2013-01-04
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 103951.2268 | 2011-06-12 | 2011-06-24
Mote WSP ( East Wollega, Wama Haglo) | OWMEB/MDTF/RPS/16/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2011-12-29 | 2012-12-28
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 87131.8267 | 2011-06-12 | 2011-06-17
Jangir WSP ( East Wollega; Gida Ayana) | OWMEB/MDTF/RPS/17/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-08 | 2013-01-07
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 63007.6652 | 2011-06-12 | 2011-06-27
Geba Defino WSP ( West Wollega; Kondala) | OWMEB/MDTF/RPS/18/2/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2011-08-10 | 2012-08-09
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 89260.3796 | 2011-06-12 | 2011-08-24
Wama Tobera WSP ( West Wollega; Menesibu) | OWMEB/MDTF/RPS/18/1/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-03-28 | 2013-03-28
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-25 | 2013-06-25
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 44951.2009 | 2011-06-07 | 2011-06-17
Nunu WSP ( Kellem Wollega; Jima Horo) | OWMEB/MDTF/RPS/19/1/2011 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-11 | 2013-01-10
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 89607.6219 | 2011-06-07 | 2011-06-30
Gorayi WSP ( Kellem Wollega; Gidami) | OWMEB/MDTF/RPS/19/2/2011 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2011-12-28 | 2012-12-27
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 106824.7967 | 2011-06-07 | 2011-06-16
Addis Alem WSP (E /Hararge; Melka Belo) | OWMEB/MDTF/RPS/04/2011 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-04 | Plan |  | 2011-01-20 | 2011-07-30 |  | 2012-02-10 | 2013-02-09
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 56660.3496 | 2011-06-07 | 2011-07-08
Chela Negeya WSP (E /Hararge; Deder) | OWMEB/MDTF/RPS/05/2011 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-07-30 |  | 2012-02-10 | 2013-02-09
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 50597.0173 | 2011-06-07 | 2011-07-14
Burka Gemechu, Umer & Elfeta WSP (E /Hararge; Meta) | OWMEB/MDTF/RPS/06/2011 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-02 | 2013-01-01
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 130899.9487 | 2011-06-07 | 2011-06-21
Ledo WSP (Borena, Abaya) | OWMEB/MDTF/RPS/66/2011 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-08-20 | 2010-09-05 |  | 2010-09-15 | 2010-10-15 | 2010-10-30 | 2011-11-15 | Plan |  | 2010-11-20 | 2010-11-27 |  | 2011-05-27 | 2012-05-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-04-20 | 2013-04-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 86931.2843 | 2011-06-07 | 2011-07-29
Abure, Dilo &Bore WSPs (Arsi, Munesa) | OWMEB/MDTF/RPS/10/2011 |  | BOQ | NCB | 131412.8612 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-10 | 2013-01-09
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 67194.0023 | 2011-06-07 | 2011-06-29
Gudina Adola, Lege Dana Gonjo, Lole & Kotile WSPs (Arsi, Munesa) | OWMEB/MDTF/RPS/11/2011 |  | BOQ | NCB | 175217.1482 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-16 | 2013-01-15
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 67586.4927 | 2011-06-07 | 2011-07-05
Malekicho Asendabo WSP (Arsi, Amigna) | OWMEB/MDTF/RPS/11/2011 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2011-07-27 | 2012-07-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 138550.0349 | 2011-07-26 | 10-Aug-11
Harbefano WSP (W/Hararge, Gemechis) | OWMEB/MDTF/RPS/07/1/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-03 | 2013-01-02
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 37832.2619 | 2011-06-07 | 2011-06-22
Goro Meta WSP (W/Hararge, Guba Koricha) | OWMEB/MDTF/RPS/07/2/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2011-07-27 | 2012-07-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 64368.1693 | 2011-06-07 | 2011-07-14
Kebeso WSP (W/Hararge, Mesela) | OWMEB/MDTF/RPS/07/3/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-02 | 2013-01-01
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 95184.4887 | 2011-06-07 | 2011-06-21
Fefate, Gelcha & Goda WSPs (East Shoa; Fentale) | OWMEB/MDTF/RPS/25/1/2010 |  | BOQ | NCB | 131412.8612 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-11 | 2013-01-10
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 52828.0907 | 2011-06-07 | 2011-06-30
Indode WSP(East Shoa; Gimbichu) | OWMEB/MDTF/RPS/25/2/2010 |  | BOQ | NCB | 43804.2871 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-02 | 2013-01-01
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 26101.9291 | 2011-06-07 | 2011-06-21
Ilasa WSP (Bale; Goba) | OWMEB/MDTF/RPS/58/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-12-20 | 2011-01-05 |  | 2011-01-15 | 2011-02-15 | 30/2/2011 | 2011-01-15 | Plan |  | 2011-03-20 | 2011-03-27 |  | 2012-01-04 | 2013-01-03
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 45836.8417 | 2011-06-07 | 2011-06-23
Dirira WSP (Bale; Delo Mena) | OWMEB/MDTF/RPS/13/2010 |  | BOQ | NCB | 89914.0629 | Post | Post | Plan | 2010-10-20 | 2010-11-05 |  | 2010-11-15 | 2010-12-15 | 2010-12-30 | 2011-01-15 | Plan |  | 2011-01-20 | 2011-01-27 |  | 2012-01-04 | 2013-01-03
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 18291.883 | 2011-06-07 | 2011-06-23
Beda Kesa WSP (Guji; Odo Shakiso) | OWMEB/MDTF/RPS/67/2010 |  | BOQ | NCB | 85591.2714 | Post | Post | Plan | 2010-08-20 | 2010-09-05 |  | 2010-09-15 | 2010-10-15 | 2010-10-30 | 2011-11-15 | Plan |  | 20/11/2010 | 2010-11-27 |  | 2012-01-03 | 2013-01-02
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-06-20 | 2013-06-20
[8 empty] | Actual | 2011-01-27 | 2011-02-12 |  | 2011-02-22 | 2011-03-21 | 2011-05-10 |  | Actual | 59759.7663 | 2011-06-07 | 2011-06-22
Galesa Negeso WSP (Borena, Bule Hora) | OWMEB/MDTF/RPS/15-1/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 38755.5548 | 2012-04-30 | 2012-05-10
Arero Tune WSP (Borena, Arero) | OWMEB/MDTF/RPS/15-2/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 74464.4868 | 2012-04-30 | 2012-05-10
Rare Beha WSP (Borena, Dire) | OWMEB/MDTF/RPS/16/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 250430.2878 | 2012-04-30 | 2012-05-10
Dhokole WSP (Borena, Dire) | OWMEB/MDTF/RPS/17/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 38333.6083 | 2012-04-30 | 2012-05-10
Kebena'a/Mega (Borena, Dire) | OWMEB/MDTF/RPS/18/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 152701.1182 | 2012-04-30 | 2012-05-10
Birate Sayo (OSZSF, Sululta) | OWMEB/MDTF/RPS/01/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 78090.1169 | 2012-04-30 | 2012-05-10
Roben Jirecha Tamse (OSZSF, Sebeta Hawas) | OWMEB/MDTF/RPS/02/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 62352.1496 | 2012-04-30 | 2012-05-10
Chole Sokole (North Shoa, Aleltu) | OWMEB/MDTF/RPS/03/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-06 | 2013-09-06
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 74921.1753 | 2012-04-30 | 2012-05-09
Kura Kemele (OSZSF, Mulo) | OWMEB/MDTF/RPS/04/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-06 | 2013-09-06
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 84142.187 | 2012-04-30 | 2012-05-09
Chabi Sire Goyo (OSZSF, Berek) | OWMEB/MDTF/RPS/05/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 20714.3038 | 2012-04-30 | 2012-05-10 |  | 2012-09-07 | 2013-09-07
Menjikso Tede (East Shoa, Gimbichu) | OWMEB/MDTF/RPS/06/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2011-10-15 | 2011-10-18 | Plan |  | 2011-10-19 | 2011-10-26 |  | 2012-02-23 | 2013-02-22
[8 empty] | Revised | [12 empty] | 2012-09-11 | 2013-09-11
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 78159.3225 | 2012-04-30 | 2012-05-14
Kiltu Kara (West Wollega, Kiltu kara) | OWMEB/MDTF/RPS/22-1/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised |  |  |  | 2012-02-09 | 2012-03-10 | 2012-03-25 |  |  |  | 2012-07-30 | 2012-08-19 |  | 1900-04-29 | 1901-04-29
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual
Wama Tobera 2 (West Wollega, Menesibu) | OWMEB/MDTF/RPS/22-2/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-08 | 2013-09-08
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 20714.3038 | 2012-05-01 | 2012-05-11
Sardo (Ilu Aba Bora, Dega) | OWMEB/MDTF/RPS/07/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-27 | 2013-09-27
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 120670.7457 | 2012-05-30 | 2012-05-14
Ire Tokuma (East Hararge, Meta) | OWMEB/MDTF/RPS/11/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-06 | 2013-09-06
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 54477.3751 | 2012-05-30 | 2012-05-09
Kumuto (East Hararge, Melka Belo) | OWMEB/MDTF/RPS/12-1/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-21 | 2013-09-21
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 117908.9868 | 2012-04-30 | 2012-05-24
Goro Abu (East Hararge, Gola Oda) | OWMEB/MDTF/RPS/12-2/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-06 | 2013-09-06
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 104192.6253 | 2012-04-30 | 2012-05-09
Burka Bereka (East Hararge, Deder) | OWMEB/MDTF/RPS/13/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-14 | 2013-09-14
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 139038.357 | 2012-04-30 | 2012-05-17
Alentu Dobedo & Fifota Wesherbi (W/Arsi,Dodola) | OWMEB/MDTF/RPS/19/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 161945.1196 | 2012-04-30 | 2012-05-10
Ititu Sura & Darole (Bale & Arsi; Goba & Bele Gesgar) | OWMEB/MDTF/RPS/20-1/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-13 | 2013-09-13
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 117719.0877 | 2012-04-30 | 2012-05-16
Chobi (Bale, Sawena) | OWMEB/MDTF/RPS/20-2/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [9 empty] | 1900-01-06 |  |  | 2012-09-13 | 2013-09-13
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 215178.8229 | 2012-04-30 | 2012-05-16
Irba & Goro Uko (Bale, Delomena) | OWMEB/MDTF/RPS/21-1/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 65709.0825 | 2012-04-30 | 2012-05-10
Oda Dima (Bale, Delomena) | OWMEB/MDTF/RPS/21-2/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2011-10-15 | 2011-10-18 | Plan |  | 2011-10-19 | 2011-10-26 |  | 2012-02-23 | 2013-02-22
[8 empty] | Revised | [12 empty] | 2012-09-07 | 2013-09-07
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 163991.4034 | 2012-04-30 | 2012-05-10
Didibe Goro 2 (South West Shoa, Goro) | OWMEB/MDTF/RPS/08/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-08 | 2013-09-08
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 54651.6591 | 2012-04-30 | 2012-05-11
Echa (South West Shoa, Wonchi) | OWMEB/MDTF/RPS/09/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-08 | 2013-09-08
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 57678.6258 | 2012-04-30 | 2012-05-11
Gulti Bola (South West Shoa, Ameya) | OWMEB/MDTF/RPS/21/2010 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 74353.0309 | 2012-04-30 | 2012-05-08
Malko (Jima, Seka Chokorsa) | OWMEB/MDTF/RPS/14-1/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-11 | 2013-09-11
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 67107.2202 | 2012-04-30 | 2012-05-14
Sombo (Jima, Shabe Sombo) | OWMEB/MDTF/RPS/14-2/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-11 | 2013-09-11
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 136444.3691 | 2012-04-30 | 2012-05-14
Dame (Jima, Lemu Seka) | OWMEB/MDTF/RPS/14-3/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-11 | 2013-09-11
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 112033.4469 | 2012-04-30 | 2012-05-14
Ilala Chobi, Ilala Jeba 2 & Goda Arba 2 (West shoa, Mida Kegn) | OWMEB/MDTF/RPS/10/2011 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-15 | 2013-09-15
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 | 2012-04-09 | 2012-04-12 | Actual | 221189.9337 | 2012-04-30 | 2012-05-18
Chando (West Shoa, Nono) | OWMEB/MDTF/RPS/50/2010 |  | BOQ | NCB | 118273.2111 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2012-03-17 | 2012-03-20 | Plan |  | 2012-03-21 | 2012-03-28 |  | 2012-07-26 | 2013-07-26
[8 empty] | Revised | [12 empty] | 2012-09-05 | 2013-09-05
[8 empty] | Actual | 2011-12-15 | 2011-12-20 |  | 2012-02-09 | 2012-03-07 |  |  | Actual | 46163.9721 | 2012-04-30 | 2012-05-08
C. New projects (10 RPS)
Construction of 5 RPS 5 contracts | OWMEB/MDTF/RPS/1-5/2012 |  | BOQ | NCB | 473092.8445 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2011-10-20 | 2011-10-25 | Plan |  | 2011-10-30 | 2011-11-15 |  | 2012-05-28 | 2013-05-28
[8 empty] | Revised | 2011-05-27 | 03-Jun-11 |  | 2012-06-14 | 2012-07-14 | 2012-07-29 | 2012-08-02 |  |  | 2012-08-05 | 2012-08-25 |  | 2012-12-23 | 2013-12-23
[8 empty] | Actual | [7 empty] | Actual
Construction of 5 RPS, 5 contracts | OWMEB/MDTF/RPS/6-10/2011 |  | BOQ | NCB | 591366.0556 | Post | Post | Plan | 2011-08-20 | 2011-08-25 |  | 2011-09-05 | 2011-10-05 | 2011-10-20 | 2011-10-25 | Plan |  | 2011-10-30 | 2011-11-15 |  | 2012-05-28 | 2013-05-28
[8 empty] | Revised | 2011-05-27 | 03-Jun-11 |  | 2012-06-14 | 2012-07-14 | 2012-07-29 | 2012-08-02 |  |  | 2012-08-05 | 2012-08-25 |  | 2012-12-23 | 2013-12-23
[8 empty] | Actual | [7 empty] | Actual
Formulas:
Prep & Submission by Ex Agency = [No-objection Date]-8
No-objection Date = [Bidding Period]-10
No-objection Date = [Bid Evaluation]+13
Date Contract Award = [Date Contract Signature]-7
Date Contract Award = [No-objection Date]+5
Final Acceptance = [Substantial Completion]+365
Final Acceptance = 365+[Substantial Completion]
Date Contract Signature = [Date Contract Award]+10
Date Contract Signature = [Date Contract Award, row below]+10
Substantial Completion = [Date Contract Signature]+120
Substantial Completion = [Date Contract Signature, row below]+195
Bidding Period = [No-objection Date]+4
Bidding Period = [Spec Proc Notice Advert]+15
Bid Closing-Opening = [Bidding Period]+35
Bid Evaluation = [Bid Closing-Opening]+7
Bid Evaluation = [Bid Closing-Opening]+[Bid Evaluation, row above]-[Bid Closing-Opening, row above]
Note on K6: P.Off: No Duration is required for no-objection!
Note on L6: P.Off: Why is this column completely ommitted?
Note on P6: P.Off: No Duration is required for no-objection!
Note on A19: user: + Ilasa
Note on A25: user: Additional well drilled in Cheliya
Note on A38: Original contract 9 (6 Rural +3urban) dw, additional 2 Dw Dhidhesa Ana
Note on A44: original contract 9 but one additional well Sebeta
Note on A47: Same contract with 4 deep & 3 Shallow wells, repeatedly rebided, NDE
Note on A75: user: Arengema and Gurra additional
Note on A109: Same contract with 4 deep & 3 Shallow wells, repeatedly rebided, NDE
Note on W118: P.Off: The project closing date of March 31, 2013 should be observed!

## Rural Consultancy
Procurement Plan Consultancy
Country/Organization: Oromia National Regional State Water Resource Bureau
Project/Programme: IDA-DFID (MDTF)
Loan #:
THE PROPER TEMPLATE!
Country/Organisation: |  | For Contracts under projects approved after the May 2002 Guidelines
Project/Programme: |  | If Post-Review, No-objection Dates are not needed
Loan #:
Description* | Selection Method | Contract Type | Estimated Amount in US$ | Prior/Post Review | Plan vs. Actual | Preparation Request for Proposals |  | Request for EOI (where required) |  | Short List |  | Plan vs. Actual | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  | Contract Implementation
|  | Lumpsum or Time-Based |  |  |  | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date |  | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks | Plan
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [5 empty] | Actual
List of Contracts
A. Woreda Support Groups
Milkoftu Business and Development PLC, OWRB/CS/WSG/01/09 | CQ | LS& TB | 129265 | Post | Plan | 2008-08-08 | 2008-08-23 | 2008-09-02 | 2008-09-09 | 2008-09-14 | 2008-09-19 | Plan | 2008-10-01 | 2008-12-15 | 2009-03-15 | 2009-03-21 | 2009-03-31 | 2009-04-10 | 2009-04-15 | Plan | 2009-04-25 | 2009-05-02 |  | 2009-05-15 | 2009-12-01 | Plan | 2009-12-11 | NA | 2011-02-28
[5 empty] | Actual | 2008-09-30 | 2008-10-10 |  | 2008-10-20 | 2008-10-24 | 2008-11-01 | Actual | 2008-11-10 | 2008-12-23 | 2009-08-24 | 2009-08-30 | 2009-09-09 | 2009-09-19 | 2009-09-24 | Actual | 2009-10-04 | 2009-10-11 | 116189.07 | 2009-12-05 | 15-Dec-09 | Actual | 2009-12-20 |  | 2011-03-19
Abdi Jiregna PLC, OWRB/CS/WSG/02/09 | CQ | LS& TB | 129265 | Post | Plan | 2008-08-08 | 2008-08-23 | 2008-09-02 | 2008-09-09 | 2008-09-14 | 2008-09-19 | Plan | 2008-10-01 | 2008-12-15 | 2009-03-15 | 2009-03-21 | 2009-03-31 | 2009-04-10 | 2009-04-15 | Plan | 2009-04-25 | 2009-05-02 |  | 2009-05-15 | 2009-12-01 | Plan | 2009-12-11 | NA | 2011-02-28
[5 empty] | Actual | 2008-09-30 | 2008-10-10 |  | 2008-10-20 | 2008-10-24 | 2008-11-01 | Actual | 2008-11-10 | 2008-12-23 | 2009-08-24 | 2009-08-30 | 2009-09-09 | 2009-09-19 | 2009-09-24 | Actual | 2009-10-04 | 2009-10-11 | 132128.97 | 2009-12-05 | 15-Dec-09 | Actual | 2009-12-20 |  | 2011-03-19
Latinsa S.C, OWRB/CS/WSG/03/09 | CQ | LS& TB | 129265 | Post | Plan | 2008-08-08 | 2008-08-23 | 2008-09-02 | 2008-09-09 | 2008-09-14 | 2008-09-19 | Plan | 2008-10-01 | 2008-12-15 | 2009-03-15 | 2009-03-21 | 2009-03-31 | 2009-04-10 | 2009-04-15 | Plan | 2009-04-25 | 2009-05-02 |  | 2009-05-15 | 2009-12-01 | Plan | 2009-12-11 | NA | 2011-02-28
[5 empty] | Actual | 2008-09-30 | 2008-10-10 |  | 2008-10-20 | 2008-10-24 | 2008-11-01 | Actual | 2008-11-10 | 2008-12-23 | 2009-08-24 | 2009-08-30 | 2009-09-09 | 2009-09-19 | 2009-09-24 | Actual | 2009-10-04 | 2009-10-11 | 110530.8 | 2009-12-05 | 15-Dec-09 | Actual | 2009-12-20 |  | 2011-03-19
Awash Consult PLC, OWRB/CS/WSG/04/09 | CQ | LS& TB | 129265 | Post | Plan | 2008-08-08 | 2008-08-23 | 2008-09-02 | 2008-09-09 | 2008-09-14 | 2008-09-19 | Plan | 2008-10-01 | 2008-12-15 | 2009-03-15 | 2009-03-21 | 2009-03-31 | 2009-04-10 | 2009-04-15 | Plan | 2009-04-25 | 2009-05-02 |  | 2009-05-15 | 2009-12-01 | Plan | 2009-12-11 | NA | 2011-02-28
[5 empty] | Actual | 2008-09-30 | 2008-10-10 |  | 2008-10-20 | 2008-10-24 | 2008-11-01 | Actual | 2008-11-10 | 2008-12-23 | 2009-08-24 | 2009-08-30 | 2009-09-09 | 2009-09-19 | 2009-09-24 | Actual | 2009-10-04 | 2009-10-11 | 126338.63 | 2009-12-05 | 15-Dec-09 | Actual | 2009-12-20 |  | 2011-03-19
GAMI United Consultancy PLC, OWRB/CS/WSG/05/09 | CQ | LS& TB | 129265 | Post | Plan | 2008-08-08 | 2008-08-23 | 2008-09-02 | 2008-09-09 | 2008-09-14 | 2008-09-19 | Plan | 2008-10-01 | 2008-12-15 | 2009-03-15 | 2009-03-21 | 2009-03-31 | 2009-04-10 | 2009-04-15 | Plan | 2009-04-25 | 2009-05-02 |  | 2009-05-15 | 2009-12-01 | Plan | 2009-12-11 | NA | 2011-02-28
[5 empty] | Actual | 2008-09-30 | 2008-10-10 |  | 2008-10-20 | 2008-10-24 | 2008-11-01 | Actual | 2008-11-10 | 2008-12-23 | 2009-08-24 | 2009-08-30 | 2009-09-09 | 2009-09-19 | 2009-09-24 | Actual | 2009-10-04 | 2009-10-11 | 103350.44 | 2009-12-05 | 15-Dec-09 | Actual | 2009-12-20 |  | 2011-03-19
Fanta Feyisa RWaSH Consultancy PLC, OWRB/CS/WSG/06/09 | CQ | LS& TB | 129265 | Post | Plan | 2008-08-08 | 2008-08-23 | 2008-09-02 | 2008-09-09 | 2008-09-14 | 2008-09-19 | Plan | 2008-10-01 | 2008-12-15 | 2009-03-15 | 2009-03-21 | 2009-03-31 | 2009-04-10 | 2009-04-15 | Plan | 2009-04-25 | 2009-05-02 |  | 2009-05-15 | 2009-12-01 | Plan | 2009-12-11 | NA | 2011-02-28
[5 empty] | Actual | 2008-09-30 | 2008-10-10 |  | 2008-10-20 | 2008-10-24 | 2008-11-01 | Actual | 2008-11-10 | 2008-12-23 | 2009-08-24 | 2009-08-30 | 2009-09-09 | 2009-09-19 | 2009-09-24 | Actual | 2009-10-04 | 2009-10-11 | 101342.69 | 2009-12-05 | 15-Dec-09 | Actual | 2009-12-20 |  | 2011-03-19
Boneya PLC, OWRB/CS/WSG/07/09 | CQ | LS& TB | 129265 | Post | Plan | 2008-08-08 | 2008-08-23 | 2008-09-02 | 2008-09-09 | 2008-09-14 | 2008-09-19 | Plan | 2008-10-01 | 2008-12-15 | 2009-03-15 | 2009-03-21 | 2009-03-31 | 2009-04-10 | 2009-04-15 | Plan | 2009-04-25 | 2009-05-02 |  | 2009-05-15 | 2009-12-01 | Plan | 2009-12-11 | NA | 2011-02-28
[5 empty] | Actual | 2008-09-30 | 2008-10-10 |  | 2008-10-20 | 2008-10-24 | 2008-11-01 | Actual | 2008-11-10 | 2008-12-23 | 2009-08-24 | 2009-08-30 | 2009-09-09 | 2009-09-19 | 2009-09-24 | Actual | 2009-10-04 | 2009-10-11 | 125402.66 | 2009-12-05 | 15-Dec-09 | Actual | 2009-12-20 |  | 2011-03-19
Consultancy service for capacity building & data upadating works (2 teams), OWMEB/CS/WSG/01-02/2012 | QCBS | LS& TB | 138336.5035 | Post | Plan | 2012-01-05 | 2012-01-20 | 2012-01-30 | 2012-02-06 | 2008-09-14 | 2012-02-16 | Plan | 2012-02-28 | 2012-04-03 | 2012-04-18 | 2012-04-24 | 2012-05-04 | 2012-05-14 | 2012-05-19 | Plan | 2012-05-29 | 2012-06-05 |  | 2012-05-03 | 2012-05-13 | Plan | 2012-05-23 | NA | 2013-01-08
[5 empty] | Revised | 2012-05-01 | 2012-05-11 | 2012-05-18 | 2012-05-28 | 2008-10-24 | 2012-06-05 |  | 2012-06-17 | 2012-07-22 | 2012-08-06 | 2012-08-12 | 2012-08-22 | 2012-09-01 | 2012-09-06 |  | 2012-09-16 | 2012-09-23 |  | 2012-10-03 | 2012-10-10 |  | 2013-01-23 |  | 2013-02-07
[5 empty] | Actual | 2012-05-06 | 2012-05-16 | 2012-05-23 | 2012-06-02 |  |  | Actual | [7 empty] | Actual | [5 empty] | Actual
B. Capac ity Building at Wereda Level
WaSHCO, WaSH Vol and Care Takers Training | QCBS | LS& TB | 145253.3287 | Post | Plan | 2012-07-30 | 2012-08-09 | 2012-08-16 | 2012-08-26 | 2012-08-29 | 2012-09-03 |  | 2012-09-15 | 2012-10-20 | 2012-11-04 | 2012-11-10 | 2012-11-20 | 2012-11-30 | 2012-12-05 |  | 2012-12-15 | 2012-12-22 |  | 2013-01-01 | 2013-01-08 |  | 2013-02-22 | NA | 2013-03-09
Actual
Training on WQTK and Computer for Weredas | CQ | LS& TB | 47933.5985 | Post | Plan | 2012-07-30 | 2012-08-09 | 2012-08-16 | 2012-08-26 | 2012-08-29 | 2012-09-03 |  | 2012-09-15 | 2012-10-20 | 2012-11-04 | 2012-11-10 | 2012-11-20 | 2012-11-30 | 2012-12-05 |  | 2012-12-15 | 2012-12-22 |  | 2013-01-01 | 2013-01-08 |  | 2013-02-22 | NA | 2013-03-09
Actual
Total Cost |  |  | 1236378.4307 |  | Plan
[5 empty] | Actual | [17 empty] | 815283.26
Formulas:
Preparation Request for Proposals = [No-objection Date]-15
No-objection Date = [Request for EOI (where required)]-10
No-objection Date = [Consultant Proposals]-12
Request for EOI (where required) = [Lead-time before shortlist]-7
Request for EOI (where required) = [No-objection Date]+7
Lead-time before shortlist = [No-objection Date]-10
Lead-time before shortlist = [Request for EOI (where required)]+10
No-objection Evaluation Report (T) = [Submission Evaluation Report (T)]+6
Opening Financial Proposals = [No-objection Evaluation Report (T)]+10
Preparation Eval Report (T) (F) = [Opening Financial Proposals]+10
Negotiations (N) = [Preparation Eval Report (T) (F)]+5
Draft Contract = [Negotiations (N)]+10
Contract Implementation = [Contract Signature]+10
Contract Implementation = [Final Report]-15
Contract Award = [Contract Signature]-10
Contract Award = [No-objection Date]+10
Submission/ Opening Date = [Consultant Proposals]+35
Submission Evaluation Report (T) = 15+[Submission/ Opening Date]
Contract Signature = 10+[Contract Award]
Contract Signature = [Contract Award]+7
Consultant Proposals = [No-objection Date]+12
Final Report = [Contract Signature]+120

## GoodsLT
Procurement of Goods (Urban)
Organisation: | Oromia Towns Water Supply and Sewerage Service Entrprises | [16 empty] | 17.3499
Project/Programme: | Urban Water Supply and Sanitation Project
Loan No: | IDA Credit 3901-ET and IDA Grant 085-ET
Description | BASIC DATA | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN | [10 empty] | Contract Implementation
[10 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization
| Package Number | Lot Number | Estimated Amount in USD | Procurement Method | Pre-or Post Qual. | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection (Internal Approval for NCB) Date | On-line UNDB Gateway National Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in USD | Date Contract Award | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
[8 empty] | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks |  |  | 1 wk | 1.5-3 wks
Supply of Pipe, fittings and Accessories for Ambo Town | OWRB/UWSG/01/2010 |  | 1554116.7747 | ICB | Post | Prior | Plan | 2011-02-10 | 2011-02-20 | 2011-02-27 | 2011-03-09 | 2011-04-23 | 2011-05-03 | 2011-05-13 | Plan |  | 2011-05-20 | 2011-05-27 | 2011-06-01 | 2011-09-29 | 2011-10-04
[7 empty] | Revised | 2012-02-03 | 2012-02-13 | 2012-02-20 | 2012-03-01 | 2012-04-15 | 2012-04-25 | 2012-05-05 |  |  | 2012-05-12 | 2012-05-19 | 2012-05-29 | 2012-09-26 | 2012-10-06
[7 empty] | Actual | 2011-04-03 | 2011-04-13 | 2011-04-20 | 2011-04-30 | 2011-06-14 | 17-Jul-11 | 09-Dec.-2011 | Actual | 1314667.0263 | 15-Dec-11 | 23-Jan-12 | 29- Mar-12 | 2012-07-27 | 2012-08-06
Supply of Pipe, fittings and Accessories for Bule Hora Town | OWRB/UWSG/02/2010 |  | 2148157.9583 | ICB | Post | Prior | Plan | 2011-02-10 | 2011-02-20 | 2011-02-27 | 2011-03-09 | 2011-04-23 | 2011-05-03 | 2011-05-13 | Plan |  | 2011-05-20 | 2011-05-27 | 2011-06-01 | 2011-09-29 | 2011-10-04
[7 empty] | Revised | 2012-02-03 | 2012-02-13 | 2012-02-20 | 2012-03-01 | 2012-04-15 | 2012-04-25 | 2012-05-05 |  |  | 2012-05-12 | 2012-05-19 | 2012-05-29 | 2012-09-26 | 2012-10-06
[7 empty] | Actual | 2122-06-11 | 2122-06-21 | 2122-06-28 | 2011-04-30 | 2011-06-14 | 17-Jul-11 | 09-Dec.-2011 | Actual | 1619650.9658 | 15-Dec-11 | 23-Jan-12 | 29- Mar-12 | 2012-07-27 | 2012-08-06
Supply of Pipe, fittings and Accessories for Meki Town | OWRB/UWSG/03/2010 |  | 902282.9382 | ICB | Post | Prior | Plan | 2011-02-10 | 2011-02-20 | 2011-02-27 | 2011-03-06 | 2011-04-20 | 2011-04-30 | 2011-05-10 | Plan |  | 2011-05-17 | 2011-05-24 | 2011-05-29 | 2011-09-26 | 2011-10-01
[7 empty] | Revised | [10 empty] | 2012-05-19 | 2012-05-29 | 2012-09-26 | 2012-10-06
[7 empty] | Actual | 2011-04-06 | 2011-04-16 | 2011-04-23 | 2011-04-30 | 27-May-11 | 14-Jun-11 | 25-Nov-2011 | Actual | 480430.3323 | 7-Dec-11 | 23-Jan-12 | 29- Mar-12 | 2012-07-27 | 2012-08-06
Supply and Installation of Electro-mechanical equipment for Ambo Town | OWRB/UWS/EM/01/2010 |  | 1372708.1343 | ICB | Post | Prior | Plan | 2011-11-15 | 2011-11-25 | 2011-12-02 | 2011-12-09 | 2012-01-23 | 2012-02-02 | 2012-02-12 | Plan |  | 2012-02-19 | 2012-02-26 | 2012-03-02 | 2012-06-30 | 2012-07-05
[7 empty] | Revised | 2012-03-18 | 2012-03-28 | 2012-04-04 | 2012-04-11 | 2012-05-26 | 2012-06-05 | 2012-06-15 | Revised |  | 2012-06-22 | 2012-06-29 | 2012-07-04 | 2012-11-01
[7 empty] | Revised |  | 2012-04-26 | 2012-07-03 | 2012-07-10 | 2012-08-24 | 2012-09-13 | 2012-09-23 | Revised |  | 2012-09-30 | 2012-10-20 | 2012-10-25 | 2013-02-22 | 2013-03-04
[7 empty] | Actual | [7 empty] | Actual
Supply and Installation of Electro-mechanical equipment for Bule Hora Town | OWRB/UWS/EM/02/2010 |  | 684096.6807 | ICB | Post | Prior | Plan | 2011-08-15 | 2011-08-25 | 2011-09-01 | 2011-09-08 | 2011-10-23 | 2011-11-02 | 2011-11-12 | Plan |  | 2011-11-19 | 2011-11-26 | 2011-12-01 | 2012-03-30 | 2012-04-04
[7 empty] | Revised | 2012-04-15 | 2012-04-25 | 2012-05-02 | 2012-05-09 | 2012-06-23 | 2012-07-03 | 2012-07-13 | Revised |  | 2012-07-20 | 2012-07-27 | 2012-08-01 | 2012-11-29
[7 empty] | Revised |  | 2012-06-15 | 2012-06-30 | 2012-07-07 | 2012-08-21 | 2012-09-10 | 2012-09-20 | Revised |  | 2012-09-27 | 2012-10-17 | 2012-10-22 | 2013-02-19 | 2013-03-01
[7 empty] | Actual | [7 empty] | Actual
Supply and Installation of Electro-mechanical equipment for Meki Town | OWRB/UWS/EM/03/2010 |  | 387599.6035 | NCB | Post | Post | Plan | 2011-08-15 | 2011-08-20 | 2011-08-27 | 2011-09-03 | 2011-10-18 | 2011-10-28 | 2011-11-07 | Plan |  | 2011-11-14 | 2011-11-21 | 2011-11-26 | 2012-03-25 | 2012-03-30
[7 empty] | Revised | 2012-03-18 | 2012-03-28 | 2012-04-04 | 2012-04-11 | 2012-05-26 | 2012-06-05 | 2012-06-15 | Revised |  | 2012-06-22 | 2012-06-29 | 2012-07-04 | 2012-11-01
[7 empty] | Revised |  | 2012-06-15 | 2012-06-30 | 2012-07-07 | 2012-08-06 | 2012-08-26 | 2012-08-26 | Revised |  | 2012-09-02 | 2012-09-22 | 2012-09-27 | 2013-01-25 | 2013-02-04
[7 empty] | Actual | [7 empty] | Actual
Supply and Installation of Electro-mechanical equipment for Chiro Town | OWRB/UWS/EM/04/2010 |  | 247840.0452 | NCB | Post | Post | Plan | 2011-08-15 | 2011-08-20 | 2011-08-27 | 2011-09-03 | 2011-10-18 | 2011-10-28 | 2011-11-07 | Plan |  | 2011-11-14 | 2011-11-21 | 2011-11-26 | 2012-03-25 | 2012-03-30
[7 empty] | Revised | 2012-07-10 | 2012-07-15 | 2012-07-22 | 2012-07-29 | 2012-09-12 | 2012-09-22 | 2012-10-02 | Revised |  | 2012-10-09 | 2012-10-16 | 2012-10-21 | 2013-02-18
[7 empty] | Revised |  | 2012-06-15 | 2012-06-30 | 2012-07-07 | 2012-08-06 | 2012-08-26 | 2012-08-26 | Revised |  | 2012-09-02 | 2012-09-22 | 2012-09-27 | 2013-01-25 | 2013-02-04
[7 empty] | Actual | [7 empty] | Actual
Supply and Installation of Electro-mechanical equipment for Bishoftu Town | OWRB/UWS/EM/05/2010 |  | 260809.0686 | NCB | Post | Post | Plan | 2011-01-05 | 2011-01-10 | 2011-01-17 | 2011-01-24 | 2011-03-10 | 2011-03-20 | 2011-03-30 | Plan |  | 2011-04-06 | 2011-04-13 | 2011-04-18 | 2011-08-16 | 2011-08-21
[7 empty] | Revised | 2012-07-10 | 2012-07-15 | 2012-07-22 | 2012-07-29 | 2012-09-12 | 2012-09-22 | 2012-10-02 | Revised |  | 2012-10-09 | 2012-10-16 | 2012-10-21 | 2013-02-18
[7 empty] | Revised |  | 2012-06-15 | 2012-06-30 | 2012-07-07 | 2012-08-06 | 2012-08-26 | 2012-08-26 | Revised |  | 2012-09-02 | 2012-09-22 | 2012-09-27 | 2013-01-25 | 2013-02-04
[7 empty] | Actual | [7 empty] | Actual
Supply and Installation of Electro-mechanical equipment for Mojo Town | OWRB/UWS/EM/06/2010 |  | 145534.629 | NCB | Post | Post | Plan | 2011-01-05 | 2011-01-10 | 2011-01-17 | 2011-01-24 | 2011-03-10 | 2011-03-20 | 2011-03-30 | Plan |  | 2011-04-06 | 2011-04-13 | 2011-04-18 | 2011-08-16 | 2011-08-21
[7 empty] | Revised | 2012-07-10 | 2012-07-15 | 2012-07-22 | 2012-07-29 | 2012-09-12 | 2012-09-22 | 2012-10-02 | Revised |  | 2012-10-09 | 2012-10-16 | 2012-10-21 | 2013-02-18
[7 empty] | Revised |  | 2012-06-15 | 2012-06-30 | 2012-07-07 | 2012-08-06 | 2012-08-26 | 2012-08-26 | Revised |  | 2012-09-02 | 2012-09-22 | 2012-09-27 | 2013-01-25 | 2013-02-04
[7 empty] | Actual | [7 empty] | Actual
Sebeta Town Procurement of office equipment | SWSSE/WDF/G/02/2010 |  | 1978.28 | NS | Post | Post | Plan | 2010-04-01 | N/A | NA | 2010-05-15 | NA | 2010-05-25 | NA | Plan |  | 2010-06-11 | 2010-06-12 | N/A | 2010-06-19 | 2010-06-21
[7 empty] | Actual | [6 empty] | 08-Apr-10 | Actual | 1978.28
Sebeta Town Procurement of GPS | SWSSE/WDF/G/03/2010 |  | 3458.23 | NS | Post | Post | Plan | 2010-10-17 | N/A | NA | 2010-11-01 | NA | 2010-11-11 | NA | Plan |  | 2010-11-21 | 2010-11-26 | N/A | 2010-12-11 | 2010-12-13
[7 empty] | Actual | [7 empty] | Actual | 3458.23
Sebeta Town Supply of Pipes and Fittings for Tertiary line | SWSSE/WDF/G/04/2010 |  | 2469935.21 | ICB | Post | Prior | Plan | 2010-10-15 | 2010-10-25 | 2010-11-01 | 2010-11-08 | 2010-12-23 | 2011-01-07 | 2011-01-17 | Plan |  | 2011-01-24 | 2011-02-08 | 2011-03-10 | 2011-07-08 | 2011-07-13
[7 empty] | Revised plan |  |  |  |  | 2012-01-02 | 2012-01-12 | 2012-01-19 | Revised plan |  | 2012-01-26 | 2012-02-10 | 2012-02-25 | 2012-05-25 | 2012-05-30
[7 empty] | Actual |  |  |  |  | 1-Feb-11 | 18-Mar-11 | 25-Apr-11 | Actual | 4346160.38
Sebeta Town Supply and Installation of Electro-mechanical equipment | SWSSE/WDF/G/05/2010 |  | 841156.8 | ICB | Post | Prior | Plan | 2011-01-05 | 2011-01-15 | 2011-01-25 | 2011-02-01 | 2011-03-23 | 2011-04-02 | 2011-04-12 | Plan |  | 2011-04-19 | 2011-05-04 | 2011-06-03 | 2011-11-30 | 2011-12-05
[7 empty] | Revised plan | 2012-03-29 | 2012-04-08 | 2012-04-18 | 2012-04-25 | 2012-06-14 | 2012-06-24 | 2012-07-04 | Revised plan |  | 2012-07-11 | 2012-07-26 | 2012-08-25 | 2012-12-23 | 2012-12-28
[7 empty] | Actual | [7 empty] | Actual
Total Cost For Goods for Large Towns |  |  | 11019674.3525 | [12 empty] | 7766345.2145
Formulas:
Spec Proc Notice Advert = [Bidding Period]-10
Bidding Period = [Spec Proc Notice Advert]+10
Bidding Period = [Bid Closing-Opening]-45
Bid Closing-Opening = [Bidding Period]+45
Bid Closing-Opening = [Bid Evaluation]-10
Bid Evaluation = [Bid Closing-Opening]+10
Bid Evaluation = [No-objection Date]-10
No-objection Date = [Bid Evaluation]+10
No-objection Date = [Date Contract Award]-7
Date Contract Award = [No-objection Date]+7
Date Contract Award = [Date Contract Signature]-7
Date Contract Signature = [Date Contract Award]+7
Date Contract Signature = [Contract Implementation]-10
Contract Implementation = [Date Contract Signature]+5
Contract Implementation = [Arrival of Goods]-120
Arrival of Goods = [Contract Implementation]+120
Arrival of Goods = [Date Contract Signature]+7
Inspection Final Acceptance = [Arrival of Goods]+5

## WorksLT
Procurement of Works for Large Towns (Urban)
Country/Organization: | FDR of Ethiopia/OromiaTowns Water Supply and Sewerage Service Improvement and Expansion Project | [16 empty] | 17.3499
Project/Programmed: | Urban Water Supply and Sanitation Project
Loan #: | IDA Credit 3901-ET and IDA Grant 085-ET
Description* | Package Number | Basic Data | [5 empty] | Plan vs. Actual | Draft Bid Documents, including specs and quantities, draft SPN |  | For All Non ICB, No-objection will be requested from MOWR PMU | [5 empty] | Contract Finalization |  |  | Contract Implementation
[11 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Plan vs. Actual
|  | Lot Number | Lump sum or Bill of Quantities | Procurement Method | Estimated Amount in USD | Pre/Post Qualification | Prior or Post Review |  | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway National Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date |  | Contract Amount in USD | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
List of Contracts | [8 empty] | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks |  |  | 1 wk | 1.5-3 wks
Test Water Well Drilling for Bule Hora Town | OWRB\UPWD/01/2010 |  | BOQ | NCB | 48415.2646 | Post | Post | Plan | 2011-02-15 | 2011-02-20 | 2011-02-27 | 2011-03-06 | 2011-04-05 | 2011-04-15 | 2011-04-18 | Plan |  | 2011-04-23 | 2011-04-28 | 2011-05-08 | 2011-07-07 | 2012-04-27
[8 empty] | Actual | 2011-02-27 | 2011-03-04 | 2011-03-11 | 2011-03-18 | 2011-04-07 | 2011-04-20 | 2011-04-25 | Actual | 44957.0315 | 2-Jul-10 | 30-Jul-10 | 2010-08-09 | 2010-11-07 | 2011-07-30
Test Water Well Drilling for Meki Town | OWRB\UPWD/02/2010 |  | BOQ | NCB | 24207.6323 | Post | Post | Plan | 2011-02-15 | 2011-02-20 | 2011-02-27 | 2011-03-06 | 2011-04-05 | 2011-04-15 | 2011-04-18 | Plan |  | 2011-04-23 | 2011-04-28 | 2011-05-08 | 2011-07-07 | 2012-07-06
[8 empty] | Actual | 2011-02-27 | 2011-03-04 | 2011-03-11 | 2011-03-18 | 2011-04-07 | 2011-04-20 | 2011-04-25 | Actual | 18545.8129 | 2-Jul-10 | 30-Jul-10 | 2010-08-09 | 2010-10-28 | 2011-07-30
Test Water Well Drilling for Chiro & Shashemene Towns | OWRB\UPWD/03/2010 |  | BOQ | NCB | 57637.2198 | Post | Post | Plan | 2011-03-15 | 2011-03-20 | 2011-03-27 | 2011-04-03 | 2011-05-03 | 2011-05-13 | 2011-05-16 | Plan |  | 2011-05-21 | 2011-05-26 | 2011-06-05 | 2011-08-04 | 2012-08-03
[8 empty] | Actual | 2011-02-27 | 2011-03-04 | 2011-03-11 | 2011-03-18 | 2011-04-07 | 2011-04-20 | 2011-04-25 | Actual | 71397.6449 | 2-Jul-10 | 30-Jul-10 | 2010-08-09 | 2010-10-28 | 29-Feb-11
Production Water Well Drilling for Bule Hora Town | OWRB\UPWD/01/2010 |  | BOQ | NCB | 277842.6965 | Post | Post | Plan | 2011-02-15 | 2011-02-20 | 2011-02-27 | 2011-03-06 | 2011-04-05 | 2011-04-15 | 2011-04-18 | Plan |  | 2011-04-23 | 2011-04-28 | 2011-05-08 | 2011-07-07 | 2011-07-17
[8 empty] | Rev-2 | [7 empty] | Rev-2 |  |  |  | 2012-06-15 | 2012-08-14 | 2012-08-24
[8 empty] | Actual | 24-May-11 | 27-May-11 |  | 25-Jul-11 | 26-Aug-11 | 16-Sep-11 | NA | Actual | 207065.62 | 06-Oct-11 | 21-Nov-11
Production Water Well Drilling for Meki Town | OWRB\UPWD/02/2010 |  | BOQ | NCB | 176080.2656 | Post | Post | Plan | 2011-02-15 | 2011-02-20 | 2011-02-27 | 2011-03-06 | 2011-04-05 | 2011-04-15 | 2011-04-18 | Plan |  | 2011-04-23 | 2011-04-28 | 2011-05-08 | 2011-07-07 | 2011-07-17
[8 empty] | Actual | 24-May-11 | 27-May-11 |  | 25-Jul-11 | 26-Aug-11 | 16-Sep-11 |  | Actual | 92907.6104 | 6-10-11 | 28-Oct-11 | 2011-11-07 | 2012-01-26 | 2013-01-25
[8 empty] | Plan | 2011-02-15 | 2011-02-15 | 2011-02-22 | 2011-03-01 | 2011-03-31 | 2011-04-10 | 2011-04-20 | Plan |  | 2011-04-25 | 2011-04-30 | 2011-05-10 | 2011-07-09 | 2012-07-08
Production Water Well Drilling for Bishoftu, | OWRB\UPWD/02/2010 |  | BOQ | NCB | 186386.72 | Post | Post | Revised | [6 empty] | 2012-02-20 | Revised |  | 2012-02-24 | 2012-03-15 | 2012-03-25 | 2012-05-24 | 2012-06-03
[8 empty] | Rev-2 | [7 empty] | Rev-2 |  |  |  |  | 2012-08-29 | 2013-08-29
[8 empty] | Actual | 20-Sep-11 | 28-Sep-11 |  | 23-Dec-11 | 23-Jan-12 | 15-Feb-12 |  | Actual | 948354.4574 | 26-Apr-12 | 9-may-12 | 2012-05-19
[8 empty] | Plan | 2011-02-15 | 2011-02-15 | 2011-02-22 | 2011-03-01 | 2011-03-31 | 2011-04-10 | 2011-04-20 | Plan |  | 2011-04-25 | 2011-04-30 | 2011-05-10 | 2011-07-09 | 2012-07-08
Production Water Well Drilling for Modjo | OWRB\UPWD/05/2010 |  | BOQ | NCB | 186386.72 | Post | Post | Revised | [6 empty] | 2012-02-20 | Revised |  | 2012-02-24 | 2012-03-15 | 2012-03-25 | 2012-05-24 | 2013-05-24
[8 empty] | Rev-2 | [7 empty] | Rev-2 |  |  |  |  | 2012-08-29 | 2013-08-29
[8 empty] | Actual | 20-Sep-11 | 28-Sep-11 |  | 23-Dec-11 | 23-Jan-12 | 15-Feb-12 |  | Actual | 948354.4574 | 26-Apr-12 | 9-May-12 | 2012-05-19
Production Water Well Drilling Chiro Towns | OWRB\UPWD/02/2010 |  | BOQ | NCB | 186386.72 | Post | Post | Revised | [6 empty] | 2012-02-20 | Revised |  | 2012-02-24 | 2012-03-15 | 2012-03-25 | 2012-05-24 | 2013-05-24
[8 empty] | Rev-2 | [7 empty] | Rev-2 |  | 2012-06-10 | 2012-06-15 | 2012-06-30 | 2012-08-29 | 2012-09-08
[8 empty] | Actual | 20-Sep-11 | 28-Sep-11 |  | 23-Dec-11 | 23-Jan-12 | 15-Feb-12 |  | Actual
[8 empty] | Plan | 2010-10-01 | 2010-10-01 | 2010-10-08 | 2010-10-15 | 2010-11-14 | 2010-11-24 | 2010-12-04 | Plan |  | 2010-12-09 | 2010-12-14 | 2010-12-24 | 2012-06-16 | 2012-12-13
Ambo Town Civil Work Construction | OWRB\UCWC/01/2010 |  | BOQ | NCB | 2282402.3706 | Post | Post | Rev-2 | [7 empty] | Rev-2 |  | 2012-06-10 | 2012-06-15 | 2012-06-30 | 2012-08-29 | 2012-09-08
[8 empty] | Actual |  |  |  | 3-Feb-11 | 1-Apr-11 | 19-May-11 |  | Actual | 2459650.6112
[8 empty] | Plan | 2011-03-01 | 2011-03-01 | 2011-03-08 | 2011-03-15 | 2011-04-14 | 2011-04-24 | 2011-05-04 | Plan |  | 2011-05-09 | 2011-05-14 | 2011-05-24 | 2012-06-17 | 2012-12-14
Bule Hora Town Civil Work Construction | OWRB\UCWC/02/2010 |  | BOQ | NCB | 1909024.5056 | Post | Post | Rev-2 | [7 empty] | Rev-2 |  |  |  | 2012-06-10 | 2012-08-09 | 2012-08-19
[8 empty] | Actual |  |  |  | 3-Feb-11 | 1-Apr-11 | 26-Apr-11 |  | Actual | 1909024.5056 |  | 15-Jul-11
[8 empty] | Plan | 2011-03-01 | 2011-03-01 | 2011-03-08 | 2011-03-15 | 2011-04-14 | 2011-04-24 | 2011-05-04 | Plan |  | 2011-05-09 | 2011-05-14 | 2011-05-24 | 2012-06-17 | 2012-12-14
Meki Town Civil Work Construction | OWRB\UCWC/02/2010 |  | BOQ | NCB | 684523.705 | Post | Post | Rev-2 | [7 empty] | Rev-2 |  | 2012-06-10 | 2012-06-15 | 2012-06-30 | 2012-08-29 | 2012-09-08
[8 empty] | Actual |  |  |  | 24-Mar-11 | 2-May-11 | 19-May-11 |  | Actual | 684523.705
[8 empty] | Plan | 2011-04-01 | 2011-04-06 | 2011-04-13 | 2011-04-20 | 2011-05-20 | 2011-05-30 | 2011-06-02 | Plan |  | 2011-06-07 | 2011-06-12 | 2011-06-22 | 2012-08-15 | 2013-02-11
Chiro Town Civil Work Construction and Supply of Pipe and fittings | OWRB\UCWC/04/2010 |  | BOQ | NCB | 1824133.1627 | Post | Post | Revised |  |  |  | 2012-02-20 | 2012-03-31 | 2012-04-07 | 2012-04-10 |  |  | 2012-04-20 | 2012-04-30 | 2012-05-15 | 2013-01-10 | 2014-01-10
[8 empty] | Rev-2 | [7 empty] | Rev-2 | [5 empty] | 30-Mar-14
[8 empty] | Actual | [7 empty] | Actual | 2910896.9856 | 30-May-12 | 8-Jun-2012 | 2012-06-18 | 30-Mar-13
[8 empty] | Plan | 2011-04-01 | 2011-04-06 | 2011-04-13 | 2011-04-20 | 2011-05-20 | 2011-05-30 | 2011-06-02 | Plan |  | 2011-06-07 | 2011-06-12 | 2011-06-22 | 2012-08-15 | 2013-02-11
BishoftuTown Civil Work Construction & supply of Pipe and Fittings | OWRB\UCWC/05/2010 |  | BOQ | NCB | 2901127.6297 | Post | Post | Revised |  |  |  | 2012-02-20 | 2012-03-31 | 2012-04-07 | 2012-04-10 |  |  | 2012-04-20 | 2012-04-30 | 2012-05-15 | 2013-01-10 | 2014-01-10
[8 empty] | Rev-2 | 2012-06-05 |  | 2012-06-15 | 2012-06-25 | 2012-07-25 | 2012-08-04 |  | Rev-2 |  | 2012-08-11 | 2012-08-16 | 2012-08-31 | 2012-10-30 | 2013-10-30
[8 empty] | Actual | [7 empty] | Actual
[8 empty] | Plan | 2011-04-01 | 2011-04-06 | 2011-04-13 | 2011-04-20 | 2011-05-20 | 2011-05-30 | 2011-06-02 | Plan |  | 2011-06-07 | 2011-06-12 | 2011-06-22 | 2012-08-15 | 2013-02-11
Modjo Town Civil Work Construction ans Supply of Pipe & Fittings | OWRB\UCWC/06/2010 |  | BOQ | NCB | 1720772.3368 | Post | Post | Revised |  |  |  | 2012-02-20 | 2012-03-31 | 2012-04-07 | 2012-04-10 |  |  | 2012-04-20 | 2012-04-30 | 2012-05-15 | 2013-01-10 | 2014-01-10
[8 empty] | Rev-2 | [7 empty] | Rev-2 |  |  |  |  | 2013-03-28 | 2014-03-28
[8 empty] | Actual | [7 empty] | Actual | 3059265.1508 | 2012-05-30 | 2012-06-11 | 2012-06-21
Sebeta Town Water Well Drilling | NCB -SWSSE/WDF/02/2010 |  | BOQ | NCB | 425777.67 | Post | Post | Plan | 2010-05-25 | 2010-06-04 | 2010-06-11 | 2010-06-28 | 2010-07-28 | 2010-08-18 | 2010-08-28 | Plan |  | 2010-09-07 | 2010-09-17 | 2010-10-02 | 2011-09-27 | 2012-09-26
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  | 05 Dec 11 | 2011-12-12 | 2012-04-10 | 2013-04-10
[8 empty] | Actual |  |  |  | 2011-08-02 | 2011-09-05 | 15-Aug-10 | 22 Nov 11 | Actual | 631006.98 | 2011-11-30
Sebeta Town Civil Work Construction | NCB -SWSSE/WDF/03/2010 |  | BOQ | NCB | 1954957.94 | Post | Post | Plan | 2010-08-15 | 2010-08-25 | 2010-09-01 | 2010-09-01 | 2010-10-01 | 2010-10-22 | 2010-11-01 | Plan |  | 2010-11-11 | 2010-11-21 | 2010-12-06 | 2011-12-01 | 2012-11-30
[8 empty] | Revised plan | [7 empty] | Revised plan |  |  |  |  | 2012-09-29 | 2013-09-29
[8 empty] | Actual | [7 empty] | Actual | 1998071.74 | 2011-03-16 | 23-Mar-11 | 8-Apr-11
Large towns Total Cost |  |  |  |  | 14846062.5594 | [11 empty] | 15984022.3128
Formulas:
No-objection Date = [Prep & Submission by Ex Agency]+5
No-objection Date = [Bid Evaluation]+3
Spec Proc Notice Advert = [No-objection Date]+7
Spec Proc Notice Advert = [Bidding Period]-([Bidding Period, row above]-[Spec Proc Notice Advert, row above])
Bidding Period = [Spec Proc Notice Advert]+7
Bidding Period = [Spec Proc Notice Advert]
Bid Closing-Opening = [Bidding Period]+30
Bid Evaluation = [Bid Closing-Opening]+10
Date Contract Award = [No-objection Date]+5
Date Contract Award = [Bid Evaluation]+7
Date Contract Signature = [Date Contract Award]+5
Contract Implementation = [Date Contract Signature]+10
Substantial Completion = [Contract Implementation]+60
Substantial Completion = [Date Contract Signature]+90
Final Acceptance = [Date Contract Signature]+365
Final Acceptance = [Substantial Completion]+365
Prep & Submission by Ex Agency = [No-objection Date]-([No-objection Date, row above]-[Prep & Submission by Ex Agency, row above])
Prep & Submission by Ex Agency = [No-objection Date]-10

## ConsultancyLT
Procurement of Consultancy Services (Urban)
Country/Organization: | FDR of Ethiopia/OromiaTowns Water Supply and Sewerage Service Improvement and Expansion Project | [16 empty] | 17.3499
Project/Programmed: | Urban Water Supply and Sanitation Project
Loan #: | IDA Credit 3901-ET and IDA Grant 085-ET
Description* | Selection Method | Contract Id | Lumpsum or Time-Based | Estimated Amount in USD | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway/ National Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan Vs Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Evaluation (T) (F) | No-objection Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Eval Report (T) (F) & Negotiated Draft Contract | No-objection Eval Report (T) (F)/ Negotiated Draft Contract | Contract Amount in USD | Contract Award | Contract Signature |  | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
List of Contracts | [6 empty] | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks |  | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks |  |  | 2 wks | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks
SABA+ARMA for Adama &Assela (to step 2a) and Ambo & Bule Hora (to Step 3) | QCBS | ICB-UWSSP-LT/06-4 /S002/2009 | LS & TB | 178675.3814 | Post | Plan | 2008-05-01 | 2008-05-11 | 2008-05-18 | 2008-05-23 | 2008-06-07 | 2008-06-17 | Plan | 2008-06-24 | 2008-07-09 | 2008-07-19 | 2008-07-26 | 2008-07-31 | 2008-08-03 |  | Plan | 2008-08-10 | 2008-08-17 | 2008-08-24 |  | 2008-09-16 | 2008-09-21 | Plan | 2010-07-21 00:05 | 2010-06-21 | 2010-07-21
[6 empty] | Actual | 2008-03-12 | 2008-04-03 | 2008-04-13 | 2008-04-18 | 2008-04-29 | NA | Actual | 2008-05-01 | 2008-05-15 | 2008-06-04 | 2008-07-02 | 2008-07-06 | 2008-07-15 |  | Actual | 2008-07-18 | 2008-07-28 | 2008-08-04 | 199650.4303 | 2008-08-04 | 2008-08-14 | Actual | 2008-08-24 |  | 30- Mar-13
Meteferia for Bishftu, Mojo & Chiro (to Step 2a) and for Meki (to Step 3) | QCBS | ICB-UWSSP-LT/06-4 /S002/2009 | LS | 41553.8994 | Post | Plan | 2008-05-01 | 2008-05-11 | 2008-05-16 | 2008-06-06 | 2008-06-21 | 2008-07-01 | Plan | 2008-07-08 | 2008-08-05 | 2008-08-15 | 2008-08-22 | 2008-08-29 | 2008-09-08 |  | Plan | 2008-09-18 | 2008-09-23 | 2008-09-28 |  | 2008-09-16 | 1900-01-04 00:03 | Plan | 1900-01-19 00:05 | 1900-12-15 00:05 | 1901-01-14 00:05
[6 empty] | Actual | 2008-03-12 | 2008-04-03 | 2008-04-13 | 2008-04-18 | 2008-04-29 | NA | Actual | 2008-05-01 | 2008-05-15 | 2008-06-04 | 2008-07-02 | 2008-07-06 | 2008-07-15 |  | Actual | 2008-07-18 | 2008-07-28 | 2008-08-04 | 41553.8994 |  | 2012-06-30 | Actual | 2012-07-10
Consultancy Service for step 2b and Step 3 for Bishftu, Chiro and Mojo towns | QCBS | LCB-UWSSP-1/2010 | LS | 163799.9066 | Post | Plan | 2010-08-21 | 2010-08-31 | 2010-09-05 | 2010-09-26 | 2010-10-11 | 2010-10-21 | Plan | 2010-10-28 | 2010-11-25 | 2010-12-05 | 2010-12-12 | 2010-12-19 | 2010-12-29 |  | Plan | 2011-01-08 | 2011-01-13 | 2011-01-18 |  | 2011-01-25 | 2011-01-30 | Plan | 2011-02-09 | 2011-10-07 | 2011-11-06
[6 empty] | Actual | 19-Jul-11 | 28-Jul-11 | NA | 20-Aug-11 | 10-Sep-11 | NA | Actual | 2011-10-22 | 2011-12-15 | 2012-04-10 | 2012-03-30 | 2012-04-08 | 2012-04-09 |  | Actual | 15-Apr-12 | 30-Apr-12 | 10-May-12 | 189369.9676 | 2012-06-20 | 30-June-12 | Actual | 2012-07-10 | 2013-02-28 | 30- Mar-13
Environmental and Social Impact Assessment for Ambo town | QCBS | LCB-UWSSP-LT/06-04/SOO/2009 | LS | 8645.59 | Post | Plan | 2011-11-07 | 2011-11-17 | 2011-12-24 | 2012-01-12 | 2012-01-28 | 2012-02-11 | Plan | 2012-02-18 | 2012-03-17 | 2012-03-27 | 2012-04-03 | 2012-04-10 | 2012-04-20 |  | Plan | 2012-04-30 | 2012-05-05 | 2012-05-10 |  | 2012-05-17 | 2012-05-22 | Plan
[6 empty] | Revised | [7 empty] | 2012-06-10 | 2012-07-10 | 2012-07-25 | 2012-08-01 | 2012-08-09 | 2012-08-24 |  | Revised | 2012-09-08 | 2012-09-23 |  |  | 2012-09-30 | 2012-10-20 |  | 2012-11-10 | 2013-02-08 | 2013-03-10
[6 empty] | Actual | 2011-12-08 | 2011-12-18 | NA | 2012-01-15 | 2012-02-01 | NA | Actual | 2012-02-21 | 2012-03-21 | 2012-03-30 | 2012-05-02 | 2012-05-05 | 2012-05-07 |  | Actual | 23-Apr-12 | 2012-05-08 | 2012-05-13 | 11815.6301 | 2012-05-16 | 24-May-12 | Actual | 2012-05-29
Environmental and Social Impact Assessment for Bule Hora | QCBS | LCB-UWSSP-LT/06-04/SOO/2009 | LS | 8645.59 | Post | Plan | 2011-11-07 | 2011-11-17 | 2011-12-24 | 2012-01-12 | 2012-01-28 | 2012-02-11 | Plan | 2012-02-18 | 2012-03-17 | 2012-03-27 | 2012-04-03 | 2012-04-10 | 2012-04-20 |  | Plan | 2012-04-30 | 2012-05-05 | 2012-05-10 |  | 2012-05-17 | 2012-05-22 | Plan
[6 empty] | Revised | [7 empty] | 2012-06-10 | 2012-07-10 | 2012-07-25 | 2012-08-01 | 2012-08-09 | 2012-08-24 |  | Revised | 2012-09-08 | 2012-09-23 |  |  | 2012-09-30 | 2012-10-20 |  | 2012-11-10 | 2013-02-08 | 2013-03-10
[6 empty] | Actual | 2011-12-08 | 2011-12-18 | NA | 2012-01-15 | 2012-02-01 | NA | Actual | 2012-02-21 | 2012-03-21 | 2012-03-30 | 2012-05-02 | 2012-05-05 | 2012-05-07 |  | Actual | 23-Apr-12 | 2012-05-08 | 2012-05-13 | 13355.9848 | 2012-05-16 | 24-May-12 | Actual | 2012-05-29
Sebeta Town Consultancy for Design Review and Supervision of sanitation Facility | QCBS | OWRB /S002/2009 | Lump Sum & Time Based | 90232.55 | Post | Plan | 2010-05-01 | 2010-05-11 | 2010-05-18 | 2010-05-23 | 2010-06-07 | 2010-06-17 | Plan | 2010-06-24 | 2010-07-09 | 2010-07-19 | 2010-07-26 | 2010-07-31 | 2010-08-03 | 2010-08-24 | Plan | 2010-08-10 | 2010-08-17 | 2010-08-24 |  | 2010-03-13 | 2010-03-13 | Plan | 2010-10-23 | 2010-07-21 | 2010-07-21
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual |  |  |  |  | 2009-10-07 | 07/10/2009 | Actual | 04/11/2009 | 2010-02-12
Sebeta Town Consultancy for ESIA | IC | SWSSE /S001/2010 | Lump sum | 17291.17 | Post | Plan | 2010-11-21 | 2010-12-01 | 2010-12-06 | 2010-12-27 | 2011-01-11 | 2011-01-21 | Plan | 2011-01-28 | 2011-02-25 | 2011-03-07 | 2011-03-14 | 2011-03-21 | 2011-03-31 | 2011-04-20 | Plan | 2011-04-10 | 2011-04-15 | 2011-04-20 |  | 1900-01-04 | 2011-05-02 | Plan | 2011-05-12 | 2012-04-06 | 2012-05-06
[6 empty] | Rev. | 2011-12-31 | NA | NA | 2012-01-10 | 2012-01-25 | NA | Revised plan | 2012-01-30 | 2012-02-27 | 2012-03-05 | NA | 2012-03-10 | 2012-03-17 | NA | Revised plan | 2012-03-22 | 2012-03-27 | NA |  | 1900-01-09 | 2012-04-11 | Revised plan | 2012-04-18 | 2012-05-18 | 2012-06-02
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost For Consultancy Services |  |  |  | 508844.0875 | [20 empty] | 455745.9121
Formulas:
No-objection Date = [Prep & Submission by Ex Agency]+10
No-objection Date = [Submission Date]+10
On-line UNDB Gateway/ National Press = [No-objection Date]+7
Lead-time before shortlist = [On-line UNDB Gateway/ National Press]+5
Lead-time before shortlist = [Prep & Submission by Ex Agency]+10
Submission Date = [Lead-time before shortlist]+15
Invitation Date = [No-objection Date]+7
Invitation Date = [Submission Date]+5
Submission/ Opening Date = [Invitation Date]+15
Submission Evaluation Report (T) = [Submission/ Opening Date]+10
No-objection Evaluation Report (T) = [Submission Evaluation Report (T)]+7
Opening Financial Proposals = [No-objection Evaluation Report (T)]+5
Opening Financial Proposals = [Submission Evaluation Report (T)]+15
Evaluation (T) (F) = [Opening Financial Proposals]+3
Negotiations = [Evaluation (T) (F)]+7
Contract Signature = [Contract Award]+5
Mobilization Advance Payment = 23/3/2010+[Final Report]
Mobilization Advance Payment = [Contract Signature]+10
Contract Award = [Contract Signature]-10
Contract Award = [Contract Amount in USD]+10
Draft Report = [Mobilization Advance Payment]+330
Draft Report = [Final Report]-30
Final Report = [Draft Report]+30

## GoodsST
Procurement of Goods
Organisation: | Oromia Towns Water Supply and Sewerage Service Entrprises | [16 empty] | 17.3499
Project/Programme: | Urban Water Supply and Sanitation Project | [16 empty] | 17.54
Loan No: | IDA Credit 3901-ET and IDA Grant 085-ET | [12 empty] | REVISED!!!
Description* | BASIC DATA | [6 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | For All Non ICB, No-objection will be requested from MOWR PMU | [8 empty] | Contract Implementation
[10 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization
| Package Number | Lot Number | Estimated Amount in USD | Procurement Method | Pre-or Post Qual. | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway National Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in USD | Date Contract Award | Date Contract Signature | Opening Let of Credit | Arrival of Goods | Inspection Final Acceptance
[8 empty] | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks |  |  | 1 wk | 1.5-3 wks
Supply of Generating Sets for 8 small Towns | OWMEB/UWS/EM/01/2011 |  | 67320.2727 | NCB | Post | Post | Plan | 2011-04-05 | 2011-04-15 | 2011-04-22 | 2011-04-29 | 2011-05-29 | 2011-06-13 | 2011-06-23 | Plan |  | 2011-06-30 | 2011-07-15 | 2011-08-14 | 2011-12-12 | 2011-12-17
[7 empty] | Revised | [6 empty] | 2012-02-25 | Revised |  | 2012-03-03 | 2012-03-18 | 2012-04-17 | 2012-08-15 | 2012-08-20
[7 empty] | Rev-2 |  |  | 2012-04-02 | 2012-04-09 | 2012-05-09 | 2012-05-24 | 2012-06-03 | Rev-2 |  | 2012-06-10 | 2012-06-20 | 2012-07-20 | 2012-11-17 | 2012-11-27
[7 empty] | Actual | 16-Nov-11 | 20-Nov-11 |  | 2011-12-04 | 2012-01-15 | 15-Feb-12 |  | Actual | 125565.9641 | 2012-03-13 | 2012-05-04 |  | 2012-08-02 | 2012-08-07
Supply of pumps for 16 small Towns | OWMEB/UWS/EM/02/2011 |  | 128185.1769 | NCB | Post | Post | Plan | 2011-05-15 | 2011-05-25 | 2011-06-01 | 2011-06-08 | 2011-07-08 | 2011-07-23 | 2011-08-02 | Plan |  | 2011-08-09 | 2011-08-24 | 2011-09-23 | 2012-01-21 | 2012-01-26
[7 empty] | Revised | [6 empty] | 2012-02-25 | Revised |  | 2012-03-03 | 2012-03-18 | 2012-04-17 | 2012-08-15 | 2012-08-20
[7 empty] | Rev-2 | 2012-03-11 | 2012-03-21 | 2012-03-28 | 2012-04-04 | 2012-05-04 | 2012-05-19 | 2012-06-03 | Rev-2 |  | 2012-06-10 | 2012-06-20 | 2012-07-20 | 2012-11-17 | 2012-11-27
[7 empty] | Actual | 16-Nov-11 | 20-Nov-11 |  | 2011-12-04 | 2012-01-15 | 15-Feb-12 |  | Actual | 229802.4772 | 2012-05-19 | 29-May-12 |  | 2012-08-27 | 2012-09-01
Connection 8 small towns to EEPCO Grid | OWMEB/UWS/EM/03/2011 |  | 75158.9346 | NCB | Post | Post | Plan | 2011-07-15 |  |  |  |  | 2012-01-05 |  | Plan |  |  | 30-Feb-12
[7 empty] | Revised | 2012-05-29 |  | 2012-06-08 | 2012-06-15 | 2012-07-15 | 2012-07-25 |  | Rev-2 |  | 2012-08-01 | 2012-08-11 | 2012-08-26 | 2012-12-24 | 2013-01-03
[7 empty] | Actual | [7 empty] | Actual
Supply of compueters, laptop and printers for 24 small towns | OWMEB/UWS/OEQ/01/2012 |  | 32839.2246 | NCB | Post | Post | Plan | 2012-03-15 |  |  | 2012-03-25 | 2012-04-24 | 2012-05-09 |  | Plan |  | 2012-05-16 | 2012-05-30 |  | 2012-07-29
[7 empty] | Revised | 2012-05-29 |  | 2012-06-08 | 2012-06-15 | 2012-07-15 | 2012-07-25 |  | Rev-2 |  | 2012-08-01 | 2012-08-11 | 2012-08-26 | 2012-12-24 | 2013-01-03
[7 empty] | Actual | [7 empty] | Actual
Supply of motor bike for 24 small towns | OWMEB/UWS/MB/02/2012 |  | 113568.9852 | NCB | Post | Post | Plan | 2012-03-20 |  |  | 2012-03-30 | 2012-04-29 | 2012-05-14 |  | Plan |  | 2012-05-21 | 2012-06-04 | 2012-06-19 | 2012-08-03 | 2012-08-13
[7 empty] | Revised | 2012-05-29 |  | 2012-06-08 | 2012-06-15 | 2012-07-15 | 2012-07-25 |  | Rev-2 |  | 2012-08-01 | 2012-08-11 | 2012-08-26 | 2012-12-24 | 2013-01-03
[7 empty] | Actual | [7 empty] | Actual
Supply of maintenance tools for 24 small towns | OWMEB/UWS/MT/03/2012 |  | 95781.0718 | NCB | Post | Post | Plan | 2012-03-20 |  |  | 2012-03-30 | 2012-04-29 | 2012-05-14 |  | Plan |  | 2012-05-21 | 2012-06-04 |  | 2012-08-03
[7 empty] | Revised | 2012-05-29 |  | 2012-06-08 | 2012-06-15 | 2012-07-15 | 2012-07-25 |  | Rev-2 |  | 2012-08-01 | 2012-08-11 | 2012-08-26 | 2012-12-24 | 2013-01-03
[7 empty] | Actual | [7 empty] | Actual
Total Cost For Goods for Small Towns |  |  | 512853.6659 | [12 empty] | 355368.4413
Formulas:
No-objection Date = [Prep & Submission by Ex Agency]+10
No-objection Date = [Spec Proc Notice Advert]-7
Spec Proc Notice Advert = [No-objection Date]+7
Spec Proc Notice Advert = [Bidding Period]-7
Bidding Period = [Spec Proc Notice Advert]+7
Bidding Period = [Bid Closing-Opening]-30
Bid Closing-Opening = [Bidding Period]+30
Bid Closing-Opening = [Bid Evaluation]-15
Bid Evaluation = [Bid Closing-Opening]+15
Bid Evaluation = [REVISED!!!]-10
REVISED!!! = [Bid Evaluation]+10
REVISED!!! = [Date Contract Award]-7
Date Contract Award = [REVISED!!!]+7
Date Contract Award = [Date Contract Signature]-10
Date Contract Signature = [Date Contract Award]+15
Opening Let of Credit = [Date Contract Signature]+30
Arrival of Goods = [Opening Let of Credit]+120
Arrival of Goods = [Date Contract Signature]+90
Inspection Final Acceptance = [Arrival of Goods]+5
Prep & Submission by Ex Agency = [No-objection Date]-10
Note on A10: user: Ali, Bake,Busa, Getema, Kombolcha, Solomo, & Olonkomi
Note on A15: user: Bokoji, Bure, Dabaso, Guliso, Hirna, Surupha, Megado, Yanfa, Olankomi, Hirna, Solomo, Beke, Kombolcha,
Note on A20: user: Beke, Guliso, Hirna, Olenkomi, Debeso, Bure, Bokoji,
Note on A24: Beke, Guliso, Hirna, Olenkomi, Debeso, Bure, Bokoji, Megado, Surupha, Atnago, Babu, Kombolcha, Dilela, Busa,Yanfa,Getema, Solomo, Toba, Segno Gebeya, Ali, Ejere, Babile, Kobo, Dhera, towns not included are Melka Rafu, Dilo, Goljota, Delomene
Note on A28: Beke, Guliso, Hirna, Olenkomi, Debeso, Bure, Bokoji, Megado, Surupha, Atnago, Babu, Kombolcha, Dilela, Busa,Yanfa,Getema, Solomo, Toba, Segno Gebeya, Ali, Ejere, Babile, Kobo, Dhera, towns not included are Melka Rafu, Dilo, Goljota, Delomene
Note on A32: user: Beke, Guliso, Hirna, Olenkomi, Debeso, Bure, Bokoji,

## WorkST
Procurement of Works
Country/Organization: | FDR of Ethiopia/OromiaTowns Water Supply and Sewerage Service Improvement and Expansion Project | [16 empty] | 17.3499
Project/Programmed: | Urban Water Supply and Sanitation Project
Loan #: | IDA Credit 3901-ET and IDA Grant 085-ET
Description* | Package Number | Basic Data | [5 empty] | Plan vs. Actual | Draft Bid Documents, including specs and quantities, draft SPN |  | For All Non ICB, No-objection will be requested from MOWR PMU | [5 empty] | Contract Finalization |  |  | Contract Implementation
|  | Lot Number | Lump sum or Bill of Quantities | Procurement Method | Estimated Amount in USD | Pre/Post Qualification | Prior or Post Review |  | Prep & Submission by Ex Agency | No-objection Date | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Plan vs. Actual | Contract Amount in USD | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
List of Contracts | [11 empty] | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date
A. Drilling
A.1. Completed
Production Water Well Drilling for Guliso Town | OWRB\MDTF\UDW/02/2010 |  | BOQ | NCB | 176178.4765 | Post | Post | Plan | 2010-09-15 | 2010-09-15 | 2010-09-22 | 2010-09-29 | 2010-10-29 | 2010-11-08 | 2010-11-18 | Plan |  | 2010-11-23 | 2010-11-28 | 2010-12-08 | 2011-02-06 | 2012-02-06 | 0
[8 empty] | Actual | 2-Jan-10 | 4-Jan-10 |  | 12-Feb-11 | 14-Mar-11 | 8-Apr-11 | 2011-04-18 | Actual | 38386.5805 | 2011-05-24 | 28-Jun-11 |  | 25-Dec-11 | 2012-12-24
Production Water Well Drilling for Bokoji, Bake & Hirna Towns | OWRB\MDTF\UDW/01/2010 |  | BOQ | NCB | 72622.897 | Post | Post | Plan | 2010-08-01 | 2010-08-01 | 2010-08-08 | 2010-08-15 | 2010-09-14 | 2010-09-24 | 2010-10-04 | Plan |  | 2010-10-09 | 2010-10-14 | 2010-10-24 | 2010-12-23 | 2011-01-02 | 0
[8 empty] | Actual | 20-Nov-09 | 22-Nov-09 |  | 13-Dec-09 | 13-Jan-10 | 25-Jan-10 | 27-Jan-10 | Actual | 122091.5971 | 08-Feb-10 | 19-Feb-10 |  | 18-May-10 | 2011-05-18
Production Water Well Drilling for Bure & Yanfa Town | OWRB/MDTF/DW/02/2/2010 |  | BOQ | NCB | 72622.897 | Post | Post | Plan | 2010-09-15 | 2010-09-15 | 2010-09-22 | 2010-09-29 | 2010-10-29 | 2010-11-08 | 2010-11-18 | Plan |  | 2010-11-23 | 2010-11-28 | 2010-12-08 | 2011-02-06 | 2011-02-16 | 0
[8 empty] | Actual | 2-Jan-10 | 4-Jan-10 |  | 12-Feb-11 | 14-Mar-11 | 8-Apr-11 |  | Actual | 73402.7285 | 2011-05-24 | 30-Jun-11 |  | 25-Dec-11 | 2012-12-24
Production Water Well Drilling for Olonkomi Towns | OWRB\MDTF\UDW/02/2010 |  | BOQ | NCB | 24207.6323 | Post | Post | Plan | 2010-09-15 | 2010-09-15 | 2010-09-22 | 2010-09-29 | 2010-10-29 | 2010-11-08 | 2010-11-18 | Plan |  | 2010-11-23 | 2010-11-28 | 2010-12-08 | 2011-02-06 | 2011-02-16 | 0
[8 empty] | Actual | 20-Nov-09 | 22-Nov-09 |  | 13-Dec-09 | 13-Jan-10 | 25-Jan-10 | 27-Jan-10 | Actual | 40697.199 | 08-Feb-10 | 19-Feb-10 |  | 18-May-10 | 2011-05-18
Production Water Well Drilling for Magado Town | OWME/MDTF/DW/06/1/2010 |  | BOQ | NCB | 46109.7758 | Post | Post | Plan | 2011-02-20 | 2011-02-23 | 2011-03-02 | 2011-03-09 | 2011-04-08 | 2011-04-18 | 2011-04-22 | Plan |  | 2011-04-27 | 2011-05-02 | 2011-05-12 | 2011-06-01 | 2011-06-11 | 0
[8 empty] | Actual | 26-Feb-11 | 02-Mar-11 |  | 12-Feb-11 | 14-Mar-11 | 8-Apr-11 | 30-Dec-11 | Actual | 167170.7618 | 2011-05-24 | 30-Jun-11 |  | 25-Dec-11 | 2012-12-24
A.2. Ongoing
Production Water Well Drilling for Dabaso Town | OWME\MDTF\DW&SHW/02/03/2010 |  | BOQ | NCB | 57637.2198 | Post | Post | Plan | 2011-02-20 | 2011-02-23 | 2011-03-02 | 2011-03-09 | 2011-04-08 | 2011-04-18 | 2011-04-22 | Plan |  | 2011-04-27 | 2012-02-10 | 2012-02-20 | 2012-03-11 | 2012-03-21 | 0
[8 empty] | Rev-2 | 2011-02-20 | 2011-02-23 | 2011-03-02 | 2012-04-12 | 2012-05-12 | 2012-05-22 | 2012-05-26 | Rev-2 |  | 2012-05-31 | 2012-06-10 | 2012-06-20 | 2012-07-10 | 2012-07-30
[8 empty] | Actual | 26-Feb-11 | 02-Mar-11 |  | 1-Dec-11 | 28-Dec-11 | 05-Jan-12 | 08-Jan-12 | Actual | 57637.2198 | 03-Feb-12
B. Civil Work
B.1. Completed
Ali Town Civil Work Construction | OWRB\UWSSCWC/005/7/2008 |  | BOQ | NCB | 91066.8073 | Post | Post | Plan | 2009-04-01 | 2009-04-11 | 2009-04-18 | 2009-04-25 | 2009-05-25 | 2009-06-04 | 2009-06-14 | Plan |  | 2009-06-19 | 2009-10-13 | 2009-10-23 | 2010-04-21 | 2011-04-21 | 91066.8073
[8 empty] | Actual | 13-May-09 | 1-Jun-09 |  | 20-Jun-09 | 21-Jul-09 | 28-Jul-09 | 28-Jul-09 | Actual | 64285.382 | 31-Jul-09 | 2009-10-13 |  | 12-May-11 | 2012-05-11
Atinago Town Civil Work Construction | OWRB\UWSSCWC/005/1/2008 |  | BOQ | NCB | 135000 | Post | Post | Plan | 2009-04-01 | 2009-04-11 | 2009-04-18 | 2009-04-25 | 2009-05-25 | 2009-06-04 | 2009-06-14 | Plan |  | 2009-06-19 | 2009-08-20 | 2009-08-30 | 2010-10-24 | 2011-10-24 | 135000
[8 empty] | Actual | 13-May-09 | 1-Jun-09 |  | 20-Jun-09 | 21-Jul-09 | 28-Jul-09 | 28-Jul-09 | Actual | 23496.8622 | 31-Jul-09 | 2009-08-20 |  | 17-Jan-10 | 2011-01-17
BaboTown Civil Work Construction | OWRB\UWSSCWC/005/2/2008 |  | BOQ | NCB | 105000 | Post | Post | Plan | 2009-04-01 | 2009-04-11 | 2009-04-18 | 2009-04-25 | 2009-05-25 | 2009-06-04 | 2009-06-14 | Plan |  | 2009-06-19 | 2009-08-20 | 2009-08-30 | 2010-10-24 | 2011-10-24 | 105000
[8 empty] | Actual | 13-May-09 | 1-Jun-09 |  | 20-Jun-09 | 21-Jul-09 | 28-Jul-09 | 28-Jul-09 | Actual | 17518.9096 | 30-Jul-09 | 2009-08-20 |  | 18-Sep-10 | 2011-09-18
Busa Town Civil Work Construction | OWRB\UWSSCWC/004/2008 |  | BOQ | NCB | 105000 | Post | Post | Plan | 2009-01-20 | 2009-01-30 | 2009-02-06 | 2009-02-13 | 2009-03-15 | 2009-03-25 | 2009-04-04 | Plan |  | 2009-04-09 | 2009-04-09 | 2009-04-19 | 2010-06-13 | 2010-12-10 | 105000
[8 empty] | Actual | 13-May-09 | 1-Jun-09 |  | 20-Jun-09 | 21-Jul-09 | 28-Jul-09 | 28-Jul-09 | Actual | 62834.6792 | 31-Jul-09 | 2009-04-09 |  | 07-Dec-09 | 2010-12-07
Dilala Town Civil Work Construction | OWRB\UWSSCWC/004/2008 |  | BOQ | NCB | 105000 | Post | Post | Plan | 2009-01-20 | 2009-01-30 | 2009-02-06 | 2009-02-13 | 2009-03-15 | 2009-03-25 | 2009-04-04 | Plan |  | 2009-04-09 | 2009-04-09 | 2009-04-19 | 2010-06-13 | 2011-06-13 | 105000
[8 empty] | Actual | 06-Feb-09 | 2009-02-14 |  | 02-Mar-09 | 3-Mar-09 | 18-Mar-09 | 19-Mar-09 | Actual | 62834.6792 | 25-Mar-09 | 2009-04-09 |  | 07-Dec-09 | 2010-12-07
Ejere Town Civil Work Construction | OWRB\UWSSCWC/005/4/2008 |  | BOQ | NCB | 105000 | Post | Post | Plan | 2009-03-20 | 2009-03-30 | 2009-04-06 | 2009-04-13 | 2009-05-13 | 2009-05-23 | 2009-06-02 | Plan |  | 2009-06-07 | 2009-06-01 | 2009-09-04 | 2010-10-29 | 2011-10-29 | 105000
[8 empty] | Actual | 13-May-09 | 1-Jun-09 |  | 20-Jun-09 | 21-Jul-09 | 28-Jul-09 | 28-Jul-09 | Actual | 31320.139 | 30-Jul-09 | 2009-08-25 |  | 24-Oct-10 | 2011-10-24
Kombolcha Town Civil Work Construction | OWRB\UWSSCWC/005/5/2008 |  | BOQ | NCB | 36311.4485 | Post | Post | Plan | 2009-03-20 | 2009-03-30 | 2009-04-06 | 2009-04-13 | 2009-05-13 | 2009-05-23 | 2009-06-02 | Plan |  | 2009-06-07 | 2009-06-12 | 2009-06-22 | 2010-08-16 | 2011-08-16 | 36311.4485
[8 empty] | Actual | 13-May-09 | 1-Jun-09 |  | 20-Jun-09 | 21-Jul-09 | 28-Jul-09 | 28-Jul-09 | Actual | 42281.4696 | 30-Jul-09 | 2009-08-28 |  | 12-Oct-10 | 2011-10-12
Segno Gabaya Town Civil Work Construction | OWRB\UWSSCWC/005/6/2008 |  | BOQ | NCB | 47550.7063 | Post | Post | Plan | 2009-03-20 | 2009-03-30 | 2009-04-06 | 2009-04-13 | 2009-05-13 | 2009-05-23 | 2009-06-02 | Plan |  | 2009-06-07 | 2009-06-01 | 2009-08-21 | 2010-10-15 | 2011-10-15 | 47550.7063
[8 empty] | Actual | 16-Feb-09 | 29-Feb-09 |  | 01-Apr-09 | 05-My-09 | 28-May-09 | 06-Jun-09 | Actual | 77108.7983 | 30-Jul-09 | 2009-08-11 |  | 22-Sep-10 | 2011-09-22
Solomo Town Civil Work Construction | OWRB\UWSSCWC/005/7/2008 |  | BOQ | NCB | 75850.5813 | Post | Post | Plan | 2009-04-01 | 2009-04-11 | 2009-04-18 | 2009-04-25 | 2009-05-25 | 2009-06-04 | 2009-06-14 | Plan |  | 2009-06-19 | 2009-08-20 | 2009-08-30 | 2010-02-26 | 2011-02-26 | 75850.5813
[8 empty] | Actual | 16-Feb-09 | 29-Feb-09 |  | 01-Apr-09 | 05-My-09 | 28-May-09 | 06-Jun-09 | Actual | 37006.2139 | 30-Jul-09 | 2009-08-20 |  | 09-Dec-10 | 2011-12-09
B.2. Ongoing
BakeTown Civil Work Construction | OWME\MDTF\UCWC/01/2011 |  | BOQ | NCB | 369445.2607 | Post | Post | Plan | 2011-02-25 | 2011-02-28 | 2011-03-07 | 2011-03-14 | 2011-04-13 | 2011-04-23 | 2011-04-27 | Plan |  | 2011-05-02 | 2011-05-07 | 2011-07-10 | 2012-01-21 | 2012-07-19 | 369445.2607
[8 empty] | Actual | 26-Feb-11 | 02-Mar-11 |  | 19-Mar-11 | 25-Apr-11 | 24-May-11 | 26-May-11 | Actual | 196918.2278 | 02-Jun-11 | 30-Jun-11 | 2011-07-10 | 2012-01-21 | 2012-07-19
Olonkomi Town Civil Work Construction | OWME\MDTF\UCWC/02/2011 |  | BOQ | NCB | 320425.0825 | Post | Post | Plan | 2011-02-25 | 2011-02-28 | 2011-03-07 | 2011-03-14 | 2011-04-13 | 2011-04-23 | 2011-04-27 | Plan |  | 2011-05-02 | 2011-05-07 | 2011-07-10 | 2012-01-21 | 2012-07-19 | 320425.0825
[8 empty] | Actual | 26-Feb-11 | 02-Mar-11 |  | 19-Mar-11 | 25-Apr-11 | 24-May-11 | 26-May-11 | Actual | 148708.3516 | 02-Jun-11 | 30-Jun-11 | 2011-07-10 | 2012-01-21 | 2012-07-19
Bokoji Town Civil Work Construction | OWME\MDTF\UCWC/03/2011 |  | BOQ | NCB | 328532.1529 | Post | Post | Plan | 2011-03-10 | 2011-03-13 | 2011-03-20 | 2011-03-27 | 2011-04-26 | 2011-05-06 | 2011-05-10 | Plan |  | 2011-05-15 | 2011-05-20 | 2011-08-05 | 2012-02-16 | 2012-08-14 | 328532.1529
[8 empty] | Actual | 26-Feb-11 | 02-Mar-11 |  | 19-Mar-11 | 25-Apr-11 | 24-May-11 | 26-May-11 | Actual | 308792.5095 | 07-Jul-11 | 26-Jul-11 | 2011-08-05 | 2012-02-16 | 2012-08-14
Hirna Town Civil Work Construction | OWME\MDTF\UCWC/04/2011 |  | BOQ | NCB | 417167.3531 | Post | Post | Plan | 2010-10-01 | 2010-10-04 | 2010-10-11 | 2010-10-18 | 2010-11-17 | 2010-11-27 | 2010-12-01 | Plan |  | 2010-12-06 | 2010-12-11 | 2011-07-01 | 2012-01-12 | 2012-07-10 | 417167.3531
[8 empty] | Actual | 26-Feb-11 | 02-Mar-11 |  | 19-Mar-11 | 25-Apr-11 | 24-May-11 | 26-May-11 | Actual | 298880.812 | 2-Jun-11 | 21-Jun-11 | 2011-07-01 | 2012-01-12 | 2012-07-10
Guliso Town Civil Work Construction | OWME\MDTF\UCWC/05/2011 |  | BOQ | NCB | 516160.8033 | Post | Post | Plan | 2010-09-01 | 2010-09-04 | 2010-09-11 | 2010-09-18 | 2010-10-18 | 2010-10-28 | 2010-11-01 | Plan |  | 2010-11-06 | 2010-11-11 | 2011-07-06 | 2012-01-17 | 2012-07-15 | 516160.8033
[8 empty] | Actual | 26-Feb-11 | 02-Mar-11 |  | 19-Mar-11 | 25-Apr-11 | 24-May-11 | 26-May-11 | Actual | 411878.7912 | 2-Jun-11 | 21-Jun-11 | 2011-07-06 | 2012-01-17 | 2012-07-15
Bure Town Civil Work Construction | OWME\MDTF\UCWC/06/2011 |  | BOQ | NCB | 383339.3057 | Post | Post | Plan | 2010-09-01 | 2010-09-04 | 2010-09-11 | 2010-09-18 | 2010-10-18 | 2010-10-28 | 2010-11-01 | Plan |  | 2010-11-06 | 2010-11-11 | 2010-11-21 | 2011-11-16 | 2012-05-14 | 383339.3057
[8 empty] | Revised | [5 empty] | 2012-02-19 | 2012-02-22 | Revised |  | 2012-02-27 | 2012-03-03 | 2012-03-13 | 2013-03-08 | 2013-09-04 | 383339.3057
[8 empty] | Rev-2 | 2012-04-02 | 2012-04-05 | 2012-04-12 | 2012-04-19 | 2012-05-19 | 2012-05-29 | 2012-06-01 | Rev-2 |  | 2012-06-05 | 2012-06-15 | 2012-06-25 | 2012-12-22 | 2013-12-22
[8 empty] | Actual | 12-Dec-11 | 20-Dec-11 | 2011-12-03 | 2-Jan-12 | 2012-02-07 | 2012-03-08 | 2012-03-11 | Actual | 279355.632 | 14-Mar-12 | 22 -Mar-12 | 2012-04-01 | 2012-09-18 | 2013-03-17
Yanfa Town Civil Work Construction | OWME\MDTF\UCWC/07/2011 |  | BOQ | NCB | 386169.3726 | Post | Post | Plan | 2011-03-01 | 2011-03-04 | 2011-03-11 | 2011-03-18 | 2012-02-07 | 2012-02-17 | 2012-02-21 | Plan |  | 2012-02-26 | 2012-03-02 | 2012-03-12 | 2013-03-07 | 2013-09-03 | 386169.3726
[8 empty] | Revised | [5 empty] | 2012-02-19 | 2012-02-22 | Revised |  | 2012-02-27 | 2012-03-03 | 2012-03-13 | 2013-03-08 | 2013-09-04
[8 empty] | Rev-2 | 2012-04-02 | 2012-04-05 | 2012-04-12 | 2012-04-19 | 2012-05-19 | 2012-05-29 | 2012-06-01 | Rev-2 |  | 2012-06-05 | 2012-06-15 | 2012-06-25 | 2012-12-22 | 2013-12-22
[8 empty] | Actual | 12-Dec-11 | 20-Dec-11 | 2011-12-03 | 2-Jan-12 | 2012-02-07 | 2012-03-08 | 2012-03-11 | Actual | 279355.632 | 14-Mar-12 | 22 -Mar-12 | 2012-04-01 | 2012-09-18 | 2013-03-17
Megado Town Civil Work Construction | OWME\MDTF\UCWC/08/2011 |  | BOQ | NCB | 239194.4622 | Post | Post | Plan | 2011-04-01 | 2011-04-04 | 2011-04-11 | 2011-04-18 | 2011-05-18 | 2011-05-28 | 2011-06-01 | Plan |  | 2011-06-06 | 2011-06-11 | 2012-02-04 | 2012-08-17 | 2013-02-13 | 239194.4622
[8 empty] | Actual | 06-Dec-11 | 10-Dec-11 |  | 25-Dec-11 | 28-Nov-11 | 05-Jan-12 | 06-Jan-12 | Actual | 235673.948 | 13-Jan-12 | 25-Jan-12 | 2012-02-04 | 2012-08-07 | 2013-02-03
Surupha Town Civil Work Construction | OWME\MDTF\UCWC/09/2011 |  | BOQ | NCB | 569972.8696 | Post | Post | Plan | 2011-04-01 | 2011-04-04 | 2011-04-11 | 2011-04-18 | 2011-05-18 | 2011-05-28 | 2011-06-01 | Plan |  | 2011-06-06 | 2011-06-11 | 2011-07-10 | 2012-07-04 | 2012-12-31 | 569972.8696
[8 empty] | Actual | 26-Feb-11 | 02-Mar-11 |  | 19-Mar-11 | 25-Apr-11 | 24-May-11 | 26-May-11 | Actual | 571975.2673 | 2-Jun-11 | 30-Jun-11 | 2011-07-10 | 2012-01-11 | 2012-07-09
Getema Town Civil Work Construction | OWRB\UWSSCWC/005/8/2008 |  | BOQ | NCB | 267248.6304 | Post | Post | Plan | 2010-06-05 | 2010-06-15 | 2010-06-22 | 2010-06-29 | 2010-07-29 | 2010-08-08 | 2010-08-18 | Plan |  | 2010-08-23 | 2010-08-28 | 2010-09-07 | 2012-03-30 | 2012-09-26 | 267248.6304
[8 empty] | Actual | 01-Jun-10 | 10-Jun-10 |  | 2010-06-20 | 2010-07-24 | 2010-08-11 | 2010-08-21 | Actual | 175014.845 |  | 2010-10-18 | 2010-10-28 | 2011-05-11 | 2011-11-07
DabasoTown Civil Work Construction | OWRB\UWSSCWC/005/3/2008 |  | BOQ | NCB | 219610.2441 | Post | Post | Plan | 2009-06-10 | 2009-06-20 | 2009-06-27 | 2009-07-04 | 2009-08-03 | 2009-08-13 | 2009-08-23 | Plan |  | 2009-08-28 | 2009-08-20 | 2012-02-02 | 2012-08-15 | 2013-02-11 | 219610.2441
[8 empty] | Actual | 06-Dec-11 | 10-Dec-11 |  | 25-Dec-11 | 28-Nov-11 | 05-Jan-12 | 06-Jan-12 | Actual | 688768.9975 | 13-Jan-12 | 23-Jan-12 | 2012-02-02 | 2012-08-05 | 2013-02-01
Dhera Town Civil Work Construction | OWRB\UWSSCWC/002/2008 |  | BOQ | NCB | 922195.517 | Post | Post | Plan | 2009-01-01 | 2009-01-11 | 2009-01-18 | 2009-01-25 | 2009-02-24 | 2009-03-06 | 2009-03-16 | Plan |  | 2009-05-17 | 2009-05-22 | 2009-06-01 | 2010-07-26 | 2011-01-22 | 922195.517
[8 empty] | Actual | 13-May-09 | 1-Jun-09 |  | 20-Jun-09 | 21-Jul-09 | 28-Jul-09 | 28-Jul-09 | Actual | 875756.9208 | 31-Jul-09 | 2009-05-22 | 2009-06-01 | 1900-07-13 | 1901-01-09
Small towns Sub Total Cost for Work |  |  |  |  | 6018441.0194 | [11 empty] | 5389153.1546 | [5 empty] | 5745240.5975
30
30
0
30
Formulas:
No-objection Date = [Prep & Submission by Ex Agency]
No-objection Date = [Bid Evaluation]+10
Spec Proc Notice Advert = [No-objection Date]+7
Spec Proc Notice Advert = [Bidding Period, row above]-7
Bidding Period = [Spec Proc Notice Advert]+7
Bidding Period = [Bid Closing-Opening]-30
Bid Closing-Opening = [Bidding Period]+30
Bid Closing-Opening = [Bid Evaluation]-10
Bid Evaluation = [Bid Closing-Opening]+10
Bid Evaluation = [No-objection Date]-4
Date Contract Award = [No-objection Date]+5
Date Contract Award = [Date Contract Signature]-10
Date Contract Signature = [Date Contract Award]+5
Contract Implementation = [Date Contract Signature]+10
Contract Implementation = [Date Contract Signature, row below]+10
Substantial Completion = [Contract Implementation]+60
Substantial Completion = [Date Contract Signature]+180
Final Acceptance = [Substantial Completion]+365
Prep & Submission by Ex Agency = [No-objection Date]-3

## ConsultantST
Procurement of Consultancy Services
Country/Organization: | FDR of Ethiopia/OromiaTowns Water Supply and Sewerage Service Improvement and Expansion Project | [16 empty] | 17.3499
Project/Programmed: | Urban Water Supply and Sanitation Project
Loan #: | IDA Credit 3901-ET and IDA Grant 085-ET
If Post-Review, No-objection will be requested from MOWR PMU | [12 empty] | Plan vs. Actual | [7 empty] | Plan Vs Actual | Negotiations |  |  | Contract Finalization |  |  | Plan Vs Actual | Contract Implementation
|  | Contract Type |  |  |  |  | Preparation Request for Proposals
Description* | Selection Method | Contract Id | Lumpsum or Time-Based | Estimated Amount in Eth. Birr | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway/ National Press | Lead-time before shortlist | Submission Date | No-objection Date |  | Invitation Date | Submission/Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Submission of Evaluation (T) (F) | No-objection Eval Report (T) (F) |  | Negotiations | Submission Draft Contract | No-objection Eval Report (T) (F)/ Negotiated Draft Contract | Contract Amount in US$ '000 | Contract award | Contract Signature |  | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
List of Contracts | [6 empty] | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks |  | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 1 - 1,5 wks
Consultancy Service for Step 3 for Towns Less Than 15000 Population | QCBS | OWRB/CS/01/2012 | Lump sum | 86455.8297 | Post | Plan | 2012-03-15 | 2012-03-25 | 2012-03-30 | 2012-04-20 | 2012-05-05 | 2012-05-15 | Plan | 2012-05-22 | 2012-06-19 | 2012-06-29 | 2012-07-06 | 2012-07-13 | 2012-07-23 |  | Plan | 2012-07-28 | 2012-08-02 | 2012-08-07 |  | 2012-08-14 | 2012-08-19 | Plan | 2012-08-29 | 2012-12-27 | 2013-01-11
[6 empty] | Rev-2 | 2012-05-29 | 2012-06-08 | 2012-06-08 | 2012-06-18 | 2012-06-28 | 2012-07-13 | Rev-2 | 2012-07-13 | 2012-08-12 | 2012-08-27 |  | 2012-09-11 | 2012-09-26 |  | Rev-2 | 2012-10-06 | 2012-10-11 |  |  | 2012-10-16 | 2012-10-21 |  | 2012-10-31 | 2013-02-28 | 2013-03-15
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost For Consultancy Services |  |  |  | 86455.8297 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
Formulas:
No-objection Date = [Prep & Submission by Ex Ag]+10
No-objection Date = [Submission Date]+10
On-line UNDB Gateway/ National Press = [No-objection Date]+5
On-line UNDB Gateway/ National Press = [Prep & Submission by Ex Ag]+10
Lead-time before shortlist = [On-line UNDB Gateway/ National Press]+21
Submission Date = [Lead-time before shortlist]+15
Invitation Date = [No-objection Date]+7
Invitation Date = [Submission Date]+15
Submission/Opening Date = [Invitation Date]+28
Submission Evaluation Report (T) = [Submission/Opening Date]+10
No-objection Evaluation Report (T) = [Submission Evaluation Report (T)]+7
Opening Financial Proposals = [No-objection Evaluation Report (T)]+7
Opening Financial Proposals = [Submission Evaluation Report (T)]+15
Submission of Evaluation (T) (F) = [Opening Financial Proposals]+10
Negotiations = [Opening Financial Proposals]+15
Negotiations = [Submission of Evaluation (T) (F)]+10
Submission Draft Contract = [Negotiations]+5
Contract award = [Submission Draft Contract]+5
Contract Signature = [Contract award]+5
Contract Implementation = [Contract Signature]+10
Draft Report = [Contract Implementation]+120
Final Report = [Draft Report]+15