|  |
| --- |
| **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 05/09/2011 |

|  |
| --- |
| **1. Basic Information** |
| Project ID & Name | P069896: BJ-GEF Forests & Adjcnt Lnds Mgmt (FY06) |
| Country | Benin |
| Task Team Leader | Emeran Serge M. Menang Evouna |
| Sector Manager/Director | Idah Z. Pswarayi-Riddihough |
| Country Director | Madani M. Tall |
| Original Board Approval Date | 06/29/2006 |
| Original Closing Date: | 11/30/2011 |
| Current Closing Date | 11/30/2011 |
| Proposed Closing Date [if applicable] | 05/31/2013 |
| EA Category | B-Partial Assessment |
| Revised EA Category | B-Partial Assessment-Partial Assessment |
| EA Completion Date | 01/13/2003 |
| Revised EA Completion Date |  |

|  |
| --- |
| **2. Revised Financing Plan (US$m)** |
| **Source** | **Original** | **Revised** |
|  BORR | 21.00 | 21.00 |
|  GEFU | 6.00 | 6.00 |
|  **Total** | 27.00 | 27.00 |

|  |
| --- |
| **3. Borrower** |
| **Organization** | **Department** | **Location** |
|  Ministry of Economy & Finance |  | Benin |

|  |
| --- |
| **4. Implementing Agency** |
| **Organization** | **Department** | **Location** |
|  Ministry of Environment | Forests and Natural Resources | Benin |

|  |
| --- |
| **5. Disbursement Estimates (US$m)** |
| **Actual amount disbursed as of 05/10/2011** **3.70** |
| **Fiscal Year** | **Annual** | **Cumulative** |
|  2010 | 0.00 | 3.70 |
|   | **Total** | **3.70** |

|  |
| --- |
| **6. Policy Exceptions and Safeguard Policies** |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes****Original/Current Project Development Objectives/Outcomes** |
| Assist Benin in its efforts to set the stage for integrated ecosystem management in selected gazetted forests and their adjacent lands and thereby strategically influencing ecosystem management trends, in medium and long terms to generate multiple global benefits.  |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|   |