Procurement Plan (PP) for Consulting Services for FY 2012-13, Feb 10, 2013

| Project Name & ID : [IRRIGATION and WATER RESOURCES MANAGEMENT PROJECT IWRMP Loan/Credit/Grant No.: [IDA Grant H 3380-NEP] | Executing Agency : [Department of IRRIGATION] Implementing Agency : [Office of the Project Director, Department of IRRIGATION Jawalakhel] |
| --- | --- |

| SNo | Description of Services & Contract ID No. | Prior/ Post Review | PP Status | Cost Estimate (NRs Million) | Method of Selection | Proc. Procedure GoN/WB | Advertising for EOI | Cost Estimate, Short list & RFP to WB | WB’s NOL to CE, SL & RFP | RFP Issued | Proposals Submission | TP Eval. Report to WB | WB’s NOL to TP EVal. Report | Public Opening of FP | FER & Award Recomm. to WB for info. | Negotiated Contract to WB | WB’s NOL to Nego. Contract | Contract Signing | Completion date of the contract | Procurement at Center/ District | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |
| 1 | Technical Assistance support for component A IWRMP/GST/CONSULT/01 | Prior | P | 86.49 | QCBS | WB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | A | 126.13 |  |  | 7 Apr 2008 | 14 Jan & 6 Feb 2008 | 11 Feb 2009 | 17 Feb 2009 | 6 Apr 2009 | 7 Jun 2009 | 29 jun 2009 | 8 July 2009 | 30 Oct 2009 | 1 Nov 2009 | 10 Nov 2009 | 22 Nov 2009 | 30 Jun 2013 |  |  |
| 2 | Technical Assistance support for Component B IWRMP/GST/CONSULT/02 | Prior | P | 115.35 | QCBS | WB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | A | 152.43 |  |  | 7 Apr 2008 | 14 Jan & 6 Feb 2008 | 11 Feb 2009 | 17 Feb 2009 | 6 Apr 2009 | 8 Jun 2009 | 26 June 2009 | 4 Aug 2009 | 1 Sept 2009 | 9 Nov 2009 | 20 Dec 2009 | 28 Dec 2009 | 30 Jun 2013 |  |  |
| 3 | Services for Baseline, MTR, Impact IWRMP/GST/CONSULT/03 | Prior | P | 6 | QCBS | WB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | A |  |  |  | 15 July 2008 | 1 Sept & 3 Oct 2008 | 15 Oct 2008 | 25 Oct 2008 | 1 Dec 2008 | 24 Dec 2008 | 26 Dec 2008 | 2 Jan 2009 | 9 Jan 2009 | 6 Mar 2009 | 4 Jun 2009 | 4 June 2009 | 13 May 2013 |  |  |
| 4 | TA Support for GMIS IWRMP/GST/CONSULT/04 | Post | P | 6 | QCBS | WB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | A |  |  |  | 5 Feb 2009 | NA | NA | 16 Mar 2009 | 21 Apr 2009 | NA | NA | NA | NA | 30 May 2009 | 9 June 2009 | 10 June 2009 | 21 June 2013 |  |  |
| 5 | Master Plan for GW Development IWRMP/DOI/S/QCBS-07 | Prior | P | 33.00 | QCBS | WB | 14 April 2010 | 30 April / 15 May 2010 | 21 May 2010 | 25 May 2010 | 10 July 2010 | 10 Aug 2010 | 1 Sept 2010 |  |  |  |  |  | 1 Sept 2011 | OPD |  |
|  |  |  | R | 23.00 |  |  | 25 Oct 2011 | 3 Dec 2011 | 10 Dec 2011 | 15 Dec 2011 | 30 Jan 2012 | 20 Feb 2012 | 30 Feb 2012 | 7 March 2012 | 15 March 2012 | 22 March 2012 | 2 April 2012 | 10 April 2012 | 10 April 2013 | OPD |  |
|  |  |  | A | This contract has been cancelled |  |  |
| 6 | Decentralized Institutional Stengthening Works (NGO Service for Institutional Strengthening ) (IWRMP/DOI/S/SSS-08) | Prior | P | 15.3 | Varition Order to TA (SSS) | WB | NA | 15 Feb 2011 | NA | NA | NA | NA | NA | NA | NA | 25 Mar 2011 | 15 April 2011 | 25 April 2011 | June 30 2013 | OPD | As per Para 21 of Aide Memoire of 5th I.S.Mission (26 Sept – 7 Oct 2010) |
|  |  |  | R |  |  |  |  |  |  |  |  |  |  |  | 31 May 2011 | 7 Dec 2011 | 15 Dec 2011 | 21 Dec 2011 | 30 June 2013 |  |  |
|  |  |  | A | This contract has been cancelled |  |
| 7 | Consulting Services for Social and Environmental Audit (IWRMP/DOI/S/QCBS-09) | Post | P | 20.00 | QCBS | WB | 15Feb 2011 | 25 Feb 2011 | 5 Mar 2011 | 15 Mar 2011 | 20 Apr 2010 | NA | NA | 20 May 2011 | NA | NA | NA | 14 June 2011 | June 30 2013 | OPD |  |
|  |  |  | R |  |  |  |  | NA | NA | 3 Nov 2011 | 3 Dec 2011 | 15 Dec 2011 | 21 Dec 2011 | 30 Dec 2011 | 7 Jan 2012 | 15 Jan 2012 | 21 Jan 2012 | 30 Jan 2012 | 30 June 2013 |  |  |
|  |  |  | A | 12.565 | QCBS | WB | 9 April 2011 | NA | NA | 9 Nov 2011 | 19 Dec 2011 | NA | NA | 16 Feb 2012 | NA | NA | NA | 4 April 2012 | 30 June 2013 | OPD |  |
| 8 | NGO Service for Micro Irrigation Implementation (IWRMP/DOI/S/QCBS-10) | Post | P | 40.00 | QCBS | WB | 7 Feb 2011 | 15 Feb 2011 | NA | 17 Feb 2011 | 21 March 2011 | NA | NA | 3 April 2011 | NA | NA | NA | 10 April 2011 | June 30, 2013 | OPD |  |
|  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | A | 30.08 | QCBS | WB | 2 March 2011 | NA | NA | 29 April 2011 | 2 June 2011 | NA | NA | 1 July 2011 | NA | NA | NA | 11 July 2011 | 30 April 2013 |  |  |
| 9 | Consultancy Services for Benchmarking study of Component B subprojects (IWRMP/DOI/S/QCBS-11a) | Post | P | 5.00 | QCBS | WB | 10 Feb 2011 | 11 March 2011 | 18 Mar 2011 | 23 March 2011 | 23 April 2011 | NA | NA | 7 May 2011 | NA | NA | NA | 20 May 2011 | June 30, 2013 | OPD | Replacement of MASSCOTTE application |
|  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | A | 2.50 | QCBS | GoN/WB | NA | NA | NA | 12 May 2011 | 12 June 2011 | NA | NA | 1 July 2011 | NA | NA | NA | 8 July 2011 | 9 Jan 2012 | OPD |  |
| 10 | Consultancy Services for performance evaluation of Component B subprojects etc. (IWRMP/DOI/S/CQS/QCBS-11 b) | Post | P | 2.50 | CQS/QCBS | WB | 10 Nov 2011 | NA | NA | 15 Dec 2011 | 15 Jan 2012 | NA | NA | 1 Feb 2012 | NA | NA | NA | 15 Feb 2012 | 15 July 2012 | OPD | Four Contract |
|  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | A | This contract has been cancelled but such work has been conducted through the Item no.12 of this PP in four package of NRs. 300 thousand each |  |  |
| 11 | Consultancy Services for Structure calibration & COP preparation in Component B subprojects. (IWRMP/DOI/S/SQ-12) | Post | P | 4.00 | QCBS | WB | 15 Nov 2011 | NA | NA | 15 Dec 2011 | 15 Jan 2012 | NA | NA | 1 Feb 2012 | NA | NA | NA | 15 Feb 2012 | 15 June 2012 | OPD | Four Contract |
|  |  |  | R | 4.00 | SQ |  | NA | NA | NA | 15 Feb 2013 | 1 Mar 2013 | NA | NA | 7 Mar 2013 | NA | NA | NA | 15 Mar 2013 | 30 June 2013 |  |  |
|  |  |  | A | This task is very important for the water management. Due to time short this work has been proposed for Sealed quotation in four contract. |  |  |
| 12 | Consultancy service for Project preparation studies for component A & B (IWRMP/DOI/S/SSS-13) | Post | P | 12.00 | SSS against listed Firm | WB | Average contract size not more than NRs 300 thousand for the SEMP preparation, Detail Feasibility and engineering Study of three development regions of western Nepal under component A and project preparation works of Irrigation Management Transfer under component B. (A roaster of consulting firms meeting minimum qualifying criteria will be established and contract is awarded to a firm only once in a fiscal year) | 16 July 2012 | RID/OPD |  |
|  |  |  | A | Some packages implemented and completed |  |  |
| 13 | Short Term Consultancy Services for monitoring and Evaluation of GMIS and subprojects etc. (IWRMP/DOI/S/SSS-14) | Post | P | 2.50 | SSS against listed Firm | WB | Average contract size not more than 300 thousand for the monitoring of GMIS and other ongoing works of the subprojects (A roaster of consulting firms meeting minimum qualifying criteria will be established and contract is awarded to a firm only once in a fiscal year) | 16 July 2012 | OPD |  |
|  |  |  | A | Some packages implemented and completed |  |  |
| 14 | Consultancy Services for digital Parcellary map prep. of Component B subprojects (IWRMP/DOI/S/SQ-15) | Post | P | 4.00 | QCBS | WB | NA | NA | NA | 15 Feb 2013 | 1 Mar 2013 | NA | NA | 7 Mar 2013 | NA | NA | NA | 15 Mar 2013 | 30 June 2013 | OPD | Four Contract |
|  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | A | This task is very important for the water management. Due to time short this work has been proposed for Sealed quotation in four contract. |  |  |
| 15 | Consultancy service for Project preparation studies for component A & B (IWRMP/DOI/S/SSS-16) | Post | P | 6.00 | SSS against listed Firm | WB | Average contract size not more than NRs 300 thousand for the SEMP preparation, Detail Feasibility and engineering Study of three development regions of western Nepal under component A and project preparation works of Irrigation Management Transfer under component B. (A roaster of consulting firm meeting minimum qualifying criteria will be established and contract is awarded to a firm only once in a fiscal year) | 30 June 2013 | RID/OPD |  |
|  |  |  | A |  |  |  |  |  |  |  |
| 16 | Short Term Consultancy Services for monitoring and Evaluation of GMIS and subprojects etc. (IWRMP/DOI/S/SSS-17) | Post | P | 1.00 | SSS against listed Firm | WB | Average contract size not more than 300 thousand for the monitoring of GMIS and other ongoing works of the subprojects (A roaster of consulting firms meeting minimum qualifying criteria will be established and contract is awarded to a firm only once in a fiscal year) | 30 June 2013 | OPD |  |
|  |  |  | A |  |  |  |  |  |  |  |

SSS: Single Source Selection

SQ: Sealed Quotation

# Text boxes

75406 v2