## Thresholds
Xinjiang Turpan Water Conservation Project
Threshold for Procurement Methods and Prior Review
Expenditure Category | Contract Value Threshold | Procurement Method | Prior Review threshold 1/
(US$ 000)
1. Civil Works | ≥20,000 | ICB | ALL
| <20,000 | NCB | ≥5,000
| <100 | Shopping | NA
2. Goods | ≥1,000 | ICB | All
| <1,000 | NCB | ≥500
| <100 | Shopping | NA
3. Consunltant Services | ≥200 | QCBS/QBS | ≥100
| <200 | CQ | ≥100
|  | Individual consultants | >50
|  | Single source selection | All single source contracts
1/: The first NCB contracts for both works and goods in the county level are subject to the Bank's prior review.
2/: Direct contract contracting shall comply with Para.3.6 & 3.7 of Procurement Guidelines.

## 2011 goods and works
Xinjiang Turpan Water Conservation Project
Procurment Plan for works and goods (2011)
Reference No |  | Description of Contract | Cost Estimate |  | Procurement Method | Bank Review(PRIOR/POST) | Expected Date of Bid Opening | Actual Date of Contract Signing | Actual Contract Price of signing | construction period in months | Procurment Status | Remarks
|  |  | RMB'000 | (US$'000)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ⅠCivil Works
2. Construction of Dams |  |  | 431797.3228 | 67679.8312
Meiyaogou Reservoir Construction Management Bureau | Meiyaogou Dam Construction
| MYG2W1 | Meiyaogou Dam Construction(44.8m concrete faced sand &gravel Rock dam) | 129445.1939 | 20289.2153 | ICB WORKS | PRIOR | 2011.12 |  |  | 21 | not started
| subtotal |  | 129445.1939 | 20289.2153
Ertanggou Reservoir Construction Management Bureau | Ertangou Dam Construction in Shanshan county
| ETG2W1 | Base Treatment and dam constructionWorks(66m asphalt concrete core sand & rock dam) | 145684.09 | 22834.4969 | ICB WORKS | PRIOR | 2011.12 |  |  | 30 | Bidding Preparation
| ETG2W2 | diversion and discharge system works（Water Release Tunnel,Water Spillway Works,Irrigation Water Supply Tunnel） | 70174.51 | 10999.1395 | NCB WORKS | PRIOR | 2011.12 |  |  | 14 | Bidding Preparation | Water release tunnel,water spillway works and irrigation water supply tunnel have been combined with a package because they belong to the same water water realease system and can not be separated int parts to construct
| ETG2W3 | House Buildings（2000m2，including water supply, water drainage, heat equipments and its installment, fire-fighting equipments） | 4664.2 | 731.0658 | NCB WORKS | POST | 2011.9.30 |  |  | 10 | Bid Evaluation Report Preparation | House buildings(ETG2W2）have been taken from original procurement plan and now is taken as a separate package in order to facilitate the project procurement and implementation.
| ETG2W4 | Transport Works（15km road to the site and 1 concrete bridge） | 12750 | 1875 | NCB WORKS | POST | 2011.12 |  |  | 6 | Bidding Preparation
| ETG2W5 | Power transmission supply works（35KV，55km） | 8809.6 | 1381 | NCB WORKS | POST | 2011.9.30 |  |  | 3 | Bid Evaluation Report Preparation
| ETG2W6 | Power transformation Works for Ertangou Reservoir Resettlement | 197 | 31 | NBF | NA | 2011.3 | 2011.6.14 | 197 | 2 | Implementation Finished | Finished with counterpart funds
| ETG2W7 | Land levelling Works for Ertangou Reservoir Resettlement | 5850 | 916.9279 | NBF | NA | 2011.6 | 211.9.22 | 1885.7057 | 4 | Contract signed | Planned to be finished with counterpart funds
[8 empty] | 2011.9.22 | 1187.134 | 3 | Contract signed | Planned to be finished with counterpart funds
| ETG2W8 | Outside Transport Works for Ertangou Reservoir Resettlement |  |  | NBF | NA | 2011.10.18 |  |  |  | Bid Award Notice issued | Planned to be finished with counterpart funds
| ETG2W9 | House Building Works for Ertangou Reservoir Resettlement |  |  | NBF | NA | 2011.6 | 2011.7.18 | 2076 |  | Contract implementing | Planned to be finished with counterpart funds
[8 empty] | 2011.7.18 | 2076 |  | Contract implementing | Planned to be finished with counterpart funds
| subtotal |  | 248129.512 | 38891.773
Alagou Reservoir Construction Management Bureau | Alagou Dam Construction in Tuokexun County
| ALG2W2 | Water Spillway Works(total length:298.3m, 20~28m wide) | 47759.8169 | 7485.8647 | NBF | NA | 2011.12 |  |  | 11 | Bidding Preparation | Planned to be finished with counterpart funds
| ALG2W4 | House Buildings（2800m2) | 6462.8 | 1013 | NBF | NA | 2011.12 |  |  | 6 | Bidding Preparation | The original package number is ALG2W5 and its content does not change.
| subtotal |  | 54222.6169 | 8499
3. Irrigated Agriculture Water Savings |  |  | 14992.2275 | 2349.8789 | [8 empty] | 项目 | 数量 | 千人民币 | 千美元 | NCB/CQS |  | Shopping/CP |  | NBF |  | 赠款 | SSS | IC | SOE
3.1 Works for water-saving Irrigation |  |  | 14992.2275 | 2349.8789 | [8 empty] | 土建 | 20 | 449678.5502 | 70482.5314 | 7 | 380463.7059 |  |  | 13 | 69214.8443
Turpan city Water Resources Bureau | Drip irrigation in Turpan city(20,000mu) | [11 empty] | 货物 | 40 | 89055.167 | 13539.8509 | 30 | #REF! | 10 | 3880.9036
| TLF3.1W1 | Ya'r township & Qiquanhu Township grape drip(5,000mu) | 2044.3144 | 320.4255 | NBF | NA | 2011.5 | 2011.8.16 | 2034.127 | 8 | Contract signed | Planned to be finished with counterpart funds | 咨询 | 19 | 30642 | 4803 | 9 | 13984.6 | 1 | 630 |  |  |  | 1200 | 1200 | 1465.1
| TLF3.1W2 | Aiding Lake Township melon &cotton drip(7,000mu) | 1236.5672 | 193.8193 | NBF | NA | 2011.5 | 2011.8.16 | 1219.378 | 8 | Contract signed | Planned to be finished with counterpart funds | 合计 | 79 | 569375.7173 | 88825.3823
| TLF3.1W3 | Qiatekale Township melon &cotton drip(8000mu) | 1172.9647 | 183.8503 | NBF | NA | 2011.5 | 2011.8.16 | 1139.0299 | 8 | Contract signed | Planned to be finished with counterpart funds
| subtotal |  | 4453.8463 | 698.095 | [8 empty] | 项目 | 土建 | 货物 | [7 empty] | 1 | 1 | 1 | 6
Shanshan County Water Resources Bureau | Drip irrigation in Shanshan County(20,000mu) | [11 empty] | 水资源 |  | 5
| SS3.1W1 | Tuyugou Township &Dalangkan Township green houses(3993mu) | 1329.8667 | 208.4431 | NBF | NA | 2011.5 | 2011.8.10 | 1255.501 | 8 | Contract signed | Planned to be finished with counterpart funds | 大坝 | 9 | 17
| SS3.1W2 | Lukeqin Township green houses (6175mu) | 2066.852 | 323.958 | NBF | NA | 2011.5 | 2011.8.10 | 1876.922 | 8 | Contract signed | Planned to be finished with counterpart funds | 滴灌 | 10 | 18
| SS3.1W3 | Dalangkan Township grape,melon &cotton (5157mu) | 822.3817 | 128.9 | NBF | NA | 2011.5 | 2011.8.10 | 805.164 | 8 | Contract signed | Planned to be finished with counterpart funds | 坎儿井 | 1
| SS3.1W4 | Qiketai Township grape drip(5087mu) | 887.7766 | 139.1499 | NBF | NA | 2011.5 | 2011.8.10 | 745 | 8 | Contract signed | Planned to be finished with counterpart funds
| subtotal |  | 5106.8771 | 800.451
Tuokexun County Water Resources Bureau | Drip irrigation in Tuokexun County(19,000mu)
| TKX3.1W1 | Alagou surface water dripping (9994mu) | 2065.2061 | 323.7 | NBF | NA | 2011.5 | 2011.8.10 | 1978.806 | 8 | Contract signed | Planned to be finished with counterpart funds
| TKX3.1W2 | Township green houses(4648mu) | 1740.0881 | 272.7411 | NBF | NA | 2011.5 | 2011.8.10 | 1596.01 | 8 | Contract signed | Planned to be finished with counterpart funds
| TKX3.1W3 | Agriculture Park green houses(4477mu) | 1626.2098 | 254.8918 | NBF | NA | 2011.5 | 2011.8.10 | 1559.3716 | 8 | Contract signed | Planned to be finished with counterpart funds
| subtotal |  | 5431.504 | 851.3329
4. Kariz Restoration
Turpan Prefecture Relic Bureau | Wudaolin Kariz Restoration in Turpan City
| KEJ4W1 | Canal and Vertical Well Construction （2.88km ) | 2889 | 452.8213 | NCB WORKS | POST | 2011.12 |  |  | 8 | Bidding Preparation
| subtotal |  | 2889 | 452.8213
Total for Civil Works |  |  | 449678.5502 | 70482.5314
ⅡProcurement of Goods
1.sofeware and hardware equipment of water resources management | PMO1G1 | Database software | 300 | 47.0219 | Shopping | POST | 2011.12 |  |  | 3 | Bidding Preparation
| PMO1G2 | GIS software | 500 | 78.3699 | Shopping | POST | 2011.12 |  |  | 3 | Bidding Preparation
| PMO1G3 | Water Resources Management Hardware Equipment | 489 | 76.6458 | Shopping | POST | 2011.12 |  |  | 2 | Bidding Preparation
| PMO1G4 | Water Resources Monitoring Equipment | 483 | 75.7053 | Shopping | POST | 2011.12 |  |  | 3 | Bidding Preparation
| subtotal |  | 1772 | 277.7429
2.Equipment for Three Dams | MechanicaL & Electric equipment,metal structure supply ,installation for Meiyaogou Dam in Turpan City
| MYG2G1 | Metal Structure Supply and installation(2 plane gates,1 radial gate and hoist installment) | 1591.59 | 249.4655 | NCB GOODS | POST | 2011.12 |  |  | 4 | not started | The original package number does not change and only it excludes from hoist equipments.
| MYG2G2 | Hoist equipment (2 winches and 1 hydraulic hoists) | 834.18 | 130.7492 | NCB GOODS | POST | 2011.12 |  |  | 4 | not started | Hoist equipment is seperated from the orignal Package No.MYG2G1 as a single package in order to facilitate project procurement because metal structure factories do not produce hoist equipment.
| MYG2G3 | Dam Safety Monitoring Equipment and installment | 1148.8 | 180.0627 | NCB GOODS | POST | 2011.12 |  |  | 7 | not started | The original package number is MYG2G2 and its content does not change.
| MYG2G4 | Generating equipment, power transmission equipment and installment | 197.96 | 31.0282 | Shopping | POST | 2011.12 |  |  | 3 | not started | Electric equipment is seperated from the orignal Package No.MYG2G3 in order to facilitate project procurement because it belongs to electric equipment.
| MYG2G5 | communication equipment and Office Automation System | 299.4 | 46.9279 | Shopping | POST | 2011.12 |  |  | 3 | not started | Communication equipment and office equipment are seperated from the orignal Package No.MYG2G3 in order to facilitate project procurement because they belong to standard equipments.
| subtotal |  | 4071.93 | 638.2335
MechanicaL & electric equipment,metal structure supply,installation for Ertanggou Dam in Shanshan County
| ETG2G1 | Metal structure supply and installment (plane gates,support seat and installment (including hoist installment) | 3561.6 | 558.2445 | NCB GOODS | PRIOR | 2011.12 |  |  | 4 | Bidding Preparation | The original package number does not change and only it excludes from hoist equipments.
| ETG2G2 | Hoist equipment(3 fixed winches, 2 hydraulic hoists and 2 monorail cranes ) | 4041.2 | 633.4169 | NCB GOODS | PRIOR | 2011.12 |  |  | 4 | Bidding Preparation | Hoist equipment is seperated from the orignal Package No.ETG2G1 as a single package in order to facilitate project procurement because metal structure factories do not produce hoist equipment.
| ETG2G3 | Dam safety monitoring equipment and installment | 5519.7 | 865.1567 | NCB GOODS | PRIOR | 2011.12 |  |  | 8 | Bidding Preparation | The original package number is ETG2G2 and its content does not change.
| ETG2G4 | Mechanical & electric equipment and installment (procurement and installment of transformer,substation, power cabinet and etc.) | 2260.3 | 354.279 | NCB GOODS | POST | 2011.12 |  |  | 3 | Bidding Preparation | Mechanical & electric equipment and installment are seperated from the orignal Package No.ETG2G3 in order to facilitate project procurement because they belong to electric equipments.
| ETG2G5 | Communication equipment and computer monitoring system, and installment | 2791.9 | 437.6019 | NCB GOODS | POST | 2011.12 |  |  | 2 | Bidding Preparation | Communication equipment and office equipment are seperated from mechanical & electric equipmentand installation of the orignal Package No.ETG2G3 in order to facilitate project procurement because they belong to standard equipments.
| ETG2G6 | Equipment and installment of water automatic telemetering system | 3839.6 | 601.8182 | NCB GOODS | PRIOR | 2011.7 |  |  | 2 | Bidding Preparation | It is seperated from the mechanical & electric equipment and installation of the original Package No.ETG2G3 in order to facilitate project procurement because it belongs to professional monitoring equipment.
| subtotal |  | 22014.3 | 3450.5172
MechanicaL & electric equipment,metal structure supply ,installation for Alagou Dam in Tuokexun County
| ALG2G1 | Metal structure supply and installation(1 plane gate, 4 radial gates and hoist installment) | 2753.79 | 431.6285 | NCB GOODS | POST | 2011.5 | 2011.9.22 | 2468 | 4 | Contract signed | The original package number does not change and it excludes from hoist equipment and steel pipe for industry water supply.
| ALG2G2 | Hoist equipment(1 winches, 4 hydraulic hoists) | 1020.77 | 159.9953 | NCB GOODS | POST | 2011.5 | 2011.9.22 | 2000 | 4 | Contract signed | Hoist equipment is seperated from the orignal Package No.ALG2G1 as a single package in order to facilitate project procurement because metal structure factoies do not produce hoist equipment.
| ALG2G4 | Dam Monitoring Equipment and installment | 5631.5 | 882.6803 | NCB GOODS | PRIOR | 2011.9.29 |  |  | 6 | Bid Evaluation Report Preparation | The original package number is ALG2G2 and its content does not change.
| ALG2G5 | Feed equipment and installment | 1336.75 | 209.5219 | NCB GOODS | POST | 2011.12 |  |  | 4 | Bidding Preparation | It is seperated from the mechanical & electric equipmentand installation of the orignal Package No.ALG2G3 in order to facilitate project procurement because it belongs to electric equipment.
| ALG2G6 | Communication equipment and office automation equipment | 1375 | 215.5172 | NCB GOODS | POST | 2011.12 |  |  | 2 | Bidding Preparation | Communication equipment and office equipment are seperated from the mechanical & electric equipment and installation of the orignal Package No.ALG2G3 in order to facilitate project procurement because they belong to standard office equipments.
| subtotal |  | 12117.81 | 1899.3433
| Total for Dam equipment |  | 38204.04 | 5988.094
3.1Drip Irrigation Equipment and pipes & fittings | Dripping irrigation pump supply,installation in Turpan City (20,000mu)
| TLF3.1G1 | PVC pipe, pipe fittings supply and installment (PVC length:153.74km) | 6522.52 | 959.1941 | NCB GOODS | PRIOR | 2011.5 | 2011.9.20 | 5730.3 | 5 | Contract signed | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan.
| TLF3.1G2 | Steel valve supply and installment (gate valve, air valve, reducing valve,butterfly valve) | 526.24 | 82 | Shopping | POST | 2011.9.30 |  |  | 1 | Bid Evaluation Report Preparation | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan.
| TLF3.1G3 | PE pipe and tape supply, installment ( PE lateral pipe:162.69km,tape:9032km) | 2886.75 | 424.5221 | NCB GOODS | POST | 2011.6 | 2011.9.23 | 2450.6 | 2 | Contract signed | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan.
| TLF3.1G4 | Glass steel pipe supply and installment （5.5km） | 2448.22 | 360.0324 | NCB GOODS | POST | 2011.9.29 |  |  | 3 | Bid Evaluation Report Preparation | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan.
| TLF3.1G5 | Tape supply and installment(2551.8km） | 2704.91 | 397.7809 | NCB GOODS | POST | 2011.7 | 2011.9.20 | 1709.7 | 3 | Contract signed | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan. |  | PVC管 | 投资
| TLF3.1G6 | Pump and its auxilliary equipment supply, installment (33 pumps, 33 start devices ） | 1114.4185 | 163.8851 | NCB GOODS | POST | 2011.7 | 2011.9.22 | 1209.6 | 4 | Contract signed | Original Package No.PMO3.1G1 has been detailed from the Prefecture level to the County Level for smooth procurement, reimbursement and repaying the loan. | 吐鲁番市 | 153.7398 | 652.2519
| TLF3.1G7 | Supply and Installment of Filtering equipment and fertilizer tanks (33 automatic filters (well), 5 automatic filters (surface water) and 33 feretilizer tanks) | 1910.014 | 280.8844 | NCB GOODS | POST | 2011.7 | 2011.9.20 | 838.2 | 3 | Contract signed | Original Package No.PMO3.1G2 has been divided from the Prefecture level to the County Level for smooth procurement, reimbursement and repaying the loan. | 鄯善县 | 205.1676 | 484.8313
| subtotal |  | 18113.0725 | 2669 | [8 empty] | 托克逊县 | 343.0615 | 583.0863
Dripping irrigation pump supply,installation in Shanshan County (20,000mu)
| SS3.1G1 | PVC pipe, pipe fittings supply and installment (PVC length:205.17km) | 4848.31 | 712.9868 | NCB GOODS | PRIOR | 2011.5 | 2011.9.22 | 5271.6 | 5 | Contract signed | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan.
| SS3.1G2 | PE pipe and tape supply and installment ( PE lateral pipe:409km,tape:8971km) | 4393.69 | 646.1309 | NCB GOODS | PRIOR | 2011.6 |  | 3357.6 | 2 | Bid Evaluation Report Preparation | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan. |  | PE管 | 滴灌带 | 投资
| SS3.1G3 | Pump and its auxilliary equipment supply and installment (69 pumps, 69 start devices） | 3951.3529 | 581.0813 | NCB GOODS | PRIOR | 2011.5 | 2011.9.22 | 3589.6 | 4 | Contract signed | Original Package No.PMO3.1G1 has been detailed from the Prefecture level to the County Level for smooth procurement, reimbursement and repaying the loan. | 吐鲁番市 | 162.6906 | 9032.208 | 288.6749
| SS3.1G4 | Supply and Installment of Filtering equipment and fertilizer tank (69 automatic filters and 69 fertilizer tanks) | 2713.494 | 399.0432 | NCB GOODS | POST | 2011.6 |  | 1117.8 | 3 | Bid Evaluation Report Preparation | Original Package No.PMO3.1G2 has been detailed from the Prefecture level to the County Level for smooth procurement, reimbursement and repaying the loan. | 鄯善县 | 408.995 | 8970.5819 | 439.3685
| subtotal |  | 15906.8469 | 2339.2422 | [8 empty] | 托克逊县 | 467.95 | 6909.463 | 420.1587
Dripping irrigation pump supply,installation in Tuokexun County (19,000mu)
| TKX3.1G1 | PVC pipe, pipe fittings supply and installment (PVC length:343.06km) | 5619.16 | 826.3471 | NCB GOODS | PRIOR | 2011.5 | 2011.9.22 | 5291.8 | 5 | Contract signed | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan.
| TKX3.1G2 | Steel valve supply and installment (gate valve, air valve, reducing valve,butterfly valve) | 208.14 | 32.6238 | Shopping | POST | 2011.9.30 |  |  | 1 | Bid Evaluation Report Preparation | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan.
| TKX3.1G3 | PE pipe and tape supply and installment ( PE lateral pipe:467.95km,tape:6909km) | 4201.59 | 658.5564 | NCB GOODS | PRIOR | 2011.6 |  |  | 2 | Bid Evaluation Report Preparation | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan.
| TKX3.1G4 | Glass steel pipe supply and installment （1.0km） | 478.27 | 74.9639 | Shopping | POST | 2011.9.30 |  |  | 3 | Bid Evaluation Report Preparation | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan.
| TKX3.1G5 | Tape supply and installment(1633.4km） | 1904.56 | 280.0824 | NCB GOODS | POST | 2011.7 | 2011.9.22 | 1078.1 | 3 | Contract signed | Original Package No.PMO3.1G3 has been detailed from the Prefecture level to the County Level in accordance with goods type and supply capacity of productor for smooth procurement, reimbursement and repaying the loan.
| TKX3.1G6 | pump and its auxilliary equipment supply and installment (19 pumps, 19 start devices） | 398.8936 | 62.5225 | Shopping | POST | 2011.9.30 |  |  | 4 | Bid Evaluation Report Preparation | Original Package No.PMO3.1G1 has been detailed from the Prefecture level to the County Level for smooth procurement, reimbursement and repaying the loan.
| TKX3.1G7 | Supply and Installment of Filtering equipment and fertilizer tank (19 automatic filters and 19 fertilizer tanks) | 948.594 | 139.4991 | NCB GOODS | POST | 2011.6 | 2011.9.22 | 345.8 | 3 | Contract signed | Original Package No.PMO3.1G2 has been detailed from the Prefecture level to the County Level for smooth procurement, reimbursement and repaying the loan.
| subtotal |  | 13759.2076 | 2074.5952
| Total for drip equipment |  | 47779.127 | 7082.8374
Institutional Capacity Building Management Equipment | PMO5G2 | Water measurement facility and others | 1300 | 191.1765 | NCB GOODS | POST | 2011.12 |  |  | 3 | Bidding Preparation | The original package number is PMO1G6 and its content does not change.
| subtotal |  | 1300 | 191.1765
total for goods |  |  | 89055.167 | 13539.8509
Re：NBF:Non Bank Financing contract，ICB：Internation Competitive Bidding，NCB：National Competitive Bidding，Shopping:request for quotations.
The estimated cost for this procurement contract is based on the cost of the preliminary design.
Works contracts for Meiyaogou, Ertanggou and Alagou dam construction are subject to prequalification
Exchange rate:RMB6.38:1$
Note on C9: 包含施工临时交通、供电、房屋和导流工程以及大坝内部观测工程
Note on C16: 不包括征地
Note on C25: 按照世行要求招标
Note on B26: 交通工程放到2012年采购
Note on C26: 不含临时永久房屋
Note on C31: 不含安装费,不含管沟开挖
Note on C36: 不含安装费,不含管沟开挖
Note on C42: 不含安装费
Note on C52: 硬件和软件分开是否支持，如果追溯，将来能否用
Note on C54: 硬件和软件分开是否支持，如果追溯，将来能否用
Note on C74: 含未招标的闸门和启闭机设备
Note on C75: 含未招标的闸门和启闭机设备
Note on B78: 水情测报系统放到2012年采购

## 2011 Services
Xinjiang Turpan Water Conservation Project
Procurement Plan for Consultant Services（2011）
Contract No | Bief Description of Contract | Cost Estimate |  | Selection Method | Bank Review(PRIOR/POST) | Implement Schedule |  |  |  | Actual Contract Price of signing(RMB'000) | Actual Date of Contract Signing | Remarks
|  | (RMB'000) | （US$'000 ) |  |  | Procurement Process |  |  | Implementation of contract
[6 empty] | Expected Inviting for Express of Interest (EOI) | Expected Receipt of Proposals | Expected Contract Award Date
ConsultantServices,Training and workshops |  | 30642 | 4803 | [8 empty] | It has been finished by water resourses staff of the prefecture, NBF
PMO1C1 | ET Quato Data Survey | 2200 | 344.8276 | NBF | NA | —— | —— | —— | 2009-2010
PMO1C2 | ET -Based Water Conservation Agriculture Supplementary Program and Analysis System in Turpan Prefecture | 1200 | 188.0878 | CQS | PRIOR | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011
PMO1C3 | Effective Water Conservation Irrigation Quota Control Plan and Analysis System in | 800 | 125.3918 | CQS | PRIOR | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011
PMO1C4 | Water Rights, Water Pricing and Implementation Plan in Project Areas | 500 | 78.3699 | CQS | POST | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011
PMO1C5 | ET-based Agricultural Water Allocation Program | 800 | 125.3918 | CQS | PRIOR | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011
PMO1C6 | Water Resources and Environmental Data Development and Input (Knowledge Management Information System) | 1000 | 156.7398 | CQS | PRIOR | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011
PMO1C7 | Intergration and application of cadastre and ET information in Turpan Prefecture | 1200 | 188.0878 | CQS | PRIOR | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011
PMO1C8 | ET-based Water Control Red Line | 1200 | 188.0878 | CQS | PRIOR | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011
PMO1C9 | Building-up Monitoring Management System of Surface Water and Groundwater | 300 | 47.0219 | CQS | POST | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011 |  |  | Grant
PMO1C10 | Study on Compensation System for Land Abandonment | 500 | 78.3699 | CQS | POST | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011 |  |  | Original eight outlines （PMO1C2-PMO1C9）were rearranged that the outline with the same or repetition content is taken as a separate content to train for facilitating the project implementation.
PMO1C11 | Basic data collection & analysis of water management and field observation | 1200 | 188.0878 | CQS | PRIOR | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011
PMO1C12 | RS-based ET Monitoring and Application in Turpan Prefecture | 6484.6 | 1016.395 | NBF | NA | Dec.,2011 | Jan,2012 | Feb.,2012 | Mar,2012 |  |  | Finished with counterpart funds(including 2.2 million for ET-Quato data survey.
PMO5C2 | Project Monitoring and Evaluation | 1000 | 157 | CQS | PRIOR | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011
PMO5C3 | Water Engineering Technical Support | 1200 | 188 | IC | POST | 2011 | 2011 | 2011 | 2011 |  |  | Totally including 15 individual consultant selections, each consultant contract price less than $50,000.
PMO5C4 | Climate Change Study in project areas | 200 | 31 | CQS | POST | Oct., 2011 | Nov., 2011 | Dec., 2011 | Dec., 2011
PMO5C5 | Establishment and maintenance of WUAs (13WUAs) | 630 | 92.6471 | CP(Shopping) | POST | —— | —— | —— | 2011
PMO5T1 | Domestic Study tour(52 person-times) | 405.6 | 64 | SOE | POST | —— | —— | —— | 2011
PMO5T2 | Oversea Study Tour(17 person-times) | 680 | 107 | SOE | POST | —— | —— | —— | 2011
PMO5T3 | Management Training(46 person-times) | 172.5 | 27 | SOE | POST | —— | —— | —— | 2011
PMO5T4 | Technic Training (30person-times) | 75 | 12 | SOE | POST | —— | —— | —— | 2011
PMO5T5 | Propaganda Activity | 72 | 10.5882 | SOE | POST | —— | —— | —— | 2011
PMO5T6 | Training Brochure | 60 | 8.8235 | SOE | POST | —— | —— | —— | 2011
PMO-CS-1 | Bidding Agency Selection | 3964 | 621 | NBF | NA | Mar.,2011 | Mar.,2011 | Apr.,2011 | 2011-2013 |  | Apr.20,2011 | Planned to be finished with counterpart funds.
PMO-PEM-1 | Project Environment Monitoring | 3089 | 484 | NBF | NA | Oct., 2011 | Nov., 2011 | Dec, 2011 | 2012-2014 |  |  | Planned to be finished with counterpart funds.
PMO-PEM-2 | Project Environment Supervision | 1708 | 268 | NBF | NA | Oct., 2011 | Nov., 2011 | Dec, 2011 | 2012-2014 |  |  | Planned to be finished with counterpart funds.
Note: QCBS/QBS：quality and cost based selection,/quality based selection；CQS：consultant's qualifications based selection；IC：individual consultant's selection；CP: community participating procurment, SOE：statement of expenditure。
PRIOR：pre-review；POST：post-review.
Exchange rate:RMB6.38:1$
65121