|  |
| --- |
| **Restructuring** **Status:** **Draft** |
| **Restructuring Type:** |
| Last modified on date : 12/30/2011 |

|  |  |
| --- | --- |
| **1. Basic Information** | |
| Project ID & Name | P082618: MZ-Beira Railway SIL (FY05) |
| Country | Mozambique |
| Task Team Leader | Henry Des Longchamps Deville |
| Sector Manager/Director |  |
| Country Director |  |
| Original Board Approval Date | 10/14/2004 |
| Original Closing Date: | 06/30/2010 |
| Current Closing Date | 12/31/2011 |
| Proposed Closing Date [if applicable] |  |
| EA Category | B-Partial Assessment |
| Revised EA Category |  |
| EA Completion Date | 11/18/2003 |
| Revised EA Completion Date |  |

|  |  |  |
| --- | --- | --- |
| **2. Revised Financing Plan (US$m)** | | |
| **Source** | **Original** | **Revised** |
| BORR | 0.00 | 0.00 |
| IDA | 110.00 | 110.00 |
| ZPCI | 48.00 | 48.00 |
| **Total** | 158.00 | 158.00 |

|  |  |  |
| --- | --- | --- |
| **3. Borrower** | | |
| **Organization** | **Department** | **Location** |
| Banco de Mocambique |  | Mozambique |

|  |  |  |
| --- | --- | --- |
| **4. Implementing Agency** | | |
| **Organization** | **Department** | **Location** |

|  |  |  |
| --- | --- | --- |
| **5. Disbursement Estimates (US$m)** | | |
| **Actual amount disbursed as of 01/03/2012** **113.81** | | |
| **Fiscal Year** | **Annual** | **Cumulative** |
| 2011 | 0.00 | 113.81 |
|  | **Total** | **113.81** |

|  |  |
| --- | --- |
| **6. Policy Exceptions and Safeguard Policies** | |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes**  **Original/Current Project Development Objectives/Outcomes** |
| The objectives of the Project are to: (i) make cost effective and efficient transport available for the freight and passenger traffic in the Zambezi valley to accelerate economic growth and reduce poverty in the sub-region; (ii) increase international traffic through the Beira Railway System; and (iii) ensure the operational, managerial and financial sustainability of the Beira Railway System. |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|  |