Document of

The World Bank

Report No: 72343-ZA

Restructuring PAPER

ON A

PROPOSED Project restructuring

of

GEF-Western Indian Ocean Marine Highway Development and Coastal and Marine Contamination Prevention PROJECT

GRANT NUMBER TF090304

GRANT APPROVAL DATE: MAY 22, 2007

TO THE

REPUBLIC OF SOUTH AFRICA

(FOR COMOROS, KENYA, MADAGASCAR, MAURITIUS, MOZAMBIQUE,

SEYCHELLES, SOUTH AFRICA, *AND* TANZANIA)

SEPTEMBER 6, 2012

Transport Sector

Country Department AFCRI

Africa Region

|  |
| --- |
| This document has a restricted distribution and may be used by recipients only in the performance of their official duties. Its contents may not otherwise be disclosed without World Bank authorization. |

|  |  |  |
| --- | --- | --- |
| Regional Vice President: |  | Makhtar Diop |
| Acting Country Director: |  | Elizabeth Lule |
|  |  |  |
| Sector Manager: |  | Supee Teravaninthorn |
| Task Team Leader: |  | Juan Gaviria |

|  |
| --- |
| **Restructuring** **Status:** **Draft** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 09/06/2012 |

|  |  |
| --- | --- |
| **1. Basic Information** | |
| Project ID & Name | P078643: 3A-GEF WIO Marine Highway Dev SIL (FY07) |
| Country | Africa |
| Task Team Leader | Juan Gaviria |
| Sector Manager/Director | Supee Teravaninthorn |
| Country Director | Elizabeth Laura Lule |
| Original Board Approval Date | 05/22/2007 |
| Original Closing Date: | 06/30/2011 |
| Current Closing Date | 12/31/2012 |
| Proposed Closing Date [if applicable] |  |
| EA Category | C-Not Required |
| Revised EA Category | C-Not Required-Not Required |
| EA Completion Date |  |
| Revised EA Completion Date |  |

|  |  |  |
| --- | --- | --- |
| **2. Revised Financing Plan (US$m)** | | |
| **Source** | **Original** | **Revised** |
| BORR | 5.00 | 1.80 |
| GEFU | 11.00 | 11.00 |
| OTHR | 10.00 | 13.00 |
| **Total** | 26.00 | 26.00 |

|  |  |  |
| --- | --- | --- |
| **3. Borrower** | | |
| **Organization** | **Department** | **Location** |
| Ministry of Water and Environmental Affairs |  | South Africa |

|  |  |  |
| --- | --- | --- |
| **4. Implementing Agency** | | |
| **Organization** | **Department** | **Location** |

|  |  |  |
| --- | --- | --- |
| **5. Disbursement Estimates (US$m)** | | |
| **Actual amount disbursed as of 09/06/2012** **5.48** | | |
| **Fiscal Year** | **Annual** | **Cumulative** |
| 2012 | 2.31 | 5.48 |
|  | **Total** | **5.48** |

|  |  |
| --- | --- |
| **6. Policy Exceptions and Safeguard Policies** | |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes**  **Original/Current Project Development Objectives/Outcomes** |
| The project's medium to long-term global environmental goals are to reduce the risk of ship-based environmental contamination (such as oil spills from groundings and illegal discharges of ballast and bilge waters) and to strengthen the capacity of countries to respond to oil or chemical spill emergencies in the region. The project has three specific global environmental objectives. The first is to ascertain the economic, technical, and institutional feasibility of introducing modern aids to navigation systems in the region, such as an electronically supported marine highway, to guide ships through sensitive areas and to encourage monitoring of the movements and activities of fishing and other vessels operating within countries' territorial waters. The second objective is to support widening the existing regional agreement (June 5, 1998) on port state control and implementation of its provisions. The third objective, focusing on Kenya, Mozambique, South Africa, and Tanzania, is to reduce risks of environmental damage to beaches, fishing grounds, and other domestic resources from spills of oil and chemicals. This will be achieved by supporting efforts of Kenya, Mozambique, South Africa, and Tanzania to become part of a regional oil spill response plan, by completing the identification and mapping of environmentally sensitive areas along coasts and sea lanes, and support regional collaboration with the west Indian Ocean island states. |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|  |

Africa — GEF-Western Indian Ocean Marine Highway Development and Coastal and Marine Contamination Prevention PROJECT

P078643

GEF GRANT No. TF090304

**Restructuring Paper**

1. Proceeds for the Africa*, GEF-*Western Indian Ocean Marine Highway Development and Coastal and Marine Contamination Prevention Project*,* Grant No. TF090304*,* P078643 will be reallocated as follows:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Category of Expenditure** | | **Allocation** | | **% of Financing** | |
| Current | Revised | Current | Revised | Current | Revised |
| 1. Works |  |  |  |  |  |
| (a) SAMSA | (a) SAMSA | 1,100,000 | 1,100,000 | 100 | 100 |
| (b) IOC | (b) IOC | 0.00 | 0.00 |  |  |
| 1. Goods   (a) SAMSA | (a) SAMSA | 1,300,000 | 1,300,000 | 100 | 100 |
|  | (b) IOC | 700,000 | 1,175,000 | 100 | 100 |
| 1. Consultant’s Services and Audits   (a) SAMSA | (a) SAMSA | 1,200,000 | 1,200,000 | 100 | 100 |
| (b) IOC | (b) IOC | 2,430,000 | 2,430,000 | 100 | 100 |
| 1. Training and Workshops   (a) SAMSA | (a) SAMSA | 520,000 | 520,000 | 100 | 100 |
| (b) IOC | (b) IOC | 1,300,000 | 1,300,000 | 100 | 100 |
| 1. Operating Costs   (a) SAMSA | (a) SAMSA | 1,200,000 | 1,200,000 | 100 | 100 |
| (b) IOC | (b) IOC | 300,000 | 300,000 | 100 | 100 |
| 1. Unallocated |  | 950,000 | 475,000 | 100 | 100 |
| TOTAL |  | 11,000,000 | 11,000,000 |  |  |

1. Project implementation and achievement of development objectives are currently rated as Satisfactory. The Project closing date was extended to December 31, 2012 after the mid-term review (November 2010). Both implementation agencies South African Maritime Safety Authority (SAMSA) and Indian Ocean Commission (IOC) are performing satisfactorily. The project’s audit reports for both implementation agencies for 2011 have been submitted; SAMSA’s audit report is satisfactory, and IOC’s audit report is acceptable but some comments were forwarded requesting IOC to work with the auditor’s to revise the report and ensure full compliance with our requirements. The Project objectives are achievable. The survey of the marine route along the Mozambique Channel was completed, and the data is now available in Electronic Nautical Charts prepared by the U.K. Hydrographic Service. The project has revised the country specific and regional oil spill contingency plans, prepared environmental sensitive area maps, is developing an ecosystems valuation methodology and is advancing with the establishment of a Regional Coordination Center for spill contingencies. The Project also implemented a US$100,000 grant from the European Space Agency to carry out earth observation to detect oil spills in real time and monitor the health of selected coral reefs along the surveyed corridor and the marine route.
2. In a letter dated June 17, 2011, the Ministry of Water and Environment of South Africa requested a reallocation of grant proceeds in accordance with the agreements reached during the Mid Term review.
3. The proposed reallocation from the unallocated category to category 2(b) finances additional goods included in the Project Description which include oil spill combating equipment kits by IOC. The reallocation does not result in a change to the project activities nor require a modification to the project description in the Grant Agreement and as such is considered to be minor in nature.