## Settings (hidden)
Prior | Version: | 1
Post | Last changed: | 2009-04-13
| Revised by: | Andrew Alexander Jacobs
Firm
Individual
Yes
No
Goods
Works
Non-Consulting Services

## General
Public Works Project IV Procurement Plan for the period June 2011-July 2014
I. General
1. | Project Information
| Project Name: | Labor Intensive Public Works Project (Public Works IV)
| Country: | Yemen
| Project ID: | P122594
| Loan/Credit Numbers: | IDA H663-0
2. | Bank's approval date of Procurement Plan | 2012-05-23 | (part of the agreement)
Revision 1: 13/04/2013
to check
3. | Date of General Procurement Notice | 2012-09-05
II. Goods, Work and Non-Consulting Services Thresholds
1. | Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement: [Thresholds for applicable procurement methods (not limited to the list below) will be determined by the Procurement Specialist /Procurement Accredited Staff based on the assessment of the implementing agency’s capacity.]
1a. | Procurement Category | Prior Review Threshold (USD) PWP III Credit No. 3859 | Comments
| Goods | > = 500,000 US$ | First contract
| Works | > 5,000,000 US$ | First contract
Non-Consultant Services
Include all categories authorized by the loan agreement
1b. | Procurement Method | Procurement Method Threshold (USD) PWP III Credit No. 3859 | Comments
| ICB and LIB (Goods) | > = 500,000US$
| NCB (Goods) | <500,000 US$
| Shopping (Goods) | < = 50,000U S$
| ICB (Works) | >5,000,000 US$
| NCB (Works) | < 5,000,000 US$
| NS (Works) | < = 50,000
ICB (Non-Consultant Services)
Include all methods authorized by the loan agreement
2. | Prequalification. Bidders for __NA___ shall be prequlified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines.
3. | Proposed Procedures for CDD Components (as per paragraph 3.17 of the Guidelines): Refer to the relevant CDD project implementation document approved by the Bank
4. | Reference to (if any) Project Operational/Procurement Manual: Manual Of Procedurs
5. | Any Other Special Procurement Arrangements: [NA]
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Procurement Category | Prior Review Threshold (USD) PWP III Credit No. 3859 | Comments
| Consulting Firms (Competitive) | >50,000 US$
| Consulting Firms (Sole Source) | All contacts
| Individual Consultants (Competitive) | > 50,000 US$
| Individual Consultants (Sole Source) | All contacts
Include all categories authorized by the loan agreement
1b. | Procurement Method | Procurement Method Threshold (USD) PWP III Credit No. 3859 | Comments
| QCSB (Firms) | >200,000
| LCS (Firms & Indivisual) | < 200,000
| QCS | <200,000
| IC | < 1000,000
| Other Methods | <200,000
Include all methods authorized by the loan agreement
Note: LCS will be used for Individuals as ateam leader for the contracts less than 10,000US$
2. | Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $_______equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
| Note: OPCPR list of ceilings can be found here: | http://go.worldbank.org/MKXO98RY40
3. | Any Other Special Selection Arrangements: [NA]
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet
IV. Implementing Agency Capacity Building Activities with Time Schedule: See attached "Capacity Building" sheet

## Goods and Works
Procurement Plan for Goods/Works/Non-Consulting Services
Yemen P122594: Labor Intensive Public Works Project (Public Works IV) IDA H663-0
** Applicable in case of Bank's prior review | [9 empty] | Prequalification
| SL No. | Package/ Reference No. | Description of Goods/ Works | Goods/ Works/ NCS | Estimated Cost and Date of Estimate | Currency of Estimated Cost | Review by Bank (Prior/ Post) | Method of Selection | Domestic Preference (yes/no) | Prequalification (yes/no) | No Objection from Bank for Draft Prequalification documents (Date)** | No Objection from Bank for Evaluation of Prequalification Application (Date)** | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | Contract Award Decision (Date) | Bank’s No Objection to Bid Evaulation Report and Contract Award (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Completion of Contract (Date) | Expenditure incurred to Date
Goods and Works for the Grant No. IDA H6630 PWPIV
Planned | 1 | GIDA-1/4 | Schools Furniture | Goods |  | US$ | Prior | NCB | No | No | NA | NA | 2011-10-01 | 2011-11-01 | 2011-11-15 | 2011-12-20 | 2011-12-20 | 2012-01-15 | NA | 2012-02-15
Revised
Actual
Planned | 2 | More than one shoping | Operational requirements | Goods |  | US$ | Post | NS | No | No | NA | NA | W H E N R E Q U I R E D
Revised
Actual
Planned | 3 | More than one tender | Operational Requirements | Goods |  | US$ | Post | NCB | No | No |  | NA | W H E N R E Q U I R E D
Revised
Actual | [9 empty] | No | NA | NA
Planned | 1 | IDA-1/4 | 27 SUB-PROJECTS OF DIFFERENT SECTORS | Works |  | US$ | Post | NCB | No | No | NA | NA | 2011-04-01 | NA | 2011-06-25 | 2011-07-30 | 2011-07-30 | 2011-09-10 | NA | 2011-09-30 | Many contracts | US$ | Many contract | Many contract | 2012-11-23
Revised | [12 empty] | 2012-08-01 | NA | 2012-09-15 | 2012-10-20 | 2012-10-20 | 2012-11-29 |  | 2012-12-19 |  |  |  |  | 2014-02-12
Actual | [13 empty] | 19.Sep.2012 | 2012-09-23 | 2012-11-05 | 2012-11-05 | 20.Nov.2012 | 28.Nov.2012 | 17.Dec.2012
Planned | 2 | IDA-2/4 | 87 SUB-PROJECTS OF DIFFERENT SECTORS | Works |  | US$ | Post | NCB | No | No | NA | NA | 2011-07-01 | NA | 2011-09-25 | 2011-10-30 | 2011-10-30 | 2011-12-15 | NA | 2012-01-15 | Many contracts | US$ | Many contract | Many contract
Revised | [12 empty] | 2012-09-01 |  | 2012-10-16 | 2012-11-20 | 2012-11-20 | 2012-12-30 | NA | 2013-01-19 |  |  |  |  | 2014-03-15
Actual | [14 empty] | 2012-11-10 | 2012-12-16 | 2012-12-16 | 07.Jan.2013 | NA | 26.Jan.2013
Planned | 3 | IDA-3/4 | 75 SUB-PROJECTS OF DIFFERENT SECTORS | Works |  | US$ | Post | NCB | No | No | NA | NA | 2011-09-01 | NA | 2011-12-25 | 2012-01-30 | 2012-01-30 | 2012-03-15 | NA | 2012-04-15 | Many contracts | US$ | Many contract | Many contract
Revised | [12 empty] | 2013-01-01 |  | 2013-02-15 | 2013-03-22 | 2013-03-22 | 2013-05-01 | NA | 2013-05-21 |  |  |  |  | 2014-06-25
Actual | [14 empty] | 06.Feb.13 | 10.Mar.13 | 10.Mar.13 |  | NA
Planned | 4 | IDA-4/4 | 45 SUB-PROJECTS OF DIFFERENT SECTORS | Works |  | US$ | Post | NCB | No | No | NA | NA | 2012-02-01 | NA | 2012-04-01 | 2012-05-05 | 2012-05-05 | 2012-06-20 | NA | 2012-07-20 | Many contracts | US$ | Many contract | Many contract
Revised | [12 empty] | 2013-03-15 |  | 2013-04-29 | 2013-06-03 | 2013-06-03 | 2013-07-13 | NA | 2013-08-02 |  |  |  |  | 2014-09-06
Actual | [14 empty] | 2013-02-27 |  |  |  | NA
Planned | 3 | IDA-5/4 | 45 SUB-PROJECTS OF DIFFERENT SECTORS | Works |  | US$ | Post | NCB | No | No | NA | NA | 2011-09-01 | NA | 2013-08-15 | 2013-09-19 | 2013-09-19 | 2013-10-29 | NA | 2013-11-18 | Many contracts | US$ | Many contract | Many contract
Revised | [12 empty] | 2013-07-01 |  | 2013-08-15 | 2013-09-19 | 2013-09-19 | 2013-10-29 | NA | 2013-11-18 |  |  |  |  | 2014-12-23
Actual | [18 empty] | NA
Planned | 4 | IDA-6/4 | 30 SUB-PROJECTS OF DIFFERENT SECTORS | Works |  | US$ | Post | NCB | No | No | NA | NA | 2012-02-01 | NA | 2013-11-15 | 2013-12-20 | 2013-12-20 | 2014-01-29 | NA | 2014-02-18 | Many contracts | US$ | Many contract | Many contract
Revised | [12 empty] | 2013-10-01 |  | 2013-11-15 | 2013-12-20 | 2013-12-20 | 2014-01-29 | NA | 2014-02-18 |  |  |  |  | 2015-03-25
Actual | [18 empty] | NA
Planned | 4 | IDA-7/4 | 30 SUB-PROJECTS OF DIFFERENT SECTORS | Works |  | US$ | Post | NCB | No | No | NA | NA | 2012-02-01 | NA | 2014-03-18 | 2014-04-22 | 2014-04-22 | 2014-06-01 | NA | 2014-06-21 | Many contracts | US$ | Many contract | Many contract
Revised | [12 empty] | 2014-02-01 |  | 2014-03-18 | 2014-04-22 | 2014-04-22 | 2014-06-01 | NA | 2014-06-21 |  |  |  |  | 2015-07-26
Actual | [18 empty] | NA
NOTES: 1) THE AVERAGE COST OF EACH SUB-PROJECT IS ARROUND 130,000 US$ SO THEY ARE SUBJECTED TO POST REVIEW. A VERY FEW SUB-PROJECTS CONTRACTS ARE SUBJECTED TO A PRIOR REVIEW, SO NOL IS REQUESTED ACCORDINGLY.
2) THE PACKAGES IN THE PLAN ARE NOT NECESSARY CONTAIN THE SAME NUMBERS OF SUB-PROJECTS ACTUALY IMPLEMENTED. THE ACTUAL BACKAGES NUMBERS AND THEIR CONTENTS CAN BE LISTED SEPARETLY.
3) Bank’s No Objection to Bidding Document have been done once, so it is not aplicable any more. In case NO is required (as a special case) it will be requested.
4) Contract Value, Contract No., Name, City, and Country of Contractor cannot appear here, it can listed with the sub-projects seperatly.
Formulas:
Completion of Contract (Date) = [Contract Signed (Date)]+420
Bid Invitation (Date) = [Preparation of Bid Document (Date)]+45
Bid Closing (Date) = [Bid Invitation (Date)]+35
Bid Opening (Date) = [Bid Closing (Date)]
Contract Award Decision (Date) = [Bid Opening (Date)]+40
Contract Signed (Date) = [Contract Award Decision (Date)]+20

## Consulting Services
Procurement Plan for Consultant Services
Yemen P122594: Labor Intensive Public Works Project (Public Works IV) IDA H663-0
| SL No. | Package/ Reference No. | Description of Services | Estimated Cost | Currency of Estimated Cost | Review by Bank (Prior/ Post) | Type of Consultant (Firm/ Individual) | Method of Selection | Advertising for Short listing (Date) | TOR/Shortlist to be Finalised (Date) | RFP Final Draft to be forwarded to the Bank (Date) | No Objection from Bank for TOR (Date)** | No Objection from Bank for Shortlist (Date)** | No Objection from Bank for Final RFP (Date)** | RFP Issued (Date) | Proposal Submission Deadline (Date) | No Objection by the Bank to the Technical Evaluation Report (Date)** | No Objection by the Bank (Technical/ #Combined/ Draft Contract/ Final Contract) (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Services Completion (Date) | Expenses Incurred to Date
Consultants for the Grant No.IDA H6630 PWPIV
Planned | 1 | CIDA-1/4 | SUPERVISION OF 27 SUB-PROJECTS OF DIFFERENT SECTORS |  | US$ | Prior | Firm | LCS |  | NA | NA | NA | NA | NA | 2011-07-25 | 2011-08-20 | NA | NA | 2011-09-30 | Many contracts | US$ | Many contracts | Many contracts
Revised | [14 empty] | 2012-10-15 | 2012-11-20 | . | . | 2012-12-19 |  |  |  |  | 2014-01-23
Actual | [7 empty] | LCS |  | NA | NA | NA | NA | NA | 2012-11-10 | 2012-11-24 | NA | NA | 25.Dec.2012
Planned | 2 | CIDA-2/4 | SUPERVISION OF 87 SUB-PROJECTS OF DIFFERENT SECTORS |  | US$ | Post | Firm | LCS |  | NA | NA | NA | NA | NA | 2011-10-25 | 2011-11-20 | NA | NA | 2012-01-15 | Many contracts | US$ | Many contracts | Many contracts
Revised | [14 empty] | 2012-11-25 | 2012-12-20 | . | . | 2013-01-19 |  |  |  |  | 2014-02-23
Actual | [9 empty] | NA | NA | NA | NA | NA | 2013-01-06 | 2013-01-20 | NA | NA | 16.Feb.2012
Planned | 3 | CIDA-3/4 | SUPERVISION OF 75 SUB-PROJECTS OF DIFFERENT SECTORS |  | US$ | Post | Firm | LCS |  | NA | NA | NA | NA | NA | 2012-01-25 | 2012-02-20 | NA | NA | 2012-04-15 | Many contracts | US$ | Many contracts | Many contracts
Revised | [14 empty] | 2013-03-26 | 2013-03-30 | . | . | 2013-05-21 |  |  |  |  | 2014-06-25
Actual | [9 empty] | NA | NA | NA | NA | NA | 2013-03-02 |  | NA | NA
Planned | 4 | CIDA-4/4 | SUPERVISION OF 45 SUB-PROJECTS OF DIFFERENT SECTORS |  | US$ | Post | Firm | LCS |  | NA | NA | NA | NA | NA | 2012-04-30 | 2012-05-30 | NA | NA | 2012-07-20 | Many contracts | US$ | Many contracts | Many contracts
Revised | [14 empty] | 2013-06-06 | 2013-07-01 | . | . | 2013-08-02 |  |  |  |  | 2014-09-06
Actual | [9 empty] | NA | NA | NA | NA | NA |  |  | NA | NA
Planned | 2 | CIDA-5/4 | SUPERVISION OF 45 SUB-PROJECTS OF DIFFERENT SECTORS |  | US$ | Post | Firm | LCS |  | NA | NA | NA | NA | NA | 2011-10-25 | 2011-11-20 | NA | NA | 2012-01-15 | Many contracts | US$ | Many contracts | Many contracts
Revised | [14 empty] | 2013-09-20 | 2013-10-15 | . | . | 2013-11-18 |  |  |  |  | 2014-12-23
Actual | [9 empty] | NA | NA | NA | NA | NA |  |  | NA | NA
Planned | 3 | CIDA-6/4 | SUPERVISION OF 30 SUB-PROJECTS OF DIFFERENT SECTORS |  | US$ | Post | Firm | LCS |  | NA | NA | NA | NA | NA | 2012-01-25 | 2012-02-20 | NA | NA | 2012-04-15 | Many contracts | US$ | Many contracts | Many contracts
Revised | [14 empty] | 2013-12-20 | 2014-01-15 | . | . | 2014-02-18 |  |  |  |  | 2015-03-25
Actual | [9 empty] | NA | NA | NA | NA | NA |  |  | NA | NA
Planned | 4 | CIDA-7/4 | SUPERVISION OF 30 SUB-PROJECTS OF DIFFERENT SECTORS |  | US$ | Post | Firm | LCS |  | NA | NA | NA | NA | NA | 2012-04-30 | 2012-05-30 | NA | NA | 2012-07-20 | Many contracts | US$ | Many contracts | Many contracts
Revised | [14 empty] | 2014-04-25 | 2014-05-20 | . | . | 2014-06-21 |  |  |  |  | 2015-07-26
Actual | [9 empty] | NA | NA | NA | NA | NA |  |  | NA | NA
Planned | 5 |  | Studies/Design (many contracts) |  | US$ | Post | Firm | LCS | As per required
Revised
Actual
Planned | 6 |  | Studies/Design(many contracts) |  | US$ | Post | Individual | IC | As per required
Revised
Actual
Planned | 7 |  | Specific Small Assignment |  | US$ | Post | Individual | IC | As per required
Revised
Actual
Planned | 8 | CIDA-7/4 | Procurement of Gender Coordinator |  | US$ | Post | Individual | IC |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2013-04-15 |  | US$ |  |  | 2014-04-14
Revised | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA
Actual | [9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA
Notes: LCS will be used for Individuals as ateam leader for the contracts less than 10,000US$
For Specific Small Assignments for contracts less than US$1000 IC will be hired using Rolling Roster approved by IDA
One LCS contract should be send for prior review
Formulas:
Services Completion (Date) = [Contract Signed (Date)]+400

## Capacity Building
Capacity Building Activities
SL No. | Expected Outcome/ Activity Description | Estimated Cost | Estimated Duration | Start Date | Completion Date | Comments