|  |
| --- |
| 74198 v2  **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 06/05/2013 |

|  |  |
| --- | --- |
| **1. Basic Information** | |
| Project ID & Name | P114609: LA-Catalytic Fund EFA/FTI |
| Country | Lao People's Democratic Republic |
| Task Team Leader | Omporn Regel |
| Sector Manager/Director | Luis Benveniste |
| Country Director | Annette Dixon |
| Original Board Approval Date | 07/20/2010 |
| Original Closing Date: | 08/31/2013 |
| Current Closing Date | 08/31/2013 |
| Proposed Closing Date [if applicable] | 08/31/2014 |
| EA Category | C-Not Required |
| Revised EA Category | C-Not Required-Not Required |
| EA Completion Date |  |
| Revised EA Completion Date |  |

|  |  |  |
| --- | --- | --- |
| **2. Revised Financing Plan (US$m)** | | |
| **Source** | **Original** | **Revised** |
| AUSL | 21.44 | 21.44 |
| BORR | 0.00 | 0.00 |
| EFAF | 30.00 | 30.00 |
| **Total** | 51.44 | 51.44 |

|  |  |  |
| --- | --- | --- |
| **3. Borrower** | | |
| **Organization** | **Department** | **Location** |
| Ministry of Finance |  | Lao People's Democratic Republic |

|  |  |  |
| --- | --- | --- |
| **4. Implementing Agency** | | |
| **Organization** | **Department** | **Location** |
| Ministry of Education and Sports | ESDF Coordination Unit | Lao People's Democratic Republic |

|  |  |  |
| --- | --- | --- |
| **5. Disbursement Estimates (US$m)** | | |
| **Actual amount disbursed as of 06/06/2013** **33.73** | | |
| **Fiscal Year** | **Annual** | **Cumulative** |
| 2012 | 9.80 | 43.53 |
| 2013 | 2.70 | 46.23 |
|  | **Total** | **46.23** |

|  |  |
| --- | --- |
| **6. Policy Exceptions and Safeguard Policies** | |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes**  **Original/Current Project Development Objectives/Outcomes** |
| The Program Development Objective is to support the Government of Lao People's Democratic Republic to increase the coverage and improve the quality of Pre-Primary and Primary education with a focus on the most educationally disadvantaged children. |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|  |