## Mahendra Ilam Goods
Procurement Plan (PP) for Goods -2012/2013(Revised and updated), Mar 22, 2013
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Mahendra Ratna Maltiple Campus , Ilam (Autonomus)
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Purchase of 4 sets of Desktop Computer (SHEP/TU/MRC/G/Shop-1) | Post | p | 0.2 | Shopping | WB | NA | NA | 2012-09-22 | 2012-10-07 | NA | NA | 2012-10-25 | 2012-11-12 | District | In Progress
R
A
2 | Purchase of 6 sets Projector for departments (SHEP/TU/MRC/G/Shop-2) | Post | p | 0.3 | Shopping | WB | NA | NA | 2012-09-22 | 2012-09-30 | NA | NA | 2012-10-25 | 2012-11-12 | District | In Progress
R
A
3 | Purchase of Laboratory Equipments : Microscope-5 Sets, Binacular-3 Sets & Others (SHEP/TU/MRC/G/SQ-3) | Post | p | 0.8 | SQ | GON | NA | NA | 2012-10-09 | 2012-10-24 | NA | NA | 2012-11-18 | 2013-04-08 | District | In Process
R
A
4 | Purchase of Furnitures for Conference Hall, Guest Room & Research Center (SHEP/TU/MRC/G/SQ-4) | Post | p | 1 | NCB | GON | NA | NA | 2012-11-20 | 2012-12-19 | NA | NA | 2013-01-11 | 2013-04-10 | District | In Progress
R
A
5 | Purchase of Books (SHEP/TU/MRC/G/NCB-5) | Post | p | 1.5 | NCB | GON | NA | NA | 2013-01-27 | 2013-02-26 | NA | NA | 2013-03-10 | 2013-04-22 | District | In Process
R
A
6 | Procurement of vehicle : 5 seaters Peak up van-1Nos,Slice-1, 30-35 seaters Bus-1 Nos.Slice -2, (SHEP/TU/G/NCB-6) | Prior | p | 5.5 | NCB | GON | 2013-01-05 | 2013-01-15 | 2013-01-27 | 2013-02-26 | 2013-03-05 | 2013-03-10 | 2013-03-15 | 2013-04-22 | District | Slice-1=2.0, Slice-2=3.50
R
A
| Total |  |  | 9.3

## Ilam Consulting Service
Procurement Plan (PP) for Consulting Service -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [10 empty] | Executing Agency : UGC TU-SHEP
Loan / Credit/Grant No: H274-NEP | [10 empty] | Implementing Agency : Mahendra Ratna Maltiple Campus , Ilam (Autonomus)
S. No. | Description of Services & Contract ID No. | Prior/ Post Review | PP Status | Cost Estimate (NRs Million) | Method of Selection | Pro. Procedure: GoN or WB? | Advertising for EOI | Cost Estimate, Short list & RFP to WB | WB’s NOL to SL & RFP | RFP Issued | Proposals Submission | TP Eval. Report to WB | WB’s NOL to TP EVal. Report | Public Opening of FP | FER & Award Recomm. to WB for info. | Negotiated Contract to WB | WB’s NOL to Nego. Contract | Contract Signing | Completion date of the contract | Procurement at Center/ District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Preparation of Horticulture/Floriculture Curriculum (SHEP/TU/MRC/S/SSS-1) | Post | p | 1 | SSS | WB | 2011-09-02 | 2011-09-12 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2011-12-15 | 2011-12-30 | 2012-01-15 | 2012-01-25 | 2012-02-05 | 2012-02-15 | 2012-02-25 | 2012-12-02 | District | Completed
R
A
2 | Need based Tranning to the staff & Teachers for capacity building by hiring short term consultants (SHEP/TU/MRC/S/CQS-2) | Post | p | 4 | CQS | WB | 2013-03-25 | 2013-04-10 | 2013-04-15 | 2013-04-20 | 2013-05-19 | 2013-05-25 | 2013-06-01 | 2013-06-05 | 2013-06-12 | 2013-06-20 | 2013-06-25 | 2013-07-01 | 2013-10-15 | District | In Process
R
A
| Total |  |  | 5

## Mahendra Ilam Works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Mahendra Ratna Maltiple Campus , Ilam (Autonomus)
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Construction of Library Building (SHEP/TU/MRC/W/NCB-1) | Post | p | 7.2 | NCB | GON | NA | NA | 2011-03-10 | 2011-04-10 | NA | NA | 2011-05-05 | 2012-05-06 | District | Completed
R
A
2 | Construction of Boundry Wall (SHEP/TU/MRC/W/SQ-2) | Post | p | 0.38 | SQ | GON | NA | NA | 2011-05-16 | 2011-05-31 | NA | NA | 2011-06-07 | 2012-07-16 | District | Completed
R
A
3 | Construction of 4 Roomed Laboratory Building (SHEP/TU/MRC/W/NCB-3 | Post | p | 10.5 | NCB | GON | NA | NA | 2012-10-24 | 2012-11-24 | NA | NA | 2012-12-21 | 2013-10-10 | District | In Progress
R
A
| Total |  |  | 18.08

## Nepal Gung Goods
Procurement Plan (PP) for Goods -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Mahendra Multiple Campus, Nepalgunj-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Class Room Furnitures : 150 Sets( 4 Seater Each) (SHEP/TU/MMC/G/NCB-1) | post | p | 1.5 | NCB | GON | NA | NA | 2012-11-17 | 2012-12-16 | NA | NA | 2012-12-25 | 2013-06-20 | District | In Progress
R
A
2 | Scientific Equipments (Microscope-2 Sets, Binaculars-1 Set) & Others (SHEP/TU/MMC/G/SQ-2) | post | p | 0.5 | SQ | GON | NA | NA | 2012-11-20 | 2012-12-05 | NA | NA | 2012-12-15 | 2013-07-14 | District | In Progress
R
A
3 | Purchase of Desktop Computer-5 Sets & Leser Printer-2 Sets (SHEP/TU/MMC/G/SQ-3) | post | p | 0.6 | SQ | GON | NA | NA | 2012-12-21 | 2013-01-06 | NA | NA | 2013-01-15 | 2013-04-15 | District | In Progress
R
A
| Total |  |  | 2.6

## Nepal Gung Works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Mahendra Multiple Campus, Nepalgunj-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Construction of 1st Floor of Regional Library Building (SHEP/TU/MMC/W/NCB-1) | post | p | 9.1 | NCB | GON | NA | NA | 2012-06-12 | 2012-07-12 | NA | NA | 2012-08-14 | 2013-03-15 | District | In Progress
R
A
2 | Maintenance of Science Building (door,window & painting) (SHEP/TU/MMC/W/NCB-2) | post | p | 0.87 | NCB | GON | NA | NA | 2012-06-28 | 2012-07-15 | NA | NA | 2012-07-25 | 2012-12-11 | District | In Progress
R
A
3 | Construction of Boundry Wall (SHEP/TU/MMC/W/NCB-3) | post | p | 6.26 | NCB | GON | NA | NA | 2012-11-09 | 2012-12-10 | NA | NA | 2013-01-15 | 2013-07-15 | District | In Progress
R
A
4 | Construction of Canteen (SHEP/TU/MMC/W/NCB-4) | post | p | 0.81 | NCB | GON | NA | NA | 2012-11-20 | 2012-12-06 | NA | NA | 2012-12-20 | 2013-06-20 | District | In Progress
R
A
5 | Maintenance of Chemistry Lab. (SHEP/TU/MMC/W/SQ-5) | post | p | 0.21 | SQ | GON | NA | NA | 2012-12-21 | 2013-01-06 | NA | NA | 2013-01-15 | 2013-07-14 | District | In Progress
R
A
6 | Construction & Maintenance of students' Toilets (SHEP/TU/MMC/W/SQ-6) | post | p | 0.61 | SQ | GON | NA | NA | 2012-12-21 | 2013-01-06 | NA | NA | 2013-01-15 | 2013-07-14 | District | In Progress
R
A
7 | Construction of 200 Mtrs Internal road with black top (SHEP/TU/MMC/W/Shop-7) | post | p | 0.45 | Shopping |  | NA | NA | 2012-12-20 | 2013-01-05 | NA | NA | 2013-01-15 | 2013-04-15 | District | In Progress
R
A
8 | Sutter Block Construction (SHEP/TU/MMC/W/NCB-8) | post | p | 4.6 | NCB | GON | NA | NA | 2013-01-15 | 2013-02-14 | NA | NA | 2013-02-25 | 2013-10-15 | District | In Progress
R
A
9 | Road Construction ( Black Topped) Pee Work (SHEP/TU/MMC/W/NCB-9) | post | p | 3.7 | NCB | GON | NA | NA | 2013-01-15 | 2013-02-14 | NA | NA | 2013-02-25 | 2013-10-15 | District | In Progress
R
A
| Total |  |  | 26.61

## Mechi Goods
Procurement Plan (PP) for Goods -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Mechi Multiple Campus, Jhapa -Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Purchase of Computers-40 Sets (SHEP/TU/MC/G/NCB-1) | post | p | 2.1 | NCB | GON | NA | NA | 2013-01-28 | 2013-02-28 | NA | NA | 2013-03-05 | 2013-06-13 | District | In Progress
R
A
2 | Purchase of Computer table Sets -40 (SHEP/TU/MC/G/SQ-2) | post | p | 0.65 | SQ | GON | NA | NA | 2013-01-28 | 2013-02-13 | NA | NA | 2013-02-25 | 2013-06-15 | District | In Progress
R
A
3 | Purchase of Educational Equipments (Projector-3 Sets, White Board-20 Sets) & Others (SHEP/TU/MC/G/SQ-3) | post | p | 0.6 | SQ | GON | NA | NA | 2012-09-24 | 2012-10-09 | NA | NA | 2012-10-15 | 2012-11-12 | District | In Progress
R
A
4 | Purchase of Soil Test Equipments (Lab.Tester ) (SHEP/TU/MC/G/NCB-4) | post | p | 2.3 | NCB | GON | NA | NA | 2012-09-23 | 2012-10-14 | NA | NA | 2012-10-31 | 2013-01-02 | District | In Progress
R
A
5 | Furniture : 24 sets for Class Rooms (SHEP/TU/MC/G/SQ-5) | post | p | 0.4 | SQ | GON | NA | NA | 2012-09-25 | 2012-10-11 | NA | NA | 2012-10-31 | 2013-01-02 | District | In Progress
R
A
6 | Purchase of Books for Library (SHEP/TU/MC/G/SQ-6) | post | p | 0.1 | SQ | GON | NA | NA | 2012-09-25 | 2012-10-11 | NA | NA | 2012-10-31 | 2012-12-20 | District | In Progress
R
A
7 | Science Equipments : - (Microscope-3 Sets, Digital Balance-3Sets) (SHEP/TU/MC/G/SQ-7) | post | p | 0.7 | SQ | GON | NA | NA | 2012-11-07 | 2012-11-22 | NA | NA | 2012-11-30 | 2013-01-27 | District | In Progress
R
A
| Total |  |  | 6.85

## Mechi Works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Mechi Multiple Campus, Jhapa-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Painting of buildings (Arts, Science, Library, Hostel, Teachers' Quarter) (SHEP/TU/MC/W/SQ-1) | post | P | 1.6 | SQ | GON | NA | NA | 2012-12-20 | 2013-01-04 | NA | NA | 2013-01-27 | 2013-05-29 | District | In Progress
R
A
2 | Maintenance of doors/windows of humanities building & hostel (SHEP/TU/MC/W/SQ-2) | post | p | 0.795 | SQ | GON | NA | NA | 2012-11-04 | 2012-11-21 | NA | NA | 2012-11-25 | 2013-01-28 | District | In Progress
R
A
3 | Repair & maintenance of Play Ground (Basket ball, Volley ball) (SHEP/TU/MC/W/SQ-3) | post | p | 0.8 | SQ | GON | NA | NA | 2013-02-19 | 2013-03-06 | NA | NA | 2013-03-28 | 2013-05-29 | District | In Process
R
A
4 | Maintenance of Laboratory & Gravelling of Road (500 mtr) (SHEP/TU/MC/W/SQ-4) | post | p | 0.7 | SQ | GON | NA | NA | 2012-09-24 | 2012-10-09 | NA | NA | 2012-10-14 | 2013-03-14 | District | In Progress
R
A
5 | Construction of Tea Lab. & Studend Toilet (SHEP/TU/MC/W/SQ-5) | post | p | 0.95 | SQ | GON | NA | NA | 2012-12-14 | 2012-12-31 | NA | NA | 2013-01-21 | 2013-03-23 | District | In Progress
R
A
6 | Maintenance of Furnitures for Lab & class rooms (SHEP/TU/MC/W/NCB-6) | post | p | 1.6 | NCB | GON | NA | NA | 2013-02-19 | 2013-03-22 | NA | NA | 2013-03-28 | 2013-05-29 | District | In Process
R
A
7 | Preparation of Land for Tea plantation using Dozor & Scabetor (SHEP/TU/MC/W/SQ-1) | post | p | 1.5 | SQ | GON | NA | NA | 2013-02-15 | 2013-03-01 | NA | NA | 2013-03-10 | 2013-07-14 | District | In Process
R
A
| Total |  |  | 7.945
Formulas:
Public Opening of Bids = [Bid Invitation]+15
Contract Signing = [Public Opening of Bids]+21

## Mechi Consulting Service
Procurement Plan (PP) for consulting services -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [10 empty] | Executing Agency : UGC TU-SHEP
Loan / Credit/Grant No: H274-NEP | [10 empty] | Implementing Agency : Mechi Multiple Campus, Jhapa-Decentralised
S. No. | Description of Services & Contract ID No. | Prior/ Post Review | PP Status | Cost Estimate (NRs Million) | Method of Selection | Pro. Procedure: GoN or WB? | Advertising for EOI | Cost Estimate, Short list & RFP to WB | WB’s NOL to SL & RFP | RFP Issued | Proposals Submission | TP Eval. Report to WB | WB’s NOL to TP EVal. Report | Public Opening of FP | FER & Award Recomm. to WB for info. | Negotiated Contract to WB | WB’s NOL to Nego. Contract | Contract Signing | Completion date of the contract | Procurement at Center/ District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
2 | Hiring Consultant for Computer Trainning to Staff (SHEP/TU/MC/S/CQ-1) | Post | p | 1.37 | CQS | WB | NA | 2013-03-15 | 2013-03-25 | 2013-03-30 | 2013-04-29 | 2013-05-14 | 2013-05-24 | NA | NA | 2013-06-08 | 2013-06-16 | 2013-06-21 | 2013-08-15 | District | In Process
R
A
| Total |  |  | 1.37
Formulas:
WB’s NOL to SL & RFP = [Cost Estimate, Short list & RFP to WB]+10
RFP Issued = [WB’s NOL to SL & RFP]+5
Proposals Submission = [RFP Issued]+30
TP Eval. Report to WB = [Proposals Submission]+15
WB’s NOL to TP EVal. Report = [TP Eval. Report to WB]+10
Negotiated Contract to WB = [WB’s NOL to TP EVal. Report]+15
WB’s NOL to Nego. Contract = [Negotiated Contract to WB]+8
Contract Signing = [WB’s NOL to Nego. Contract]+5
Completion date of the contract = [Contract Signing]+55

## Siddhnath Goods
Procurement Plan (PP) for Goods -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Siddhanath Science Campus, Mahendranagar -Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Purchase of Automatic generator-1 (25KVA) (SHEP/TU/SSC/G/SQ-1) | Post | P | 1 | SQ | GON | NA | NA | 2012-09-15 | 2012-10-01 | NA | NA | 2012-10-13 | 2013-01-15 | District | In Progress
R
A
2 | Purchase of Library Books (SHEP/TU/SSC/G/SQ-2) | Post | P | 0.5 | SQ | GON | NA | NA | 2012-11-20 | 2012-12-05 | NA | NA | 2012-12-15 | 2013-02-05 | District | In Progress
R
A
3 | Purchase of Office Furniture & Fixtures (SHEP/TU/SSC/G/SQ-3) | Post | P | 0.2 | SQ | GON | NA | NA | 2012-08-09 | 2012-08-26 | NA | NA | 2012-09-04 | 2013-01-04 | District | In Progress
R
A
4 | Purchase of Furnitures for Library & Class Rooms (SHEP/TU/SSC/G/SQ-4) | Post | P | 0.2 | SQ | GON | NA | NA | 2012-08-09 | 2012-08-26 | NA | NA | 2012-09-04 | 2013-01-04 | District | In Progress
R
A
5 | Purchase of 5 sets Computers (SHEP/TU/SSC/G/SQ-5) | Post | P | 0.3 | SQ | GON | NA | NA | 2012-11-20 | 2012-12-05 | NA | NA | 2012-12-15 | 2013-07-14 | District | In Progress
R
A
6 | Purchase of Sport materials (volley ball, basket ball, table tenis, net) (SHEP/TU/SSC/G/Shop-6) | Post | P | 0.15 | Shopping | WB | NA | NA | 2013-02-07 | 2013-02-14 | NA | NA | 2013-02-24 | 2013-03-24 | District | In Process
R
A
7 | Purchase of Euro Guard With Watercooling Machine-3 (SHEP/TU/SSC/G/Shop-7) | Post | P | 0.3 | Shopping | WB | NA | NA | 2013-02-07 | 2013-07-22 | NA | NA | 2013-03-02 | 2013-06-03 | District | In Process
R
A
8 | Purchase of Computer Software for CSIT program (SHEP/TU/SSC/G/SQ-8) | Post | P | 0.3 | SQ | WB | NA | NA | 2013-02-07 | 2013-02-22 | NA | NA | 2013-03-02 | 2013-06-03 | District | In Process
R
A
| Total |  |  | 2.95

## Siddhanath Works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Siddhanath Science Campus, Mahendranagar-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Construction of Second Floor of M.sc.,physics Lab. Building (SHEP/TU/SSC/W/NCB-1) | Post | P | 3 | NCB | GON | NA | NA | 2012-11-15 | 2012-12-14 | NA | NA | 2012-12-31 | 2013-07-13 | District | In Progress
R
A
2 | Maintenance of Office & Classroom Furnitures (SHEP/TU/SSC/W/Shop-2) | Post | P | 0.15 | Shopping | WB | NA | NA | 2012-08-09 | 2012-08-16 | NA | NA | 2012-08-25 | 2012-10-14 | District | In Progress
R
A
3 | Office Room Partition (SHEP/TU/SSC/W/SQ-3) | Post | P | 0.2 | SQ | WB | NA | NA | 2013-02-15 | 2013-03-01 | NA | NA | 2013-03-10 | 2013-05-15 | District | In Process
R
A
4 | Maintenance of Botanical Garden, Park (SHEP/TU/SSC/W/Shop-4) | Post | P | 0.2 | Shopping | WB | NA | NA | 2013-02-15 | 2013-03-01 | NA | NA | 2013-03-10 | 2013-05-10 | District | In Process
R
A
5 | Construction of Cycle and Motorcycle Stand (SHEP/TU/SSC/W/Shop-5) | Post | P | 0.3 | Shopping | WB | NA | NA | 2012-08-09 | 2012-08-24 | NA | NA | 2012-09-05 | 2012-12-30 | District | In Progress
R
A
6 | Maintenance of Play Ground of Criket, Badminton, Table Tenis (SHEP/TU/SSC/W/DP-6) | Post | P | 0.1 | DP | GON | NA | NA | 2013-02-15 | 2013-03-01 | NA | NA | 2013-03-10 | 2013-05-10 | District | In Process
R
A
7 | Construction of 500m Track roads (SHEP/TU/SSC/W/SQ-7) | Post | P | 0.5 | SQ | WB | NA | NA | 2012-10-31 | 2012-11-15 | NA | NA | 2012-11-23 | 2013-02-23 | District | In Progress
R
A
8 | Maintenance of 20000Ltrs over head Steel water Tank (SHEP/TU/SSC/W/SQ-8) | Post | P | 1.5 | SQ | GON | NA | NA | 2012-11-13 | 2012-11-28 | NA | NA | 2012-12-25 | 2013-03-11 | District | In Progress
R
A
9 | Maintenance & panting of Boys hostel, Staff Quarter (37 roomed) (SHEP/TU/SSC/W/SQ-9) | Post | P | 1.5 | SQ | GON | NA | NA | 2012-11-11 | 2012-11-26 | NA | NA | 2012-12-20 | 2013-02-27 | District | In Progress
R
A
| Total |  |  | 7.45
Formulas:
Public Opening of Bids = [Bid Invitation]+15

## siddha nath Consulting service
Procurement Plan (PP) for Consulting Service -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [10 empty] | Executing Agency : UGC TU-SHEP
Loan / Credit/Grant No: H274-NEP | [10 empty] | Implementing Agency : Siddhanath Science Campus, Mahendranagar-Decentralised
S. No. | Description of Services & Contract ID No. | Prior/ Post Review | PP Status | Cost Estimate (NRs Million) | Method of Selection | Pro. Procedure: GoN or WB? | Advertising for EOI | Cost Estimate, Short list & RFP to WB | WB’s NOL to SL & RFP | RFP Issued | Proposals Submission | TP Eval. Report to WB | WB’s NOL to TP EVal. Report | Public Opening of FP | FER & Award Recomm. to WB for info. | Negotiated Contract to WB | WB’s NOL to Nego. Contract | Contract Signing | Completion date of the contract | Procurement at Center/ District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Hiring Consulting Services for Computer Maintenance & Software Upgrading (SHEP/TU/SSC/S/SSS-1) | Post | P | 0.15 | SSS | WB | NA | NA | NA | 2013-01-15 | 2013-02-14 | NA | NA | NA | NA | NA | NA | 2013-04-17 | 2013-10-16 | District | In Process
R
A
| Total |  |  | 0.15

## Dhankuta goods
Procurement Plan (PP) for Goods -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Dhankuta Multiple Campus, Dhankuta-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Procurement of Text Books & Reference Books (SHEP/TU/DMC/G/SQ-1) | post | p | 0.7 | SQ | GON | NA | NA | 2012-05-20 | 2012-06-05 | NA | NA | 2012-06-19 | 2012-07-18 | District | In Progress
R
A
2 | Procurement of Computer-2Sets, Laptop-2Sets, Printer-1Set, Projector-2Sets for Language Lab. (SHEP/TU/DMC/G/SQ-2) | post | p | 0.43 | SQ | GON | NA | NA | 2012-09-08 | 2012-09-23 | NA | NA | 2012-10-06 | 2013-01-05 | District | In Progress
R
A
| Total |  |  | 1.13

## dhankuta consulting servies
Procurement Plan (PP) for Consulting Service -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [10 empty] | Executing Agency : UGC TU-SHEP
Loan / Credit/Grant No: H274-NEP | [10 empty] | Implementing Agency : Dhankuta Multiple Campus, Dhankuta-Decentralised
S. No. | Description of Services & Contract ID No. | Prior/ Post Review | PP Status | Cost Estimate (NRs Million) | Method of Selection | Pro. Procedure: GoN or WB? | Advertising for EOI | Cost Estimate, Short list & RFP to WB | WB’s NOL to SL & RFP | RFP Issued | Proposals Submission | TP Eval. Report to WB | WB’s NOL to TP EVal. Report | Public Opening of FP | FER & Award Recomm. to WB for info. | Negotiated Contract to WB | WB’s NOL to Nego. Contract | Contract Signing | Completion date of the contract | Procurement at Center/ District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Hiring Consultant for Tranning to the Staff of Research Centre (SHEP/TU/DMC/S/SSS-1) | Post | p | 0.76 | SSS | WB | NA | 2012-07-15 | 2012-07-30 | 2012-08-01 | 2012-08-30 | NA | 2012-09-05 | NA | NA | 2012-09-10 | 2012-09-15 | 2012-09-25 | 2012-12-15 | District | In Progress
R
A
2 | Hiring Consultant for Improvement of Student Extra Curricular Activities (SHEP/TU/DMC/S/SSS-2) | Post | p | 0.51 | SSS | WB | NA | 2012-07-15 | 2012-07-30 | 2012-08-01 | 2012-08-30 | NA | 2012-09-05 | NA | NA | 2012-09-10 | 2012-09-15 | 2012-09-25 | 2012-12-21 | District | In Progress
R
A
| Total |  |  | 1.27

## Dhankuta Works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Dhankuta Multiple Campus, Dhankuta-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Reparing of roof & Ceiling of Admin. Building & 4 Class Room (SHEP/TU/DMC/W/SQ-1) | Post | p | 0.6 | SQ | GON | NA | NA | 2012-05-08 | 2012-05-23 | NA | NA | 2012-06-05 | 2012-09-05 | District | In Progress
R
A
2 | Reparing of Drinking Water Tank & 1000m Pipe Line (SHEP/TU/DMC/W/SQ-2) | Post | p | 0.5 | SQ | GON | NA | NA | 2012-05-11 | 2012-05-26 | NA | NA | 2012-06-08 | 2012-09-08 | District | In Progress
R
A
3 | Reparing & Maintenance of 15 Toilets (SHEP/TU/DMC/W/SQ-3) | Post | p | 0.5 | SQ | GON | NA | NA | 2012-04-29 | 2012-05-14 | NA | NA | 2012-05-27 | 2012-08-27 | District | In Progress
R
A
4 | Plantation in road side of Campus Compound (SHEP/TU/DMC/W/Shop-4) | Post | p | 0.29 | Shopping | WB | NA | NA | 2012-05-27 | 2012-06-12 | NA | NA | 2012-06-25 | 2012-07-24 | District | In Progress
R
A
5 | Class Room Building Construction for Degree Class (Phy.,Chem.,Botany) (SHEP/TU/DMC/W/NCB-5) | Post | p | 8.5 | NCB | GON | NA | NA | 2012-06-30 | 2012-07-29 | NA | NA | 2012-08-30 | 2013-08-30 | District | In Progress
R
A
6 | Renovation of Science Lab. (SHEP/TU/DMC/W/SQ-6) | Post | p | 0.5 | SQ | GON | NA | NA | 2012-06-20 | 2012-07-05 | NA | NA | 2012-07-19 | 2012-10-31 | District | In Progress
R
A
7 | Construction of Campus Compound wall/Fancing (SHEP/TU/DMC/W/SQ-7) | Post | p | 0.5 | SQ | GON | NA | NA | 2012-07-19 | 2012-08-04 | NA | NA | 2012-08-17 | 2013-02-17 | District | In Progress
R
A
8 | Electricity Line Reparing of Teaching & Admn. Building (SHEP/TU/DMC/W/SQ-8) | Post | p | 0.5 | SQ | GON | NA | NA | 2012-09-04 | 2012-09-19 | NA | NA | 2012-10-01 | 2013-03-01 | District | In Progress
R
A
9 | Extention of Building for BBS Program (SHEP/TU/DMC/W/SQ-9) | Post | p | 0.8 | SQ | GON | NA | NA | 2012-09-04 | 2012-09-19 | NA | NA | 2012-10-01 | 2012-07-16 | District | In Progress
R
A
10 | Repair & maintenance of 8 Units Teachers' Quarter (door ,window , Leakage ) (SHEP/TU/DMC/W/SQ-10) | Post | p | 0.5 | SQ | GON | NA | NA | 2012-08-18 | 2012-09-02 | NA | NA | 2012-09-15 | 2012-12-15 | District | In Progress
R
A
| Total |  |  | 13.19

## Bhairahawa works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC / TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Bhairahawa Campus , Bhairahawa-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Construction of Library Building (SHEP/TU/BMC/W/NCB-1) | Post | P | 15.22 | NCB | GON | NA | NA | 2010-11-01 | 2010-12-01 | NA | NA | 2010-12-10 | 2012-06-10 | District | completed
R
A
2 | Construction of Administrative Building (SHEP/TU/BMC/W/NCB-2) | Post | P | 12.5 | NCB | GON | NA | NA | 2013-01-18 | 2013-02-19 | NA | NA | 2013-03-04 | 2013-09-30 | District | In Progress
R
A
| Total |  |  | 27.72

## Padmakanya Goods
Procurement Plan (PP) for Goods -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Padmakanya Campus, Bagabazar-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Procurement of Furnitures (SHEP/TU/PMC/G/NCB-1) | Post | P | 1.31 | NCB | GON | NA | NA | 2012-10-31 | 2012-11-30 | NA | NA | 2012-12-12 | 2013-07-29 | District | Equipping two Meeting Rooms with new Furnitures (In progress)
R
A
2 | Purchase of Books (SHEP/TU/PMC/G/NCB-2) | Post | P | 2 | NCB | GON | NA | NA | 2013-04-19 | 2013-05-19 | NA | NA | 2013-05-24 | 2013-06-25 | District | In Process
R
A
3 | Purchase of Computer-50 sets,Printer-15 sets (SHEP/TU/PMC/G/NCB-3) | Post | P | 3 | NCB | GON | NA | NA | 2013-04-06 | 2013-05-05 | NA | NA | 2013-05-28 | 2013-07-30 | District | In Process
R
A
4 | Purchase of Furniture & Furnishing of Computer Room (SHEP/TU/PMC/G/NCB-4) | Post | P | 1.3 | NCB | GON | NA | NA | 2013-04-13 | 2013-05-12 | NA | NA | 2013-05-25 | 2013-08-15 | District | In Process
R
A
| Total |  |  | 7.61
Formulas:
Public Opening of Bids = [Bid Invitation]+30

## Padmakanya Works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Padmakanya Campus, Bagabazar-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Construction of Library Building (SHEP/TU/PMC/W/NCB-1) | Post | P | 15.57 | NCB | GON | 2012-05-24 | 2012-05-30 | 2012-06-07 | 2012-07-06 | 2012-07-16 | 2012-07-22 | 2012-07-29 | 2013-07-29 | District | In Progress
R
A
2 | Maintenance of Building , Roof & wall Painting of Building (SHEP/TU/PMC/W/NCB-2) | Post | P | 2.8 | NCB | GON | NA | NA | 2013-02-17 | 2013-03-18 | NA | NA | 2013-04-11 | 2013-10-15 | District | In process
R
A
| Total |  |  | 18.37

## Trichandra Goods
Procurement Plan (PP) for Goods -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Trichandra Multiple Campus , Ghantaghar-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Purchase of Laptop-30 Sets, Printer-30 Sets for 26 Department ,Exam ,Account, Adm. Sec., Multimedia Projector set-15 for 15 Departments (SHEP/TU/TMC/G/NCB-1) | Post | P | 2.7 | NCB | GON | NA | NA | 2012-10-24 | 2012-11-23 | NA | NA | 2012-12-20 | 2013-03-20 | District | In Progress
R
A
2 | Purchase of Microscope-10 Sets (SHEP/TU/TMC/G/NCB-2) | Post | P | 2 | NCB | GON | NA | NA | 2012-10-24 | 2012-11-23 | NA | NA | 2012-12-20 | 2013-03-20 | District | In Progress
R
A
3 | Procurement of Furniture : Filling Cabinet-5,File Rack-1, Daraj-5,Office Chairs-30, Round Table-1 and Others (SHEP/TU/TMC/G/NCB-3) | Post | P | 2.6 | NCB | GON | NA | NA | 2012-10-24 | 2012-11-23 | NA | NA | 2012-12-03 | 2013-03-03 | District | In Progress
R
A
| Total |  |  | 7.3
Formulas:
Public Opening of Bids = [Bid Invitation]+30

## Trichandra Works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Trichandra Multiple Campus , Ghantaghar-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Construction of Building (2 Storey 1000sq.ft each) (SHEP/TU/TMC/W/NCB-1) | Prior | P | 20 | NCB | GON | 2013-03-25 | 2013-04-05 | 2013-04-10 | 2013-05-09 | 2013-05-15 | 2013-05-20 | 2013-05-25 | 2014-01-25 | District | Bank fund will be used for the functionally completed parts of the building by the closing date of project
R
A
2 | Building Repair (Plaster & Painting ), Toilet Construction (SHEP/TU/TMC/W/NCB-2) | Post | P | 3.1 | SQ | GON | NA | NA | 2012-10-24 | 2012-11-23 | NA | NA | 2012-12-03 | 20/10/2013 | District | In Progress
R
A
| Total |  |  | 23.1

## Palpa Goods
Procurement Plan (PP) for Goods -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Tribhuvan Campus Plapa-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Purchase of Furniture for Class rooms (SHEP/TU/TMC/G/NCB-1) | Post | P | 2.1 | NCB | GON | NA | NA | 2012-12-24 | 2013-01-25 | NA | NA | 2013-01-28 | 2013-03-25 | District | In Progress
R
A
2 | Purchase of Computer-6 Sets,UPS-6 Sets,Printer-2 Sets,Photocopy Machine-2 Sets,Generator-1 Set (SHEP/TU/TMC/G/SQ-2) | Post | P | 0.7 | SQ | GON | NA | NA | 2012-11-30 | 2012-12-15 | NA | NA | 2012-12-30 | 2013-02-25 | District | In Progress
R
A
3 | Purchase of Books (SHEP/TU/TMC/G/Shop-3) | Post | P | 0.3 | Shopping | WB | NA | NA | 2012-11-30 | 2012-12-16 | NA | NA | 2012-12-31 | 2013-02-25 | District | In Progress
R
A
| Total |  |  | 3.1

## Palpa Works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Tribhuvan Campus Plapa-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Construction of Auditorium Hall (SHEP/TU/TMC/W/NCB-1) | Post | P | 15.9 | NCB | GON | NA | NA | 2013-01-15 | 2013-02-16 | NA | NA | 2013-03-27 | 2013-10-15 | District | In progress | Lowest Bid received Rs 14.26
R
A
2 | Maintenance of Building (Lab.,class rooms, Administration) (SHEP/TU/TMC/W/NCB-2) | Post | P | 2 | NCB | GON | NA | NA | 2012-12-05 | 2013-01-04 | NA | NA | 2013-01-10 | 2013-06-15 | District | In progress
R
A
| Total |  |  | 17.9

## Central Tech Goods
Procurement Plan (PP) for Goods -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Central Technology Campus, Dharan (Autonomus)
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Purchase of Two vehicles ; Jeep 1 ,Slice-1,Bus 1, Slice-2 (SHEP/TU/KPC/G/NCB-1) | Prior | p | 10 | NCB | GON | 2013-03-25 | 2013-04-01 | 2013-04-05 | 2013-05-04 | 2013-05-10 | 2013-05-15 | 2013-05-25 | 2013-08-25 | District | Slice-1=3.5, slice-2=6.5
R
A
2 | Purchase of Computer- 50 Sets , Multimedia Projector -10 Sets for 10 Division (SHEP/TU/KPC/G/NCB-2) | Post | p | 3.2 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-02-15 | 2013-04-15 | District | In Progress
R
A
3 | Purchase of Lab Equipments (Pestro meter -2 & Others ) (SHEP/TU/KPC/G/NCB-3) | Post | p | 5 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-02-15 | 2013-04-15 | District | In Progress
R
A
4 | Purchase of Lab. Glasswares (SHEP/TU/KPC/G/NCB-4) | Post | p | 5 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-02-15 | 2013-04-15 | District | In Progress
R
A
5 | Purchase of Generator 25KVA (SHEP/TU/KPC/G/NCB-5) | Post | p | 1 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-02-15 | 2013-04-15 | District | In Progress
R
A
6 | Purchase of Furnitures for Lab,Class rooms & Office (SHEP/TU/KPC/G/NCB-6) | Post | p | 5 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-02-15 | 2013-04-15 | District | In Progress
R
A
7 | Purchase of Books (SHEP/TU/KPC/G/Shop-1) | Post | p | 0.1 | Shopping | WB | NA | NA | 2013-01-05 | 2013-01-20 | NA | NA | 2013-02-01 | 2013-05-01 | District | In Progress
R
A
| Total |  |  | 29.3

## Central Technology Works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Central Technology Campus, Dharan (Autonomus)
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Maintenance of Lab. Building (SHEP/TU/KPC/W/NCB-1) | Post | p | 1 | NCB | GON | NA | NA | 2012-12-25 | 2013-01-24 | NA | NA | 2013-02-20 | 2013-06-20 | District | In progress
R
A
2 | Maintenance of wiring for Lab.,class rooms & Administrative building (SHEP/TU/KPC/W/SQ-2) | Post | p | 1.64 | SQ | GON | NA | NA | 2013-01-05 | 2013-01-20 | NA | NA | 2013-02-15 | 2013-06-15 | District | In progress
R
A
3 | Maintenance of Dry & wet Pilot Plant Building (SHEP/TU/KPC/W/SQ-3) | Post | p | 1.5 | SQ | GON | NA | NA | 2013-05-05 | 2013-05-20 | NA | NA | 2013-05-28 | 2013-10-15 | District | In Process
R
A
4 | Construction of Main ( Front) Gate (SHEP/TU/KPC/W/SQ-4) | Post | p | 0.7 | SQ | GON | NA | NA | 2013-04-05 | 2013-04-20 | NA | NA | 2013-05-15 | 2013-10-15 | District | In Process
R
A
5 | Construction of two Storey building for Nutrition Program (SHEP/TU/KPC/W/NCB-5) | Prior | p | 24.6 | NCB | GON | 2013-03-15 | 2013-03-25 | 2013-04-05 | 2013-05-04 | 2013-05-19 | 2013-06-01 | 2013-06-17 | 2014-01-15 | District | Bank fund will be used for the functionally completed parts of the building by the closing date of project
R
A
6 | Construction of Girls Hostel for 15 Students (SHEP/TU/KPC/W/NCB-6) | Prior | p | 16.77 | NCB | GON | 2013-03-15 | 2013-03-25 | 2013-04-05 | 2013-05-04 | 2013-05-19 | 2013-06-01 | 2013-06-17 | 2014-01-15 | District | Bank fund will be used for the functionally completed parts of the building by the closing date of project
R
A
7 | Construction of Boys Hostel for 25 Students (SHEP/TU/KPC/W/ICB-7) | Prior | p | 52.6 | ICB | WB | 2013-03-15 | 2013-03-25 | 2013-04-05 | 2013-05-04 | 2013-05-19 | 2013-06-01 | 2013-06-17 | 2014-03-15 | District | Bank fund will be used for the functionally completed parts of the building by the closing date of project
R
A
8 | Construction of Basketball Court (SHEP/TU/KPC/W/NCB-8) | Post | p | 2 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-03-01 | 2013-09-15 | District | In Progress
R
A
9 | Construction of Boundry Wall (SHEP/TU/KPC/W/NCB-9) | Post | p | 15 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-02-10 | 2013-08-01 | District | In Progress
R
A
10 | Renovation of class room building (SHEP/TU/KPC/W/NCB-10) | Post | p | 4.5 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-02-28 | 2013-10-15 | District | In Progress
R
A
11 | Expansion of Building for Campus Chief Office (SHEP/TU/KPC/W/NCB-11) | Post | p | 11.1 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-02-15 | 2013-10-17 | District | In Progress
R
A
12 | Construction of Library Building (SHEP/TU/KPC/W/NCB-12) | Prior | p | 34 | NCB | GON | 2013-03-15 | 2013-03-25 | 2013-04-05 | 2013-05-04 | 2013-05-19 | 2013-06-01 | 2013-06-17 | 2014-01-15 | District | Bank fund will be used for the functionally completed parts of the building by the closing date of project
R
A
13 | Construction of Staff Quarter (Two Storey for 8 families (SHEP/TU/KPC/W/NCB-13) | Post | p | 13.56 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-02-15 | 2013-10-19 | District | In progress
R
A
14 | Construction of Teachers' Quarter for two families (SHEP/TU/KPC/W/NCB-14) | Post | p | 2.5 | NCB | GON | NA | NA | 2013-01-15 | 2013-02-14 | NA | NA | 2013-02-25 | 2013-10-20 | District | In progress
R
A
15 | Construction of Canteen and Maintenance of Lab. Building (SHEP/TU/KPC/W/NCB-15) | Post | p | 2.5 | NCB | GON | NA | NA | 2013-01-05 | 2013-02-04 | NA | NA | 2013-02-15 | 2013-10-21 | District | In progress
R
A
| Total |  |  | 183.97
Formulas:
Public Opening of Bids = [Bid Invitation]+15

## mahendra Goods
Procurement Plan (PP) for Goods -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Mahendra Multiple Campus, Dharan-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Purchase of Furniture & Fixtures (SHEP/TU/MMC/G/SQ-1) | Post | p | 0.35 | SQ | GON | NA | NA | 2012-12-25 | 2013-01-10 | NA | NA | 2013-01-20 | 2013-03-23 | District | Inprogress
R
A
2 | Procurement of Desktop Computer-5, Laptop-4, UPS-1, Photocopy-2, Hard Disk-1 (SHEP/TU/MMC/G/SQ-2) | Post | p | 0.8 | SQ | GON | NA | NA | 2013-01-05 | 2013-01-20 | NA | NA | 2013-01-30 | 2013-02-23 | District | Inprogress
R
A
3 | Purchase of Vacuum Cleaner-1 Set, Sound System-1 Set (SHEP/TU/MMC/G/SQ-3) | Post | p | 0.17 | SQ | GON | NA | NA | 2013-01-05 | 2013-01-20 | NA | NA | 2013-01-30 | 2013-02-23 | District | Inprogress
R
A
4 | Purchase of Podium-1 Set (SHEP/TU/MMC/G/Shop-4) | Post | p | 0.15 | Shopping | WB | NA | NA | 2013-01-05 | 2013-01-20 | NA | NA | 2013-01-30 | 2013-02-23 | District | Inprogress
R
A
5 | Purchase of Books (SHEP/TU/MMC/G/SQ-5) | Post | p | 0.5 | SQ | GON | NA | NA | 2013-01-05 | 2013-01-20 | NA | NA | 2013-01-28 | 2013-02-28 | District | Inprogress
R
A
| Total |  |  | 1.97

## Mahendra Works
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Mahendra Multiple Campus, Dharan-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Maintenance of Drinking Water Purification system (SHEP/TU/MMC/W/Shop-1) | Post | p | 0.25 | Shopping | WB | NA | NA | 2012-12-25 | 2013-01-10 | NA | NA | 2013-01-15 | 2013-04-20 | District | In Progress
R
A
2 | Painting (Administrative Building) and Maintenance of Hostel (SHEP/TU/MMC/W/Shop-2) | Post | p | 0.25 | Shopping | WB | NA | NA | 2012-12-25 | 2013-01-10 | NA | NA | 2013-01-15 | 2013-04-20 | District | In Progress
R
A
3 | Maintenance of Basketball Ground (SHEP/TU/MMC/W/Shop-3) | Post | p | 0.55 | Shopping | WB | NA | NA | 2013-01-05 | 2013-01-20 | NA | NA | 2013-01-28 | 2013-03-28 | District | In Progress
R
A
4 | Maintenance of Hostel and Compound Wall (SHEP/TU/KPC/W/SQ-4) | Post | p | 0.2 | SQ | GON | NA | NA | 2013-01-05 | 2013-01-20 | NA | NA | 2013-01-30 | 2013-06-15 | District | In Progress
R
A
| Total |  |  | 1.25
-

## Summary of Cost
Summary of Cost Estimates, Mar 22, 2013
S.No. | Project Implementing Selected Decentralized Campuses | Procurement Heads |  |  |  | Total
|  | Goods | Works | Consulting Servies | Non Consulting Servies
1 | Mahendra Ratna Multiple Campus, Ilam | 9.3 | 18.08 | 5 | 0 | 32.38
2 | Mahendra Multiple Campus, Nepalgunj | 2.6 | 26.61 |  | 0 | 29.21
3 | Mechi Multiple Campus, Jhapa | 6.85 | 7.945 | 1.37 | 0 | 16.165
4 | Siddhanath Science Campus, Mahendranagar | 2.95 | 7.45 | 0.15 | 0 | 10.55
5 | Dhankuta Multiple Campus, Dhankuta | 1.13 | 13.19 | 1.27 | 0 | 15.59
6 | Bhairahawa Campus, Bhairahawa | 0 | 27.72 |  | 0 | 27.72
7 | Padmakanya Multiple Campus, Bagabazar | 7.61 | 18.37 |  | 0 | 25.98
8 | Trichandra Multiple Campus, Ghantaghar | 7.3 | 23.1 |  | 0 | 30.4
9 | Tribhuvan Multiple Campus, Palpa | 3.1 | 17.9 |  | 0 | 21
10 | Central Technology Campus, Dharan | 29.3 | 183.97 |  | 0 | 213.27
11 | Mahendra Multiple Campus, Dharan | 1.97 | 1.25 |  | 0 | 3.22
12 | Public Youth Campus,Kathmandu |  | 2.61 |  | 0 | 2.61
Total |  | 72.11 | 348.195 | 7.79 |  | 428.095

## Abbreviations Used
Abbreviations Used in the Procurement Plans
A | Actual
BER | Bid Evaluation Report
G | Goods
GON | Government of Nepal
ID | Identification
NA | Not aplicable
NCB | National Competitive Bidding
NO | Number
NOL | No Objection Letter
P | Planned
PP | Procurement Plan
R | Revised
SHEP | Second Higher Education Project
SHOP | Shopping
SQ | Sealed Quotation
UGC | University Grants Commission
W | Works
WB | The World Bank
DC | Direct Contact
IC | Individual Consultants
NCS | Non Consulting Services
CS | Consulting Services

## Public Youth
Procurement Plan (PP) for Works -2012/2013(Revised and updated)
Project Name & ID : Second Higher Education Project (SHEP) | [7 empty] | Executing Agency : UGC/TU-SHEP
Loan / Credit/Grant No: H274-Nep | [7 empty] | Implementing Agency : Public Youth Campus, Dharan-Decentralised
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Class Room Extention at Block "C" Building (SHEP/TU/PYC/W/NCB-1) | Post | p | 2.61 | NCB | WB | NA | NA | 2013-01-05 | 2013-01-10 | NA | NA | 2013-01-15 | 2013-04-20 | District | In Progress
R
A
| Total |  |  | 2.61