## RFQ
Request for Quotations
Activity Reference No. / Description: | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Draft Request for Quotations |  | Specific Procurement Notice |  | Invitation to Supplier / Contractor |  | Amendments to Request for Quotations | Receive Quotations |  | Comparison of Quotations |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
LR-FDA-31226-GO-RFQ / Procurement of Field Equipment and Supplies (RIU) assorted | TF-A0929 |  | Post | Goods | Limited | 10,000.00 | Submitted | Cleared | 2017/11/10 | [6 empty] | 2017/11/29 |  | 2017/12/06 |  | 2017/12/20 |  | 2018/01/10 |  |  | 2018/01/31
LR-FDA-31227-GO-RFQ / Audio-visual equipment and supplies | TF-A0929 |  | Post | Goods | Limited | 2,000.00 | Submitted | Cleared | 2017/11/12 | [6 empty] | 2017/12/01 |  | 2017/12/08 |  | 2017/12/22 |  | 2018/01/12 |  |  | 2018/01/26
LR-FDA-31198-GO-RFQ / Camping Materials and Supplies (FAO TA support) | TF-A0929 |  | Post | Goods | Limited | 40,000.00 | Submitted | Cleared | 2017/10/09 | [6 empty] | 2017/10/28 |  | 2017/11/04 |  | 2017/11/18 |  | 2017/12/09 |  |  | 2018/02/07
LR-FDA-31228-GO-RFQ / Office Furniture (FAO TA support) | TF-A0929 |  | Post | Goods | Limited | 3,000.00 | Submitted | Cleared | 2017/10/25 | [6 empty] | 2017/11/13 |  | 2017/11/20 |  | 2017/12/04 |  | 2017/12/25 |  |  | 2018/01/08
LR-FDA-31209-GO-RFQ / Server + Installation & 14 months Hosting, GIS Softwares and Other IT Equipment (FAO TA support) | TF-A0929 |  | Post | Goods | Limited | 57,500.00 | Submitted | Cleared | 2017/10/09 | [6 empty] | 2017/10/28 |  | 2017/11/04 |  | 2017/11/18 |  | 2017/12/09 |  |  | 2018/02/07
LR-FDA-31204-GO-RFQ / Field Tech Equipment (FAO TA suport) | TF-A0929 |  | Post | Goods | Limited | 45,000.00 | Submitted | Cleared | 2017/10/09 | [6 empty] | 2017/10/28 |  | 2017/11/04 |  | 2017/11/18 |  | 2017/12/09 |  |  | 2018/06/07
LR-FDA-31234-GO-RFQ / Field Tools (FAO TA support) | TF-A0929 |  | Post | Goods | Limited | 750.00 | Submitted | Returned | 2017/09/25 | [6 empty] | 2017/10/11 |  | 2017/10/21 |  | 2017/11/04 |  | 2017/11/25 |  |  | 2017/12/25

## QCBS - FBS - LCS
Quality and Cost Based Selection (QCBS), Fixed Budget Based Selection (FBBS), Least Cost Based Selection (LCBS)
Activity Reference No. / Description: | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Request for Proposals as Issued |  | Amendments to Request for Proposals |  | Opening of Technical Proposals / Minutes |  | Evaluation of Technical Proposals |  | Opening of Financial Proposals / Minutes |  | Combined Evaluation Report and Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
LR-FDA-31210-CS-LCS / Audit (Financial audit of Additional Readiness Preparation Activities-AF FY-2017/18) | TF-A0929 |  | Post | Consultant Services | Open - National | 45,000.00 | Submitted | Cleared | 2018/02/08 |  | 2018/03/01 |  | 2018/03/31 |  | 2018/04/14 | [5 empty] | 2018/05/12 |  | 2018/06/11 |  | 2018/06/25 |  | 2018/07/16 |  | 2018/07/30 |  | 2018/08/20 |  |  | 2018/11/18

## QBS
Quality Based Selection (QBS)
Activity Reference No. / Description: | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Request for Proposals as Issued |  | Amendments to Request for Proposals |  | Opening of Technical Proposals / Minutes |  | Evaluation of Technical Proposals |  | Combined Evaluation Report and Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
LR-FDA-31229-CS-QBS / Design and Pilot Liberia REDD+ Registry System | TF-A0929 |  | Post | Consultant Services | Open - International | 175,000.00 | Submitted | Cleared | 2018/01/08 |  | 2018/01/29 |  | 2018/02/28 |  | 2018/03/14 | [5 empty] | 2018/04/11 |  | 2018/05/11 |  | 2018/06/10 |  | 2018/06/24 |  | 2018/07/15 |  |  | 2019/01/11

## CQS
Consultant Qualification
Activity Reference No. / Description: | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
LR-FDA-31238-CS-CQS / Feedback & Grievance Redress Mechanism | TF-A0929 |  | Post | Consultant Services | Open - International | 160,000.00 | Submitted | Returned | 2017/08/14 |  | 2017/09/04 |  | 2017/10/04 |  | 2017/10/18 |  | 2017/11/17 |  | 2017/12/01 |  | 2017/12/22 |  |  | 2018/07/20
LR-FDA-31231-CS-CQS / Development of a Safeguards Information System | TF-A0929 |  | Post | Consultant Services | Open - National | 100,000.00 | Submitted | Returned | 2017/07/20 |  | 2017/08/03 |  | 2017/08/13 |  | 2017/09/03 |  | 2017/11/02 |  | 2017/11/16 |  | 2017/12/07 |  |  | 2018/12/02

## CDS
Consultant Direct Selection (CDS)
Activity Reference No. / Description: | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Justification for Direct Selection |  | Invitation to Identified/Selected Consultant |  | Amendments to Terms of Reference |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
LR-FDA-31235-CS-CDS / Update of Land Cover and Forest Map (Plantations and Forest Definition consideration) | TF-A0929 |  | Post | Consultant Services | Direct | 200,000.00 | Submitted | Returned | 2017/08/12 |  | 2017/08/22 |  | 2017/08/27 |  |  |  | 2017/10/26 |  | 2017/11/09 |  | 2017/11/30 |  |  | 2018/06/28

## INDV
Individual Consultant Selection
Activity Reference No. / Description: | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Justification for Direct Selection |  | Invitation to Identified / Selected Consultant |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
LR-FDA-31193-CS-INDV / Technical Assistance (Implications of Land Rights Act and Regulatory Framework in the context of the REDD+ Strategy) | TF-A0929 |  | Post | Consultant Services | Open | 40,000.00 | Submitted | Cleared | 2018/02/15 |  | 2018/03/01 |  | 2018/03/31 |  |  |  | 2018/04/05 |  | 2018/04/26 |  | 2018/05/10 |  | 2018/05/31 |  |  | 2018/11/27
LR-FDA-31213-CS-INDV / Procurement Officer | TF-A0929 |  | Post | Consultant Services | Limited | 52,000.00 | Submitted | Returned | 2017/10/12 | [7 empty] | 2017/10/17 |  | 2017/11/07 |  | 2017/11/21 |  | 2017/12/12 |  |  | 2019/01/06
LR-FDA-31195-CS-INDV / Senior Project Accountant | TF-A0929 |  | Post | Consultant Services | Open | 72,800.00 | Submitted | Cleared | 2017/11/08 |  | 2017/11/22 |  | 2017/12/22 |  |  |  | 2017/12/27 |  | 2018/01/17 |  | 2018/01/31 |  | 2018/02/21 |  |  | 2018/08/20
LR-FDA-31239-CS-INDV / MRV Officer (LISGIS) | TF-A0929 |  | Post | Consultant Services | Open | 42,000.00 | Submitted | Returned | 2017/07/29 |  | 2017/08/12 |  | 2017/09/11 |  |  |  | 2017/09/16 |  | 2017/10/07 |  | 2017/10/21 |  | 2017/11/11 |  |  | 2018/11/06
LR-FDA-31233-CS-INDV / National Forest Inventory (NFI) Coordinator | TF-A0929 |  | Post | Consultant Services | Open | 63,000.00 | Submitted | Returned | 2017/07/17 |  | 2017/07/31 |  | 2017/08/30 |  |  |  | 2017/09/13 |  | 2017/10/04 |  | 2017/10/18 |  | 2017/11/08 |  |  | 2018/11/03