Lao PDR

Rural Electrification Phase II Project (REP II)

of the Rural Electrification APL Program

Procurement Plan

Revised as of June 28, 2012

| GOODS AND CIVIL WORKS |
| --- |
| Ref. No./Contract no. | Contract (Description) |  | Procurement Method | P-Q | Domestic Preference (yes/no) | IDA Review | Bid Opening Date Plan: Revise: Actual: | Supplier/ Contractor Contract value Signing date | Comments |
| A.1 Grid-extension Component (EdL) |
| REP II-1 | Overhead Conductors (ACSR, AAC, etc) |  | ICB | No | Yes | Prior | Plan: May 2010 Revised: Aug 26, 2011 Actual: Aug 26, 2011 | Hanaka Group Joint Stock Company, Vietnam US$ 7,145,796.20, CIP Plan: Sign Dec.13, 2011 Signed: Dec. 2011 | IDA 10%( $714,579)+IFC 90% ($6,431,216) 1.BER Oct. 26, 2011 2. Bank NOL BER Nov. 14, 2011 3. Contractor: CIP US$5,954,830.22 +20% = US$ 7,145,796.20 |
| REP II-2 | Distribution Transformer Distribution Transformer fitting material and Distribution line materials |  | ICB | No | Yes | Prior | Plan: June 2010 Revised: Aug 11, 2011 Actual: Aug 11, 2011 | Hunan Machinery & Equipment Imp. & Exp. Corp. P.R. China US$ 6,418,940.70 Signed Nov. 25, 2011 | IDA 10% ($641,894)+ IFC 90% ($5,777,046) 1.BER Oct. 26, 2011 2. Bank NOL BER Nov. 14, 2011 3. US$5,349, 117.25 +20% = US$6,418,940.70 |
| REP II-3 | Concrete Poles Concrete Cross Arms |  | ICB | No | Yes | Prior | Plan: June 2010 Revised: Aug 11, 2011 Actual: Aug 11, 2011 | Tang Chareon Co., Ltd, Lao PDR US$9,856,565.32 Signed Oct. 24, 2011 | All IDA (Payment made from remaining balance of REP I) 1.BER Sept. 23, 2011 2. Bank NOL BER Oct. 6, 2011 3. US$ 8,570,926.16 + 15% = US$9,856,565.32 |
| REP II-4 | Watt Hour Meters/Meter Boxes |  | ICB | No | Yes | Prior | Plan: June 2010 Revised: Aug 26, 2011 Actual: Aug 26, 2011 | Zhejiang Jinbang Electric Instrument Co., Ltd., China US$ 413,407.80 Plan: Sign Dec.16, 2011 Signed: Dec 16, 2012 | All IDA 1.BER Sept.23/2011 2. Bank NOL BER Dec.2/2011 3. CIP US$ 344,506.50 + 20% = US$ 413,407.80 |
| REP II-5 | Computer and Office equipment |  | ICB | No | Yes | Prior | Plan: June 2010 Revised: Aug 26, 2011; Actual: Aug 26, 2011 |  | All IDA 1.BER Nov.14/2011 2. Bank suggested to re-bid and re-packaging |
| REP II-5 – lot 1 | Computer and Office equipment for Bolikhamxay and Khammouane branches |  | NCB | No | Yes | Prior | Plan :August 2012 |  | All IDA Rebid from REP II-5 above |
| REP II-5 –lot 2 | Computer and Office equipment for Savannakhet, Champassak, Salavanh, Sekong and Attapeu branches |  | NCB | No | Yes | Prior | Plan -August 2012 |  | All IDA Rebid from REP II-5 above |
| REP II | Construction and Installation |  | - | - | - | - | Plan: Sep 2010 | ECI Lao PDR US$ 10,286,297 Signed: May. 18/2010 | EdL + $M 2.8 IFC for the survey and design EdL signed contract with ECI already and work is commencing. Cost: US$ 10,286,297 |
| REP II | Information for Outreach to village |  | - | - | - | - | Plan: August 2011 |  | EdL |
| REP II | Clearance of Unexplored (UXO) |  | - | - | - | - |  | Already signed | EdL Commence the service after survey by ECI |
| Ref. No./Contract no. | Contract (Description) |  | Procurement Method | P-Q | Domestic Preference (yes/no) | IDA Review | Bid Opening Date Plan: Revise: Actual: | Supplier/ Contractor Contract value Signing date | Comments |
| A.2 Loss Reduction Component (EdL) |
| 01 | LV Capacitor Bank |  | ICB | No | Yes | Prior | Plan: July 2010; Actual : March 12, 2012 |  | IDA 1.BER June 8, 2012 |
| 02 | LV Watt-hour Meters |  | ICB |  | Yes | Prior | Plan: July 2010; Actual: March 12, 2012 | Hunan Machinery & Equipment Imp. & Exp. Corp. P.R. China $ 333,475 Signed: June 29,2012 | IDA For replacement under loss reduction |
| 03 | Portable watt hour meter testers 3 phase (14 sets) and watt hour test bench (1 set) |  | ICB |  | Yes | Prior | Plan: July 2010; Revised: August 2012 Actual : |  | IDA |
| 04 | Watt hours meter test bench (3 sets) |  | ICB |  | Yes | Prior | Plan: July 2010; Revised: August 2012 Actual : |  | IDA |
| A.3 IT System and Financial Management (EdL) |
| 01 | VPN internet network + 17 servers |  | ICB |  | Yes | Prior | Actual: May 2012 |  | EDL (or IDA if financing agreement is amended) 1.BER under preparation |
| A.4 Safeguards Capacity Building (EdL) |
| A.5 Demand-side management and Energy Efficiency (EdL) |
| 01 | Office and IT equipment for ECs and DSM/EE Staff |  | Shopping | No | No | Post | Sept 21, 2011 | Office equipment: $ 16,000 Signed October o5, 2011 Phonesavanh Furniture IT Equipment: $ 29,516 Signed Oct 05, 2011 L7 Computer Co., Ltd. | AusAID (desks, chairs, computers, printers, etc. for 15 staff) |
| 02 | Contingency (office facilities, energy audit equipment and tools, software) |  | Shopping |  | No | Post |  |  | GEF (miscellaneous items for office management and maintenance) |
| 03 | 400,000 15 watt CFLs for EE Lighting Program in Residential Sector |  | ICB |  | Yes | Prior | Actual: May 10, 2012 |  | GEF BER June 25, 2012 |
| 04 | Supply and Installation of EE lighting and ACs Ballast for 50 Public Buildings Retrofits (Supply and Installation of Energy Measures) |  | ICB |  | Yes | Prior | Actual :May 10, 2012 |  | IDA ($220,000) + GEF ($130,000) (i)14,000 T5 Fluorescent Lamp 28W + electronic ballast, (ii) 1,000 T5 Fluorescent Lamp 14W + electronic ballast, (iii) 100 high efficiency ACs, (iv) miscellaneous (luminaries, pull-cord switches, monitoring meters, energy sub-meters, etc.) BER June 20, 2012 |
| 05 | 4-Wheel Drive Pick Up Trucks (2 units for 24 months) |  | NCB |  | No | Prior | Plan April 20 2012 Actual: April 20, 2012 |  | IDA BER : June 20, 2012 |
| B.1 Off-grid Investment Component (MEM) |
| 01 | SHS units |  | ICB | No | Yes | Prior | June 2010 | Beijing Dynamic Power Co., Ltd, China $ 3,365,805.79 Nov. 21, 2011 | AusAID $2 million under REP I + $1.3 M under IDA REP II |
| 02 | Pilot micro hydro PPP in Houaphan Province |  | PPP |  | No | Prior | Actual: Aug 22, 2011 |  | IDA $0.3 million + AusAID $0.28 million under REP I Re-bid by the end of June 2012 (no responsive bidder) |
| B.3 Alternative RE Delivery Model (MEM) |
| 01 | Design, supply and Installation of Biogas / Biomass Pilot Project |  |  |  | Yes | Prior | Plan: Sept 2011 |  | GEF 0.510; several contracts |
| B.5 Organizational Strengthening of MEM’s IREP |
| 01 | Computer, office equipment |  | NCB/ Shopping | No | No | Post | July 2010 |  | , multiple contracts They will procure this after moving to the new offices (Payment from REP 1 GEF) |
| 02 | Two 4-wheel drive pickup trucks |  | NCB |  | No | Prior |  |  | One vehicle for the PMU and one for REFS Preparing the BD |

| CONSULTANT SERVICES |
| --- |
| Ref. No. | Contract (Description) | Cost Estimate ($m) | Selection Method | IDA Review | Proposal Opening Date | Consultant Contract value Signing date | Comments |
| A.1 Grid – Extension Component (EdL) |
| REP II 1/SPN | Supervision of implementation |  | - | - | Plan: Aug 2010 Revised: |  | NORAD |
|  | Technical standards |  |  |  |  |  | NORAD (Revising TOR) |
| A.2 Loss Reduction Component (EdL) |
| 02 | Technical assistance and capacity building for none technical loss reduction |  | QCBS | - | Plan: July 2010 Revised: May 2012? | Mercados EMI $ ??? Signed: XX | GEF |
| A3. IT System Component (EdL) |
| 01 | IT Consultants |  | - | - | June 2010 |  | NORAD Evaluation Report under preparation |
| A.4 Safeguard Capacity Building (EdL) |
| 01 | Environmental and Social Safeguard Capacity Building |  | QCBS | Prior | Plan: June 2010 Revised: February 2012 Actual: May, 21 2012 |  | NORAD TER : June 14, 2012 |
| A.5 Demand-side Management and Energy Efficiency (EdL) |
| 00 | IIEC: extension of contract |  | SSS | prior | - | IIEC. Extension of contract from January 1, 2012 to May 31, 2012, US$27,690. The total amount of the original contract dated June 22, 2011 would become an amount not exceeding US$ 90,830. | NORAD Signed: December 29,2011 |
| 01 | 10 Energy Coordinators |  | IC |  | Plan: June 2011 Actual: April 2012 | Signed: October 03, 2011 | GEF=$119,000, AUSAID=$49,000 October 2011 to September 2013 (24 months) Salary was adjusted from the recruitment in Phase 1 to reflect depreciation of US$ to LAK (about 20%) |
| 02 | Capacity building of DSM/EE staff and ECs, M&E of Public Sector and Residential EE Program, Advisory services for awareness and behavioral changes program |  | QCBS | - | February 2012 Actual |  | NORAD |
| 03 | Residential EE Lighting Program Administration (distribution, management and marketing & promotion) |  | CQS |  | Actual: |  | NORAD TOR under preparation |  |  |
| 04 | TA for Awareness and Behavioral Program (including Design and Production Marketing Tools and Materials) |  | CQS |  | Actual: April 2012 |  | NORAD |
| 05 | Awareness Surveys for Key Performance Indicators and Results Framework and Monitoring (Pre and Post Phase II Implementation) |  | CQS |  | December 2011 Actual: April 2012? |  | NORAD The surveys to measure % awareness of EE will be conducted at the beginning and at the end of Phase 2 implementation. To be commenced before implementation of public sector and residential EE program. |
| B. 1 Off-grid Investment Component (MEM) |
| B.2 Institutional Strengthening |
| 01 | Consulting service for management of off-grid program (VOPS) |  | QCBS | Prior | Plan: June 2010; Revised: January 2012? | Envir Tech JV $ 1,081,539 Signed: January X, 2012 | NORAD 0.70 |
| B.3 Alternative RE Technologies and Delivery Arrangement (MEM) |
| 02 | TA for supervision of biogas study and implememtation |  | - | Prior | Plan: Dec 2011 Actual: December 2011? | ERDI Chiang Mai University $ 82,222 Signed: January 5, 2012 | GEF 0.10 + NORAD 0.10 |
| 03 | Renewable Energy Experts |  | IC | Prior | Plan: June 2011 Revised: July 2012 |  | GEF 0.189 |
| B.4 RE Master Plan and Database Component (MEM) |
| 01 | Maintenance of RE database and update RE Master Plan |  | SSS | - | Plan: June 2010; Revised: March 2012 | Lao Consulting Group $ 106,005 Signed: | NORAD 0.10 |
| B.5 Organizational Strengthening of MEM’s DOE |
| 01 | Consulting services for operation of REFS and PMU |  | IC |  | Plan: June 2010; Revised: |  | NORAD; several individual contracts |
| 02 | Mr. Phayvanh Vongsaly, FM Specialist |  | SSS | Prior |  | Contract signed on 12/13/10 $ | NORAD Bank NOL provided 5/5/10 Contract period covers 12/16/10 – 6/30/14 |
| 03 | Ms. Odalone Kommameuang, Project Secretary & Cashier |  | SSS | Prior |  | Contract signed on 12/13/10 $ | NORAD Bank NOL provided 5/5/10; Contract period covers 12/16/10 – 6/30/14 |
| 04 | Financial Audit |  | CQS | Prior |  | Price Waterhouse Coopers $32,480.8 Contract signed on 09/16/11 | NORAD NOL to award on October 7, 2011 |
| 05 | Financial Audit for REF |  |  | Prior |  |  | IDA Covered by the general auditing (row above) |  |

IDA Prior Review Thresholds

| Expenditure Category | Contract Value Threshold (US$’000) | Procurement Method | Contracts Subject to Prior Review (US$’000) |
| --- | --- | --- | --- |
| Goods | >=100 | ICB | >=100 |
|  | <100 | NCB |  |
|  | <30 | Shopping |  |
| Consultant services | >=100 | QCBS, QBS | >=100 for firms All SSS |
|  | <100 | CQS |  |
|  | NA | IC | >=50 for individuals, and all sole source selection |

Note:

ICB: 	International Competitive Bidding

NCB:	National Competitive Bidding

QCBS:	Quality and Cost Based Selection

QBS:	Quality Based Selection

CQS:	Selection Based on Consultant’s Qualifications

IC:		Individual Consultants

SSS:	Single Source Selection

# Text boxes

80801