|  |
| --- |
| 70128 v2**Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 06/27/2012 |

|  |
| --- |
| **1. Basic Information** |
| Project ID & Name | P105683: LR-Comm. Empowerment II |
| Country | Liberia |
| Task Team Leader | Endashaw Tadesse Gossa |
| Sector Manager/Director | Lynne D. Sherburne-Benz |
| Country Director | Yusupha B. Crookes |
| Original Board Approval Date | 06/14/2007 |
| Original Closing Date: | 06/30/2011 |
| Current Closing Date | 07/31/2013 |
| Proposed Closing Date [if applicable] | 07/31/2013 |
| EA Category | B-Partial Assessment |
| Revised EA Category | B-Partial Assessment-Partial Assessment |
| EA Completion Date | 05/20/2008 |
| Revised EA Completion Date |  |

|  |
| --- |
| **2. Revised Financing Plan (US$m)** |
| **Source** | **Original** | **Revised** |
|  BORR | 0.00 | 0.00 |
|  IDAT | 5.00 | 5.00 |
|  **Total** | 5.00 | 5.00 |

|  |
| --- |
| **3. Borrower** |
| **Organization** | **Department** | **Location** |
|  Republic of Liberia |  | Liberia |

|  |
| --- |
| **4. Implementing Agency** |
| **Organization** | **Department** | **Location** |
|  Liberian Agency for Community Empowerment (LACE) |  | Liberia |

|  |
| --- |
| **5. Disbursement Estimates (US$m)** |
| **Actual amount disbursed as of 06/29/2012** **3.02** |
| **Fiscal Year** | **Annual** | **Cumulative** |
|  2011 | 0.00 | 3.02 |
|  2012 | 0.00 | 3.02 |
|  2013 | 1.38 | 4.40 |
|   | **Total** | **4.40** |

|  |
| --- |
| **6. Policy Exceptions and Safeguard Policies** |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes****Original/Current Project Development Objectives/Outcomes** |
| To improve communities' access to basic infrastructures and provide economic opportunities for vulnerable households in urban and rural areas, through: (a) a community driven approach; (b) a labor-intensive public works program; and (c) the provision of capacity-building at the community and local government levels.  |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|   |