# Procurement Plan

## I. General

1.	Agreed Date of the procurement Plan

Original	: Date of Negotiations

Revision 3.1 : October 9, 2007

2. 	Date of General Procurement Notice: May 2006

##### II. Goods and Works and non consulting services.

- Prior Review Threshold: Procurement Decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines for Procurement :

|  | Procurement Method | Method Threshold | Review Comments |
| --- | --- | --- | --- |
| 1. | ICB and LIB (Goods) | > $200,000 | All subject to Prior Review |
| 2. | NCB (Goods) | < $300,000 | First two NCB subject to prior review |
| 3. | Shopping (Goods) | < $200,000 | First three SH subject to prior review |
| 4. | Direct Contracting* | - | All subject to Prior Review |
| 5. | ICB (Works) | > $1,000,000 | All subject to Prior review |
| 6. | NCB (Works) | < $1,000,000 | First two NCB contract subject to prior review |
| 7. | Shopping (Works) | < $200,000 | First two works contract subject to prior review |
| 8. | Technical Specs. and shortlists | - | All subject to agreement with task team |

* all Contracts subject to justification

2.	Pre-qualification. Bidders shall be pre-qualified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines (No pre-qualification is envisaged)

3.	CDD Procurement Manual: Project components to be carried out by community participation in accordance with the provisions of paragraph 3.17 include: No CDD is envisaged

4.	Any Other Special Procurement Arrangements: Payments under the Compensation Fund will be goverened by the Compensation Fund manual which will form an integral part of the POM

##### 5.	Procurement Items with Methods and Time Schedule: See below

| Component # | Contract # | Description of goods, works and services | Procurement type | Procurement method | Number of packages | Total estimated cost (USD) | Prior/Post Review | TS/TOR Preparation | Winning bidder | Contract amount |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I | 3a | [Central Lab] Post mortem room refurbishment (incl. working tables) | W | SH | 1 |  | Post | June-07 |  |  |
|  | 3b | [Regional Lab] Refurbishment for serology | W | SH | 2 |  | Post | June-07 |  |  |
|  | 3b1 | South regional lab reparation | W | NCB | 1 |  | Prior | Oct-07 |  |  |
|  | 3c | [Regional Lab] Post mortem room refurbishment (incl. working tables) | W | SH | 2 |  | Post | June-07 |  |  |
|  | 3d1 | Equipment for Central and Regional Laboratories (separate lots) | G | ICB | 2 |  | Prior | Sep-07 |  |  |
|  | 3d2 | Equipment for Central Laboratory (Microscope+Elisa) | G | SH | 1 |  | Prior | June-07 |  |  |
|  | 3e | Incinerator to service Central Laboratory | G | ICB | 1 |  | Prior | July-07 |  |  |
|  | 3f | IT and office equipment for Central and Regional laboratories | G | SH | 1 |  | Post | Sep-07 |  |  |
|  | 1c1 | Disinfection equipment (Automobile desinfection inst.) | G | SH | 2 |  | Post | July-07 |  |  |
|  | 1c2 | Disinfection equipment (Desinfection sprayers) | G | SH | 1 |  | Post | Apr-07 | SRL Belnis SRL Olsom | 24,539 6,820 |
|  | 1d | Disinfection installations at Central Laboratory and border crossings | W | SH | sev |  | Post | June-07 |  |  |
|  | 1e | Mobile incinerators | G | SH | 1 |  | Post | July-07 |  |  |
|  | 1f | IT and office equipment for Central and Regional laboratories | G | SH | 2 |  | Post | Sep-07 |  |  |
|  | 1g | Protective clothing | G | SH | 3 |  | Prior | Feb-07 | SRL Belnis | 82,640 |
|  | 1m | Disinfectants | G | SH | sev |  | Prior | Dec-06 | SRL Agroterra Impex SRL Agrimatco-Service | 125,000 52,500 |
| II | 1o | Consumables | G | SH | sev |  | Post | Oct-07 |  |  |
|  | 1C | IT system for surveilance | G | ICB | 1 |  | Prior | July-07 |  |  |
|  | 2A | Refurbishment of Viral lab. | W | NCB | 1 |  | Prior | Aug-07 |  |  |
|  | 2B | Furniture and specialized equipment (4 lots) | G | ICB | 1 |  | Prior | Sep-07 |  |  |
|  | 2D | Consmables and Reagents | G | SH | 1 |  | Post | Oct-07 |  |  |
|  | 2E | Desinfectants, consumables | G | SH | sev |  | Post | Sep-07 |  |  |
|  | 3C | Rapid response teams supplies and operating costs | G | SH | sev |  | Post | Apr-07 | SRL Belnis | 3,537 |
|  | 3D1 | Vehicles for Rapid Response teams (3 vehicles) | G | SH | 1 |  | Prior | Apr-07 | SA Antares | 143,483 |
|  | 3D2 | Mobile disinfection room (steam sterilizer) for RRT | G | SH | 1 |  | Post | July-07 |  |  |
|  | 4A | Pharmaceuticals for prophylaxis and therapy (Tamiflu) | G | DC | sev |  | Prior | Dec-06 | SRL Dita EstFarm | 41,187 |
|  | 4A | Pharmaceuticals for prophylaxis and therapy (several lots) | G | SH | sev |  | Post | Dec-06 | SRL Tetis International | 9,099 |
|  | 4B | Protective clothing | G | SH | 1 |  | Prior | Dec-06 | SRL Belnis | 80,534.50 |
|  | 4C | Vaccinces for risk groups (seasonal) | G | DC | 1 |  | Prior | Nov-06 | SRL Tetis International | 51,000 |
|  | 4C | Vaccinces for risk groups (seasonal) | G | SH | 2 |  | Post | May-07 |  |  |
|  | 5A | Refurbishment of ICU | W | NCB | 1 |  | Prior | Dec-07 |  |  |
|  | 5B | Equipment, furniture and consumables for ICU | G | SH | 1 |  | Post | Nov-07 |  |  |
|  | 5C | Vehicle, equipment and consumables for 3 mobile IC ambulances | G | SH | 1 |  | Post | Dec-06 | SRL Rumeon | 217,044 |
|  | 6 | 3 Notebooks and 3 multimedia projectors for training courses | G | SH | 1 |  | Post | June-07 |  |  |

##### III. Selection of Consultants

- Prior Review Threshold: Selection Decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:

|  | Selection Method | Method Threshold | Review Comments |
| --- | --- | --- | --- |
| 1. | Competitive Methods (Firms) QCBS | Any amount | All subject to prior review |
| 2. | Competitive Methods (Firms) FBS | Any amount | First 2 contracts subject to prior review |
| 3. | Competitive Methods (Firms) LCS | Any amount | First 2 contracts subject to prior review |
| 4. | Competitive Methods (Firms) CQ | < $200,000 | First 2 contracts subject to prior review |
| 5. | Individual Consultants (IC) | Any amount | > $50,000 |
| 6. | Single Source (Firms and Individuals)* | - | All subject to prior review |
| 7. | ToRs for Consulting Contracts | All methods/values | All subject to agreement with task team |

* all Contracts subject to justification

- Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $100,000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

3.	Any Other Special Selection Arrangements:

4.	Consultancy Assignments with Selection Methods and Time Schedule: See below

| Component # | Contract # | Description of goods, works and services | Procurement type | Procurement method | Number of packages | Total estimated cost (USD) | Prior/Post Review | TS/TOR Preparation | Contractor | Contract amount |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I | A1a | Inventory of available data on wild birds' monitoring | CS | SSS | 1 |  | Prior | June-07 |  |  |
|  | A1b | Wild birds' monitoring | CS | CQ | 1 |  | Prior | June-07 |  |  |
|  | A1c | Poultry sector study | CS | CQ | 1 |  | Post | July-07 |  |  |
|  | A2a | Capacity building, veterinary epidemiology & decision making support tools | CS | IC | 1 |  | Prior | June-07 |  |  |
|  | A2b | Capacity building in laboratory design and management | CS | IC | 1 |  | Post | June-07 |  |  |
|  | A2c | Laboratory design studies (waste management; satelite labs) | CS | IC | 2 |  | Post | June-07 |  |  |
|  | B1a | Training in crisis preparedness and outbreak management | CS | IC | 1 |  | Prior | June-07 | Florica Durlea | 16,688 |
|  | B1b | Training national centres and simulation exercises | CS | CQ | 1 |  | Prior | June-07 |  |  |
|  | B1i | In-house training | TR | CQ | sev |  | Post | July-07 |  |  |
|  | B1j | Regional / local workshops | TR | AP | sev |  | NA | July-07 |  |  |
|  | B1k | International seminars | TR | AP | sev |  | NA | July-07 |  |  |
|  | B1l | Bio-security training private sector stakeholders | TR | IC | sev |  | Post | July-07 |  |  |
|  | B1n | Customization LMIS | CS | IC | 1 |  | Prior | July-07 |  |  |
| II | 1A +2C | Review of regulatory system and SOP, risk groups definition, clinical protocols + training, national excersises in crisis management, and field epidemiology investigation Development of SOP, Waste management and quality controls | CS | IC | 5 |  | Prior | Jul-07 |  |  |
|  | 1B | Workshops and excersises | TR | CQ | sev |  | Post | Sep-07- 08 |  |  |
|  | 1E | International Workshops and meetings | TR | AP | sev |  | NA | 2007-2009 |  |  |
|  | 1F | Capacity buildning for outbreak management staff | TR | CQ | sev |  | Post | Nov-07 |  |  |
|  | 2A | Design and supervision for refurbishment of Viral lab. And ICU (Civil Engineer) | CS | IC | 1 |  | Post | Dec-06 | Raileanu Ion | 10,000 |
|  | 2B | Technical Design and supervision of Viral lab and ICU | CS | CQ | 1 |  | Prior | June-07 |  |  |
|  | 2F | Training of Lab technicians | TR | CQ | 5 |  | Post | 2007-2008 |  |  |
|  | 3A | Social distancing (training) | TR | CQ | 1 |  | Post | Nov-07 |  |  |
|  | 3B | Training for mobile rapid response teams | TR | CQ | 1 |  | Post | Oct-07 |  |  |
|  | 4 | Translation of printed materials | CS | IC | 1 |  | Post | June-07 |  |  |
|  | 5D | Training for ICU personnel | TR | CQ | sev |  | Post | 2007-2008 |  |  |
| III | 1A | Communication component | CS | UNA | 1 |  | Prior | Dec-06 | UNICEF | 587,300 |
| IV | 1A | M&E training | TR | CQ | sev |  | Post | Aug-07 |  |  |
|  | 1B | Impact evaluation | CS | CQ | sev |  | Post | Oct-07 |  |  |
|  | 1C | MIS Specialist | CS | IC | 1 |  | Post | June-07 |  |  |

III. Other

- Ex-Post Review: All other contracts below Bank’s prior review threshold are subject to Bank’s selective ex-post review.  Periodic ex-post review by Bank staff will be undertaken during regular supervision missions. Procurement documents, such as bidding documents, bids, bid evaluation reports and correspondence related to bids and contracts will be kept readily available for Bank’s ex-post review during supervision missions or at any other points in time.  Bank missions will review at least 2 out of every 5 contracts which are subject to ex-post review.

- Record Keeping: CAPMU will maintain complete procurement files which will be reviewed by Bank supervision missions. All procurement related documentation that requires Bank prior review will be cleared by Procurement Accredited Staff (PAS) and relevant technical staff.  No packages above mandatory review thresholds by RPA are anticipated. Procurement information will be recorded by CAPMU and submitted to Bank as part of the quarterly (FMRs) and annual progress reports. A simple management information system with a procurement module has been established to assist the CAPMU procurement specialists to monitor all procurement information.

# Text boxes

41300